## SR8 Assembly Order
Your Assembly | Project | Section | Department | Notes (Add any useful context here) | External Dependency (Put Sunswift if none needed) | External Partner (How long securing partnership / acquiring material takes) | Assigned Person | Time to complete (How long it takes after Sunswift can start working on it?) | Mat Sci Consultant | Depends on (List all underneath) | Same Time (Can/need to be designed) | Impacts (List all underneath) | Assembly 1 | Assembly 2 | Assembly 3 | Assembly 4 | Assembly 5 | Assembly 6 | Assembly 7 | Assembly 8 | Assembly 9 | Assembly 10 | Assembly 11 | Assembly 12 | Assembly 13 | Assembly 14 | Assembly 15 | Assembly 16 | Assembly 17 | Assembly 18 | Assembly 19 | Assembly 20 | Assembly 21 | Assembly 22 | Assembly 23 | Assembly 24 | Assembly 25 | Assembly 26 | Assembly 27 | Assembly 28 | Assembly 29 | Assembly 30 | Assembly 31 | Assembly 32 | Assembly 33 | Assembly 34 | Assembly 35 | Assembly 36 | Assembly 37 | Assembly 38 | Assembly 39 | Assembly 40 | Assembly 41 | Assembly 42 | Assembly 43 | Assembly 44 | Assembly 45 | Assembly 46 | Assembly 47 | Assembly 48 | Assembly 49 | Assembly 50 | Assembly 51 | Assembly 52 | Assembly 53 | Assembly 54 | Assembly 55 | Assembly 56 | Assembly | Partners | PartnerWeight | EdgeWeight | Predecessors | Successors
ASSY - CHASSIS BRAKE LINE | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - OCCUPANT CELL TUB |  |  | ASSY - FRONT BRAKE LINE | ASSY - REAR BRAKE LINE | [54 empty] | ASSY - CHASSIS BRAKE LINE | Compfriction/AP Racing | 0 | 2 | ASSY - OCCUPANT CELL TUB
ASSY - WINDSCREEN WIPER MOTOR | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK |  | Sunswift | 0 weeks | Aditya Bansal | 2 weeks |  | ASSY - WINDSCREEN WIPER |  |  | ASSY - WINDSCREEN WIPER | ASSY - WINDSCREEN WIPER MOTOR | [54 empty] | ASSY - WINDSCREEN WIPER MOTOR | Sunswift | 0 | 2 | ASSY - WINDSCREEN WIPER
ASSY - WINDSCREEN WIPER CONTROL PCB CODE | WINDSCREEN WIPERS | WINDSCREEN | EMBEDDED SYSTEMS |  | Sunswift |  |  | 4 Weeks | N/A | N/A | ASSY - STEERING WHEEL PCB CODE, ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE, ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE, ASSY - INTERIOR LIGHTS PCB CODE, ASSY - HEADLAMP/INDICATOR PCB - RH - CODE ASSY - HEADLAMP/INDICATOR PCB - LH - CODE, ASSY - HORN PCB CODE, ASSY - DOOR CONTROL BOARD - LH - CODE, ASSY - DOOR CONTROL BOARD - RH - CODE | N/A | ASSY - WINDSCREEN WIPER CONTROL PCB CODE | [55 empty] | ASSY - WINDSCREEN WIPER CONTROL PCB CODE | Sunswift | 0 | 4
ASSY - WINDSCREEN WIPER AERO GUARD | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK |  | Sunswift | 0 Weeks | Aditya Bansal | 3 weeks | Ali Ali | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - WINDSCREEN WIPER, ASSY - WINDSCREEN WASHER |  | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER | ASSY - FRONT BODY STRUCTURE | ASSY - OCCUPANT CELL SPIDER | [52 empty] | ASSY - WINDSCREEN WIPER AERO GUARD | Sunswift | 0 | 3 | ASSY - WINDSCREEN
ASSY - WINDSCREEN WIPER | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK |  | Unknown | 4 weeks | Aditya Bansal | 3 weeks | Ali Ali | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - WINDSCREEN WIPER, ASSY - WINDSCREEN WASHER | ASSY - WINDSCREEN WIPER MOTOR | ASSY - OCCUPANT CELL SPIDER | ASSY - WINDSCREEN | ASSY - WINDSCREEN WASHER | ASSY - WINDSCREEN WIPER AERO GUARD | [52 empty] | ASSY - WINDSCREEN WIPER | Unknown | 4 | 3 | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER MOTOR
ASSY - WINDSCREEN WIPER CONTROL PCB | WINDSCREEN WIPERS | WINDSCREEN | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 4 Weeks (when started) | N/A | ASSY - WINDSCREEN WIPER MOTOR |  | N/A | ASSY - WINDSCREEN WIPER MOTOR | ASSY - WINDSCREEN WIPER CONTROL PCB | [54 empty] | ASSY - WINDSCREEN WIPER CONTROL PCB | Sunswift | 0 | 4 | ASSY - WINDSCREEN WIPER MOTOR
ASSY - WINDSCREEN WASHER | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK |  | Unknown | 4 weeks | Aditya Bansal | 2 weeks | Ali Ali | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - WINDSCREEN WIPER, ASSY - WINDSCREEN WASHER |  | ASSY - WINDSCREEN WIPER | ASSY - WINDSCREEN | [54 empty] | ASSY - WINDSCREEN WASHER | Unknown | 4 | 2 | ASSY - WINDSCREEN
ASSY - REARWHEEL HUB AIR INTAKE | AIRFLOW & VENTING | HYDROGEN | ALT |  | Sunswift |  | Simeon | 8 weeks | Niamh Maybloom | ASSY - HYDROGEN COMPARTMENT STRUCTURE |  | ASSY - HYDROGEN CONTROL LOGIC | HYDROGEN COMPARTMENT STRUCTURE | [55 empty] | ASSY - REARWHEEL HUB AIR INTAKE | Sunswift | 0 | 8 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN CONTROL LOGIC
ASSY - HYDROGEN COMPARTMENT VENTILATION | AIRFLOW & VENTING | HYDROGEN | ALT |  | Sunswift (a supplier for fans or IP-rated components) |  | Simeon | 8 weeks | Ali Ali | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN COMPARTMENT EXHAUST VENT | ASSY - P&ID AIR SUPPLY LINE | HYDROGEN COMPARTMENT STRUCTURE | [55 empty] | ASSY - HYDROGEN COMPARTMENT VENTILATION | Sunswift (a supplier for fans or IP-rated components) | 0 | 8 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - P&ID AIR SUPPLY LINE
ASSY - APPLE & ANDROID COMPATABILITY MVP | APPLE & ANDROID COMPATABILITY | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - BLUETOOTH CONNECTIVITY MVP |  | ASSY - SUNSWIFT PHONE APP MVP | [56 empty] | ASSY - APPLE & ANDROID COMPATABILITY MVP | Sunswift | 0 | 0 | ASSY - BLUETOOTH CONNECTIVITY MVP | ASSY - SUNSWIFT PHONE APP MVP
ASSY - APPLE & ANDROID COMPATABILITY | APPLE & ANDROID COMPATABILITY | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - APPLE & ANDROID COMPATABILITY | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | TAILLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | N/A |  | N/A | ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3
ASSY - TAILLIGHT/INDICATOR PCB - RH | TAILIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 6 Weeks | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | ASSY - TAILLIGHT/INDICATOR PCB - LH | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | ASSY - TAILLIGHT/INDICATOR PCB - RH | [54 empty] | ASSY - TAILLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH
ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | TAILLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | N/A | ASSY - STEERING WHEEL PCB CODE, ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE, ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE, ASSY - INTERIOR LIGHTS PCB CODE, ASSY - HEADLAMP/INDICATOR PCB - RH - CODE ASSY - HEADLAMP/INDICATOR PCB - LH - CODE, ASSY - HORN PCB CODE, ASSY - DOOR CONTROL BOARD - LH - CODE, ASSY - DOOR CONTROL BOARD - RH - CODE | N/A | ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3
ASSY - TAILLIGHT/INDICATOR PCB - LH | TAILIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 6 Weeks | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - TAILLIGHT/INDICATOR PCB - RH | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - TAILLIGHT/INDICATOR PCB- LH | [54 empty] | ASSY - TAILLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH
ASSY - AUXILLARY POWER WIRING | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS |  | Unknown | 8 weeks | Darren Paradhen | 2 weeks | Merujen Chelvakumaran | ASSY - AUX BATTERY | [58 empty] | ASSY - AUXILLARY POWER WIRING | Unknown | 8 | 2 | ASSY - AUX BATTERY
ASSY - AUX BATTERY | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS |  | Unknown | 8 weeks | Darren Paradhen | 2 weeks | Merujen Chelvakumaran | - |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING | [56 empty] | ASSY - AUX BATTERY | Unknown | 8 | 2 |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING
ASSY - DC-DC CONVERTERS | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS |  | Unknown | 8 weeks | Darren Paradhen | 2 weeks |  | ASSY - AUX BATTERY | [58 empty] | ASSY - DC-DC CONVERTERS | Unknown | 8 | 2 | ASSY - AUX BATTERY
ASSY - BATTERY PACK | BATTERY | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks | Merujen Chelvakumaran | ASSY - BATTERY MODULES |  | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING | [56 empty] | ASSY - BATTERY PACK | Unknown | 8 | 2 | ASSY - BATTERY MODULES | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING
ASSY - BATTERY MODULES | BATTERY | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | David Thirugnanaraj | 4 weeks | Merujen Chelvakumaran | - |  | ASSY - BATTERY PACK | [56 empty] | ASSY - BATTERY MODULES | Unknown | 8 | 4 |  | ASSY - BATTERY PACK
ASSY - BATTERY LV WIRING | BATTERY | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks | Merujen Chelvakumaran | ASSY - BATTERY PACK |  | - | [56 empty] | ASSY - BATTERY LV WIRING | Unknown | 8 | 2 | ASSY - BATTERY PACK
ASSY - BATTERY HV WIRING | BATTERY | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks | Merujen Chelvakumaran | ASSY - BATTERY PACK |  | - | [56 empty] | ASSY - BATTERY HV WIRING | Unknown | 8 | 2 | ASSY - BATTERY PACK
ASSY - SUBWOOFER | AUDIO | AUDIO | EMBEDDED SYSTEMS |  | Sunswift |  | Merujen Chelvakumaran | 6 Weeks | N/A |  |  | ASSY - OCCUPANT CELL TUB | [56 empty] | ASSY - SUBWOOFER | Sunswift | 0 | 6 |  | ASSY - OCCUPANT CELL TUB
ASSY - STEERING WHEEL PCB CODE | STEERING WHEEL | STEERING WHEEL | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 weeks | N/A | ASSY - STEERING WHEEL PCB | ASSY - STEERING WHEEL PCB CODE, ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE, ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE, ASSY - INTERIOR LIGHTS PCB CODE, ASSY - HEADLAMP/INDICATOR PCB - RH - CODE ASSY - HEADLAMP/INDICATOR PCB - LH - CODE, ASSY - HORN PCB CODE, ASSY - DOOR CONTROL BOARD - LH - CODE, ASSY - DOOR CONTROL BOARD - RH - CODE | N/A | ASSY - STEERING WHEEL PCB | ASSY - STEERING WHEEL PCB CODE | [54 empty] | ASSY - STEERING WHEEL PCB CODE | Sunswift | 0 | 3 | ASSY - STEERING WHEEL PCB
ASSY - WINDSCREEN | WINDSCREEN | WINDSCREEN | CHASSIS & BODYWORK |  | Unknown | 4 weeks | Aditya Bansal | 3 weeks | Ali Ali |  |  | ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - WINDSCREEN WIPER, ASSY - WINDSCREEN WASHER | ASSY - OCCUPANT CELL SPIDER | [55 empty] | ASSY - WINDSCREEN | Unknown | 4 | 3 |  | ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - WINDSCREEN WIPER, ASSY - WINDSCREEN WASHER
ASSY - THERMAL BOX | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK |  | AutoFrost, PWR | 3-4 weeks | Peleg Mondry Cohen | 6 Weeks | Merujen Chelvakumaran |  |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - HVAC BOX | [52 empty] | ASSY - THERMAL BOX | AutoFrost, PWR | 3 | 6 |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX
ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | TAILIGHTS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks | Sushrut Mogarkar | ASSY - CENTRAL STOP LAMP | ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | [55 empty] | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH
ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | TAILIGHTS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks | Sushrut Mogarkar | ASSY - CENTRAL STOP LAMP | ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - SOLAR ROOF ARRAY | [54 empty] | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH
ASSY - STEERING COLUMN MOUNT | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 2 Weeks | Sushrut Mogarkar | ASSY - STEERING COLUMN |  | ASSY - OCCUPANT CELL TUB | ASSY - STEERING COLUMN | ASSY - STEERING WHEEL | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - STEERING COLUMN MOUNT | McConaghy, Scott Bader and Colan | 0 | 2 | ASSY - STEERING COLUMN | ASSY - OCCUPANT CELL TUB
ASSY - SIDE INDICATOR EXTERIOR - RH | INDICATORS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 week | Sushrut Mogarkar | ASSY - CENTRAL STOP LAMP | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH | [56 empty] | ASSY - SIDE INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH
ASSY - STEERING WHEEL PCB | STEERING WHEEL | STEERING | EMBEDDED SYSTEMS |  | Sunswift |  | Zoe Conroy | 1 Week | N/A | - |  | ASSY - STEERING WHEEL | ASSY - STEERING WHEEL | ASSY - STEERING WHEEL PCB | [54 empty] | ASSY - STEERING WHEEL PCB | Sunswift | 0 | 1 |  | ASSY - STEERING WHEEL
ASSY - SIDE INDICATOR - RH | INDICATORS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 4 Weeks | N/A | N/A |  | ASSY - SIDE CAMERA - RH | ASSY - SIDE INDICATOR - RH | [55 empty] | ASSY - SIDE INDICATOR - RH | Sunswift | 0 | 4 |  | ASSY - SIDE CAMERA - RH
ASSY - SIDE INDICATOR EXTERIOR - LH | INDICATORS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks | Sushrut Mogarkar | ASSY - CENTRAL STOP LAMP | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH | [56 empty] | ASSY - SIDE INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP | ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH
ASSY - SUN VISOR RH | CEILING | INTERIOR | INTERIOR |  | Sunswift |  | Jason Jin | 3 weeks | Merujen Chelvakumaran |  |  | ASSY - CEILING | ASSY - SUN VISOR RH | ASSY - CEILING | [54 empty] | ASSY - SUN VISOR RH | Sunswift | 0 | 3 |  | ASSY - CEILING
ASSY - SUN VISOR LH | CEILING | INTERIOR | INTERIOR |  | Sunswift |  | Jason Jin | 3 weeks | Merujen Chelvakumaran |  |  | ASSY - CEILING | ASSY - SUN VISOR LH | ASSY - CEILING | [54 empty] | ASSY - SUN VISOR LH | Sunswift | 0 | 3 |  | ASSY - CEILING
ASSY - CEILING | CEILING | INTERIOR | INTERIOR |  | Sunswift |  | Jason Jin | 4 weeks | N/A | ASSY - REAR VISION CAMERA (mount), ASSY - SUN VISOR LH, ASSY - SUN VISOR RH, |  | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL SPIDER | ASSY - CEILING | [54 empty] | ASSY - CEILING | Sunswift | 0 | 4 | ASSY - REAR VISION CAMERA (MOUNT), ASSY - SUN VISOR LH, ASSY - SUN VISOR RH | ASSY - OCCUPANT CELL SPIDER
ASSY - CENTRAL DISPLAY | CENTRAL DISPLAY | DASHBOARD | INTERIOR |  | Espresso conversation | 0 | Anubhav Sharma | 2 weeks | N/A |  |  | ASSY - DASHBOARD STRUCTURE | [56 empty] | ASSY - CENTRAL DISPLAY | Espresso conversation | 0 | 2 |  | ASSY - DASHBOARD STRUCTURE
ASSY - SIDE INDICATOR - LH | INDICATORS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 4 Weeks | N/A | N/A |  | ASSY - SIDE CAMERA - LH | ASSY - SIDE INDICATOR - LH | [55 empty] | ASSY - SIDE INDICATOR - LH | Sunswift | 0 | 4 |  | ASSY - SIDE CAMERA - LH
ASSY - SIDE CAMERA - RH | SIDE VISION SYSTEM | VISION | EMBEDDED SYSTEMS |  | Unknown for monitor/espresso | 4 weeks | Martina Antonia Casagrande | 6 weeks(when we can test cameras) | N/A | N/A |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | [56 empty] | ASSY - SIDE CAMERA - RH | Unknown for monitor/espresso | 4 | 24 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH
ASSY - SIDE CAMERA - LH | SIDE VISION SYSTEM | VISION | EMBEDDED SYSTEMS |  | Unknown for monitor/espresso | 4 weeks | Martina Antonia Casagrande | 6 weeks(when we can test cameras) | N/A | N/A |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH, | [56 empty] | ASSY - SIDE CAMERA - LH | Unknown for monitor/espresso | 4 | 24 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH
ASSY - SENSOR MOTHERBOARD - FL | SENSORS | SENSORS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 3 Months + | N/A | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - FL | [55 empty] | ASSY - SENSOR MOTHERBOARD | Sunswift | 0 | 12
ASSY - REAR SUPPORT STRUCTURE | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 5 Weeks | Sushrut Mogarkar | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB |  | ASSY - BOOT | ASSY - REAR BUMPER | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - OCCUPANT CELL TUB | ASSY - BOOT | ASSY - BOOT LOCKING BOARD | [50 empty] | ASSY - REAR SUPPORT STRUCTURE | McConaghy, Scott Bader and Colan | 0 | 5 | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB | ASSY - BOOT
ASSY - REAR QUARTER PANEL - LH | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 2 Weeks | Sushrut Mogarkar |  |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH, ASSY - OUTER DOOR HANDLE - LH | ASSY - OCCUPANT CELL TUB | ASSY - REAR BUMPER | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH | [50 empty] | ASSY - REAR QUARTER PANEL - LH | McConaghy, Scott Bader and Colan | 0 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH, ASSY - OUTER DOOR HANDLE - LH
ASSY - REAR QUARTER PANEL - RH | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 2 Weeks | Sushrut Mogarkar |  |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH, ASSY - OUTER DOOR HANDLE - RH | ASSY - OCCUPANT CELL TUB | ASSY - REAR BUMPER | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH | [50 empty] | ASSY - REAR QUARTER PANEL - RH | McConaghy, Scott Bader and Colan | 0 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH, ASSY - OUTER DOOR HANDLE - RH
ASSY - SENSOR MOTHERBOARD - BL | SENSORS | SENSORS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 3 Months + | N/A | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - BL | [55 empty] | ASSY - SENSOR MOTHERBOARD - BL | Sunswift | 0 | 12
ASSY - REAR VISION CAMERA | REAR VISION SYSTEM | VISION | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 4 Weeks | N/A | N/A |  | N/A | [56 empty] | ASSY - REAR VISION CAMERA | Sunswift | 0 | 4
ASSY - PEDAL PRESS SENSOR | PEDALS | PEDALS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 1 Week | N/A | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL |  | N/A | ASSY - PEDAL PRESS SENSOR | [55 empty] | ASSY - PEDAL PRESS SENSOR | Sunswift | 0 | 1 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL
ASSY - CYBERSECURITY MVP | CYBERSECURITY | SECURITY | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | N/A | [58 empty] | ASSY - CYBERSECURITY MVP | Sunswift | 0 | 0
ASSY - CYBERSECURITY | CYBERSECURITY | SECURITY | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - CYBERSECURITY | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - DASHBOARD STRUCTURE | DASHBOARD | DASHBOARD | INTERIOR |  | Sunswift/Mconaghy |  | Elisa Wong | 6 weeks | Merujen Chelvakumaran | ASSY - OCCUPANT CELL TUB, ASSY-DOOR CARD, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR) |  |  | ASSY - OCCUPANT CELL TUB |  | Driver's display | [53 empty] | ASSY - DASHBOARD STRUCTURE | Sunswift/Mconaghy | 0 | 6 | ASSY - OCCUPANT CELL TUB, ASSY - OOR CARD, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR)
ASSY - REAR FLUID MANAGEMENT | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK |  | Unknown | 3 Weeks | Ray | 5 Weeks | Sushrut Mogarkar | ASSY - THERMAL BOX, ASSY - MOTORS, ASSY - POWER ELECTRONICS, ASSY - HYDROGEN COOLING SYSTEM | ASSY - FRONT FLUID MANAGEMENT | ASSY - OCCUPANT CELL TUB | ASSY - BATTERY | ASSY - OCCUPANT CELL TUB | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT | [52 empty] | ASSY - REAR FLUID MANAGEMENT | Unknown | 3 | 5 | ASSY - THERMAL BOX, ASSY - MOTORS, ASSY - POWER ELECTRONICS, ASSY - HYDROGEN COOLING SYSTEM | ASSY - OCCUPANT CELL TUB
ASSY - REAR FLOOR | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 3 weeks | Sushrut Mogarkar | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH |  | ASSY - BOOT | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - REAR BUMPER | ASSY - OCCUPANT CELL TUB | [52 empty] | ASSY - REAR FLOOR | McConaghy, Scott Bader and Colan | 0 | 3 | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT
ASSY - REAR CRASH STRUCTURE | CRASH STRUCTURES | CHASSIS | CHASSIS & BODYWORK |  | Calm Aluminium | 0 | John Zhu | 3 weeks | Sushrut Mogarkar |  | ASSY - FRONT CRASH STRUCTURE | ASSY - OCCUPANT CELL TUB | [56 empty] | ASSY - REAR CRASH STRUCTURE | Calm Aluminium | 0 | 3 |  | ASSY - OCCUPANT CELL TUB
ASSY - REAR BUMPER | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 6 weeks | Sushrut Mogarkar | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH |  | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - BOOT | ASSY - BOOT LOCKING BOARD | ASSY - REAR FLOOR | ASSY - REAR SUPPORT STRUCTURE | ASSY - BLINDSPOT MONOTORING SENSOR - LH |  | REAR PARKING SENSOR | [47 empty] | ASSY - REAR BUMPER | McConaghy, Scott Bader and Colan | 0 | 6 | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE
ASSY - OUTER DOOR HANDLE - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 weeks | Sushrut Mogarkar | ASSY - DOOR LATCH - RH |  |  | ASSY - REAR QUARTER PANEL - RH | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH |  | ASSY - DOOR CONTROL BOARD - RH | [51 empty] | ASSY - OUTER DOOR HANDLE - RH | Chevalier | 4 | 2 | ASSY - DOOR LATCH - RH
ASSY - OUTER DOOR HANDLE - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 weeks | Sushrut Mogarkar | ASSY - DOOR LATCH - LH |  |  | ASSY - REAR QUARTER PANEL - LH | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH |  | ASSY - DOOR CONTROL BOARD - LH | [51 empty] | ASSY - OUTER DOOR HANDLE - LH | Chevalier | 4 | 2 | ASSY - DOOR LATCH - LH
ASSY - PEDAL BOX CONTROLLER | PEDALS | PEDALS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 2 Weeks (when resumed) | N/A | ASSY - PEDAL PRESS SENSOR |  | N/A | ASSY - PEDAL PRESS SENSOR | ASSY - PEDAL BOX CONTROLLER | [54 empty] | ASSY - PEDAL BOX CONTROLLER | Sunswift | 0 | 8 | ASSY - PEDAL PRESS SENSOR
ASSY - MAIN COMPUTER | HIGH LEVEL EMBEDDED NETWORK | EMBEDDED | EMBEDDED SYSTEMS |  | Adlink | 8 weeks | Hamish Hunter | 2 weeks | N/A |  |  | INST - INTERNAL EMBEDDED NETWORK WIRING | INST - OCCUPANT CELL TUB | INST - MAIN COMPUTER | [54 empty] | ASSY - MAIN COMPUTER | Adlink | 8 | 2
ASSY - INTERNAL EMBEDDED NETWORK WIRING | INTERNAL EMBEDDED NETWORK | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  |  | 2 Weeks | N/A | ASSY- HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY- HORN PCB, ASSY - TAILLIGHT/INDICATOR PCB- LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP PCB, ASSY - STEERING WHEEL PCB, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LiDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM,ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT, STRUCTURE, ASSY - BOOT, ASSY - BONNET |  |  | INST - INTERNAL EMBEDDED NETWORK WIRING | [55 empty] | ASSY - INTERNAL EMBEDDED NETWORK WIRING | Sunswift | 0 | 2 | ASSY - HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - HORN PCB, ASSY - TAILLIGHT/INDICATOR PCB- LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP PCB, ASSY - STEERING WHEEL PCB, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LIDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM, ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT, ASSY - BOOT, ASSY - BONNET
ASSY - INTERIOR LIGHTS PCB CODE | INTERIOR LIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 2 Weeks | N/A | ASSY - INTERIOR LIGHTS PCB | ASSY - STEERING WHEEL PCB CODE, ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE, ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE, ASSY - HEADLAMP/INDICATOR PCB - RH - CODE ASSY - HEADLAMP/INDICATOR PCB - LH - CODE, ASSY - HORN PCB CODE, ASSY - DOOR CONTROL BOARD - LH - CODE, ASSY - DOOR CONTROL BOARD - RH - CODE | N/A | ASSY - INTERIOR LIGHTS PCB CODE | [55 empty] | ASSY - INTERIOR LIGHTS PCB CODE | Sunswift | 0 | 2 | ASSY - INTERIOR LIGHTS PCB
ASSY - INTERIOR LIGHTS PCB | INTERIOR LIGHTS | STEERING | EMBEDDED SYSTEMS |  | Sunswift |  | Deniz Durensil | 6 Weeks | N/A | N/A |  | ASSY - CEILING | ASSY - INTERIOR LIGHT MODULE | ASSY - INTERIOR LIGHTS PCB | [54 empty] | ASSY - INTERIOR LIGHTS PCB | Sunswift | 0 | 6 |  | ASSY - CEILING
ASSY - HORN PCB | HORN | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  | Zoe Conroy | 1 Week | N/A |  |  | N/A | ASSY- HORN PCB | [55 empty] | ASSY - HORN PCB | Sunswift | 0 | 1
ASSY - OCCUPANT CELL TUB | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 5 Weeks | Sushrut Mogarkar | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEATBELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTING, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEATBELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULE, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD LH | ASSY - OCCUPANT CELL SPIDER | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - FRONT CLAMSHELL | ASSY - BATTERY | ASSY - OCCUPANT CELL SPIDER | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - LH | ASSY - DOOR LATCH - LH | ASSY - DOOR LATCH - RH | ASSY - FRONT TOP WISHBONE - LH | ASSY - FRONT TOP WISHBONE - RH | ASSY - FRONT LOWER WISHBONE - LH | ASSY - FRONT LOWER WISHBONE - LH | ASSY - FRONT DAMPER - LH | ASSY - FRONT DAMPER - RH | ASSY - REAR TOP WISHONE - LH | ASSY - REAR TOP WISHONE - LH | ASSY - REAR LOWER WISHBONE LH | ASSY - REAR LOWER WISHBONE RH | ASSY - REAR PUSHROD | ASSY - REAR TOELINK | ASSY - REAR DAMPER - LH | ASSY - REAR DAMPER - RH | ASSY - FRONT MASTER CYLINER | ASSY - HAND BRAKE | ASSY - REAR MASTER CYLINDER | ASSY - STEERING COLUMN | ASSY - STEERING RACK | ASSY - BRAKE PEDAL | ASSY - DASHBOARD | ASSY - FRONT SEAT DRIVER | ASSY - FRONT SEAT PASSENGER | ASSY - FRONT SEAT BEL DRIVER | ASSY - FRONT SEATBELT PASSENGER | ASSY - MOTOR UNIT - LH | ASSY - MOTOR UNIT - RH | ASSY - HV WRING - LH | ASSY - HV WIRING - RH | ASSY - AXLE CV - LH | ASSY - AXLE CV - RH | ASSY - SUBWOOFER | ASSY - FRONT CRASH STRUCTURE | ASSY - REAR CRASH STRUCTURE | ASSY - HVAC BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - FRONT FLOOR | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - BONNET | ASSY - DOOR HINGE - LH | ASSY - DOOR HINGE - RH | ASSY - CHASSIS SUBFRAME | ASSY - THERMAL BOX | ASSY - STEERING COLUMN MOUNT | ASSY - OCCUPANT CELL TUB | ASSY - OCCUPANT CELL TUB | McConaghy, Scott Bader and Colan | 0 | 5 | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEATBELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTING, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEATBELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULE, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - FRONT CLAMSHELL
ASSY - OCCUPANT CELL SPIDER | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 5 Weeks | Sushrut Mogarkar | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH, ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD | ASSY - OCCUPANT CELL TUB |  | ASSY - SOLAR ROOF ARRAY | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - LH | ASSY - WINDSCREEN | ASSY - CEILING | ASSY - OCCUPANT CELL SPIDER | [49 empty] | ASSY - OCCUPANT CELL SPIDER | McConaghy, Scott Bader and Colan | 0 | 5 | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH, ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD
ASSY - INNER DOOR HANDLE - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 weeks | Merujen Chelvakumaran | ASSY - DOOR CARD - RH |  |  | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH |  | ASSY - DOOR CONTROL BOARD - RH | [51 empty] | ASSY - INNER DOOR HANDLE - RH | Chevalier | 4 | 2 | ASSY - DOOR CARD - RH
ASSY - INNER DOOR HANDLE - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 weeks | Merujen Chelvakumaran | ASSY - DOOR CARD - LH |  |  | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH |  | ASSY - DOOR CONTROL BOARD - LH | [51 empty] | ASSY - INNER DOOR HANDLE - LH | Chevalier | 4 | 2 | ASSY - DOOR CARD - LH
ASSY - DOOR CARD - RH | DOORS | BODYWORK | INTERIOR |  | Sunswift |  | Yaheng Li | 3 Weeks | Sushrut Mogarkar |  |  | ASSY - INNER DOOR HANDLE - LH, ASSY- DASHBOARD STRUCTURE | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - DOOR CARD - RH | [52 empty] | ASSY - DOOR CARD - RH | Sunswift | 0 | 3 |  | ASSY - INNER DOOR HANDLE - LH, ASSY - DASHBOARD STRUCTURE
ASSY - DOOR CARD - LH | DOORS | BODYWORK | INTERIOR |  | Sunswift |  | Yaheng Li | 3 weeks | Sushrut Mogarkar | ASSY- OCUPANT CELL SPIDER,ASSY- OCUUPANT CELL TUB ,ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE, ASSY - DOOR AUDIO - LH |  | ASSY - INNER DOOR HANDLE - LH, ASSY- DASHBOARD STRUCTURE | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH | ASSY - DOOR CARD - LH | [52 empty] | ASSY - DOOR CARD - LH | Sunswift | 0 | 3 | ASSY - OCUPANT CELL SPIDER, ASSY - OCUUPANT CELL TUB, ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE, ASSY - DOOR AUDIO - LH | ASSY - INNER DOOR HANDLE - LH, ASSY - DASHBOARD STRUCTURE
ASSY - HORN | HORN | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  | Zoe Conroy | 1 Week | N/A |  |  | N/A | ASSY- HORN PCB | ASSY - HORN | [54 empty] | ASSY - HORN | Sunswift | 0 | 1
ASSY - HEADLIGHT/INDICATOR PCB - RH | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 2 Weeks (when I can work on it again) | N/A |  |  | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - HEADLIGHT/INDICATOR PCB - RH | [54 empty] | ASSY - HEADLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 2 |  | ASSY - HEADLIGHT EXTERIOR - RH
ASSY - DRIVER DISPLAY | DRIVER DISPLAY | DASHBOARD | INTERIOR |  | Espresso conversation | 0 | Anubhav Sharma | 2 weeks | Ali Ali | ASSY - STEERING WHEEL |  | ASSY - DASHBOARD STRUCTURE | [56 empty] | ASSY - DRIVER DISPLAY | Espresso conversation | 0 | 2 | ASSY - STEERING WHEEL | ASSY - DASHBOARD STRUCTURE
ASSY - HVAC PIPING | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK |  | Unknown | 3 weeks | Peleg Mondry Cohen | 7 Weeks | Ali Ali | ASSY - THERMAL BOX | ASSY - HVAC BOX | ASSY - FRONT FLUID MANAGEMENT | ASSY - HVAC BOX | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT | [53 empty] | ASSY - HVAC PIPING | Unknown | 3 | 7 | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT
ASSY - HVAC BOX | AIR CONDITIONING | INTERIOR | CHASSIS & BODYWORK |  | AutoFrost | 0 | Peleg Mondry Cohen | 8 Weeks | Ali Ali | ASSY - THERMAL BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING | ASSY - HVAC BOX | [55 empty] | ASSY - HVAC BOX | AutoFrost | 0 | 8 | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING
ASSY - HEADLIGHT/INDICATOR PCB - LH | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 2 Weeks (when I can work on it again) | N/A |  |  | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT/INDICATOR PCB - LH | [54 empty] | ASSY - HEADLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 2 |  | ASSY - HEADLIGHT EXTERIOR - LH
ASSY - ECS MODULE | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | Vincet Younes | 3 weeks | Ali Ali |  |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC | [56 empty] | ASSY - ECS MODULE | Unknown | 8 | 3 |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC
ASSY - ECS LV WIRING | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | Vincet Younes | 2 weeks | Ali Ali | ASSY - BATTERY PACK | [58 empty] | ASSY - ECS LV WIRING | Unknown | 8 | 2 | ASSY - BATTERY PACK
ASSY - ECS HV WIRING | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | Vincet Younes | 2 weeks | Ali Ali | ASSY - BATTERY PACK | [58 empty] | ASSY - ECS HV WIRING | Unknown | 8 | 2 | ASSY - BATTERY PACK
ASSY - CONTROL LOGIC | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | Vincet Younes | 3 weeks | Ali Ali | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, | [58 empty] | ASSY - CONTROL LOGIC | Unknown | 8 | 3 | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING
ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | N/A |  | N/A | ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3
ASSY - FRONT MASTER CYLINDER RESERVOIR | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER | [54 empty] | ASSY - FRONT MASTER CYLINDER RESERVOIR | Compfriction/AP Racing | 0 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - FRONT MASTER CYLINDER | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER | [54 empty] | ASSY - FRONT MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - FRONT CALIPER - RH | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | ASSY - FRONT UPRIGHT | ASSY - BRAKE DISC | [54 empty] | ASSY - FRONT CALIPER - RH | Compfriction/AP Racing | 0 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE
ASSY - FRONT CALIPER - LH | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | ASSY - FRONT UPRIGHT | ASSY - BRAKE DISC | [54 empty] | ASSY - FRONT CALIPER - LH | Compfriction/AP Racing | 0 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE
ASSY - FRONT BRAKE LINE | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - OCCUPANT CELL TUB |  |  | ASSY - FRONT UPRIGHT | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE DISC | [53 empty] | ASSY - FRONT BRAKE LINE | Compfriction/AP Racing | 0 | 2 | ASSY - OCCUPANT CELL TUB
ASSY - FRONT BRAKE DISC | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH | ASSY - FRONT UPRIGHT | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE | [53 empty] | ASSY - FRONT BRAKE DISC | Compfriction/AP Racing | 0 | 2 | ASSY - FRONT WHEEL | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH
ASSY - FRONT DAMPER - RH | FRONT DAMPERS | FRONT SUSPENSION | VEHICLE DYNAMICS |  | Bilstein | 0 | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | [54 empty] | ASSY - FRONT DAMPER - RH | Bilstein | 0 | 2 | ASSY - FRONT WHEEL
ASSY - FRONT DAMPER - LH | FRONT DAMPERS | FRONT SUSPENSION | VEHICLE DYNAMICS |  | Bilstein | 0 | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | [54 empty] | ASSY - FRONT DAMPER - LH | Bilstein | 0 | 2 | ASSY - FRONT WHEEL
ASSY - FRONT SEAT MOUNT PASSENGER | FRONT SEAT MOUNT | SEATS | INTERIOR |  | Bride Racing | Just ordering- 1 week | Elisa Wong | 4 weeks | Merujen Chelvakumaran |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER(space for bottom mount ) | ASSY - OCCUPANT CELL TUB | [55 empty] | ASSY - FRONT SEAT MOUNT PASSENGER | Bride Racing | 1 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER(SPACE FOR BOTTOM MOUNT )
ASSY - FRONT SEAT MOUNT DRIVER | FRONT SEAT MOUNT | SEATS | INTERIOR |  | Bride Racing | Just ordering- 1 week | Elisa Wong | 4 weeks | Merujen Chelvakumaran |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER ,ASSY - FRONT SEAT BELT DRIVER(space for bottom mount ) | ASSY - OCCUPANT CELL TUB | [55 empty] | ASSY - FRONT SEAT MOUNT DRIVER | Bride Racing | 1 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER, ASSY - FRONT SEAT BELT DRIVER(SPACE FOR BOTTOM MOUNT )
ASSY - FRONT SEAT BELT PASSENGER | FRONT SEAT MOUNT | SEATS | INTERIOR |  | Unknown(just ordering) |  | Martina Casagrande | 1 week | Merujen Chelvakumaran | ASSY - FRONT SEAT PASSENGER |  | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL | ASSY - FRONT SEATBELT PASSENGER | [54 empty] | ASSY - FRONT SEAT BELT PASSENGER | Unknown(just ordering) | 0 | 1 | ASSY - FRONT SEAT PASSENGER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER
ASSY - FRONT SEAT BELT DRIVER | FRONT SEATBELTS | SEATS | INTERIOR |  | Unknown(just ordering) | 1 Week | Martina Casagrande | 1 week | Merujen Chelvakumaran | ASSY - FRONT SEAT DRIVER |  | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | ASSY - FRONT SEAT DRIVER | ASSY - FRONT SEAT BEL DRIVER | [54 empty] | ASSY - FRONT SEAT BELT DRIVER | Unknown(just ordering) | 1 | 1 | ASSY - FRONT SEAT DRIVER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER
ASSY - FRONT SEAT RAIL DRIVER | FRONT SEATS | SEATS | INTERIOR |  | Bride Racing | 0 | Elisa Wong | 4 weeks | Merujen Chelvakumaran | ASSY - FRONT SEAT DRIVER |  |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT RAIL DRIVER | ASSY - FRONT SEAT DRIVER | [53 empty] | ASSY - FRONT SEAT RAIL DRIVER | Bride Racing | 0 | 4 | ASSY - FRONT SEAT DRIVER
ASSY - FRONT SEAT PASSENGER | FRONT SEATS | SEATS | INTERIOR |  | Sunswift |  | Anubhav Sharma | 4 weeks | Merujen Chelvakumaran |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT PASSENGER | ASSY - FRONT SEAT PASSENGER | [53 empty] | ASSY - FRONT SEAT PASSENGER | Sunswift | 0 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER
ASSY - FRONT SEAT DRIVER | FRONT SEATS | SEATS | INTERIOR |  | Sunswift |  | Anubhav Sharma | 4 weeks | Merujen Chelvakumaran |  |  | ASSY - FRONT SEAT RAIL DRIVER | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT RAIL DRIVER | ASSY - FRONT SEAT DRIVER | [53 empty] | ASSY - FRONT SEAT DRIVER | Sunswift | 0 | 4 |  | ASSY - FRONT SEAT RAIL DRIVER
ASSY - FRONT TOP WISHBONE - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT TOP WISHBONE - RH | SUNSWIFT | 2 | 2 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB
ASSY - FRONT TOP WISHBONE - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT TOP WISHBONE - LH | SUNSWIFT | 2 | 2 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB
ASSY - FRONT TIEROD - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - STEERING RACK | ASSY - STEERING COLUMN | [52 empty] | ASSY - FRONT TIEROD - RH | SUNSWIFT | 2 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - FRONT TIEROD - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - STEERING RACK | ASSY - STEERING COLUMN | [52 empty] | ASSY - FRONT TIEROD - LH | SUNSWIFT | 2 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - FRONT PUSHROD RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  |  |  | Oliver Freeman |  | Niamh Maybloom | - |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT PUSHROD RH | 0 | 0 | 0
ASSY - FRONT PUSHROD LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  |  |  | Oliver Freeman |  | Niamh Maybloom | - |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT PUSHROD LH | 0 | 0 | 0
ASSY - FRONT LOWER WISHBONE - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT LOWER WISHBONE - RH | SUNSWIFT | 2 | 2 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB
ASSY - FRONT LOWER WISHBONE - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB | [53 empty] | ASSY - FRONT LOWER WISHBONE - LH | SUNSWIFT | 2 | 2 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB
ASSY - FRONT UPRIGHT - RH | FRONT UPRIGHTS | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE | ASSY - FRONT BRAKE DISC | ASSY - FRONT DAMPER | ASSY - FRONT UPPER WISHBONE | ASSY - FRONT LOWER WISHBONE | [49 empty] | ASSY - FRONT UPRIGHT - RH | SUNSWIFT | 4 | 2 | ASSY - FRONT WHEEL
ASSY - FRONT UPRIGHT - LH | FRONT UPRIGHTS | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE | ASSY - FRONT BRAKE DISC | ASSY - FRONT DAMPER | ASSY - FRONT UPPER WISHBONE | ASSY - FRONT LOWER WISHBONE | [49 empty] | ASSY - FRONT UPRIGHT - LH | SUNSWIFT | 4 | 2 | ASSY - FRONT WHEEL
ASSY - FRONT WHEEL | FRONT WHEEL | FRONT SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - FRONT QUARTER PANEL ASSY - REAR VISION CAMERA |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | [54 empty] | ASSY - FRONT WHEEL | SUNSWIFT | 0 | 2 | ASSY - FRONT QUARTER PANELASSY | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC
ASSY - HAND BRAKE | HANDBRAKE | BRAKES | VEHICLE DYNAMICS |  | SUNSWIFT |  | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC, ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER |  | ASSY CHASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE | ASSY - REAR UPRIGHT | ASSY - CHASSIS BRAKE LINE | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE CALIPER | [52 empty] | ASSY - HAND BRAKE | SUNSWIFT | 0 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC, ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER | ASSY - HASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE
ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | N/A |  | N/A | ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3
ASSY - FATIGUE MONITORING SYSTEM | FATIGUE MONITORING SYSTEM | ADAS | EMBEDDED SYSTEMS |  | Sunswift |  | N/A |  | N/A | ASSY - OCCUPANT CELL TUB |  | N/A | [56 empty] | ASSY - FATIGUE MONITORING SYSTEM | Sunswift | 0 | 0 | ASSY - OCCUPANT CELL TUB
ASSY - EMBEDDED HIGH LEVEL SOFTWARE | EMBEDDED HIGH LEVEL SOFTWARE | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  | Henry Jiang | 5 Weeks | N/A | ASSY - MAIN COMPUTER |  | N/A | INST - MAIN COMPUTER | INST - EMBEDDED HIGH LEVEL SOFTWARE | [54 empty] | ASSY - EMBEDDED HIGH LEVEL SOFTWARE | Sunswift | 0 | 5 | ASSY - MAIN COMPUTER
ASSY - DRIVE CONTROL UNIT SOFTWARE | DRIVE CONTROL SYSTEMS | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Months + | N/A | ASSY - DRIVE CONTROL UNIT |  | N/A | ASSY - DRIVE CONTROL UNIT | ASSY - DRIVE CONTROL UNIT SOFTWARE | [54 empty] | ASSY - DRIVE CONTROL UNIT SOFTWARE | Sunswift | 0 | 12 | ASSY - DRIVE CONTROL UNIT
ASSY - DRIVE CONTROL UNIT | DRIVE CONTROL SYSTEMS | EMBEDDED | EMBEDDED SYSTEMS |  | Sunswift |  | N/A | 0 (REDUNDANT) | N/A | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH |  | N/A | ASSY - REAR BOOT | ASSY - DRIVE CONTROL UNIT | [54 empty] | ASSY - DRIVE CONTROL UNIT | Sunswift | 0 | 0 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH
ASSY - DOOR CONTROL BOARD - RH - CODE | DOORS | DOORS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | ASSY - DOOR CONTROL BOARD - RH |  | N/A | ASSY - DOOR CONTROL BOARD - LH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3 | ASSY - DOOR CONTROL BOARD - RH
ASSY - DOOR CONTROL BOARD - RH | DOORS | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 5 Weeks | N/A | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH |  | N/A | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH | ASSY - DOOR CONTROL BOARD - RH | [53 empty] | ASSY - DOOR CONTROL BOARD - RH | Sunswift | 0 | 5 | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH
ASSY - HUMAN MACHINE INTERFACE (HMI) MVP | HUMAN MACHINE INTERFACE | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - DASHBOARD STRUCTURE |  | ASSY - INFOTAINMENT MVP | [56 empty] | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP | Sunswift | 0 | 0 | ASSY - DASHBOARD STRUCTURE | ASSY - INFOTAINMENT MVP
ASSY - HUMAN MACHINE INTERFACE (HMI) | HUMAN MACHINE INTERFACE | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - HUMAN MACHINE INTERFACE (HMI) | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - POWER ELECTRONICS | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | [65 empty] | ASSY - POWER ELECTRONICS | 0 | 0 | 0
ASSY - HYDROGEN SENSOR ARRAY | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT |  | TBD (sensor supplier) |  | Adit | 8 weeks | Ali Ali | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | PRESSURE REGULATION & SAFETY | HYDROGEN SUPPLY LINE | FUEL CELL STACK | [53 empty] | ASSY - HYDROGEN SENSOR ARRAY | TBD (sensor supplier) | 0 | 8 | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY
ASSY - HYDROGEN CONTROL LOGIC | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT |  | Sunswift + External Supplier/Partner (unknown) |  | Mohammad | 8 weeks | Ali Ali | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN CONTROL SYSTEM | HYDROGEN SENSOR ARRAY | FUEL CELL STACK | HYDROGEN CONTROL SYSTEM | [53 empty] | ASSY - HYDROGEN CONTROL LOGIC | Sunswift + External Supplier/Partner (unknown) | 0 | 8 | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL SYSTEM
ASSY - HYDROGEN CONTROL SYSTEM | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT |  | Siltrax, External Supplier/Partner (unknown) |  | Adit | 8 weeks | Ali Ali | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS, ASSY - FC ELECTRICAL CONNECTIONS | ASSY - HYDROGEN CONTROL LOGIC, ASSY - FC ELECTRICAL CONNECTIONS |  | HYDROGEN CONTROL LOGIC | ECS | FC ELECTRICAL CONNECTIONS | [53 empty] | ASSY - HYDROGEN CONTROL SYSTEM | Siltrax, External Supplier/Partner (unknown) | 0 | 8 | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS, ASSY - FC ELECTRICAL CONNECTIONS
ASSY - FUEL CELL ELECTRICAL CONNECTIONS | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT |  | Sunswift |  | Adit | 12 weeks | Parikant (Shivom) Shandil | ASSY - FUEL CELL STACK, ASSY - POWER ELECTRONICS |  | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | FUEL CELL STACK | POWER ELECTRONICS | [54 empty] | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | Sunswift | 0 | 12 | ASSY - FUEL CELL STACK, ASSY - POWER ELECTRONICS | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY
ASSY - FUEL CELL ANCILLARY SYSTEM | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | [65 empty] | ASSY - FUEL CELL ANCILLARY SYSTEM | 0 | 0 | 0
ASSY - P&ID AIR DOWNSTREAM LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Sunswift + Beswick + Swagelok |  | Liam | 8 weeks |  | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE, ASSY - P&ID AIR SUPPLY LINE |  |  | ASSY - REARWHEEL HUB AIR INTAKE | ASSY - HYDROGEN COMPARTMENT VENTILATION | [54 empty] | ASSY - P&ID AIR DOWNSTREAM LINE | Sunswift + Beswick + Swagelok | 0 | 8 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE, ASSY - P&ID AIR SUPPLY LINE
ASSY - HYDROGEN COMPARTMENT EXHAUST VENT | AIRFLOW & VENTING | HYDROGEN | ALT |  | Supplier |  |  | 8 weeks |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, HYDROGEN COMPARTMENT VENTILATION |  | ASSY - HYDROGEN SENSOR ARRAY | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN COMPARTMENT VENTILATION | [54 empty] | ASSY - HYDROGEN COMPARTMENT EXHAUST VENT | Supplier | 0 | 8 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN SENSOR ARRAY
ASSY - P&ID HYDROGEN RECYCLE STREAM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Siltrax |  | Kurtis | 16 weeks | Ali Ali | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN SENSOR ARRAY | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK | [54 empty] | ASSY - P&ID HYDROGEN RECYCLE STREAM | Siltrax | 0 | 16 | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK | ASSY - HYDROGEN SENSOR ARRAY
ASSY - P&ID HYDROGEN DOWNSTREAM LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Sunswift + Swagelok |  | Natalie | 8 weeks | Ali Ali | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT |  | ASSY - P&ID AIR SUPPLY LINE | HYDROGEN SUPPLY LINE | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK | [53 empty] | ASSY - P&ID HYDROGEN DOWNSTREAM LINE | Sunswift + Swagelok | 0 | 8 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT | ASSY - P&ID AIR SUPPLY LINE
ASSY - P&ID AIR SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Sunswift + Beswick + Swagelok |  | Liam | 8 weeks | Ali Ali | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - P&ID AIR DOWNSTREAM LINE | ASSY - OCCUPANT CELL SHUTDOWN VALVE | REARWHEEL HUB AIR INTAKE | AIR SOURCE | [54 empty] | ASSY - P&ID AIR SUPPLY LINE | Sunswift + Beswick + Swagelok | 0 | 8 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - OCCUPANT CELL SHUTDOWN VALVE
ASSY - OCCUPANT CELL SHUTDOWN VALVE | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT |  | Swagelok or equivalent supplier |  | Mohammad | 8 weeks | Ali Ali | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC |  |  | OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN CONTROL LOGIC | [54 empty] | ASSY - OCCUPANT CELL SHUTDOWN VALVE | Swagelok or equivalent supplier | 0 | 8 | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC
ASSY - OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT |  | Gas detection supplier (Honeywell/CityTech etc.) |  | Adit | 8 weeks | Ali Ali | ASSY - HYDROGEN COMPARTMENT STRUCTURE |  | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS | HYDROGEN COMPARTMENT STRUCTURE | [55 empty] | ASSY - OCCUPANT CELL HYDROGEN SENSOR | Gas detection supplier (Honeywell/CityTech etc.) | 0 | 8 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS
ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT |  | Internal + electrical team |  | Adit | 8 weeks | Ali Ali | ASSY - FC ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY |  |  | HYDROGEN SENSOR ARRAY | FC ELECTRICAL CONNECTIONS | [54 empty] | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | Internal + electrical team | 0 | 8 | ASSY - FC ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY
ASSY - HYDROGEN SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Swagelok |  | Mohammad | 8 weeks | Ali Ali | ASSY - PRESSURE REGULATION & SAFETY |  | ASSY - PURGE MANAGEMENT, ASSY - SENSOR ARRAY | PRESSURE REGULATION & SAFETY | [55 empty] | ASSY - HYDROGEN SUPPLY LINE | Swagelok | 0 | 8 | ASSY - PRESSURE REGULATION & SAFETY | ASSY - PURGE MANAGEMENT, ASSY - SENSOR ARRAY
ASSY - HYDROGEN STORAGE SYSTEM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  |  |  | Liam |  | Ali Ali | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE |  | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - P&ID AIR SUPPLY LINE | REARWHEEL HUB AIR INTAKE | AIR SOURCE | [54 empty] | ASSY - HYDROGEN STORAGE SYSTEM | 0 | 0 | 0 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - P&ID AIR SUPPLY LINE
ASSY - HYDROGEN PURGE MANAGEMENT | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Siltrax, Swagelok |  | Kurtis | 8 weeks | Ali Ali | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE |  | ASSY - P&ID HYDROGEN RECYCLE STREAM | FUEL CELL STACK | HYDROGEN SUPPLY LINE | [54 empty] | ASSY - HYDROGEN PURGE MANAGEMENT | Siltrax, Swagelok | 0 | 8 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE | ASSY - P&ID HYDROGEN RECYCLE STREAM
ASSY - HYDROGEN COOLING SYSTEM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Sunswift |  | Natalie | 8 weeks | Ali Ali | ASSY - FUEL CELL STACK, |  | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FC ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT | REAR FLUID MANAGEMENT | FRONT FLUID MANAGEMENT | FUEL CELL STACK | [53 empty] | ASSY - HYDROGEN COOLING SYSTEM | Sunswift | 0 | 8 | ASSY - FUEL CELL STACK | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FC ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT
ASSY - HEADS-UP DISPLAY | HEADS-UP DISPLAY | DASHBOARD | INTERIOR |  | Espresso conversation | 0 | Sebastian Moore |  |  |  |  | ASSY - DASHBOARD STRUCTURE | [56 empty] | ASSY - HEADS-UP DISPLAY | Espresso conversation | 0 | 0 |  | ASSY - DASHBOARD STRUCTURE
ASSY - HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  | Sunswift |  | Simeon | 8 weeks | Ali Ali | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE, ASSY - PRESSURE VESSEL SHELL | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE | [54 empty] | ASSY - HYDROGEN COMPARTMENT STRUCTURE | Sunswift | 0 | 8 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR
ASSY - FUEL CELL STACK | HYDROGEN FUEL CELL | HYDROGEN | ALT |  | Siltrax |  | Doha | 8 weeks | Parikant (Shivom) Shandil | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN SUPPLY LINE | HYDROGEN COOLING SYSTEM | BATTERY | [52 empty] | ASSY - FUEL CELL STACK | Siltrax | 0 | 8 | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE
ASSY - HEADLIGHT EXTERIOR - RH | HEADLIGHTS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks |  | ASSY - CENTRAL STOP LAMP, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - RH | [58 empty] | ASSY - HEADLIGHT EXTERIOR - RH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - RH
ASSY - HEADLIGHT EXTERIOR - LH | HEADLIGHTS | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks |  | ASSY - CENTRAL STOP LAMP, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - RH | [58 empty] | ASSY - HEADLIGHT EXTERIOR - LH | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - SIDE INDICATOR EXTERIOR - RH
ASSY - FUEL CELL SENSOR | HYDROGEN FUEL CELL | HYDROGEN | ALT | [65 empty] | ASSY - FUEL CELL SENSOR | 0 | 0 | 0
ASSY - FUEL CELL MONITORING SYSTEM | HYDROGEN FUEL CELL | HYDROGEN | ALT | [65 empty] | ASSY - FUEL CELL MONITORING SYSTEM | 0 | 0 | 0
ASSY - FUEL CELL COOLING SYSTEM | HYDROGEN FUEL CELL | HYDROGEN | ALT | [65 empty] | ASSY - FUEL CELL COOLING SYSTEM | 0 | 0 | 0
r | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | [65 empty] | #VALUE! | 0 | 0 | 0
ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT |  | Sunswift |  | Simeon | 8 weeks | Ali Ali |  |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL | REAR FLOOR | OCCUPANT CELL TUB | [54 empty] | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | Sunswift | 0 | 8 |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL
ASSY - PRESSURE VESSEL SHELL | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT |  | Coregas, Swagelok (if we custom buy), or alternate vendor |  | Doha | 8 weeks | Ali Ali | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY | PRESSURE VESSEL SUPPORT STRUCTURE | [55 empty] | ASSY - PRESSURE VESSEL SHELL | Coregas, Swagelok (if we custom buy), or alternate vendor | 0 | 8 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY
ASSY - PRESSURE REGULATION & SAFETY | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT |  | Swagelok (valves, PRD, tubing) |  | Doha | 12 weeks | Ali Ali | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE |  | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE | [54 empty] | ASSY - PRESSURE REGULATION & SAFETY | Swagelok (valves, PRD, tubing) | 0 | 12 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE
ASSY - PRESSURE MONITORING AND CONTROL | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | [65 empty] | ASSY - PRESSURE MONITORING AND CONTROL | 0 | 0 | 0
ASSY - FRONT FLUID MANAGEMENT | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK |  | Unknown | 3 Weeks | Tim | 4 Weeks | Niamh Maybloom | ASSY - BATTERY MODULE, ASSY - BATTERY PACK, ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX | ASSY - REAR FLUID MANAGEMENT | ASSY - CHASSIS VENTILATION, ASSY - OCCUPANT CELL TUB | ASSY - BATTERY | ASSY - OCCUPANT CELL TUB | ASSY - HVAC BOX | ASSY - THERMAL BOX | [52 empty] | ASSY - FRONT FLUID MANAGEMENT | Unknown | 3 | 4 | ASSY - BATTERY MODULE, ASSY - BATTERY PACK, ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX | ASSY - CHASSIS VENTILATION, ASSY - OCCUPANT CELL TUB
ASSY - FRONT CRASH STRUCTURE | CRASH STRUCTURES | CHASSIS | CHASSIS & BODYWORK |  | Calm Aluminium | 0 | John Zhu | 4 Weeks | Sushrut Mogarkar |  | ASSY - REAR CRASH STRUCTURE | ASSY - OCCUPANT CELL TUB | [56 empty] | ASSY - FRONT CRASH STRUCTURE | Calm Aluminium | 0 | 4 |  | ASSY - OCCUPANT CELL TUB
ASSY - DOOR CONTROL BOARD - LH - CODE | DOORS | DOORS | EMBEDDED SYSTEMS |  | Sunswift |  |  | 3 Weeks | N/A | ASSY - DOOR CONTROL BOARD - LH |  | N/A | ASSY - DOOR CONTROL BOARD - LH - CODE | [55 empty] | #VALUE! | Sunswift | 0 | 3 | ASSY - DOOR CONTROL BOARD - LH
ASSY - DOOR CONTROL BOARD - LH | DOORS | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 5 Weeks | N/A | ASSY - DOOR HINGE - LH , ASSY - DOOR SHELL - LH |  | N/A | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH | ASSY - DOOR CONTROL BOARD - LH | [53 empty] | ASSY - DOOR CONTROL BOARD - LH | Sunswift | 0 | 5 | ASSY - DOOR HINGE - LH, ASSY - DOOR SHELL - LH
ASSY - INFOTAINMENT MVP | INFOTAINMENT | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP |  | ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - SUNSWIFT PHONE APP MVP | [56 empty] | ASSY - INFOTAINMENT MVP | Sunswift | 0 | 0 | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP | ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - SUNSWIFT PHONE APP MVP
ASSY - INFOTAINMENT | INFOTAINMENT | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - INFOTAINMENT | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - DOOR AUDIO - RH | AUDIO | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 8 Weeks | N/A |  |  | ASSY - DOOR SHELL - RH | [56 empty] | ASSY - DOOR AUDIO - RH | Sunswift | 0 | 8 |  | ASSY - DOOR SHELL - RH
ASSY - DOOR AUDIO - LH | AUDIO | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 8 Weeks | N/A |  |  | ASSY - DOOR SHELL - LH | [56 empty] | ASSY - DOOR AUDIO - LH | Sunswift | 0 | 8 |  | ASSY - DOOR SHELL - LH
ASSY - DOOR ACTUATOR BOARD - RH | DOORS | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 5 Weeks | N/A | N/A |  | N/A | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH | [54 empty] | ASSY - DOOR ACTUATOR BOARD - RH | Sunswift | 0 | 5
ASSY - DOOR ACTUATOR BOARD - LH | DOORS | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 5 Weeks | N/A | N/A |  | N/A | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH | [54 empty] | ASSY - DOOR ACTUATOR BOARD - LH | Sunswift | 0 | 5
ASSY - INTRANET MVP | INTRANET | INTERNAL TOOLS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | N/A |  | ASSY - TRACKSIDE RADIO COMMUNICATION MVP, ASSY - TELEMETRY MVP, ASSY - PERFORMANCE OPTIMISATION MVP, ASSY - TRIP ENERGY PREDICTION MVP | [56 empty] | ASSY - INTRANET MVP | Sunswift | 0 | 0 |  | ASSY - TRACKSIDE RADIO COMMUNICATION MVP, ASSY - TELEMETRY MVP, ASSY - PERFORMANCE OPTIMISATION MVP, ASSY - TRIP ENERGY PREDICTION MVP
ASSY - INTRANET | INTRANET | INTERNAL TOOLS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP | [58 empty] | ASSY - INTRANET | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP
ASSY - MOTOR UNIT - RH | MOTORS | MOTORS | POWERTRAIN |  | Schaeffler | 0 weeks (done) | Anthony Wang | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM | ASSY - MOTOR UNIT - RH | [55 empty] | ASSY - MOTOR UNIT - RH | Schaeffler | 0 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM
ASSY - MOTOR UNIT - LH | MOTORS | MOTORS | POWERTRAIN |  | Schaeffler | 0 weeks (done) | Anthony Wang | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM | ASSY - MOTOR UNIT - LH | [55 empty] | ASSY - MOTOR UNIT - LH | Schaeffler | 0 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM
ASSY - MOTOR MOUNTING FRAME - RH | MOTORS | MOTORS | POWERTRAIN |  | Sunswift | 0 weeks | Anthony Wang | 6 weeks | Niamh Maybloom | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - MOTOR MOUNTING FRAME - RH | [54 empty] | ASSY - MOTOR MOUNTING FRAME - RH | Sunswift | 0 | 6 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH
ASSY - MOTOR MOUNTING FRAME - LH | MOTORS | MOTORS | POWERTRAIN |  | Sunswift | 0 weeks | Anthony Wang | 6 weeks | Niamh Maybloom | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - MOTOR MOUNTING FRAME - LH | [54 empty] | ASSY - MOTOR MOUNTING FRAME - LH | Sunswift | 0 | 6 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH
ASSY - MPPT JUNCTION BOX | MPPT JUNCTION BOX | PV | ENERGY SYSTEMS |  | Sunswift? |  | Mohamad Bazzi | 2 weeks | N/A | ASSY - MPPT |  | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC | [56 empty] | ASSY - MPPT JUNCTION BOX | Sunswift? | 0 | 2 | ASSY - MPPT | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC
ASSY - MPPT | MPPT JUNCTION BOX | PV | ENERGY SYSTEMS |  | Sunswift? |  | Mohamad Bazzi | 4 weeks | N/A | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels |  | ASSY-occupant cell spider | [56 empty] | ASSY - MPPT | Sunswift? | 0 | 4 | ASSY - SOLAR ROOF ARRAY, ASSY - SOLAR BOOT ARRAY, ASSY - SOLAR BONNET ARRAY, ASSY - SHINGLED MATRIX PANELS | ASSY - CCUPANT CELL SPIDER
ASSY - FRONT CLAM SHELL | BODYPANELS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 7 Weeks | Sushrut Mogarkar | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LiDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB |  | ASSY - SOLAR BONNET ARRAY, ASSY - BONNET | ASSY - OCCUPANT CELL TUB | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - BONNET LOCKING BOARD | ASSY - BONNET | ASSY - DOOR SHELL - LH | ASSY - DOOR SHELL - RH | ASSY - DOOR HINGE - LH | ASSY - SIDE INDICATOR EXTERIOR - LH | ASSY - SIDE INDICATOR EXTERIOR - RH | ASSY - SIDE CAMERA - LH | ASSY - SIDE CAMERA - RH | ASSY - CHASSIS VENTILATION | FRONT RADAR | FRONT PARKING | [41 empty] | ASSY - FRONT CLAM SHELL | McConaghy, Scott Bader and Colan | 0 | 7 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LIDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB | ASSY - SOLAR BONNET ARRAY, ASSY - BONNET
ASSY - ELECTRIC WINDOWS - RH | ELECTRIC WINDOWS | BODYWORK | CHASSIS & BODYWORK |  | Unknown | 4 weeks | Kaityln Hua | 2 weeks | Ali Ali |  |  | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - RH | ASSY - DOOR CONTROL BOARD - RH | [54 empty] | ASSY - ELECTRIC WINDOWS - RH | Unknown | 4 | 2 |  | ASSY - DOOR SHELL - RH
ASSY - ELECTRIC WINDOWS - LH | ELECTRIC WINDOWS | BODYWORK | CHASSIS & BODYWORK |  | Unknown | 4 weeks | Kaityln Hua | 2 weeks | Ali Ali |  |  | ASSY - DOOR SHELL - LH | ASSY - DOOR SHELL - LH | ASSY - DOOR CONTROL BOARD - LH | [54 empty] | ASSY - ELECTRIC WINDOWS - LH | Unknown | 4 | 2 |  | ASSY - DOOR SHELL - LH
ASSY - ONBOARD CHARGING WIRING | ONBOARD CHARGING | CHARGING | ENERGY SYSTEMS |  | Inner Electric |  | Eric Lin | 2 weeks | N/A | ASSY - ONBOARD CHARGING INSTALLATION | [58 empty] | ASSY - ONBOARD CHARGING WIRING | Inner Electric | 0 | 2 | ASSY - ONBOARD CHARGING INSTALLATION
ASSY - ONBOARD CHARGER INSTALLATION | ONBOARD CHARGING | CHARGING | ENERGY SYSTEMS |  | Inner Electric |  | Eric Lin | 3 weeks | N/A |  |  | ASSY - ONBOARD CHARGER WIRING | [56 empty] | ASSY - ONBOARD CHARGER INSTALLATION | Inner Electric | 0 | 3 |  | ASSY - ONBOARD CHARGER WIRING
ASSY - CENTRAL STOP LAMP PCB | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Maria Lee | 4 Weeks (once started) | N/A | ASSY - CENTRAL STOP LAMP |  |  | ASSY - CENTRAL STOP LAMP PCB | [55 empty] | ASSY - CENTRAL STOP LAMP PCB | Sunswift | 0 | 4 | ASSY - CENTRAL STOP LAMP
ASSY - CENTRAL STOP LAMP CONTROLLER | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Maria Lee | 3 Weeks | N/A | ASSY - CENTRAL STOP LAMP | [58 empty] | ASSY - CENTRAL STOP LAMP CONTROLLER | Sunswift | 0 | 3 | ASSY - CENTRAL STOP LAMP
ASSY - THROTTLE PEDAL | PEDALS | PEDALS | INTERIOR |  | Sunswift |  | Jason Jin | 1 week | Merujen Chelvakumaran |  |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER | ASSY - PEDAL PRESS SENSOR | ASSY - THROTTLE PEDAL | [54 empty] | ASSY - THROTTLE PEDAL | Sunswift | 0 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER
ASSY - PEDAL BOX | PEDALS | PEDALS | INTERIOR |  | Sunswift |  | Jason Jin | 2 weeks | Sushrut Mogarkar | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR |  | ASSY - OCCUPANT CELL TUB | ASSY - OCCUPANT CELL TUB | ASSY - THROTTLE PEDAL | ASSY - BRAKE PEDAL | ASSY - PEDAL BOX | ASSY - MASTER CYLINDER | [51 empty] | ASSY - PEDAL BOX | Sunswift | 0 | 2 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR | ASSY - OCCUPANT CELL TUB
ASSY - BRAKE PEDAL | PEDALS | PEDALS | INTERIOR |  | Sunswift |  | Jason Jin | 1 week | Niamh Maybloom |  |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER | ASSY - FRONT MASTER CYLINDER | ASSY - BRAKE PEDAL | [54 empty] | ASSY - BRAKE PEDAL | Sunswift | 0 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER
ASSY - PERFORMANCE OPTIMISATION MVP | PERFORMANCE OPTIMISATION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | N/A | [58 empty] | ASSY - PERFORMANCE OPTIMISATION MVP | Sunswift | 0 | 0
ASSY - PERFORMANCE OPTIMISATION | PERFORMANCE OPTIMISATION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - PERFORMANCE OPTIMISATION | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - PWT HV WIRING - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Unknown | 4 weeks | Thomas Ngo | 2 weeks | Ali Ali | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH | ASSY - PWT HV WIRING - RH | [53 empty] | ASSY - PWT HV WIRING - RH | Unknown | 4 | 2 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH
ASSY - PWT HV WIRING - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Unknown | 4 weeks | Thomas Ngo | 2 weeks | Ali Ali | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH | ASSY - PWT HV WRING - LH | [53 empty] | ASSY - PWT HV WIRING - LH | Unknown | 4 | 2 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH
ASSY - INVERTER MOUNTING FRAME - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Sunswift | 0 weeks | Kabir Kohli | 6 weeks | Niamh Maybloom | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH | ASSY - INVERTER MOUNTING FRAME - RH | [53 empty] | ASSY - INVERTER MOUNTING FRAME - RH | Sunswift | 0 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH
ASSY - INVERTER MOUNTING FRAME - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Sunswift | 0 weeks | Kabir Kohli | 6 weeks | Ali Ali | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH | ASSY - INVERTER MOUNTING FRAME - LH | [53 empty] | ASSY - INVERTER MOUNTING FRAME - LH | Sunswift | 0 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH
ASSY - INVERTER - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Schaeffler | 0 weeks (done) | Thomas Ngo | 2 weeks | Ali Ali | ASSY - MOTOR UNIT - RH |  | ASSY - HYDROGEN COOLING SYSTEM | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH | [54 empty] | ASSY - INVERTER - RH | Schaeffler | 0 | 2 | ASSY - MOTOR UNIT - RH | ASSY - HYDROGEN COOLING SYSTEM
ASSY - INVERTER - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN |  | Schaeffler | 0 weeks (done) | Thomas Ngo | 2 weeks | Ali Ali | ASSY - MOTOR UNIT - LH |  | ASSY - HYDROGEN COOLING SYSTEM | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH | [54 empty] | ASSY - INVERTER - LH | Schaeffler | 0 | 2 | ASSY - MOTOR UNIT - LH | ASSY - HYDROGEN COOLING SYSTEM
ASSY - REAR MASTER CYLINDER RESERVOIR | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER | ASSY - FRONT MASTER CYLINDER RESERVOIR | [53 empty] | ASSY - REAR MASTER CYLINDER RESERVOIR | Compfriction/AP Racing | 0 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - REAR MASTER CYLINDER | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom |  |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR BRAKE LINE | ASSY - FRONT UPRIGHT | [54 empty] | ASSY - REAR MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 |  | ASSY - OCCUPANT CELL TUB
ASSY - REAR BRAKE LINE | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - REAR QUARTER PANEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE DISC | [54 empty] | ASSY - REAR BRAKE LINE | Compfriction/AP Racing | 0 | 2 | ASSY - REAR QUARTER PANEL | ASSY - OCCUPANT CELL TUB
ASSY - REAR BRAKE DISC | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL |  | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE | [53 empty] | ASSY - REAR BRAKE DISC | Compfriction/AP Racing | 0 | 2 | ASSY - REAR WHEEL | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE
ASSY - REAR BRAKE CALIPER - RH | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC |  | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | [53 empty] | ASSY - REAR BRAKE CALIPER - RH | Compfriction/AP Racing | 0 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE
ASSY - REAR BRAKE CALIPER - LH | REAR BRAKES | BRAKES | VEHICLE DYNAMICS |  | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC |  | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | [53 empty] | ASSY - REAR BRAKE CALIPER - LH | Compfriction/AP Racing | 0 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE
ASSY - REAR TOP WISHBONE - RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL ASSY - REAR QUARTER PANEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR TOP WISHBONE - RH | SUNSWIFT | 0 | 2 | ASSY - REAR WHEELASSY | ASSY - OCCUPANT CELL TUB
ASSY - REAR TOP WISHBONE - LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL ASSY - REAR QUARTER PANEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR TOP WISHBONE - LH | SUNSWIFT | 0 | 2 | ASSY - REAR WHEELASSY | ASSY - OCCUPANT CELL TUB
ASSY - REAR TOELINK | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL ASSY - REAR QUARTER PANEL |  | - | ??? | [55 empty] | ASSY - REAR TOELINK | SUNSWIFT | 0 | 2 | ASSY - REAR WHEELASSY
ASSY - REAR LOWER WISHBONE RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL ASSY - REAR QUARTER PANEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR LOWER WISHBONE RH | SUNSWIFT | 0 | 2 | ASSY - REAR WHEELASSY | ASSY - OCCUPANT CELL TUB
ASSY - REAR LOWER WISHBONE LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT |  | Oliver Freeman | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL ASSY - REAR QUARTER PANEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR LOWER WISHBONE LH | SUNSWIFT | 0 | 2 | ASSY - REAR WHEELASSY | ASSY - OCCUPANT CELL TUB
ASSY - REAR DAMPER - RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | Bilstein | 0 | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL |  |  | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR DAMPER - RH | Bilstein | 0 | 2 | ASSY - REAR WHEEL
ASSY - REAR DAMPER - LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS |  | Bilstein | 0 | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL |  |  | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR DAMPER - LH | Bilstein | 0 | 2 | ASSY - REAR WHEEL
ASSY - REAR UPRIGHT - RH | REAR UPRIGHTS | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL |  | ASSY - REAR DAMPER - RH | ASSY - REAR SUSPENSION | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE DISC | ASSY - REAR DAMPER | ASSY - REAR UPPER WISHBONE | ASSY - REAR LOWER WISHBONE | [49 empty] | ASSY - REAR UPRIGHT - RH | SUNSWIFT | 4 | 2 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - RH
ASSY - REAR UPRIGHT - LH | REAR UPRIGHTS | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks | Niamh Maybloom | ASSY - REAR WHEEL |  | ASSY - REAR DAMPER - LH | ASSY - REAR SUSPENSION | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE DISC | ASSY - REAR DAMPER | ASSY - REAR UPPER WISHBONE | ASSY - REAR LOWER WISHBONE | [49 empty] | ASSY - REAR UPRIGHT - LH | SUNSWIFT | 4 | 2 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - LH
ASSY - CENTRAL STOP LAMP CASING | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Hitesh Bhuta | 4 Weeks | N/A | ASSY - CENTRAL STOP LAMP | [58 empty] | ASSY - CENTRAL STOP LAMP CASING | Sunswift | 0 | 4 | ASSY - CENTRAL STOP LAMP
ASSY - REAR WHEEL | REAR WHEEL | REAR SUSPENSION | VEHICLE DYNAMICS |  | SUNSWIFT | 4 weeks (?) | Madhav Katarya | 2 weeks | Niamh Maybloom | - |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE LH, ASSY - REAR LOWER WISHBONE RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT | [54 empty] | ASSY - REAR WHEEL | SUNSWIFT | 4 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE LH, ASSY - REAR LOWER WISHBONE RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE
ASSY - CENTRAL STOP LAMP | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS |  | Sunswift |  | Maria Lee | 3 Weeks | N/A | N/A |  | ASSY - CENTRAL STOP LAMP CASING, ASSY - CENTRAL STOP LAMP CONTROLLER | [56 empty] | ASSY - CENTRAL STOP LAMP | Sunswift | 0 | 3 |  | ASSY - CENTRAL STOP LAMP CASING, ASSY - CENTRAL STOP LAMP CONTROLLER
ASSY - C-V2X PCB | C-V2X | V2X | EMBEDDED SYSTEMS |  | Sunswift |  | N/A | 2 Months | N/A | N/A |  | N/A | ASSY - C-V2V ANTENNA | ASSY - C-V2V RADAR/LiDAR | [54 empty] | ASSY - C-V2X PCB | Sunswift | 0 | 8
ASSY - C-V2V RADAR/LiDAR | C-V2X | V2X | EMBEDDED SYSTEMS |  |  |  | N/A | 3 Months + | N/A |  |  | ASSY - FRONT CLAMSHELL | ASSY - FRONT BODY STRUCTURE | ASSY - C-V2V RADAR/LiDAR | [54 empty] | ASSY - C-V2V RADAR/LIDAR | 0 | 0 | 12 |  | ASSY - FRONT CLAMSHELL
ASSY - C-V2V ANTENNA | C-V2X | V2X | EMBEDDED SYSTEMS |  | Sunswift |  | N/A | 3 Weeks | N/A | N/A |  | N/A | ASSY - C-V2V ANTENNA | [55 empty] | ASSY - C-V2V ANTENNA | Sunswift | 0 | 3
Assy - Shingled Matrix Panels | Shingled/Solar Array | PV | ENERGY SYSTEMS |  | Sunswift | 0 | Parikant (Shivom) Shandil | 3 months + | Parikant (Shivom) Shandil |  |  | ASSY-boot, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BOOT | Assy - Shingled Matrix Panels | [54 empty] | ASSY - SHINGLED MATRIX PANELS | Sunswift | 0 | 12 |  | ASSY - OOT, ASSY - PPT, ASSY - C4 CABLING
ASSY - BOOT LOCKING BOARD | BOOT | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 4 Weeks | N/A | ASSY - BOOT |  | N/A | [56 empty] | ASSY - BOOT LOCKING BOARD | Sunswift | 0 | 4 | ASSY - BOOT
ASSY - BONNET LOCKING BOARD | BONNET | BODYWORK | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 4 Weeks | N/A | ASSY - BONNET |  | N/A | ASSY - BONNET | ASSY - BONNET LOCKING BOARD | [54 empty] | ASSY - BONNET LOCKING BOARD | Sunswift | 0 | 4 | ASSY - BONNET
ASSY - SOLAR ROOF ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS |  | Sundrive (cell supplier), Corning (or alt provider), McCognaughy (for lamination), REOO (alt., laminator provider) | 12 weeks | Harry Schaut | 8 weeks | Parikant (Shivom) Shandil |  |  | ASSY-occupant cell spider, ASSY - occupant cell tub, ASSY-ceiling, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - SOLAR ROOF ARRAY | [55 empty] | ASSY - SOLAR ROOF ARRAY | Sundrive (cell supplier), Corning (or alt provider), McCognaughy (for lamination), REOO (alt., laminator provider) | 12 | 8 |  | ASSY - CCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - EILING, ASSY - PPT, ASSY - C4 CABLING
ASSY - SOLAR BOOT ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS |  | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 weeks | Harry Schaut | 8 Weeks | Parikant (Shivom) Shandil |  |  | ASSY-boot, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BOOT | ASSY - SOLAR BOOT ASSAY | [54 empty] | ASSY - SOLAR BOOT ARRAY | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 | 8 |  | ASSY - OOT, ASSY - PPT, ASSY - C4 CABLING
ASSY - SOLAR BONNET ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS |  | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 weeks | Harry Schaut | 8 Weeks | Parikant (Shivom) Shandil |  |  | ASSY-bonnet, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BONNET | ASSY - SOLAR BONNET ARRAY | [54 empty] | ASSY - SOLAR BONNET ARRAY | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 | 8 |  | ASSY - ONNET, ASSY - PPT, ASSY - C4 CABLING
ASSY - MC4 Cabling | SOLAR ARRAY | PV | ENERGY SYSTEMS |  | None, by off shelf, Maybe SunDrive | 0 | Harry Schaut | 4 Weeks | N/A | ASSY- solar boot array, ASSY- Solar bonnet array, ASSY- Solar roof array, ASSY- Shingled Matrix Panels |  | ASSY- Occupant cell spider, ASSY- boot, ASSY- Bonnet, ASSY - MPPT | ASSY - SOLAR BONNET ARRAY | ASSY - SOLAR ROOF ARRAY | ASSY - SOLAR BOOT ARRAY | Assy - Shingled Matrix Panels | ASSY - MPPT | ASSY - MC4 Cabling | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | [48 empty] | ASSY - MC4 CABLING | None, by off shelf, Maybe SunDrive | 0 | 4 | ASSY - SOLAR BOOT ARRAY, ASSY - SOLAR BONNET ARRAY, ASSY - SOLAR ROOF ARRAY, ASSY - SHINGLED MATRIX PANELS | ASSY - OCCUPANT CELL SPIDER, ASSY - BOOT, ASSY - BONNET, ASSY - MPPT
ASSY - STEERING COLUMN | STEERING COLUMN | STEERING | VEHICLE DYNAMICS |  | Flaming River (1st Option) | 4 weeks (?) | Oliver Freeman | 2 weeks | Sushrut Mogarkar | ASSY - STEERING WHEEL, ASSY - STEERING RACK |  | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE | ASSY - STEERING RACK | ASSY - STEERING WHEEL | [54 empty] | ASSY - STEERING COLUMN | Flaming River (1st Option) | 4 | 2 | ASSY - STEERING WHEEL, ASSY - STEERING RACK | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE
ASSY - STEERING RACK | STEERING RACK | STEERING | VEHICLE DYNAMICS |  | Flaming River (1st Option) | 4 weeks (?) | Oliver Freeman | 2 weeks | Sushrut Mogarkar |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - STEERING COLUMN | ASSY - STEERING COLUMN | [55 empty] | ASSY - STEERING RACK | Flaming River (1st Option) | 4 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - STEERING COLUMN
ASSY - BLINDSPOT MONITORING SENSOR - RH | BLIND SPOT MONITORING | ADAS | EMBEDDED SYSTEMS |  | Sunswift |  | EMB Member | 8 Weeks | N/A | ASSY - SIDE CAMERA - RH, ASSY - SENSOR MOTHERBOARD - FL ASSY - SENSOR MOTHERBOARD- FR ASSY - SENSOR MOTHERBOARD - BL ASSY - SENSOR MOTHERBOARD- BR |  | N/A | [56 empty] | ASSY - BLINDSPOT MONITORING SENSOR - RH | Sunswift | 0 | 8 | ASSY - SIDE CAMERA - RH, ASSY - SENSOR MOTHERBOARD
ASSY - BLINDSPOT MONITORING SENSOR - LH | BLIND SPOT MONITORING | ADAS | EMBEDDED SYSTEMS |  | Sunswift |  | EMB Member | 8 Week | N/A | ASSY - SIDE CAMERA - LH, ASSY - SENSOR MOTHERBOARD - FL ASSY - SENSOR MOTHERBOARD- FR ASSY - SENSOR MOTHERBOARD - BL ASSY - SENSOR MOTHERBOARD- BR |  | N/A | [56 empty] | ASSY - BLINDSPOT MONITORING SENSOR - LH | Sunswift | 0 | 8 | ASSY - SIDE CAMERA - LH, ASSY - SENSOR MOTHERBOARD
ASSY - STEERING WHEEL | STEERING WHEEL | STEERING | INTERIOR |  | Sunswift |  | Anubhav Sharma | 4 weeks | Sushrut Mogarkar | ASSY-STEERING WHEEL PCB |  | ASSY - DRIVER DISPLAY (BUTTONS & FUNCTIONS), ASSY - STEERING COLUMN | ASSY - STEERING COLUMN | ASSY - STEERING WHEEL | [54 empty] | ASSY - STEERING WHEEL | Sunswift | 0 | 4 | ASSY - TEERING WHEEL PCB | ASSY - DRIVER DISPLAY (BUTTONS & FUNCTIONS), ASSY - STEERING COLUMN
ASSY - DOOR SHELL - RH | DOORS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Kaityln Hua | 3 weeks | Sushrut Mogarkar | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH |  | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - RH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR HINGE - RH | ASSY - DOOR AUDIO - RH | ASSY - DOOR CONTROL BOARD - RH | ASSY - DOOR ACTUATOR BOARD - RH | ASSY - INNER DOOR HANDLE - RH | ASSY - OUTER DOOR HANDLE - RH | ASSY - DOOR LATCH - RH | ASSY - ELECTRIC WINDOWS - RH | ASSY - FRONT BODY STRUCTURE | [45 empty] | ASSY - DOOR SHELL - RH | McConaghy, Scott Bader and Colan | 0 | 3 | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - RH
ASSY - SUNSWIFT PHONE APP MVP | SUNSWIFT PHONE APP | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen | 3 months + | N/A | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP, ASSY - INFOTAINMENT MVP, ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - APPLE & ANDROID COMPATABILITY MVP | [58 empty] | ASSY - SUNSWIFT PHONE APP MVP | Sunswift | 0 | 12 | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP, ASSY - INFOTAINMENT MVP, ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - APPLE & ANDROID COMPATABILITY MVP
ASSY - SUNSWIFT PHONE APP | SUNSWIFT PHONE APP | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen | 3 months + | N/A |  |  | ASSY - INTRANET | [56 empty] | ASSY - SUNSWIFT PHONE APP | Sunswift | 0 | 12 |  | ASSY - INTRANET
ASSY - DOOR SHELL - LH | DOORS | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Kaityln Hua | 3 weeks | Sushrut Mogarkar | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH |  | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - LH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR HINGE - LH | ASSY - DOOR AUDIO - LH | ASSY - DOOR CONTROL BOARD - LH | ASSY - DOOR ACTUATOR BOARD - LH | ASSY - INNER DOOR HANDLE - LH | ASSY - OUTER DOOR HANDLE - LH | ASSY - DOOR LATCH - LH | ASSY - ELECTRIC WINDOWS - LH | ASSY - FRONT BODY STRUCTURE | [45 empty] | ASSY - DOOR SHELL - LH | McConaghy, Scott Bader and Colan | 0 | 3 | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - LH
ASSY - DOOR LATCH - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 week | Sushrut Mogarkar |  |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - INNER DOOR HANDLE - RH | ASSY - OUTER DOOR HANDLE - RH |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR QUARTER PANEL - RH | ASSY - DOOR CONTROL BOARD - RH | [49 empty] | ASSY - DOOR LATCH - RH | Chevalier | 4 | 2 |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB
ASSY - AUDIO CONTROL SYSTEM | AUDIO | AUDIO | EMBEDDED SYSTEMS |  | Sunswift |  | Sebastian Moore | 2 Months | N/A | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER |  | N/A | ASSY - DOOR AUDIO - LH | ASSY - DOOR AUDIO - RH | ASSY - SUBWOOFER | ASSY - AUDIO CONTROL SYSTEM | [52 empty] | ASSY - AUDIO CONTROL SYSTEM | Sunswift | 0 | 8 | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER
ASSY - ACTIVE AERO CONTROL PCB | ACTIVE AERO | AERO | EMBEDDED SYSTEMS |  | Sunswift |  | Hamish Hunter | 6 Weeks (when started) | N/A | ASSY - ACTIVE AERO MOTORS |  | N/A | ASSY - ACTIVE AERO MOTORS | ASSY-ACTIVE AERO CONTROLI PCB | [54 empty] | ASSY - ACTIVE AERO CONTROL PCB | Sunswift | 0 | 6 | ASSY - ACTIVE AERO MOTORS
ASSY - ABS BRAKES CONTROL SYSTEM | ABS BRAKES | ADAS | EMBEDDED SYSTEMS |  | Bosch, or just Sunswift | 0 | Hamish Hunter | 4 Weeks | N/A | ASSY - EMBEDDED HIGH LEVEL SOFTWARE, ASSY - DRIVE CONTROL UNIT |  | N/A | [56 empty] | ASSY - ABS BRAKES CONTROL SYSTEM | Bosch, or just Sunswift | 0 | 4 | ASSY - EMBEDDED HIGH LEVEL SOFTWARE, ASSY - DRIVE CONTROL UNIT
ASSY - SENSOR MOTHERBOARD - FR | SENSORS | SENSORS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 3 Months + | N/A | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - FR | [55 empty] | ASSY - SENSOR MOTHERBOARD | Sunswift | 0 | 12
ASSY - TELEMETRY MVP | TELEMETRY | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | AWS |  | Nathan Nguyen | 3 months + | N/A | ASSY - PERFORMANCE OPTIMSATION MVP |  | ASSY - SUNSWIFT PHONE APP MVP | [56 empty] | ASSY - TELEMETRY MVP | AWS | 0 | 12 | ASSY - PERFORMANCE OPTIMSATION MVP | ASSY - SUNSWIFT PHONE APP MVP
ASSY - DOOR LATCH - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK |  | Chevalier | 4 weeks | Melissa Thein | 2 weeks | Sushrut Mogarkar |  |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH | ASSY - INNER DOOR HANDLE - LH | ASSY - OUTER DOOR HANDLE - LH |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR QUARTER PANEL - LH | ASSY - DOOR CONTROL BOARD - LH | [49 empty] | ASSY - DOOR LATCH - LH | Chevalier | 4 | 2 |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB
ASSY - BMS WIRING | BATTERY | BATTERY | ENERGY SYSTEMS |  | Unknown | 8 weeks | David Thirugnanaraj | 3 weeks |  | ASSY - BATTERY PACK |  | ASSY - CONTROL LOGIC | [56 empty] | ASSY - BMS WIRING | Unknown | 8 | 3 | ASSY - BATTERY PACK | ASSY - CONTROL LOGIC
ASSY - BLUETOOTH CONNECTIVITY MVP | BLUETOOTH CONNECTIVITY | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  |  | ASSY - INFOTAINMENT MVP |  | ASSY - APPLE & ANDROID COMPATABILITY MVP, ASSY - SUNSWIFT PHONE APP MVP | [56 empty] | ASSY - BLUETOOTH CONNECTIVITY MVP | Sunswift | 0 | 0 | ASSY - INFOTAINMENT MVP | ASSY - APPLE & ANDROID COMPATABILITY MVP, ASSY - SUNSWIFT PHONE APP MVP
ASSY - BLUETOOTH CONNECTIVITY | BLUETOOTH CONNECTIVITY | HMI | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - BLUETOOTH CONNECTIVITY | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - TELEMETRY | TELEMETRY | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | AWS |  | Nathan Nguyen | 3 months + | N/A | ASSY - PERFORMANCE OPTIMSATION, ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - TELEMETRY | AWS | 0 | 12 | ASSY - PERFORMANCE OPTIMSATION, ASSY - SUNSWIFT PHONE APP MVP
ASSY - DOOR HINGE - RH | DOORS | BODYWORK | CHASSIS & BODYWORK |  | Stabillus | 1 week | Jack Wilson | 3 weeks | Sushrut Mogarkar |  |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD -RH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | [53 empty] | ASSY - DOOR HINGE - RH | Stabillus | 1 | 3 |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD -RH
ASSY - DOOR HINGE - LH | DOORS | BODYWORK | CHASSIS & BODYWORK |  | Stabillus | 1 week | Jack Wilson | 3 weeks | Sushrut Mogarkar |  |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH | [53 empty] | ASSY - DOOR HINGE - LH | Stabillus | 1 | 3 |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH
ASSY - CHASSIS VENTILATION | VENTILATION | CHASSIS | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Peleg Mondry Cohen | 8 Weeks | Sushrut Mogarkar | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS |  | ASSY - FRONT CLAMSHELL | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - THERMAL BOX | ASSY - FRONT CRASH STRUCTURE | [52 empty] | ASSY - CHASSIS VENTILATION | McConaghy, Scott Bader and Colan | 0 | 8 | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ASSY - FRONT CLAMSHELL
ASSY - CHASSIS SUBFRAME | SUBFRAMES | CHASSIS | CHASSIS & BODYWORK |  | Divergent | 8 weeks | Aditya Bansal | 4 Weeks | Sushrut Mogarkar | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH |  | ASSY - OCCUPANT CELL TUB | ASSY - MOTOR UNIT - LH | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - LH | ASSY - GEARBOX - RH | ASSY - AXLE CV - LH | ASSY - AXLE CV - RH | [50 empty] | ASSY - CHASSIS SUBFRAME | Divergent | 8 | 4 | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB
ASSY - TRACKSIDE RADIO COMMUNICATION MVP | TRACKSIDE RADIO COMMUNICATION | COMMUNICATIONS | TECHNICAL SUPPORT SYSTEMS |  | D2N |  | Nathan Nguyen |  | N/A | N/A | [58 empty] | ASSY - TRACKSIDE RADIO COMMUNICATION MVP | D2N | 0 | 0
ASSY - TRACKSIDE RADIO COMMUNICATION | TRACKSIDE RADIO COMMUNICATION | COMMUNICATIONS | TECHNICAL SUPPORT SYSTEMS |  | D2N |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP | [58 empty] | ASSY - TRACKSIDE RADIO COMMUNICATION | D2N | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP
ASSY - GEARBOX - RH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Beginning Design | Sunswift | 8 weeks | Jack Lawson | 3 weeks | Niamh Maybloom | ASSY - MOTOR UNIT - RH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - RH | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - RH | [54 empty] | ASSY - GEARBOX - RH | Sunswift | 8 | 3 | ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - RH
ASSY - GEARBOX - LH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Beginning Design | Sunswift | 8 weeks | Jack Lawson | 3 weeks | Niamh Maybloom | ASSY - MOTOR UNIT - LH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - LH | ASSY - MOTOR UNIT - LH | ASSY - GEARBOX - LH | [54 empty] | ASSY - GEARBOX - LH | Sunswift | 8 | 3 | ASSY - MOTOR UNIT - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - LH
ASSY - AXLE CV - RH | TRANSMISSION | TRANSMISSION | POWERTRAIN |  | Ricardo/Off the shelf | 8 weeks | Jack Lawson | 6 weeks | Ali Ali | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLES | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - RH | ASSY - AXLE CV - RH | [53 empty] | ASSY - AXLE CV - RH | Ricardo/Off the shelf | 8 | 6 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLES
ASSY - AXLE CV - LH | TRANSMISSION | TRANSMISSION | POWERTRAIN |  | Ricardo/Off the shelf | 8 weeks | Jack Lawson | 6 weeks | Ali Ali | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | ASSY - MOTOR UNIT - LH | ASSY - GEARBOX - LH | ASSY - AXLE CV - LH | [53 empty] | ASSY - AXLE CV - LH | Ricardo/Off the shelf | 8 | 6 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME
ASSY - TRIP ENERGY PREDICTION MVP | TRIP ENERGY PREDICTION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - TELEMETRY MVP, ASSY - INFOTAINMENT MVP | [58 empty] | ASSY - TRIP ENERGY PREDICTION MVP | Sunswift | 0 | 0 | ASSY - TELEMETRY MVP, ASSY - INFOTAINMENT MVP
ASSY - TRIP ENERGY PREDICTION | TRIP ENERGY PREDICTION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS |  | Sunswift |  | Nathan Nguyen |  | N/A | ASSY - SUNSWIFT PHONE APP MVP, ASSY - TELEMETRY, ASSY - INFOTAINMENT | [58 empty] | ASSY - TRIP ENERGY PREDICTION | Sunswift | 0 | 0 | ASSY - SUNSWIFT PHONE APP MVP, ASSY - TELEMETRY, ASSY - INFOTAINMENT
ASSY - CENTRAL STOP LAMP | CENTRAL STOP LAMP | LIGHTS | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks | N/A |  |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH | ASSY - REAR BOOT | ASSY - CENTRAL STOP LAMP PCB | ASSY - CENTRAL STOP LAMP | [53 empty] | ASSY - CENTRAL STOP LAMP | Sunswift | 0 | 3 |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - HEADLIGHT EXTERIOR - LH
ASSY - BOOT | BOOT | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader, Colan and Stabillus | 1 week | Luca (PQ) Nguyen | 5 Weeks | Ali Ali | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH |  | ASSY - BOOT LOCKING BOARD | ASSY - SOLAR BOOT ASSAY | ASSY - CENTRAL STOP LAMP | ASSY - PRESSURE VESSEL SHELL | Hydrogen venting | ASSY - BOOT LOCKING BOARD | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | ASSY - CENTRAL STOP LAMP | [46 empty] | ASSY - BOOT | McConaghy, Scott Bader, Colan and Stabillus | 1 | 5 | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT LOCKING BOARD
ASSY - BONNET | BONNET | BODYWORK | CHASSIS & BODYWORK |  | McConaghy, Scott Bader and Colan | 0 | Luca (PQ) Nguyen | 4 Weeks |  | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAMSHELL |  | ASSY - BONNET LOCKING BOARD | ASSY - SOLAR BONNET ARRAY | ASSY - FRONT BODY STRUCTURE | [54 empty] | ASSY - BONNET | McConaghy, Scott Bader and Colan | 0 | 4 | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAMSHELL | ASSY - BONNET LOCKING BOARD
ASSY - ACTIVE AERO MOTORS | ACTIVE AERO | AERO | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Melissa Thein | 2 weeks | Ali Ali | [59 empty] | ASSY - ACTIVE AERO MOTORS | Sunswift | 0 | 2
ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ACTIVE AERO | AERO | CHASSIS & BODYWORK |  | Sunswift | 0 Wekes | Melissa Thein | 3 weeks | Ali Ali |  |  |  | ASSY - ACTIVE AERO MOTORS | ASSY - CHASSIS VENTILATION | ASSY - FRONT BODY STRUCTURE | [53 empty] | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | Sunswift | 0 | 3
ASSY - SENSOR MOTHERBOARD - BR | SENSORS | SENSORS | EMBEDDED SYSTEMS |  | Sunswift |  | Angus Macdonald | 3 Months + | N/A | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - BR | [55 empty] | ASSY - SENSOR MOTHERBOARD - BR | Sunswift | 0 | 12
ASSY - HORN PCB CODE | HORN | HORN | EMBEDDED SYSTEMS |  | Sunswift |  |  | 2 Weeks | N/A | N/A |  | N/A | ASSY - HORN PCB CODE | [55 empty] | ASSY - HORN PCB CODE | Sunswift | 0 | 2
ASSY - DOOR CARD STRCUTURE | DOORS | DOOR CARDS | INTERIOR |  | Sunswift | [63 empty] | ASSY - DOOR CARD STRCUTURE | Sunswift | 0 | 0
COLOUR CODING
Added in by project management but unordered
Added in by project management, ordered under correct project | [7 empty] | Needs accurate timeframe (added in with 14 days timeframe) |  | Needs dependencies added (added in with none)
Added in by Systems but unordered
Added in by Systems, ordered under project
Added in by ELT as new assembly
Needs Clarification
IF THERE ARE NO DEPENDENCIES, WRITE N/A OR "-"
Note on A40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Side cameras in workshop?
Note on K70: Henry Jiang: Any dependencies from other assemblies/projects?
Note on A82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reservoir assembly repeated twice -> check if just cylinder dependencies are the same
Note on M109: Andy Danis:
Note on I110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design timeline, design basically finished
Note on A132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove all red ALT assemblies
Note on A147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete all red assemblies relating to ALT
Note on A166: Henry Jiang: Assuming clamshell means fenders + bumper in one so adding to front bumper project
Note on A185: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please Check

## SR8 MASTER
SUNSWIFT 8 - PARTS MANAGEMENT SCREEN
DEPARTMENT | SECTION | PROJECT # | PROJECT | APPROVED | STATUS | ONCAR SOFTWARE OFFCAR | BOM LEVEL | PART NUMBER | PART DESCRIPTION | QTY PER | CAR BUILD | SHAKE-DOWN | TRACK TEST 01 | TRACK TEST 02 | CAR LAUNCH | PRESS LAUNCH | ROAD TEST 01 | ST | ADR'S | ENG DWG REQ | EST WEIGHT kg | ACTUAL WEIGHT kg | PROCUREMENT | SUPPLIER / PARTNER | ASSYEMBLY EST COST | ASSEMLY ACTUAL COST | ORDER STATUS | STOCK QTY | STOCK LOCATION
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35
SUNSWIFT RACING | CAR | SRP8 | SUNSWIFT 8 |  | ACTIVE | ONCAR | 0 | SR8- | INST - SUNSWIFT 8 | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | CHASSIS | SRP8-065 | OCCUPANT CELL |  | ACTIVE | ONCAR | 1 | SR8- | INST - OCCUPANT CELL | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | CHASSIS | SRP8-065 | OCCUPANT CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - OCCUPANT CELL SPIDER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | CHASSIS | SRP8-065 | OCCUPANT CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - OCCUPANT CELL TUB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | CHASSIS | SRP8-065 | OCCUPANT CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - STEERING COLUMN MOUNT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | CHASSIS | SRP8-066 | CRASH STRUCTURES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT CRASH STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | CHASSIS | SRP8-066 | CRASH STRUCTURES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR CRASH STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | CHASSIS | SRP8-010 | VENTILATION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CHASSIS VENTILATION | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | CHASSIS | SRP8-081 | SUBFRAMES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CHASSIS SUBFRAME | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-093 | AIR CONDITIONING |  | ACTIVE | ONCAR | 1 | SR8- | INST - AIR CONDITIONING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | INTERIOR | SRP8-093 | AIR CONDITIONING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HVAC BOX | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-094 | THERMAL MANAGEMENT |  | ACTIVE | ONCAR | 1 | SR8- | INST - THERMAL MANAGEMENT | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-094 | THERMAL MANAGEMENT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - THERMAL BOX | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-094 | THERMAL MANAGEMENT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HVAC PIPING | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-094 | THERMAL MANAGEMENT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT FLUID MANAGEMENT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | INTERIOR | SRP8-094 | THERMAL MANAGEMENT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR FLUID MANAGEMENT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 1 | SR8- | INST - BODYWORK | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR BUMPER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR QUARTER PANEL - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR QUARTER PANEL - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT BODY STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR FLOOR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-122 | BODYPANELS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR SUPPORT STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-004 | BOOT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BOOT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
EMBEDDED SYSTEMS | BODYWORK | SRP8-004 | BOOT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BOOT LOCKING BOARD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-005 | BONNET |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BONNET | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
EMBEDDED SYSTEMS | BODYWORK | SRP8-005 | BONNET |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BONNET LOCKING BOARD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 1 | SR8- | INST - DOORS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | ADR 2, ADR 29, ADR 43, ADR 92 |  |  |  |  | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR SHELL - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR SHELL - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | MCCONAGHY
CHASSIS & BODYWORK | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR HINGE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR HINGE - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR CARD - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR CARD - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR AUDIO - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR AUDIO - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR CONTROL BOARD - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR CONTROL BOARD - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR ACTUATOR BOARD - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR ACTUATOR BOARD - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 1 | SR8- | INST - DOOR HANDLES | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | ADR 2, ADR 29, ADR 43, ADR 92 |  |  |  |  | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INNER DOOR HANDLE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INNER DOOR HANDLE - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - OUTER DOOR HANDLE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - OUTER DOOR HANDLE - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR LATCH - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-002 | DOOR HANDLES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR LATCH - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | BODYWORK | SRP8-112 | ELECTRIC WINDOWS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ELECTRIC WINDOWS - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-112 | ELECTRIC WINDOWS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ELECTRIC WINDOWS - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | AERO | SRP8-080 | TRACK AERO KIT |  | ACTIVE | ONCAR | 1 | SR8- | INST - TRACK AERO KIT | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | AERO | SRP8-083 | ACTIVE AERO |  | ACTIVE | ONCAR | 1 | SR8- | INST ACTIVE AERO KIT | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | AERO | SRP8-083 | ACTIVE AERO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AERO | SRP8-083 | ACTIVE AERO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ACTIVE AERO MOTORS | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AERO | SRP8-083 | ACTIVE AERO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ACTIVE AERO CONTROLl PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | WINDSCREEN | SRP8-003 | WINDSCREEN |  | ACTIVE | ONCAR | 1 | SR8- | INST - WINDSCREEN WIPERS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | WINDSCREEN | SRP8-003 | WINDSCREEN |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 1 | SR8- | INST - WINDSCREEN WIPERS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN WIPER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN WASHER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN WIPER AERO GUARD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN WIPER MOTOR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - WINDSCREEN WIPER CONTROL PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INSTALLATION | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 1 | SR8- | INST - FRONT SUSPENSION | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT TOP WISHBONE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT TOP WISHBONE - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT LOWER WISHBONE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT LOWER WISHBONE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT PUSHROD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT TRACKROD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-088 | FRONT UPRIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT UPRIGHT - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-088 | FRONT UPRIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT UPRIGHT - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT DAMPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY FRONT DAMPER - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-043 | FRONT DAMPERS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY FRONT DAMPER - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-050 | FRONT WHEEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT WHEEL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-050 | FRONT WHEEL |  | ACTIVE | ONCAR | 3 | SR8- | FRONT WHEEL | 2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-050 | FRONT WHEEL |  | ACTIVE | ONCAR | 3 |  | FRONT TYRE | 2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 1 | SR8- | INST - REAR SUSPENSION | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR TOP WISHBONE - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR TOP WISHBONE - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR LOWER WISHBONE LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR LOWER WISHBONE RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR PUSHROD | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR TOELINK | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-089 | REAR UPRIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR UPRIGHT - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-089 | REAR UPRIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR UPRIGHT - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR DAMPER - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-044 | REAR SUSPENSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR DAMPER - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-051 | REAR WHEEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR WHEEL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-051 | REAR WHEEL |  | ACTIVE | ONCAR | 3 | SR8- | REAR WHEEL | 2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | REAR SUSPENSION | SRP8-051 | REAR WHEEL |  | ACTIVE | ONCAR | 3 |  | REAR TYRE | 2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 1 | SR8- | INST - FRONT BRAKE SYSTEM | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT CALIPER - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT CALIPER - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT MASTER CYLINER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT MASTER CYLINDER RESERVOIR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT BRAKE DISC | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT BRAKE LINE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-045 | FRONT BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY CHASSIS BRAKE LINE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR BRAKE CALIPER - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR BRAKE CALIPER - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR MASTER CYLINDER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR MASTER CYLINDER RESERVOIR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR BRAKE DISC | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-046 | REAR BRAKES |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR BRAKE LINE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-047 | HANDBRAKE |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HAND BRAKE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | ADAS | SRP8-115 | TYRE PRESSURE MONITORING SYSTEM |  | ACTIVE | ONCAR | 1 | SR8- | INST - TPMS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
VEHICLE DYNAMICS | STEERING | SRP8 | STEERING |  | ACTIVE | ONCAR | 1 | SR8- | INST - STEERING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
VEHICLE DYNAMICS | STEERING | SRP8-048 | STEERING COLUMN |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - STEERING COLUMN | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | STEERING | SRP8-049 | STEERING RACK |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - STEERING RACK | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | STEERING | SRP8-022 | STEERING WHEEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - STEERING WHEEL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | STEERING | SRP8-022 | STEERING WHEEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - STEERING WHEEL PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | STEERING | SRP8-023 | INTERIOR LIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INTERIOR LIGHTS PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | VISION | SRP8-024 | REAR VISION SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - REAR VISION CAMERA | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | VISION | SRP8-025 | SIDE VISION SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SIDE CAMERA - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | VISION | SRP8-025 | SIDE VISION SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SIDE CAMERA - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 1 | SR8- | INST - PEDALS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PEDAL BOX | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - THROTTLE PEDAL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BRAKE PEDAL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PEDAL BOX CONTROLLER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | PEDALS | SRP8-026 | PEDALS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PEDAL POSITION SENSOR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-027 | CEILING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CEILING | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-027 | CEILING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SUN VISOR LH |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-027 | CEILING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SUN VISOR RH |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | DASHBOARD | SRP8-037 | DASHBOARD |  | ACTIVE | ONCAR | 1 | SR8- | INST - DASHBOARD | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | DASHBOARD | SRP8-037 | DASHBOARD |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DASHBOARD STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | DASHBOARD | SRP8-028 | CENTRAL DISPLAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CENTRAL DISPLAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | DASHBOARD | SRP8-029 | DRIVER DISPLAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DRIVER DISPLAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | DASHBOARD | SRP8-030 | HEADS-UP DISPLAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HEADS-UP DISPLAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-085 | NOISE VIBRATION AND HARSHNESS |  | ACTIVE | ONCAR |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-032 | FRONT SEATS |  | ACTIVE | ONCAR | 1 | SR8- | INST - FRONT SEATS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
INTERIOR | SEATS | SRP8-032 | FRONT SEATS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEAT DRIVER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-032 | FRONT SEATS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEAT PASSENGER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-034 | FRONT SEAT MOUNT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEAT MOUNT DRIVER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-034 | FRONT SEAT MOUNT |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEAT MOUNT PASSENGER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-034 | FRONT SEATBELTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEAT BEL DRIVER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | SEATS | SRP8-036 | FRONT SEATBELTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FRONT SEATBELT PASSENGER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | MOTORS | SRP8-038 | MOTORS |  | ACTIVE | ONCAR | 1 | SR8- | INST - MOTORS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
POWERTRAIN | MOTORS | SRP8-038 | MOTORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MOTOR UNIT - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | MOTORS | SRP8-038 | MOTORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MOTOR UNIT - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | MOTORS | SRP8-038 | MOTORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MOTOR MOUNTING FRAME - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | MOTORS | SRP8-038 | MOTORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MOTOR MOUNTING FRAME - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INVERTER - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INVERTER - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INVERTER MOUNTING FRAME - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - INVERTER MOUNTING FRAME - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PWT HV WRING - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | ELECTRICAL | SRP8-039 | POWERTRAIN ELECTRONICS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PWT HV WIRING - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | ACTIVE | ONCAR | 1 | SR8- | INST - GEARBOX | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - GEARBOX - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - GEARBOX - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - AXLE CV - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - AXLE CV - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-086 | TRANSMISSION |  | OBSOLETE | ONCAR | 2 | SR8- | ASSY - DRIVESHAFT | 2 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | POWERTRAIN | SRP8-117 | DRIVE MODES |  | ACTIVE | SOFTWARE |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 1 | SR8- | INST - BATTERY SYSTEM | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BATTERY MODULES | 9 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BATTERY PACK | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BMS WIRING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BATTERY HV WIRING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-016 | BATTERY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BATTERY LV WIRING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | AUX | SRP8-017 | AUXILLARY POWER DISTRIBUTION |  | ACTIVE | ONCAR | 1 | SR8- | INST - AUX POWER SYSTEM | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | AUX | SRP8-017 | AUXILLARY POWER DISTRIBUTION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - AUXILLARY POWER WIRING | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | AUX | SRP8-017 | AUXILLARY POWER DISTRIBUTION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DC-DC CONVERTERS | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | AUX | SRP8-017 | AUXILLARY POWER DISTRIBUTION |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - AUX BATTERY | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-018 | ENERGY CONTROL SYSTEM |  | ACTIVE | ONCAR | 1 | SR8- | INST - ENERGY CONTROL SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | BATTERY | SRP8-018 | ENERGY CONTROL SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ECS HV WIRING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-018 | ENERGY CONTROL SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ECS LV WIRING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-018 | ENERGY CONTROL SYSTEM |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - CONTROL LOGIC | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-018 | ENERGY CONTROL SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ECS MODULE | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | CHARGING | SRP8-021 | CHARGING |  | ACTIVE | ONCAR | 1 | SR8- | INST - CHARGING | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | CHARGING | SRP8-021 | CHARGING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ONBOARD CHARGING WIRING | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | CHARGING | SRP8-021 | CHARGING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - ONBOARD CHARGER INSTALLATION | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-019 | MPPT JUNCTION BOX |  | ACTIVE | ONCAR | 1 | SR8- | INST - MPPT | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-019 | MPPT JUNCTION BOX |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MPPT JUNCTION BOX | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | PV | SRP8-020 | SOLAR ARRAY |  | ACTIVE | ONCAR | 1 | SR8- | INST - SOLAR ARRAYS | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | PV | SRP8-020 | SOLAR ARRAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SOLAR ROOF ARRAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-020 | SOLAR ARRAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SOLAR BOOT ASSAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-020 | SOLAR ARRAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SOLAR BONNET ARRAY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-119 | SHINGLED MATRIX SOLAR CELLS |  | ACTIVE | ONCAR | 1 | SR8- | INST - SHINGLED MATRIX SOLAR | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 1 | SR8- | INST - TAILIGHTS/INDICATOR | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB- LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | LIGHTS | SRP8-077 | CENTRAL STOP LAMP |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CENTRAL STOP LAMP | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-077 | CENTRAL STOP LAMP |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - CENTRAL STOP LAMP PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HEADLIGHT EXTERIOR - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
CHASSIS & BODYWORK | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HEADLIGHT EXTERIOR - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | LIGHTS | SRP8-013 | INDICATORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SIDE INDICATOR EXTERIOR - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | LIGHTS | SRP8-013 | INDICATORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SIDE INDICATOR EXTERIOR - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-014 | REGEN BRAKING |  | ACTIVE | ONCAR | 1 | SR8- | INST - REGEN BRAKING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | ADAS | SRP8-015 | CRUISE CONTROL |  | ACTIVE | SOFTWARE |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | EMBEDDED | SRP8-055 | INTERNAL EMBEDDED NETWORK |  | ACTIVE | ONCAR | 1 | SR8- | INST - INTERNAL EMBEDDED NETWORK WIRING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | EMBEDDED | SRP8-056 | EMBEDDED TESTBED |  | ACTIVE | SOFTWARE |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-103 | EMBEDDED STANDARD LOW LEVEL CIRCUITRY |  | ACTIVE | ONCAR |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-057 | HORN |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HORN | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-057 | HORN |  | ACTIVE | ONCAR | 2 | SR8- | ASSY- HORN PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-057 | HORN |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HORN PCB CODE | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-058 | DRIVE CONTROL SYSTEMS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DRIVE CONTROL UNIT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | SENSORS | SRP8-059 | SENSORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SENSOR MOTHERBOARD - FL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | SENSORS | SRP8-059 | SENSORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SENSOR MOTHERBOARD- FR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | SENSORS | SRP8-059 | SENSORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SENSOR MOTHERBOARD - BL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | SENSORS | SRP8-059 | SENSORS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SENSOR MOTHERBOARD- BR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-060 | FATIGUE MONITORING SYSTEM |  | ACTIVE | ONCAR | 1 | SR8- | INST - FATIGUE MONITORING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | ADAS | SRP8-060 | FATIGUE MONITORING SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FATIGUE MONITORING SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BODYWORK | SRP8-111 | CENTRAL LOCKING |  | ACTIVE | ONCAR | 1 | SR8- | INST - CENTRAL LOCKING | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | ADAS | SRP8-095 | BLIND SPOT MONITORING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BLINDSPOT MONITORING SENSOR - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-095 | BLIND SPOT MONITORING |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - BLINDSPOT MONITORING SENSOR - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | V2X | SRP8-091 | C-V2X |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - C-V2V ANTENNA | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | V2X | SRP8-091 | C-V2X |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - C-V2X PCB | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AUDIO | SRP8-084 | AUDIO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR AUDIO - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AUDIO | SRP8-084 | AUDIO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - DOOR AUDIO - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AUDIO | SRP8-084 | AUDIO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SUBWOOFER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | AUDIO | SRP8-084 | AUDIO |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - AUDIO CONTROL SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-092 | AUXILIARY SYSTEMS LOGIC |  | ACTIVE | SOFTWARE | N/A |  |  | #VALUE! | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-104 | OVER THE AIR FLASHING |  | ACTIVE | SOFTWARE | N/A |  |  | #VALUE! | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-105 | SROS2 MIDDLEWARE |  | ACTIVE | SOFTWARE | N/A |  |  | #VALUE! | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-126 | STANDARD EMBEDDED HOUSING |  | ACTIVE | SOFTWARE |  |  |  | -1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BRAKES | SRP8-128 | ABS BRAKES |  | ACTIVE | ONCAR | 1 | SR8- | INST - ABS BRAKES | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | EMBEDDED | SRP8-129 | EMBEDDED LOW LEVEL CODE |  | ACTIVE | SOFTWARE | N/A |  |  | #VALUE! | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-130 | EMBEDDED HIGH LEVEL SOFTWARE |  | ACTIVE | SOFTWARE | N/A |  | INST - MAIN COMPUTER SOFTWARE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8 | HYDROGEN SYSTEM |  | ACTICE | ONCAR | 1 | SR8- | INST - HYDROGEN SYSTEM | 0 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ALTERNATIVE ENERGY | HYDROGEN | SRP8-131 | HYDROGEN PRESSURE VESSEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PRESSURE VESSEL SHELL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-131 | HYDROGEN PRESSURE VESSEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PRESSURE REGULATION | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-131 | HYDROGEN PRESSURE VESSEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - SAFETY VALVE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-131 | HYDROGEN PRESSURE VESSEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-131 | HYDROGEN PRESSURE VESSEL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - PRESSURE MONITORING AND CONTROL | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FUEL CELL STACK | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FUEL CELL COOLING SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - POWER ELECTRONICS | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FUEL CELL ANCILLIARY SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY- FUEL CELL SENSOR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-133 | HYDROGEN FUEL CELL |  | ACTIVE | ONCAR | 2 | SR8- | ASSY- FUEL CELL MONITORING SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-124 | HYDROGEN ENERGY SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HYDROGEN STORAGE SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-124 | HYDROGEN ENERGY SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HYDROGEN CONTROL SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-124 | HYDROGEN ENERGY SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HYDROGEN SUPPLY LINE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-124 | HYDROGEN ENERGY SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HYDROGEN EXHAUST MANAGEMENT | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ALTERNATIVE ENERGY | HYDROGEN | SRP8-124 | HYDROGEN ENERGY SYSTEM |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - HYDROGEN LEAK DETECTION SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-030 | HEAD-UP DISPLAY | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-054 | PERFORMANCE OPTIMISATION | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-134 | CAR LIFTING | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-144 | BLUETOOTH AUDIO | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-156 | PHONE CHARGING | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-157 | APPLE & ANDROID COMPATABILITY | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-099 | TRACTION CONTROL | [7 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | V2X | SRP8-091 | C-V2X |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - C-V2V RADAR/LiDAR | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | PV | SRP8-020 | SOLAR ARRAY |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MC4 Cabling |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-055 | INTERNAL EMBEDDED NETWORK |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - MAIN COMPUTER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | STEERING | SRP8-022 | STEERING WHEEL |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - STEERING WHEEL PCB CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-023 | INTERIOR LIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - INTERIOR LIGHTS PCB CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DOOR CONTROL BOARD - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DOOR CONTROL BOARD - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - WINDSCREEN WIPER CONTROL PCB CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-058 | DRIVE CONTROL SYSTEMS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DRIVE CONTROL UNIT SOFTWARE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-023 | INTERIOR LIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - INTERIOR LIGHTS PCB CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DOOR CONTROL BOARD - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | BODYWORK | SRP8-001 | DOORS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DOOR CONTROL BOARD - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | WINDSCREEN | SRP8-082 | WINDSCREEN WIPERS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - WINDSCREEN WIPER CONTROL PCB CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | Column7 |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | EMBEDDED | SRP8-058 | DRIVE CONTROL SYSTEMS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - DRIVE CONTROL UNIT SOFTWARE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-012 | HEADLIGHTS |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS | SRP8-011 | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI |  | HUMAN MACHINE INTERFACE (HMI) |  | ACTIVE | SOFTWARE | 1 |  | INST - HUMAN MACHINE INTERFACE (HMI) |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-157 | APPLE & ANDROID COMPATABILITY |  | ACTIVE | SOFTWARE | 2 |  | ASSY - APPLE & ANDROID COMPATABILITY |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-108 | HUMAN MACHINE INTERFACE (HMI) |  | ACTIVE | SOFTWARE | 2 |  | ASSY - HUMAN MACHINE INTERFACE (HMI) |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-132 | INFOTAINMENT |  | ACTIVE | SOFTWARE | 2 |  | ASSY - INFOTAINMENT |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-144 | BLUETOOTH CONNECTIVITY |  | ACTIVE | SOFTWARE | 2 |  | ASSY - BLUETOOTH CONNECTIVITY |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS |  | DATA ANALYSIS |  | ACTIVE | SOFTWARE | 1 |  | INST - DATA ANALYSIS |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-054 | PERFORMANCE OPTIMISATION |  | ACTIVE | SOFTWARE | 2 |  | ASSY - PERFORMANCE OPTIMISATION |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-061 | TELEMETRY |  | ACTIVE | SOFTWARE | 2 |  | ASSY - TELEMETRY | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-101 | TRIP ENERGY PREDICTION |  | ACTIVE | SOFTWARE | 2 |  | ASSY - TRIP ENERGY PREDICTION | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | COMMUNICATIONS |  | COMMUNICATIONS |  | ACTIVE | SOFTWARE | 1 | SR8- | INST - COMMUNICATIONS |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | COMMUNICATIONS | SRP8-063 | TRACKSIDE RADIO COMMUNICATION |  | ACTIVE | SOFTWARE | 2 | SR8- | ASSY - TRACKSIDE RADIO COMMUNICATION | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | COMMUNICATIONS | SRP8-102 | SUNSWIFT PHONE APP |  | ACTIVE | SOFTWARE | 2 |  | ASSY - SUNSWIFT PHONE APP | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | INTRANET |  | INTRANET |  | ACTIVE | SOFTWARE | 1 |  | INST - INTRANET |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | INTRANET | SRP8-178 | INTRANET |  | ACTIVE | SOFTWARE | 2 |  | ASSY - INTRANET |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-097 | ELECTRONIC STABILITY PROGRAM |  | ACTIVE | ONCAR | 1 |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | MAIN COMPUTER | SRP8-130 | EMBEDDED HIGH LEVEL SOFTWARE ARCHITECTURE |  | ACTIVE | ONCAR | 1 |  | ASSY - MAIN COMPUTER | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-128 | ABS BRAKES |  | ACTIVE | SOFTWARE | 1 |  | ASSY - ABS BRAKES CONTROL SYSTEM | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR STOP LAMP - LH | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR STOP LAMP - RH | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR INDICATOR LAMPS - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR INDICATOR LAMPS - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR RUNNING LIGHTS | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR REVERSE LAMP - LH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTS |  | TAILIGHTS |  | ACTIVE | ONCAR | 2 | SR8- | ASSY - TAILLIGHT/INDICATOR REVERSE LAMP - RH | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTs |  | CENTRAL STOP LAMP |  | ACTIVE | ONCAR | 1 | SR8- | ASSY - CENTRAL STOPLAMP | 1 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTs |  | CENTRAL STOP LAMP |  | ACTIVE | ONCAR | 1 | SR8- | ASSY - CENTRAL STOPLAMP CASING | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | LIGHTs |  | CENTRAL STOP LAMP |  | ACTIVE | ONCAR | 1 | SR8- | ASSY - CENTRAL STOPLAMP CONTROLLER | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Sheet1 (hidden)
Your Assembly | Project | Section | Department | Assigned Person | Time to complete | Depends on (List all underneath) | Impacts (List all underneath) | Assembly 1 | Assembly 2 | Assembly 3 | Assembly 4 | Assembly 5 | Assembly 6 | Assembly 7 | Assembly 8 | Assembly 9 | Assembly 10 | Assembly 11 | Assembly 12 | Assembly 13 | Assembly 14 | Assembly 15 | Assembly 16 | Assembly 17 | Assembly 18 | Assembly 19 | Assembly 20 | Assembly 21 | Assembly 22 | Assembly 23 | Assembly 24 | Assembly 25 | Assembly 26 | Assembly 27 | Assembly 28 | Assembly 29 | Assembly 30 | Assembly 31 | Assembly 32 | Assembly 33 | Assembly 34 | Assembly 35 | Assembly 36 | Assembly 37 | Assembly 38 | Assembly 39 | Assembly 40 | Assembly 41 | Assembly 42 | Assembly 43 | Assembly 44 | Assembly 45 | Assembly 46 | Assembly 47 | Assembly 48 | Assembly 49 | Assembly 50 | Assembly 51 | Assembly 52 | Assembly 53 | Assembly 54 | Assembly 55 | Assembly 56
ASSY - PRESSURE VESSEL SHELL | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Doha |  | PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN COMPARTMENT STRUCTURE, PRESSURE REGULATION & SAFETY | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Simeon |  | REAR FLOOR, OCCUPANT CELL TUB | PRESSURE VESSEL SHELL, HYDROGEN COMPARTMENT STRUCTURE, PRESSURE REGULATION & SAFETY | REAR FLOOR | OCCUPANT CELL TUB
ASSY - HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Simeon |  | PRESSURE VESSEL SHELL, PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN COMPARTMENT VENTILATION, OCCUPANT CELL HYDROGEN SENSOR, FUEL CELL STACK | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - PRESSURE REGULATION & SAFETY | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Doha |  | PRESSURE VESSEL SHELL, PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN SUPPLY LINE, HYDROGEN SENSOR ARRAY, P&ID HYDROGEN DOWNSTREAM LINE | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - HYDROGEN SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Mohammad |  | PRESSURE REGULATION & SAFETY | PURGE MANAGEMENT, SENSOR ARRAY, FUEL CELL STACK | PRESSURE REGULATION & SAFETY
ASSY - HYDROGEN PURGE MANAGEMENT | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Kurtis |  | FUEL CELL STACK, HYDROGEN SUPPLY LINE | P&ID HYDROGEN RECYCLE STREAM | FUEL CELL STACK | HYDROGEN SUPPLY LINE
ASSY - HYDROGEN COMPARTMENT VENTILATION | AIRFLOW & VENTING | HYDROGEN | ALT | Simeon |  | HYDROGEN COMPARTMENT STRUCTURE | P&ID AIR SUPPLY LINE, REARWHEEL HUB AIR INTAKE | HYDROGEN COMPARTMENT STRUCTURE
ASSY- OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Adit |  | HYDROGEN COMPARTMENT STRUCTURE | OCCUPANT CELL SHUTDOWN VALVE, FC ELECTRICAL CONNECTIONS | HYDROGEN COMPARTMENT STRUCTURE
ASSY- P&ID HYDROGEN RECYCLE STREAM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Kurtis |  | HYDROGEN PURGE MANAGEMENT, FUEL CELL STACK | HYDROGEN SENSOR ARRAY | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK
ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Adit |  | FC ELECTRICAL CONNECTIONS, HYDROGEN SENSOR ARRAY | HYDROGEN SYSTEM PERFORMANCE DISPLAY | HYDROGEN SENSOR ARRAY | FC ELECTRICAL CONNECTIONS
ASSY- OCCUPANT CELL SHUTDOWN VALVE | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Mohammad |  | OCCUPANT CELL HYDROGEN SENSOR, HYDROGEN CONTROL LOGIC | OCCUPANT CELL SHUTDOWN VALVE | OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN CONTROL LOGIC
ASSY - HYDROGEN SENSOR ARRAY | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Adit |  | HYDROGEN SUPPLY LINE, PRESSURE REGULATION & SAFETY, FUEL CELL STACK | HYDROGEN CONTROL LOGIC, HYDROGEN SYSTEM PERFORMANCE DISPLAY | PRESSURE REGULATION & SAFETY | HYDROGEN SUPPLY LINE | FUEL CELL STACK
ASSY - HYDROGEN CONTROL LOGIC | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Mohammad |  | HYDROGEN SENSOR ARRAY, FUEL CELL STACK, HYDROGEN CONTROL SYSTEM | FUEL CELL STACK, HYDROGEN CONTROL SYSTEM | HYDROGEN SENSOR ARRAY | FUEL CELL STACK | HYDROGEN CONTROL SYSTEM
ASSY - FUEL CELL STACK | HYDROGEN FUEL CELL | HYDROGEN | ALT | Doha |  | HYDROGEN SUPPLY LINE, HYDROGEN COOLING SYSTEM, HYDROGEN COMPARTMENT STRUCTURE, BATTERY | HYDROGEN SENSOR ARRAY, FUEL CELL STACK, HYDROGEN CONTROL SYSTEM | HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN SUPPLY LINE | HYDROGEN COOLING SYSTEM | BATTERY
ASSY - HYDROGEN COOLING SYSTEM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Natalie |  | FUEL CELL STACK, REAR FLUID MANAGEMENT, FRONT FLUID MANAGEMENT | P&ID HYDROGEN DOWNSTREAM LINE, FC ELECTRICAL CONNECTIONS | REAR FLUID MANAGEMENT | FRONT FLUID MANAGEMENT | FUEL CELL STACK
ASSY - FC ELECTRICAL CONNECTIONS | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Adit |  | FUEL CELL STACK, POWER ELECTRONICS | HYDROGEN SYSTEM PERFORMANCE DISPLAY | FUEL CELL STACK | POWER ELECTRONICS
ASSY - P&ID HYDROGEN DOWNSTREAM LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Natalie |  | FUEL CELL STACK, HYDROGEN SUPPLY LINE, HYDROGEN PURGE MANAGEMENT | P&ID AIR SUPPLY LINE | HYDROGEN SUPPLY LINE | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK
ASSY - P&ID AIR SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Liam |  | REARWHEEL HUB AIR INTAKE, AIR SOURCE | OCCUPANT CELL SHUTDOWN VALVE, P&ID AIR SUPPLY LINE | REARWHEEL HUB AIR INTAKE | AIR SOURCE
ASSY - REARWHEEL HUB AIR INTAKE | AIRFLOW & VENTING | HYDROGEN | ALT | Simeon |  | HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN CONTROL LOGIC | HYDROGEN COMPARTMENT STRUCTURE
ASSY - HYDROGEN CONTROL SYSTEM | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Adit |  | HYDROGEN CONTROL LOGIC, ECS, FC ELECTRICAL CONNECTIONS | N/A (final system-level integration) | HYDROGEN CONTROL LOGIC | ECS | FC ELECTRICAL CONNECTIONS

## SR8 OBSOLETE
DEPARTMENT | SECTION | PROJECT # | PROJECT | APPROVED | STATUS | ONCAR SOFTWARE OFFCAR | BOM LEVEL | PART NUMBER | PART DESCRIPTION | QTY PER | CAR BUILD | SHAKE-DOWN | TRACK TEST 01 | TRACK TEST 02 | CAR LAUNCH | PRESS LAUNCH | ROAD TEST 01 | ST | ADR'S | ENG DWG REQ | EST WEIGHT kg | ACTUAL WEIGHT kg | PROCUREMENT | SUPPLIER / PARTNER | ASSYEMBLY EST COST | ASSEMLY ACTUAL COST | ORDER STATUS | STOCK QTY | STOCK LOCATION
Column111 | Column110 | Column2 | Column3 | Column33 | Column32 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column92 | Column10 | Column11 | Column102 | Column103 | Column112 | Column12 | Column13 | Column136 | Column137 | Column138 | Column139 | Column134 | Column135 | Column133 | Column16 | Column17 | Column18 | Column182 | Column183 | Column184 | Column185 | Column19
CHASSIS & BODYWORK | CHASSIS | SRP8-009 | CHASSIS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [15 empty] | N/A
CHASSIS & BODYWORK | N/A | SRP8-087 | PACKAGING |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-135 | INTERIOR DOOR PANEL |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-145 | LOCK AND KEY |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-006 | EXTERIOR DESIGN |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CHASSIS & BODYWORK | BODYWORK | SRP8-007 | FRONT WHEEL COVERS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [15 empty] | N/A
CHASSIS & BODYWORK | BODYWORK | SRP8-008 | REAR WHEEL COVERS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [15 empty] | N/A
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-162 | HUBS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-151 | MASTER CYLINDERS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-152 | BRAKE LINES |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | STEERING | SRP8-159 | POWER STEERING |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-166 | ENTERTAINMENT MODULE |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-147 | ERGONOMIC CENTRAL DISPLAY TABLET | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-033 | REAR SEATBELTS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-035 | REAR SEAT MOUNT |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-148 | AIR BAGS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-161 | DRINKS HOLDERS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-070 | CHARGING PORT |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-053 | REQUIREMENTS MANAGEMENT |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-072 | SUSPENSION SENSOR | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-073 | BRAKE PRESSURE SENSOR | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-074 | SOLAR IRRADIANCE SENSOR | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-071 | SOLAR CURRENT SENSOR | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-136 | LEVEL 2 AUTONOMY | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-137 | LEVEL 3 AUTONOMY | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-064 | WIRING | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-067 | SECONDARY BATTERY BOX |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-068 | BATTERY MOUNTING |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-075 | ICE PACK VESTS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-076 | SAFESTATE BUTTON |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-158 | HYDROGEN |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-138 | SECURITY AUDIT |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-143 | GPS NAVIGATION |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-146 | IN-CAR WIRELESS CHARGING |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-153 | IN CAR ENTERTAINMENT |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-160 | TOWING |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-031 | XXXX |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-040 | XXXX |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-041 | RD EMERGENCY BRAKE |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-042 | NOT |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-052 | BOM |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-107 | INTERIOR LAYOUT |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
INTERIOR | INTERIOR | SRP8-078 | INTERIOR STORAGE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS |  | SRP8-079 | JUNCTION BOX | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | ELECTRICAL | SRP8-125 | ELECTRICAL GUIDELINES |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-120 | BATTERY GAS RELEASE TUNNELS |  | RESEARCH | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-062 | ADAS |  | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## SRT MASTER
PARTS MANAGEMENT SCREEN - SUNSWIFT
DEPARTMENT | SECTION | PROJECT # | PROJECT | APPROVED | STATUS | ONCAR SOFTWARE OFFCAR | BOM LEVEL | PART NUMBER | PART DESCRIPTION | QTY PER | CAR BUILD | SHAKE-DOWN | TRACK TEST 01 | TRACK TEST 02 | CAR LAUNCH | PRESS LAUNCH | ROAD TEST 01 | ST | ADR'S | ENG DWG REQ | EST WEIGHT kg | ACTUAL WEIGHT kg | PROCUREMENT | SUPPLIER / PARTNER | ASSYEMBLY EST COST | ASSEMLY ACTUAL COST | ORDER STATUS | STOCK QTY | STOCK LOCATION
Column111 | Column110 | Column2 | Column3 | Column33 | Column32 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column92 | Column10 | Column11 | Column102 | Column103 | Column112 | Column12 | Column13 | Column136 | Column137 | Column138 | Column139 | Column134 | Column135 | Column133 | Column16 | Column17 | Column18 | Column182 | Column183 | Column184 | Column185 | Column19
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-154 | ELECTROMAGNETIC DAMPERS |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-149 | BRAKE CALIPERS - BESPOKE |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | BRAKES | SRP8-150 | BRAKE DISCS & PADS |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-140 | LANE KEEP | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-141 | ADAPTIVE HEADLIGHTS |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-100 | AUTOMATED EMERGENCY BRAKING | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-155 | AUTONOMOUS DRIVING | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-163 | V2I - VEHICLE TO INFRASTRUCTURE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-164 | V2V - VEHICLE TO VEHICLE | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-165 | V2X - VEHICLE TO ANYTHING | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | SRP8-123 | OFF-CAR HYDROGEN ELECTROLYSER |  |  | OFFCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-139 | AUTOMOTIVE ETHERNET FEASIBILITY |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX |  | SRP8-142 | PROGRAMMABLE SEAT POSITIONING |  | ???? | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS |  | SRP8-106 | IN-CAR DRIVING SIMULATOR | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | TRANSMISSION | SRP8-127 | CLUTCH |  | ???? | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
POWERTRAIN | MOTORS | SRPR-38 | IN-HOUSE MOTOR DEVELOPMENT |  | RESEARCH | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
XXXXX | ???? | SRP8-114 | PV REAR LIGHTS |  | RESEARCH | ONCAR | 1 | SR8- | INST - PV REAR LIGHTS | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
ENERGY SYSTEMS | CHARGING | SRP8-118 | AC CHARGING CONTROL |  | RESEARCH | ONCAR | 1 |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | V2X | SRP8-110 | VEHICLE TO GRID |  | RESEARCH | OFFCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
ENERGY SYSTEMS | BATTERY | SRP8-109 | SUPER CAPACITORS |  | RESEARCH | ONCAR | 1 | SR8- | INST - SUPER CAPACITORS | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | [5 empty] | SUNSWIFT
EMBEDDED SYSTEMS | ADAS | SRP8-116 | INTEGRATED AGILITY CONTROL SYSTEM |  | RESEARCH | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-096 | PARK ASSIST |  | RESEARCH | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-097 | ELECTRONIC STABILITY PROGRAM |  | RESEARCH | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EMBEDDED SYSTEMS | ADAS | SRP8-098 | AUTOMATED PARKING |  | RESEARCH | ONCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | SECURITY | SRP8-121 | CYBERSECURITY | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
VEHICLE DYNAMICS | FRONT SUSPENSION | SRP8-113 | CARBON WHEELS |  | RESEARCH | ONCAR | 2 | SR8- | CARBON WHEEL |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
ENERGY SYSTEMS | CHARGING | SRP8-090 | WIRELESS CHARGING |  | ACTIVE | ONCAR | 1 | SR8- | INST - WIRELESS CHARGING | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | [5 empty] | SUNSWIFT
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-054 | PERFORMANCE OPTIMISATION |  | ACTIVE | SOFTWARE |  |  | ASSY - DRIVE MODES |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-061 | TELEMETRY |  | ACTIVE | SOFTWARE |  |  | ASSY - DRIVE MODES |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | COMMUNICATIONS | SRP8-063 | TRACKSIDE RADIO COMMUNICATION |  | ACTIVE | SOFTWARE |  |  | ASSY - COMMUNICATION |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | DATA ANALYSIS | SRP8-101 | TRIP ENERGY PREDICTION |  | ACTIVE | SOFTWARE |  |  | ASSY - DRIVE MODES |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-108 | HUMAN MACHINE INTERFACE (HMI) |  | ACTIVE | ONCAR |  |  | ASSY - HMI |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-132 | INFOTAINMENT |  | ACTIVE | ONCAR |  |  | ASSY - HMI |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-144 | BLUETOOTH CONNECTIVITY |  | ACTIVE | ONCAR |  |  | ASSY - HMI |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-157 | APPLE & ANDROID COMPATABILITY |  | ACTIVE | ONCAR |  |  | ASSY - HMI |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | HMI | SRP8-102 | SUNSWIFT PHONE APP |  | ACTIVE | SOFTWARE |  |  | ASSY - USER INTERACTION |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
TECHNICAL SUPPORT SYSTEMS | N/A | SRP8-178 | INTRANET |  | ACTIVE | SOFTWARE |  |  | N/A |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[11 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## SR8 Mk1
SUNSWIFT 8 PARTS MANAGEMENT
RH COMMENTS | DEPARTMENT | SECTION | PROJECT # | PART NUMBER | PROJECT | STATUS | ONCAR OFFCAR | BOM LEVEL | PART NUMBER | PART DESCRIPTION | QTY PER | SHAKEDOWN JUNE 2025 | TEST #1 JULY 2025 | BWSC AUGUST 2025 | 2026 | SUPPLIER | WEIGHT | COST | ORDER STATUS | STOCK
Column1 | Column111 | Column110 | Column2 | Column22 | Column3 | Column32 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19
|  |  | N/A |  | SUNSWIFT 8 | N/A | ONCAR | 0 | N/A | N/A | N/A | FALSE | FALSE | FALSE | FALSE | SUNSWIFT |  |  | N/A | 0
| CHASSIS & BODYWORK | CHASSIS | SRP8-009 |  | CHASSIS | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CHASSIS & BODYWORK | CHASSIS | Column2: SRP8-065; Column3: OCCUPANT CELL; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
BODYWORK | CHASSIS & BODYWORK | CHASSIS | Column2: SRP8-066; Column3: CRASH STRUCTURES; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | CHASSIS | Column2: SRP8-010; Column3: VENTILATION; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
SHOULD THIS BE SPLIT FRONT AND REAR | CHASSIS & BODYWORK | CHASSIS | Column2: SRP8-081; Column3: SUBFRAMES; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
BREAKDOWN TO INDIVIDUAL PANELS - TO BE OBSOLETED | CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-122; Column3: BODY PANELS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-001; Column3: DOORS; Column32: ACTIVE; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-002; Column3: DOOR HANDLES; Column32: ACTIVE; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-111; Column3: CENTRAL LOCKING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-112; Column3: ELECTRIC WINDOWS; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-135; Column3: INTERIOR DOOR PANEL; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-145; Column3: LOCK AND KEY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-004; Column3: BOOT; Column32: ACTIVE; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-005; Column3: BONNET; Column32: ACTIVE; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
THIS IS A TASK, NOT A PROJECT - TO BE OBSOLETED | CHASSIS & BODYWORK | BODYWORK | SRP8-006 |  | EXTERIOR DESIGN | INACTIVE | N/A | N/A | N/A | N/A | N/A | FALSE | FALSE | FALSE | FALSE | SUNSWIFT
| CHASSIS & BODYWORK | BODYWORK | SRP8-007 |  | FRONT WHEEL COVERS | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CHASSIS & BODYWORK | BODYWORK | SRP8-008 |  | REAR WHEEL COVERS | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-080; Column3: TRACK AERO KIT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | BODYWORK | Column2: SRP8-083; Column3: ACTIVE AERO; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| CHASSIS & BODYWORK | WINDSCREEN | Column2: SRP8-003; Column3: WINDSCREEN; Column32: ACTIVE; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
| CHASSIS & BODYWORK | WINDSCREEN | Column2: SRP8-082; Column3: WINDSCREEN WIPERS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
|  | LIGHTS | Column2: SRP8-011; Column3: TAILIGHTS; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
PART OF TAILIGHTS SRP8-011 - TO BE OBSOLETED |  | LIGHTS | Column2: SRP8-077; Column3: CENTRAL STOP LAMP; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | LIGHTS | Column2: SRP8-012; Column3: HEADLIGHTS; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | LIGHTS | Column2: SRP8-013; Column3: INDICATORS; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | ADAS | Column2: SRP8-014; Column3: REGEN BRAKING; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | ADAS | Column2: SRP8-015; Column3: CRUISE CONTROL; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | BATTERY | Column2: SRP8-016; Column3: BATTERY; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-017 |  | AUXILLARY POWER DISTRIBUTION | ACTIVE | [5 empty] | FALSE | FALSE | FALSE | FALSE | SUNSWIFT
|  |  | SRP8-018 |  | ENERGY CONTROL SYSTEM | ACTIVE | [5 empty] | FALSE | FALSE | FALSE | FALSE | SUNSWIFT
ONCAR? |  | CHARGING | Column2: SRP8-021; Column3: CHARGING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | CHARGING | Column2: SRP8-118; Column3: AC CHARGING CONTROL; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | CHARGING | Column2: SRP8-069; Column3: CHARGING MOUNTING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | CHARGING | Column2: SRP8-070; Column3: CHARGING PORT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
|  | INTERIOR | Column2: SRP8-022; Column3: STEERING WHEEL; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | INTERIOR | Column2: SRP8-023; Column3: INTERIOR LIGHTS; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-024; Column3: REAR VISION SYSTEM; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-025; Column3: SIDE VISION SYSTEM; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-026; Column3: PEDALS; Column32: ACTIVE; Column5: 1; Column7: INST - PEDALS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-026; Column32: ACTIVE; Column5: 2; Column7: ASSY - PEDALS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-026; Column32: ACTIVE; Column5: 2; Column7: ASSY THROTTLE PEDAL; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-026; Column32: ACTIVE; Column5: 2; Column7: ASSY - BRAKE PEDAL; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-027; Column3: CEILING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-037; Column3: DASHBOARD; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-028; Column3: CENTRAL DISPLAY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-029; Column3: DRIVER DISPLAY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-030; Column3: HEAD-UP DISPLAY; Column9: FALSE; Column10: FALSE; Column11: TRUE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-132; Column3: INFOTAINMENT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-166; Column3: ENTERTAINMENT MODULE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-147; Column3: ERGONOMIC CENTRAL DISPLAY TABLET; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-032; Column3: FRONT SEATS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-033; Column3: REAR SEATBELTS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-034; Column3: FRONT SEATBELTS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-035; Column3: REAR SEAT MOUNT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-036; Column3: FRONT SEAT MOUNT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-078; Column3: INTERIOR STORAGE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-090; Column3: WIRELESS CHARGING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
|  | INTERIOR | Column2: SRP8-093; Column3: AIR CONDITIONING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-148; Column3: AIR BAGS; Column32: OBSOLETE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | INTERIOR | Column2: SRP8-161; Column3: DRINKS HOLDERS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
|  | MOTORS | Column2: SRP8-038; Column3: MOTORS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
CHANGE TO SRP8-167 |  | MOTORS | Column2: SRPR-38; Column3: IN-HOUSE MOTOR DEVELOPMENT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
|  | ELECTRICAL | Column2: SRP8-039; Column3: POWERTRAIN ELECTRONICS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column3: FRONT SUSPENSION; Column5: 1; Column7: INST - FRONT SUSPENSION; Column8: 0; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT TOP WISHBONE - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT TOP WISHBONE - RH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT LOWER WISHBONE - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT LOWER WISHBONE - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT PUSHROD; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-043; Column5: 2; Column7: ASSY - FRONT TRACKROD; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-088; Column3: FRONT UPRIGHTS; Column5: 2; Column7: ASSY - FRONT UPRIGHT - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-088; Column5: 2; Column7: ASSY - FRONT UPRIGHT - RH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-050; Column3: FRONT WHEEL; Column5: 2; Column7: ASSY - FRONT WHEEL; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-162; Column3: HUBS; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-113; Column3: CARBON WHEELS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
BRING BACK TO LIFE | VEHICLE DYNAMICS | FRONT SUSPENSION | Column2: SRP8-154; Column3: ELECTROMAGNETIC DAMPERS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column3: REAR SUSPENSION; Column5: 1; Column7: INST - REAR SUSPENSION; Column8: 0; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column5: 2; Column7: ASSY - REAR TOP WISHONE - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column5: 2; Column7: ASSY - REAR TOP WISHONE - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column5: 2; Column7: ASSY - REAR LOWER WISHBONE LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column5: 2; Column7: ASSY - REAR PUSHROD; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-044; Column5: 2; Column7: ASSY - REAR TOELINK; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-089; Column3: REAR UPRIGHTS; Column5: 2; Column7: ASSY - REAR UPRIGHT - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-089; Column5: 2; Column7: ASSY - REAR UPRIGHT - RH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | REAR SUSPENSION | Column2: SRP8-051; Column3: REAR WHEEL; Column5: 2; Column7: ASSY - REAR WHEEL; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column3: FRONT BRAKES; Column5: 1; Column7: INST - FRONT BRAKE SYSTEM; Column8: 0; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT CALIPER - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT CALIPER - RH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT MASTER CYLINER; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT MASTER CYLINDER RESERVOIR; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT BRAKE DISC; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY - FRONT BRAKE LINE; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-045; Column5: 2; Column7: ASSY CHASSIS BRAKE LINE; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column3: REAR BRAKES; Column5: 2; Column7: ASSY - REAR BRAKE CALIPER - LH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column5: 2; Column7: ASSY - REAR BRAKE CALIPER - RH; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column5: 2; Column7: ASSY - REAR MASTER CYLINDER; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column5: 2; Column7: ASSY - REAR MASTER CYLINDER RESERVOIR; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column5: 2; Column7: ASSY - REAR BRAKE DISC; Column8: 2; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-046; Column5: 2; Column7: ASSY - REAR BRAKE LINE; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-047; Column3: HANDBRAKE; Column5: 2; Column7: ASSY - HAND BRAKE; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-128; Column3: ABS BRAKES; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-149; Column3: BRAKE CALIPERS - BESPOKE; Column32: OBSOLETE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-150; Column3: BRAKE DISCS & PADS; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-151; Column3: MASTER CYLINDERS; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | BRAKES | Column2: SRP8-152; Column3: BRAKE LINES; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | STEERING | Column2: N/A; Column5: 1; Column7: INST - STEERING; Column8: 0; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | STEERING | Column2: SRP8-048; Column3: STEERING COLUMN; Column4: ONCAR; Column5: 2; Column7: ASSY - STEERING COLUMN; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
| VEHICLE DYNAMICS | STEERING | Column2: SRP8-049; Column3: STEERING RACK; Column4: ONCAR; Column5: 2; Column7: ASSY - STEERING RACK; Column8: 1; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
PART OF STEERING RACK? | VEHICLE DYNAMICS | STEEREING | Column2: SRP8-159; Column3: POWER STEERING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-053 |  | REQUIREMENTS MANAGEMENT | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-054 |  | PERFORMANCE OPTIMISATION | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-055 |  | INTERNAL EMBEDDED NETWORK | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  | EMBEDDED | Column2: SRP8-056; Column3: EMBEDDED TESTBED; Column4: OFFCAR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-103; Column3: EMBEDDED STANDARD LOW LEVEL CIRCUITRY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-057 |  | HORN | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-058 |  | DRIVE CONTROL SYSTEMS | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  | SENSORS | Column2: SRP8-059; Column3: SENSORS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | SENSOR | Column2: SRP8-072; Column3: SUSPENSION SENSOR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | SENSOR | Column2: SRP8-073; Column3: BRAKE PRESSURE SENSOR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | SENSOR | Column2: SRP8-074; Column3: SOLAR IRRADIANCE SENSOR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | PV | Column2: SRP8-071; Column3: SOLAR CURRENT SENSOR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | PV | Column2: SRP8-114; Column3: PV REAR LIGHTS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
|  | PV | Column2: SRP8-019; Column3: MPPT JUNCTION BOX; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
MAYBE SHOULD BREAK DOWN TO EACH ARRAY |  | PV | Column2: SRP8-020; Column3: SOLAR ARRAY; Column32: ACTIVE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE; Column13: SUNSWIFT
|  | PV | Column2: SRP8-119; Column3: SHINGLED MATRIX SOLAR CELLS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-061 |  | TELEMETRY | [6 empty] | FALSE | FALSE | FALSE | FALSE
BREAKDOWN TO INDIVIDUAL FUNCTIONS - TO BE OBSOLETED |  | ADAS | Column2: SRP8-062; Column3: ADAS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-136; Column3: LEVEL 2 AUTONOMY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-137; Column3: LEVEL 3 AUTONOMY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-140; Column3: LANE KEEP; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-141; Column3: ADAPTIVE HEADLIGHTS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-060; Column3: FATIGUE MONITORING SYSTEM; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-115; Column3: TYRE PRESSURE MONITORING SYSTEM; Column9: FALSE; Column10: FALSE; Column11: TRUE; Column12: FALSE
|  | ADAS | Column2: SRP8-116; Column3: INTEGRATED AGILITY CONTROL SYSTEM; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-096; Column3: PARK ASSIST; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-095; Column3: BLIND SPOT MONITORING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-097; Column3: ELECTRONIC STABILITY PROGRAM; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-098; Column3: AUTOMATED PARKING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-099; Column3: TRACTION CONTROL; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-100; Column3: AUTOMATED EMERGENCY BRAKING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | ADAS | Column2: SRP8-155; Column3: AUTONOMOUS DRIVING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | v2 | Column2: SRP8-110; Column3: VEHICLE TO GRID; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
|  | v2 | Column2: SRP8-091; Column3: C-V2X; Column9: FALSE; Column10: FALSE; Column11: TRUE; Column12: FALSE
|  | v2 | Column2: SRP8-163; Column3: V2I - VEHICLE TO INFRASTRUCTURE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | v2 | Column2: SRP8-164; Column3: V2V - VEHICLE TO VEHICLE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | v2 | Column2: SRP8-165; Column3: V2X - VEHICLE TO ANYTHING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | COMMUNICATION | Column2: SRP8-063; Column3: TRACKSIDE RADIO COMMUNICATION; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
WHAT PROJECT CONTAINS WIRING HARNESSES?? |  | ELECTRICAL | Column2: SRP8-064; Column3: WIRING; Column32: OBSOLETE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BATTERY | Column2: SRP8-067; Column3: SECONDARY BATTERY BOX; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BATTERY | Column2: SRP8-068; Column3: BATTERY MOUNTING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-075 |  | ICE PACK VESTS | OBSOLETE | OFFCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-076 |  | SAFESTATE BUTTON | [6 empty] | FALSE | FALSE | FALSE | FALSE
JUNCTION BOX FOR WHAT? |  |  | Column2: SRP8-079; Column3: JUNCTION BOX; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-084 |  | AUDIO | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-085 |  | NOICE VIBRATION AND HARSHNESS | [6 empty] | FALSE | FALSE | FALSE | FALSE
CHANGE NAME TO GEARBOX |  | GEARBOX | Column2: SRP8-086; Column3: TRANSMISSION; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | GEARBOX | Column2: SRP8-127; Column3: CLUTCH; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
THIS IS A TASK, NOT A PROJECT - TO BE OBSOLETED |  |  | Column2: SRP8-087; Column3: PACKAGING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-092 |  | AUXILIARY SYSTEMS LOGIC | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-094 |  | THERMAL MANAGEMENT | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-101 |  | TRIP ENERGY PREDICTION | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-102 |  | SUNSWIFT PHONE APP |  | OFFCAR |  |  |  |  | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-104 |  | OVER THE AIR FLASHING | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-105 |  | SROS2 MIDDLEWARE | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-106 |  | IN-CAR DRIVING SIMULATOR | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  | BATTERY | Column2: SRP8-109; Column3: SUPER CAPACITORS; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: TRUE
|  |  | SRP8-117 |  | DRIVE MODES | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-120 |  | BATTERY GAS RELEASE TUNNELS | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  | SECURITY | Column2: SRP8-121; Column3: CYBERSECURITY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
NOT PART OF THE CAR - TO BE OBSOLETED |  | ELECTRICAL | Column2: SRP8-125; Column3: ELECTRICAL GUIDELINES; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-126; Column3: STANDARD EMBEDDED HOUSING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-129; Column3: EMBEDDED LOW LEVEL CODE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | EMBEDDED | Column2: SRP8-130; Column3: EMBEDDED HIGH LEVEL SOFTWARE; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | HYDROGEN | Column2: SRP8-131; Column3: HYDROGEN PRESSURE VESSEL; Column4: ONCAR; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | HYDROGEN | Column2: SRP8-133; Column3: HYDROGEN FUEL CELL; Column4: ONCAR; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | HYDROGEN | Column2: SRP8-158; Column3: HYDROGEN; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | HYDROGEN | Column2: SRP8-123; Column3: OFF-CAR HYDROGEN ELECTROLYSER; Column4: OFFCAR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | HYDROGEN | Column2: SRP8-124; Column3: HYDROGEN ENERGY SYSTEM; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | OFFCAR | Column2: SRP8-134; Column3: CAR LIFTING; Column4: OFFCAR; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | SECURITY | Column2: SRP8-138; Column3: SECURITY AUDIT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-139 |  | AUTOMOTIVE ETHERNET FEASIBILITY | [6 empty] | FALSE | FALSE | FALSE | FALSE
MAYBE BIOMETRIC |  | INTERIOR | Column2: SRP8-142; Column3: PROGRAMMABLE SEAT POSITIONING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BLUETOOTH | Column2: SRP8-143; Column3: GPS NAVIGATION; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BLUETOOTH | Column2: SRP8-144; Column3: BLUETOOTH AUDIO; Column9: TRUE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BLUETOOTH | Column2: SRP8-146; Column3: IN-CAR WIRELESS CHARGING; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  | BLUETOOTH | Column2: SRP8-153; Column3: IN CAR ENTERTAINMENT; Column32: REDUNDANT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
BRING BACK TO LIFE |  | BLUETOOTH | Column2: SRP8-156; Column3: PHONE CHARGING; Column9: FALSE; Column10: FALSE; Column11: TRUE; Column12: FALSE
|  | BLUETOOTH | Column2: SRP8-157; Column3: APPLE & ANDROID COMPATABILITY; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
|  |  | SRP8-160 |  | TOWING | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-031 |  | XXXX | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-040 |  | XXXX | OBSOLETE | [5 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-041 |  | RD EMERGENCY BRAKE | [6 empty] | FALSE | FALSE | FALSE | FALSE
|  |  | SRP8-042 |  | RD LSP UNITS | [6 empty] | FALSE | FALSE | FALSE | FALSE
NOT PART OF THE CAR - TO BE OBSOLETED |  | OBSOLETE | Column2: SRP8-052; Column3: BOM; Column4: OFFCAR; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
THIS IS A TASK, NOT A PROJECT - TO BE OBSOLETED |  | OBSOLETE | Column2: SRP8-107; Column3: INTERIOR LAYOUT; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
THIS IS A TASK, NOT A PROJECT - TO BE OBSOLETED |  | OBSOLETE | Column2: SRP8-108; Column3: HMI; Column9: FALSE; Column10: FALSE; Column11: FALSE; Column12: FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | DOOR WINDOWS | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | PV ARRAY GLASS | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | EMOTION | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | DIGITAL TWIN | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | AI | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | AUGMENTED REALITY | [6 empty] | FALSE | FALSE | FALSE | FALSE
[5 empty] | CANCEL RESEARCH PROJECT NAMING | [6 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE
[12 empty] | FALSE | FALSE | FALSE | FALSE

## SR8 Assembly Order (COPY)
Your Assembly | Project | Section | Department | External Dependency (Put Sunswift if none needed) | External Partner (How long securing partnership / acquiring material takes) | Assigned Person | Time to complete (How long it takes after Sunswift can start working on it?) | Mat Sci Consultant | Depends on (List all underneath) | Same Time (Can/need to be designed) | Impacts (List all underneath) | Assembly 1 | Assembly 2 | Assembly 3 | Assembly 4 | Assembly 5 | Assembly 6 | Assembly 7 | Assembly 8 | Assembly 9 | Assembly 10 | Assembly 11 | Assembly 12 | Assembly 13 | Assembly 14 | Assembly 15 | Assembly 16 | Assembly 17 | Assembly 18 | Assembly 19 | Assembly 20 | Assembly 21 | Assembly 22 | Assembly 23 | Assembly 24 | Assembly 25 | Assembly 26 | Assembly 27 | Assembly 28 | Assembly 29 | Assembly 30 | Assembly 31 | Assembly 32 | Assembly 33 | Assembly 34 | Assembly 35 | Assembly 36 | Assembly 37 | Assembly 38 | Assembly 39 | Assembly 40 | Assembly 41 | Assembly 42 | Assembly 43 | Assembly 44 | Assembly 45 | Assembly 46 | Assembly 47 | Assembly 48 | Assembly 49 | Assembly 50 | Assembly 51 | Assembly 52 | Assembly 53 | Assembly 54 | Assembly 55 | Assembly 56
ASSY CHASSIS BRAKE LINE | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT BRAKE LINE | ASSY - REAR BRAKE LINE
ASSY - WINDSCREEN WIPER MOTOR | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Aditya Bansal | 2 weeks |  |  |  |  | ASSY - WINDSCREEN WIPER | ASSY - WINDSCREEN WIPER MOTOR
ASSY - WINDSCREEN WIPER CONTROL PCB CODE | WINDSCREEN WIPERS | WINDSCREEN | EMBEDDED SYSTEMS | Sunswift |  |  | 4 Weeks |  | N/A |  | N/A | ASSY - WINDSCREEN WIPER CONTROL PCB CODE
ASSY - WINDSCREEN WIPER CONTROL PCB | WINDSCREEN WIPERS | WINDSCREEN | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 4 Weeks (when started) |  | ASSY - WINDSCREEN WIPER MOTOR |  | N/A | ASSY - WINDSCREEN WIPER MOTOR | ASSY - WINDSCREEN WIPER CONTROL PCB
ASSY - WINDSCREEN WIPER AERO GUARD | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK | Sunswift | 0 Weeks | Aditya Bansal | 3 weeks |  |  |  |  | ASSY - WINDSCREEN | ASSY - WINDSCREEN WIPER | ASSY - FRONT BODY STRUCTURE | ASSY - OCCUPANT CELL SPIDER
ASSY - WINDSCREEN WIPER | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK | Unknown | 4 weeks | Aditya Bansal | 3 weeks |  |  |  |  | ASSY - OCCUPANT CELL SPIDER | ASSY - WINDSCREEN | ASSY - WINDSCREEN WASHER | ASSY - WINDSCREEN WIPER AERO GUARD
ASSY - WINDSCREEN WASHER | WINDSCREEN WIPERS | WINDSCREEN | CHASSIS & BODYWORK | Unknown | 4 weeks | Aditya Bansal | 2 weeks |  |  |  |  | ASSY - WINDSCREEN WIPER | ASSY - WINDSCREEN
ASSY - WINDSCREEN | WINDSCREEN | WINDSCREEN | CHASSIS & BODYWORK | Unknown | 4 weeks | Aditya Bansal | 3 weeks |  |  |  |  | ASSY - OCCUPANT CELL SPIDER
ASSY - TRIP ENERGY PREDICTION MVP | TRIP ENERGY PREDICTION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - TELEMETRY MVP, ASSY - INFOTAINMENT MVP
ASSY - TRIP ENERGY PREDICTION | TRIP ENERGY PREDICTION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP, ASSY - TELEMETRY, ASSY - INFOTAINMENT
ASSY - TRACKSIDE RADIO COMMUNICATION MVP | TRACKSIDE RADIO COMMUNICATION | COMMUNICATIONS | TECHNICAL SUPPORT SYSTEMS | D2N |  | Nathan Nguyen |  |  | N/A
ASSY - TRACKSIDE RADIO COMMUNICATION | TRACKSIDE RADIO COMMUNICATION | COMMUNICATIONS | TECHNICAL SUPPORT SYSTEMS | D2N |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - THROTTLE PEDAL | PEDALS | PEDALS | INTERIOR | Sunswift |  | Ray He | 1 week |  |  |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER | ASSY - PEDAL PRESS SENSOR | ASSY - THROTTLE PEDAL
ASSY - THERMAL BOX | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK | AutoFrost, PWR | 3-4 weeks | Peleg Mondry Cohen | 6 Weeks |  |  |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - HVAC BOX
ASSY - TELEMETRY MVP | TELEMETRY | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | AWS |  | Nathan Nguyen | 3 months + |  | ASSY - PERFORMANCE OPTIMSATION MVP |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - TELEMETRY | TELEMETRY | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | AWS |  | Nathan Nguyen | 3 months + |  | ASSY - PERFORMANCE OPTIMSATION, ASSY - SUNSWIFT PHONE APP MVP
ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | TAILLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | N/A |  | N/A | ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE
ASSY - TAILLIGHT/INDICATOR PCB - RH | TAILIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 6 Weeks |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH |  | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | ASSY - TAILLIGHT/INDICATOR PCB - RH
ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | TAILLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | N/A |  | N/A | ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE
ASSY - TAILLIGHT/INDICATOR PCB - LH | TAILIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 6 Weeks |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH |  | N/A | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - TAILLIGHT/INDICATOR PCB- LH
ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | TAILIGHTS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks |  |  |  |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH
ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | TAILIGHTS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks |  |  |  |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - SOLAR ROOF ARRAY
ASSY - SUNSWIFT PHONE APP MVP | SUNSWIFT PHONE APP | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen | 3 months + |  | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP, ASSY - INFOTAINMENT MVP, ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - APPLE & ANDROID COMPATABILITY MVP
ASSY - SUNSWIFT PHONE APP | SUNSWIFT PHONE APP | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen | 3 months + |  |  |  | ASSY - INTRANET
ASSY - SUN VISOR RH | CEILING | INTERIOR | INTERIOR | Sunswift |  | Jason Jin | 3 weeks |  |  |  | ASSY - CEILING | ASSY - SUN VISOR RH | ASSY - CEILING
ASSY - SUN VISOR LH | CEILING | INTERIOR | INTERIOR | Sunswift |  | Jason Jin | 3 weeks |  |  |  | ASSY - CEILING | ASSY - SUN VISOR LH | ASSY - CEILING
ASSY - SUBWOOFER | AUDIO | AUDIO | EMBEDDED SYSTEMS | Sunswift |  | Merujen Chelvakumaran | 3 Weeks |  |  |  | ASSY - OCCUPANT CELL TUB
ASSY - STEERING WHEEL PCB CODE | STEERING WHEEL | STEERING WHEEL | EMBEDDED SYSTEMS | Sunswift |  |  | 4 Weeks |  | ASSY - STEERING WHEEL PCB |  | N/A | ASSY - STEERING WHEEL PCB | ASSY - STEERING WHEEL PCB CODE
ASSY - STEERING WHEEL PCB | STEERING WHEEL | STEERING | EMBEDDED SYSTEMS | Sunswift |  | Zoe Conroy | 6 Weeks |  | - |  | ASSY - STEERING WHEEL | ASSY - STEERING WHEEL | ASSY - STEERING WHEEL PCB
ASSY - STEERING WHEEL | STEERING WHEEL | STEERING | INTERIOR | Sunswift |  | Anubhav Sharma | 4 weeks |  | ASSY-STEERING WHEEL PCB |  | ASSY - DRIVER DISPLAY (BUTTONS & FUNCTIONS), ASSY - STEERING COLUMN | ASSY - STEERING COLUMN | ASSY - STEERING WHEEL
ASSY - STEERING RACK | STEERING RACK | STEERING | VEHICLE DYNAMICS | Flaming River (1st Option) | 4 weeks (?) | Oliver Freeman | 2 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - STEERING COLUMN | ASSY - STEERING COLUMN
ASSY - STEERING COLUMN MOUNT | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 2 Weeks |  | ASSY - STEERING COLUMN |  | ASSY - OCCUPANT CELL TUB | ASSY - STEERING COLUMN | ASSY - STEERING WHEEL | ASSY - OCCUPANT CELL TUB
ASSY - STEERING COLUMN | STEERING COLUMN | STEERING | VEHICLE DYNAMICS | Flaming River (1st Option) | 4 weeks (?) | Oliver Freeman | 2 weeks |  | ASSY - STEERING WHEEL, ASSY - STEERING RACK |  | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE | ASSY - STEERING RACK | ASSY - STEERING WHEEL
ASSY - SOLAR ROOF ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS | Sundrive (cell supplier), Corning (or alt provider), McCognaughy (for lamination), REOO (alt., laminator provider) | 12 weeks | Harry Schaut | 8 weeks |  |  |  | ASSY-occupant cell spider, ASSY - occupant cell tub, ASSY-ceiling, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - SOLAR ROOF ARRAY
ASSY - SOLAR BOOT ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 weeks | Harry Schaut | 8 Weeks |  |  |  | ASSY-boot, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BOOT | ASSY - SOLAR BOOT ASSAY
ASSY - SOLAR BONNET ARRAY | SOLAR ARRAY | PV | ENERGY SYSTEMS | Sundrive (cell supplier), Corning (or other glass provider), McCognaughy (Provides heat/pressure room for laminator), REOO (alt., potential chinese laminator provider) | 12 weeks | Harry Schaut | 8 Weeks |  |  |  | ASSY-bonnet, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BONNET | ASSY - SOLAR BONNET ARRAY
ASSY - SIDE INDICATOR EXTERIOR - RH | INDICATORS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 week
ASSY - SIDE INDICATOR EXTERIOR - LH | INDICATORS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks
ASSY - SIDE INDICATOR - RH | INDICATORS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 4 Weeks |  | N/A |  | ASSY - SIDE CAMERA - RH | ASSY - SIDE INDICATOR - RH
ASSY - SIDE INDICATOR - LH | INDICATORS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 4 Weeks |  | N/A |  | ASSY - SIDE CAMERA - LH | ASSY - SIDE INDICATOR - LH
ASSY - SIDE CAMERA - RH | SIDE VISION SYSTEM | VISION | EMBEDDED SYSTEMS | Unknown for monitor/espresso | 4 weeks | Martina Antonia Casagrande | 6 weeks(when we can test cameras) |  | N/A |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH
ASSY - SIDE CAMERA - LH | SIDE VISION SYSTEM | VISION | EMBEDDED SYSTEMS | Unknown for monitor/espresso | 4 weeks | Martina Antonia Casagrande | 6 weeks(when we can test cameras) |  | N/A |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH,
Assy - Shingled Matrix Panels | Shingled/Solar Array | PV | Energy systems | Sunswift | 0 | Parikant (Shivom) Shandil | 3 months + |  |  |  | ASSY-boot, ASSY-MPPT, ASSY-MC4 Cabling | ASSY - BOOT | Assy - Shingled Matrix Panels
ASSY - SENSOR MOTHERBOARD - FL | SENSORS | SENSORS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 3 Months + |  | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - FL
ASSY - SENSOR MOTHERBOARD - BL | SENSORS | SENSORS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 3 Months + |  | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - BL
ASSY - SAFETY VALVE | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT
ASSY - REARWHEEL HUB AIR INTAKE | AIRFLOW & VENTING | HYDROGEN | ALT | Sunswift |  | Simeon |  |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE |  | ASSY - HYDROGEN CONTROL LOGIC | HYDROGEN COMPARTMENT STRUCTURE
ASSY - REAR WHEEL | REAR WHEEL | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 4 weeks (?) | Madhav Katarya | 2 weeks |  | - |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE LH, ASSY - REAR LOWER WISHBONE RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR VISION CAMERA | REAR VISION SYSTEM | VISION | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 4 Weeks |  | N/A |  | N/A
ASSY - REAR UPRIGHT - RH | REAR UPRIGHTS | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - REAR DAMPER - RH | ASSY - REAR SUSPENSION | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE DISC | ASSY - REAR DAMPER | ASSY - REAR UPPER WISHBONE | ASSY - REAR LOWER WISHBONE
ASSY - REAR UPRIGHT - LH | REAR UPRIGHTS | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - REAR DAMPER - LH | ASSY - REAR SUSPENSION | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE DISC | ASSY - REAR DAMPER | ASSY - REAR UPPER WISHBONE | ASSY - REAR LOWER WISHBONE
ASSY - REAR TOP WISHBONE - RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Oliver Freeman | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR TOP WISHBONE - LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Oliver Freeman | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR TOELINK | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Oliver Freeman | 2 weeks |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE LH, ASSY - REAR LOWER WISHBONE RH |  | - | ???
ASSY - REAR SUPPORT STRUCTURE | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 5 Weeks |  | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB |  | ASSY - BOOT | ASSY - REAR BUMPER | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - OCCUPANT CELL TUB | ASSY - BOOT | ASSY - BOOT LOCKING BOARD
ASSY - REAR QUARTER PANEL - LH | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 2 Weeks |  |  |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH, ASSY - OUTER DOOR HANDLE - LH | ASSY - OCCUPANT CELL TUB | ASSY - REAR BUMPER | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH
ASSY - REAR QUARTER PANEL - RH | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 2 Weeks |  |  |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH, ASSY - OUTER DOOR HANDLE - RH | ASSY - OCCUPANT CELL TUB | ASSY - REAR BUMPER | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH
ASSY - REAR MASTER CYLINDER RESERVOIR | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACKASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER | ASSY - FRONT MASTER CYLINDER RESERVOIR
ASSY - REAR MASTER CYLINDER | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR BRAKE LINE | ASSY - FRONT UPRIGHT
ASSY - REAR LOWER WISHBONE RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Oliver Freeman | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR LOWER WISHBONE LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Oliver Freeman | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR FLUID MANAGEMENT | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK | Unknown | 3 Weeks | Ray | 5 Weeks |  | ASSY - THERMAL BOX, ASSY - FRONT FLUID MANAGEMENT, ASSY - MOTORS, ASSY - POWER ELECTRONICS, ASSY - HYDROGEN COOLING SYSTEM |  | ASSY - OCCUPANT CELL TUB | ASSY - BATTERY | ASSY - OCCUPANT CELL TUB | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT
ASSY - REAR FLOOR | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 3 weeks |  | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH |  | ASSY - BOOT | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - REAR BUMPER | ASSY - OCCUPANT CELL TUB
ASSY - REAR DAMPER - RH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | Bilstein | 0 | Alex McArdle | 2 weeks |  | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - RH |  |  | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR DAMPER - LH | REAR SUSPENSION | REAR SUSPENSION | VEHICLE DYNAMICS | Bilstein | 0 | Alex McArdle | 2 weeks |  | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - LH |  |  | ASSY - REAR SUSPENSION | ASSY - REAR UPRIGHT
ASSY - REAR CRASH STRUCTURE | CRASH STRUCTURES | CHASSIS | CHASSIS & BODYWORK | Calm Aluminium | 0 | John Zhu | 3 weeks |  |  | ASSY - FRONT CRASH STRUCTURE | ASSY - OCCUPANT CELL TUB
ASSY - REAR BUMPER | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 6 weeks |  | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH |  | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - BOOT | ASSY - BOOT LOCKING BOARD | ASSY - REAR FLOOR | ASSY - REAR SUPPORT STRUCTURE | ASSY - BLINDSPOT MONOTORING SENSOR - LH |  | REAR PARKING SENSOR
ASSY - REAR BRAKE LINE | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE DISC
ASSY - REAR BRAKE DISC | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - REAR WHEEL |  | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE CALIPER | ASSY - REAR BRAKE LINE
ASSY - REAR BRAKE CALIPER - RH | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC |  | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT
ASSY - REAR BRAKE CALIPER - LH | REAR BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC |  | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT | ASSY - REAR BRAKE LINE | ASSY - REAR UPRIGHT
ASSY - PWT HV WIRING - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Unknown | 4 weeks | Thomas Ngo | 2 weeks |  | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH | ASSY - PWT HV WIRING - RH
ASSY - PWT HV WIRING - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Unknown | 4 weeks | Thomas Ngo | 2 weeks |  | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH | ASSY - PWT HV WRING - LH
ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Sunswift |  | Simeon |  |  |  |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL | REAR FLOOR | OCCUPANT CELL TUB
ASSY - PRESSURE VESSEL SHELL | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Coregas, Swagelok (if we custom buy), or alternate vendor | 6 weeks | Doha |  |  | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - PRESSURE REGULATION & SAFETY | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT | Swagelok (valves, PRD, tubing) | 12 weeks | Doha |  |  | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE |  | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - PRESSURE MONITORING AND CONTROL | HYDROGEN PRESSURE VESSEL | HYDROGEN | ALT
ASSY - POWER ELECTRONICS | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT
ASSY - PERFORMANCE OPTIMISATION MVP | PERFORMANCE OPTIMISATION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | N/A
ASSY - PERFORMANCE OPTIMISATION | PERFORMANCE OPTIMISATION | DATA ANALYSIS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - PEDAL PRESS SENSOR | PEDALS | PEDALS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 1 Week |  | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL |  | N/A | ASSY - PEDAL PRESS SENSOR
ASSY - PEDAL BOX CONTROLLER | PEDALS | PEDALS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 2 Weeks (when resumed) |  | ASSY - PEDAL PRESS SENSOR |  | N/A | ASSY - PEDAL PRESS SENSOR | ASSY - PEDAL BOX CONTROLLER
ASSY - PEDAL BOX | PEDALS | PEDALS | INTERIOR | Sunswift |  | Ray He | 2 weeks |  | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR |  | ASSY - OCCUPANT CELL TUB | ASSY - OCCUPANT CELL TUB | ASSY - THROTTLE PEDAL | ASSY - BRAKE PEDAL | ASSY - PEDAL BOX | ASSY - MASTER CYLINDER
ASSY - P&ID HYDROGEN RECYCLE STREAM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Siltrax | 6 weeks | Kurtis |  |  | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN SENSOR ARRAY | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK
ASSY - P&ID HYDROGEN DOWNSTREAM LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Sunswift + Swagelok | 6 weeks | Natalie |  |  | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT |  | ASSY - P&ID AIR SUPPLY LINE | HYDROGEN SUPPLY LINE | HYDROGEN PURGE MANAGEMENT | FUEL CELL STACK
ASSY - P&ID AIR SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Sunswift + Beswick + Swagelok | 8 weeks | Liam |  |  | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE |  | ASSY - OCCUPANT CELL SHUTDOWN VALVE | REARWHEEL HUB AIR INTAKE | AIR SOURCE
ASSY - OUTER DOOR HANDLE - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 weeks |  | ASSY - DOOR LATCH - RH |  |  | ASSY - REAR QUARTER PANEL - RH | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH |  | ASSY - DOOR CONTROL BOARD - RH
ASSY - OUTER DOOR HANDLE - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 weeks |  | ASSY - DOOR LATCH - LH |  |  | ASSY - REAR QUARTER PANEL - LH | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH |  | ASSY - DOOR CONTROL BOARD - LH
ASSY - ONBOARD CHARGING WIRING | ONBOARD CHARGING | CHARGING | ENERGY SYSTEMS | Inner Electric |  | Eric Lin | 2 weeks |  | ASSY - ONBOARD CHARGING INSTALLATION
ASSY - ONBOARD CHARGER INSTALLATION | ONBOARD CHARGING | CHARGING | ENERGY SYSTEMS | Inner Electric |  | Eric Lin | 3 weeks |  |  |  | ASSY - ONBOARD CHARGER WIRING
ASSY - OCCUPANT CELL TUB | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 5 Weeks |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEATBELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTING, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEATBELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULE, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD LH | ASSY - OCCUPANT CELL SPIDER | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - DOOR CARD - LH, ASSY - FRONT CLAMSHELL | ASSY - BATTERY | ASSY - OCCUPANT CELL SPIDER | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - LH | ASSY - DOOR LATCH - LH | ASSY - DOOR LATCH - RH | ASSY - FRONT TOP WISHBONE - LH | ASSY - FRONT TOP WISHBONE - RH | ASSY - FRONT LOWER WISHBONE - LH | ASSY - FRONT LOWER WISHBONE - LH | ASSY - FRONT DAMPER - LH | ASSY - FRONT DAMPER - RH | ASSY - REAR TOP WISHONE - LH | ASSY - REAR TOP WISHONE - LH | ASSY - REAR LOWER WISHBONE LH | ASSY - REAR LOWER WISHBONE RH | ASSY - REAR PUSHROD | ASSY - REAR TOELINK | ASSY - REAR DAMPER - LH | ASSY - REAR DAMPER - RH | ASSY - FRONT MASTER CYLINER | ASSY - HAND BRAKE | ASSY - REAR MASTER CYLINDER | ASSY - STEERING COLUMN | ASSY - STEERING RACK | ASSY - BRAKE PEDAL | ASSY - DASHBOARD | ASSY - FRONT SEAT DRIVER | ASSY - FRONT SEAT PASSENGER | ASSY - FRONT SEAT BEL DRIVER | ASSY - FRONT SEATBELT PASSENGER | ASSY - MOTOR UNIT - LH | ASSY - MOTOR UNIT - RH | ASSY - HV WRING - LH | ASSY - HV WIRING - RH | ASSY - AXLE CV - LH | ASSY - AXLE CV - RH | ASSY - SUBWOOFER | ASSY - FRONT CRASH STRUCTURE | ASSY - REAR CRASH STRUCTURE | ASSY - HVAC BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - FRONT FLOOR | ASSY - REAR FLOOR | ASSY - BOOT | ASSY - BONNET | ASSY - DOOR HINGE - LH | ASSY - DOOR HINGE - RH | ASSY - CHASSIS SUBFRAME | ASSY - THERMAL BOX | ASSY - STEERING COLUMN MOUNT | ASSY - OCCUPANT CELL TUB
ASSY - OCCUPANT CELL SPIDER | OCCUPANT CELL | CHASSIS | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Aditya Bansal | 5 Weeks |  | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH | ASSY - OCCUPANT CELL TUB | ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD | ASSY - SOLAR ROOF ARRAY | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - LH | ASSY - WINDSCREEN | ASSY - CEILING | ASSY - OCCUPANT CELL SPIDER
ASSY - OCCUPANT CELL SHUTDOWN VALVE | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Swagelok or equivalent supplier | 6 weeks | Mohammad |  |  | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC |  |  | OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN CONTROL LOGIC
ASSY - OCCUPANT CELL HYDROGEN SENSOR | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Gas detection supplier (Honeywell/CityTech etc.) | 10 weeks | Adit |  |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE |  | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS | HYDROGEN COMPARTMENT STRUCTURE
ASSY - MPPT JUNCTION BOX | MPPT JUNCTION BOX | PV | ENERGY SYSTEMS | Sunswift? |  | Mohamad Bazzi | 2 weeks |  | ASSY - MPPT |  | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC
ASSY - MPPT | MPPT JUNCTION BOX | PV | ENERGY SYSTEMS | Sunswift? |  | Mohamad Bazzi | 4 weeks |  | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels |  | ASSY-occupant cell spider
ASSY - MOTOR UNIT - RH | MOTORS | MOTORS | POWERTRAIN | Schaeffler | 0 weeks (done) | Anthony Wang | 2 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM | ASSY - MOTOR UNIT - RH
ASSY - MOTOR UNIT - LH | MOTORS | MOTORS | POWERTRAIN | Schaeffler | 0 weeks (done) | Anthony Wang | 2 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME, ASSY - INVERTER, ASSY - INVERTER MOUNTING FRAME, ASSY - PWT HV WIRING, ASSY - GEARBOX, ASSY - CV AXLES, ASSY - ENERGY CONTROL SYSTEM, ASSY - FUEL CELL COOLING SYSTEM, ASSY - HYDROGEN STORAGE SYSTEM | ASSY - MOTOR UNIT - LH
ASSY - MOTOR MOUNTING FRAME - RH | MOTORS | MOTORS | POWERTRAIN | Sunswift | 0 weeks | Anthony Wang | 6 weeks |  | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - MOTOR MOUNTING FRAME - RH
ASSY - MOTOR MOUNTING FRAME - LH | MOTORS | MOTORS | POWERTRAIN | Sunswift | 0 weeks | Anthony Wang | 6 weeks |  | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - MOTOR MOUNTING FRAME - LH
ASSY - MC4 Cabling | SOLAR ARRAY | PV | ENERGY SYSTEMS | None, by off shelf, Maybe SunDrive | 0 | Harry Schaut | 4 Weeks |  | ASSY- solar boot array, ASSY- Solar bonnet array, ASSY- Solar roof array, ASSY- Shingled Matrix Panels |  | ASSY- Occupant cell spider, ASSY- boot, ASSY- Bonnet, ASSY - MPPT | ASSY - SOLAR BONNET ARRAY | ASSY - SOLAR ROOF ARRAY | ASSY - SOLAR BOOT ARRAY | Assy - Shingled Matrix Panels | ASSY - MPPT | ASSY - MC4 Cabling | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB
ASSY - MAIN COMPUTER | INTERNAL EMBEDDED NETWORK | EMBEDDED | EMBEDDED SYSTEMS | Adlink | 8 weeks | Hamish Hunter | 1 Week |  |  |  | INST - INTERNAL EMBEDDED NETWORK WIRING | INST - OCCUPANT CELL TUB | INST - MAIN COMPUTER
ASSY - INVERTER MOUNTING FRAME - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Sunswift | 0 weeks | Kabir Kohli | 6 weeks |  | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | - | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH | ASSY - INVERTER MOUNTING FRAME - RH
ASSY - INVERTER MOUNTING FRAME - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Sunswift | 0 weeks | Kabir Kohli | 6 weeks |  | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | - | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH | ASSY - INVERTER MOUNTING FRAME - LH
ASSY - INVERTER - RH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Schaeffler | 0 weeks (done) | Thomas Ngo | 2 weeks |  | ASSY - MOTOR UNIT - RH |  | ASSY - HYDROGEN COOLING SYSTEM | ASSY - MOTOR UNIT - RH | ASSY - INVERTER - RH
ASSY - INVERTER - LH | POWERTRAIN ELECTRONICS | ELECTRICAL | POWERTRAIN | Schaeffler | 0 weeks (done) | Thomas Ngo | 2 weeks |  | ASSY - MOTOR UNIT - LH |  | ASSY - HYDROGEN COOLING SYSTEM | ASSY - MOTOR UNIT - LH | ASSY - INVERTER - LH
ASSY - INTRANET MVP | INTRANET | INTERNAL TOOLS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | N/A |  | ASSY - TRACKSIDE RADIO COMMUNICATION MVP, ASSY - TELEMETRY MVP, ASSY - PERFORMANCE OPTIMISATION MVP, ASSY - TRIP ENERGY PREDICTION MVP
ASSY - INTRANET | INTRANET | INTERNAL TOOLS | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP
ASSY - INTERNAL EMBEDDED NETWORK WIRING | INTERNAL EMBEDDED NETWORK | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  |  | 2 Weeks |  | ASSY- HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY- HORN PCB, ASSY - TAILLIGHT/INDICATOR PCB- LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP PCB, ASSY - STEERING WHEEL PCB, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LiDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM,ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT, STRUCTURE, ASSY - BOOT, ASSY - BONNET |  |  | INST - INTERNAL EMBEDDED NETWORK WIRING
ASSY - INTERIOR LIGHTS PCB CODE | INTERIOR LIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | N/A |  | N/A | ASSY - INTERIOR LIGHTS PCB CODE
ASSY - INTERIOR LIGHTS PCB | INTERIOR LIGHTS | STEERING | EMBEDDED SYSTEMS | Sunswift |  | Deniz Durensil | 6 Weeks |  | N/A |  | ASSY - CEILING | ASSY - INTERIOR LIGHT MODULE | ASSY - INTERIOR LIGHTS PCB
ASSY - INNER DOOR HANDLE - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 weeks |  | ASSY - DOOR CARD - RH |  |  | ASSY - DOOR LATCH - RH | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH |  | ASSY - DOOR CONTROL BOARD - RH
ASSY - INNER DOOR HANDLE - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 weeks |  | ASSY - DOOR CARD - LH |  |  | ASSY - DOOR LATCH - LH | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH |  | ASSY - DOOR CONTROL BOARD - LH
ASSY - INFOTAINMENT MVP | INFOTAINMENT | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - HUMAN MACHINE INTERFACE (HMI) MVP |  | ASSY - BLUETOOTH CONNECTIVITY MVP, ASSY - SUNSWIFT PHONE APP MVP
ASSY - INFOTAINMENT | INFOTAINMENT | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | HYDROGEN ENERGY SYSTEM | OCCUPANT CELL | ALT | Internal + electrical team |  | Adit |  |  | ASSY - FC ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY |  |  | HYDROGEN SENSOR ARRAY | FC ELECTRICAL CONNECTIONS
ASSY - HYDROGEN SUPPLY LINE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Swagelok | 6 weeks | Mohammad |  |  | ASSY - PRESSURE REGULATION & SAFETY |  | ASSY - PURGE MANAGEMENT, ASSY - SENSOR ARRAY | PRESSURE REGULATION & SAFETY
ASSY - HYDROGEN STORAGE SYSTEM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT |  |  | Liam |  |  | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE |  | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - P&ID AIR SUPPLY LINE | REARWHEEL HUB AIR INTAKE | AIR SOURCE
ASSY - HYDROGEN SENSOR ARRAY | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | TBD (sensor supplier) | 10 weeks | Adit |  |  | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | PRESSURE REGULATION & SAFETY | HYDROGEN SUPPLY LINE | FUEL CELL STACK
ASSY - HYDROGEN PURGE MANAGEMENT | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Siltrax, Swagelok | 0, 6 weeks | Kurtis |  |  | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE |  | ASSY - P&ID HYDROGEN RECYCLE STREAM | FUEL CELL STACK | HYDROGEN SUPPLY LINE
ASSY - HYDROGEN COOLING SYSTEM | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Sunswift |  | Natalie |  |  | ASSY - FUEL CELL STACK, |  | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FC ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT | REAR FLUID MANAGEMENT | FRONT FLUID MANAGEMENT | FUEL CELL STACK
ASSY - HYDROGEN CONTROL LOGIC | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Sunswift + External Supplier/Partner (unknown) | 16 weeks | Mohammad |  |  | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK |  | ASSY - HYDROGEN CONTROL SYSTEM | HYDROGEN SENSOR ARRAY | FUEL CELL STACK | HYDROGEN CONTROL SYSTEM
ASSY - HYDROGEN COMPARTMENT VENTILATION | AIRFLOW & VENTING | HYDROGEN | ALT | Sunswift (a supplier for fans or IP-rated components) |  | Simeon |  |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE |  | ASSY - P&ID AIR SUPPLY LINE, ASSY - REARWHEEL HUB AIR INTAKE | HYDROGEN COMPARTMENT STRUCTURE
ASSY - HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN ENERGY SYSTEM | HYDROGEN | ALT | Sunswift |  | Simeon |  |  | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE |  | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR | PRESSURE VESSEL SHELL | PRESSURE VESSEL SUPPORT STRUCTURE
ASSY - HYDROGEN CONTROL SYSTEM | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Siltrax, External Supplier/Partner (unknown) | Ballard or Intelligent Energy (2-3 months) | Adit |  |  | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS, ASSY - FC ELECTRICAL CONNECTIONS |  |  | HYDROGEN CONTROL LOGIC | ECS | FC ELECTRICAL CONNECTIONS
ASSY - HVAC PIPING | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK | Unknown | 3 weeks | Peleg Mondry Cohen | 7 Weeks |  | ASSY - THERMAL BOX | ASSY - HVAC BOX | ASSY - FRONT FLUID MANAGEMENT | ASSY - HVAC BOX | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT
ASSY - HVAC BOX | AIR CONDITIONING | INTERIOR | CHASSIS & BODYWORK | AutoFrost | 0 | Peleg Mondry Cohen | 8 Weeks |  | ASSY - THERMAL BOX | ASSY - HVAC PIPING | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING | ASSY - HVAC BOX
ASSY - HUMAN MACHINE INTERFACE (HMI) MVP | HUMAN MACHINE INTERFACE | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - DASHBOARD STRUCTURE |  | ASSY - INFOTAINMENT MVP
ASSY - HUMAN MACHINE INTERFACE (HMI) | HUMAN MACHINE INTERFACE | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - HORN PCB | HORN | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  | Zoe Conroy | 3 Weeks |  |  |  | N/A | ASSY- HORN PCB
ASSY - HORN | HORN | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  | Zoe Conroy | 1 Week |  |  |  | N/A | ASSY- HORN PCB | ASSY - HORN
ASSY - HEADS-UP DISPLAY | HEADS-UP DISPLAY | DASHBOARD | INTERIOR | Espresso conversation | 0 | Sebastian Moore |  |  |  |  | ASSY - DASHBOARD STRUCTURE
ASSY - HEADLIGHT/INDICATOR PCB - RH | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 2 Weeks (when I can work on it again) |  |  |  | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - HEADLIGHT/INDICATOR PCB - RH
ASSY - HEADLIGHT/INDICATOR PCB - LH | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 2 Weeks (when I can work on it again) |  |  |  | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT/INDICATOR PCB - LH
ASSY - HEADLIGHT EXTERIOR - RH | HEADLIGHTS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks
ASSY - HEADLIGHT EXTERIOR - LH | HEADLIGHTS | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks
ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | N/A |  | N/A | ASSY - HEADLAMP/INDICATOR PCB - RH - CODE
ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | HEADLIGHTS | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | N/A |  | N/A | ASSY - HEADLAMP/INDICATOR PCB - LH - CODE
ASSY - HAND BRAKE | HANDBRAKE | BRAKES | VEHICLE DYNAMICS | SUNSWIFT |  | Madhav Katarya | 2 weeks |  | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC |  | ASSY CHASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE | ASSY - REAR UPRIGHT | ASSY - CHASSIS BRAKE LINE | ASSY - REAR BRAKE LINE | ASSY - REAR BRAKE CALIPER
ASSY - GEARBOX - RH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Ricardo/Unknown | 8 weeks | Jack Lawson | 3 weeks |  | ASSY - MOTOR UNIT - RH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - RH | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - RH
ASSY - GEARBOX - LH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Ricardo/Unknown | 8 weeks | Jack Lawson | 3 weeks |  | ASSY - MOTOR UNIT - LH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLE - LH | ASSY - MOTOR UNIT - LH | ASSY - GEARBOX - LH
ASSY - FUEL CELL STACK | HYDROGEN FUEL CELL | HYDROGEN | ALT | Siltrax | 6 weeks | Doha |  |  | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY |  | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN COMPARTMENT STRUCTURE | HYDROGEN SUPPLY LINE | HYDROGEN COOLING SYSTEM | BATTERY
ASSY - FUEL CELL SENSOR | HYDROGEN FUEL CELL | HYDROGEN | ALT
ASSY - FUEL CELL MONITORING SYSTEM | HYDROGEN FUEL CELL | HYDROGEN | ALT
ASSY - FUEL CELL ELECTRICAL CONNECTIONS | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT | Sunswift |  | Adit |  |  | ASSY - FUEL CELL STACK, ASSY - POWER ELECTRONICS |  | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | FUEL CELL STACK | POWER ELECTRONICS
ASSY - FUEL CELL COOLING SYSTEM | HYDROGEN FUEL CELL | HYDROGEN | ALT
ASSY - FUEL CELL ANCILLARY SYSTEM | HYDROGEN ELECTRICAL SYSTEM | HYDROGEN | ALT
ASSY - FRONT WHEEL | FRONT WHEEL | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT |  | Madhav Katarya | 2 weeks |  | - |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT
ASSY - FRONT UPRIGHT - RH | FRONT UPRIGHTS | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks |  | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE | ASSY - FRONT BRAKE DISC | ASSY - FRONT DAMPER | ASSY - FRONT UPPER WISHBONE | ASSY - FRONT LOWER WISHBONE
ASSY - FRONT UPRIGHT - LH | FRONT UPRIGHTS | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 4 weeks (?) | Alex McArdle | 2 weeks |  | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE | ASSY - FRONT BRAKE DISC | ASSY - FRONT DAMPER | ASSY - FRONT UPPER WISHBONE | ASSY - FRONT LOWER WISHBONE
ASSY - FRONT TOP WISHBONE - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT TOP WISHBONE - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT TIEROD - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - RH, ASSY - FRONT BRAKE DISC, ASSY - STEERING RACK |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - STEERING RACK | ASSY - STEERING COLUMN
ASSY - FRONT TIEROD - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT UPRIGHT - LH, ASSY - FRONT DAMPER - LH, ASSY - FRONT CALIPER - LH, ASSY - FRONT BRAKE DISC |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - STEERING RACK | ASSY - STEERING COLUMN
ASSY - FRONT SEAT RAIL DRIVER | FRONT SEATS | SEATS | INTERIOR | Bride Racing | 0 | Elisa Wong | 4 weeks |  | ASSY - FRONT SEAT DRIVER |  |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT RAIL DRIVER | ASSY - FRONT SEAT DRIVER
ASSY - FRONT SEAT PASSENGER | FRONT SEATS | SEATS | INTERIOR | Sunswift |  | Sebastian Williams | 4 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT PASSENGER | ASSY - FRONT SEAT PASSENGER
ASSY - FRONT SEAT MOUNT PASSENGER | FRONT SEAT MOUNT | SEATS | INTERIOR | Bride Racing | Just ordering- 1 week | Elisa Wong | 4 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER(space for bottom mount ) | ASSY - OCCUPANT CELL TUB
ASSY - FRONT SEAT MOUNT DRIVER | FRONT SEAT MOUNT | SEATS | INTERIOR | Bride Racing | Just ordering- 1 week | Elisa Wong | 4 weeks |  |  |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER ,ASSY - FRONT SEAT BELT DRIVER(space for bottom mount ) | ASSY - OCCUPANT CELL TUB
ASSY - FRONT SEAT DRIVER | FRONT SEATS | SEATS | INTERIOR | Sunswift |  | Sebastian Williams | 4 weeks |  |  |  | ASSY - FRONT SEAT RAIL DRIVER | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SEAT RAIL DRIVER | ASSY - FRONT SEAT DRIVER
ASSY - FRONT SEAT BELT PASSENGER | FRONT SEAT MOUNT | SEATS | INTERIOR | Unknown(just ordering) |  | Sebastian Williams | 1 week |  | ASSY - FRONT SEAT PASSENGER |  | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL | ASSY - FRONT SEATBELT PASSENGER
ASSY - FRONT SEAT BELT DRIVER | FRONT SEATBELTS | SEATS | INTERIOR | Unknown(just ordering) | 1 week | Sebastian Williams | 1 week |  | ASSY - FRONT SEAT DRIVER |  | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | ASSY - FRONT SEAT DRIVER | ASSY - FRONT SEAT BEL DRIVER
ASSY - FRONT PUSHROD RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  |  | Oliver Freeman |  |  | - |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT PUSHROD LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS |  |  | Oliver Freeman |  |  | - |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT MASTER CYLINDER RESERVOIR | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER
ASSY - FRONT MASTER CYLINDER | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - PEDAL BOX | ASSY - FRONT MASTER CYLINDER
ASSY - FRONT LOWER WISHBONE - RH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT LOWER WISHBONE - LH | FRONT SUSPENSION | FRONT SUSPENSION | VEHICLE DYNAMICS | SUNSWIFT | 2 weeks | Oliver Freeman | 2 weeks |  | ASSY - FRONT WHEEL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT | ASSY - OCCUPANT CELL TUB
ASSY - FRONT FLUID MANAGEMENT | THERMAL MANAGEMENT | INTERIOR | CHASSIS & BODYWORK | Unknown | 3 Weeks | Tim | 4 Weeks |  | ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX |  | ASSY - CHASSIS VENTILATION, ASSY - REAR FLUID MANAGEMENT, ASSY - BATTERY MODULE, ASSY - OCCUPANT CELL TUB | ASSY - BATTERY | ASSY - OCCUPANT CELL TUB | ASSY - HVAC BOX | ASSY - THERMAL BOX
ASSY - FRONT DAMPER - RH | FRONT DAMPERS | FRONT SUSPENSION | VEHICLE DYNAMICS | Bilstein | 0 | Alex McArdle | 2 weeks |  | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT
ASSY - FRONT DAMPER - LH | FRONT DAMPERS | FRONT SUSPENSION | VEHICLE DYNAMICS | Bilstein | 0 | Alex McArdle | 2 weeks |  | ASSY - FRONT WHEEL |  | - | ASSY - FRONT SUSPENSION | ASSY - FRONT UPRIGHT
ASSY - FRONT CRASH STRUCTURE | CRASH STRUCTURES | CHASSIS | CHASSIS & BODYWORK | Calm Aluminium | 0 | John Zhu | 4 Weeks |  |  | ASSY - REAR CRASH STRUCTURE | ASSY - OCCUPANT CELL TUB
ASSY - FRONT CLAM SHELL | BODYPANELS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Joshua Johnson | 7 Weeks |  | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LiDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB |  | ASSY - SOLAR BONNET ARRAY, ASSY - BONNET | ASSY - OCCUPANT CELL TUB | ASSY - HEADLIGHT EXTERIOR - LH | ASSY - HEADLIGHT EXTERIOR - RH | ASSY - BONNET LOCKING BOARD | ASSY - BONNET | ASSY - DOOR SHELL - LH | ASSY - DOOR SHELL - RH | ASSY - DOOR HINGE - LH | ASSY - SIDE INDICATOR EXTERIOR - LH | ASSY - SIDE INDICATOR EXTERIOR - RH | ASSY - SIDE CAMERA - LH | ASSY - SIDE CAMERA - RH | ASSY - CHASSIS VENTILATION | FRONT RADAR | FRONT PARKING
ASSY - FRONT CALIPER - RH | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | ASSY - FRONT UPRIGHT | ASSY - BRAKE DISC
ASSY - FRONT CALIPER - LH | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | ASSY - FRONT UPRIGHT | ASSY - BRAKE DISC
ASSY - FRONT BRAKE LINE | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD LH, ASSY - FRONT TIEROD RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | ASSY - OCCUPANT CELL TUB | ASSY - FRONT UPRIGHT | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE DISC
ASSY - FRONT BRAKE DISC | FRONT BRAKES | BRAKES | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 weeks | Madhav Katarya | 2 weeks |  | ASSY - FRONT WHEEL |  | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH | ASSY - FRONT UPRIGHT | ASSY - FRONT BRAKE CALIPER | ASSY - FRONT BRAKE LINE
ASSY - FATIGUE MONITORING SYSTEM | FATIGUE MONITORING SYSTEM | ADAS | EMBEDDED SYSTEMS | Sunswift |  | N/A |  |  | ASSY - OCCUPANT CELL TUB |  | N/A
ASSY - EMBEDDED HIGH LEVEL SOFTWARE | EMBEDDED HIGH LEVEL SOFTWARE | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Months + |  | ASSY - MAIN COMPUTER |  | N/A | INST - MAIN COMPUTER | INST - EMBEDDED HIGH LEVEL SOFTWARE
ASSY - ELECTRIC WINDOWS - RH | ELECTRIC WINDOWS | BODYWORK | CHASSIS & BODYWORK | Unknown | 4 weeks | Kaityln Hua | 2 weeks |  |  |  | ASSY - DOOR SHELL - RH | ASSY - DOOR SHELL - RH | ASSY - DOOR CONTROL BOARD - RH
ASSY - ELECTRIC WINDOWS - LH | ELECTRIC WINDOWS | BODYWORK | CHASSIS & BODYWORK | Unknown | 4 weeks | Kaityln Hua | 2 weeks |  |  |  | ASSY - DOOR SHELL - LH | ASSY - DOOR SHELL - LH | ASSY - DOOR CONTROL BOARD - LH
ASSY - ECS MODULE | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | Vincet Younes | 3 weeks |  |  |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC
ASSY - ECS LV WIRING | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | Vincet Younes | 2 weeks |  | ASSY - BATTERY PACK
ASSY - ECS HV WIRING | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | Vincet Younes | 2 weeks |  | ASSY - BATTERY PACK
ASSY - DRIVER DISPLAY | DRIVER DISPLAY | DASHBOARD | INTERIOR | Espresso conversation | 0 | Anubhav Sharma | 2 weeks |  | ASSY - STEERING WHEEL |  | ASSY - DASHBOARD STRUCTURE
ASSY - DRIVE CONTROL UNIT SOFTWARE | DRIVE CONTROL SYSTEMS | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Months + |  | ASSY - DRIVE CONTROL UNIT |  | N/A | ASSY - DRIVE CONTROL UNIT | ASSY - DRIVE CONTROL UNIT SOFTWARE
ASSY - DRIVE CONTROL UNIT | DRIVE CONTROL SYSTEMS | EMBEDDED | EMBEDDED SYSTEMS | Sunswift |  | N/A | 3 Months + |  | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH |  | N/A | ASSY - REAR BOOT | ASSY - DRIVE CONTROL UNIT
ASSY - DOOR SHELL - RH | DOORS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Kaityln Hua | 3 weeks |  | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH |  | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - RH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR HINGE - RH | ASSY - DOOR AUDIO - RH | ASSY - DOOR CONTROL BOARD - RH | ASSY - DOOR ACTUATOR BOARD - RH | ASSY - INNER DOOR HANDLE - RH | ASSY - OUTER DOOR HANDLE - RH | ASSY - DOOR LATCH - RH | ASSY - ELECTRIC WINDOWS - RH | ASSY - FRONT BODY STRUCTURE
ASSY - DOOR SHELL - LH | DOORS | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Kaityln Hua | 3 weeks |  | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH |  | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAMSHELL, ASSY - DOOR CARD - LH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR HINGE - LH | ASSY - DOOR AUDIO - LH | ASSY - DOOR CONTROL BOARD - LH | ASSY - DOOR ACTUATOR BOARD - LH | ASSY - INNER DOOR HANDLE - LH | ASSY - OUTER DOOR HANDLE - LH | ASSY - DOOR LATCH - LH | ASSY - ELECTRIC WINDOWS - LH | ASSY - FRONT BODY STRUCTURE
ASSY - DOOR LATCH - RH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 week |  |  |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - INNER DOOR HANDLE - RH | ASSY - OUTER DOOR HANDLE - RH |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR QUARTER PANEL - RH | ASSY - DOOR CONTROL BOARD - RH
ASSY - DOOR LATCH - LH | DOOR HANDLES | BODYWORK | CHASSIS & BODYWORK | Chevalier | 4 weeks | Melissa Thein | 2 weeks |  |  |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH | ASSY - INNER DOOR HANDLE - LH | ASSY - OUTER DOOR HANDLE - LH |  | ASSY - OCCUPANT CELL TUB | ASSY - REAR QUARTER PANEL - LH | ASSY - DOOR CONTROL BOARD - LH
ASSY - DOOR HINGE - RH | DOORS | BODYWORK | CHASSIS & BODYWORK | Stabillus | 1 week | Jack Wilson | 3 weeks |  |  |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD -RH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH
ASSY - DOOR HINGE - LH | DOORS | BODYWORK | CHASSIS & BODYWORK | Stabillus | 1 week | Jack Wilson | 3 weeks |  |  |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH
ASSY - DOOR CONTROL BOARD - RH - CODE | DOORS | DOORS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | ASSY - DOOR CONTROL BOARD - RH |  | N/A | ASSY - DOOR CONTROL BOARD - LH - CODE
ASSY - DOOR CONTROL BOARD - RH | DOORS | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 5 Weeks |  | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH |  | N/A | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH | ASSY - DOOR CONTROL BOARD - RH
ASSY - DOOR CONTROL BOARD - LH - CODE | DOORS | DOORS | EMBEDDED SYSTEMS | Sunswift |  |  | 3 Weeks |  | ASSY - DOOR CONTROL BOARD - LH |  | N/A | ASSY - DOOR CONTROL BOARD - LH - CODE
ASSY - DOOR CONTROL BOARD - LH | DOORS | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 5 Weeks |  | ASSY - DOOR HINGE - LH , ASSY - DOOR SHELL - LH |  | N/A | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH | ASSY - DOOR CONTROL BOARD - LH
ASSY - DOOR CARD - RH | DOORS | BODYWORK | INTERIOR | Sunswift |  | Yaheng Li | 3 Weeks |  | ASSY- OCUPANT CELL SPIDER,ASSY- OCUPANT CELL TUB ,ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE, ASSY - DOOR AUDIO - RH |  | ASSY - INNER DOOR HANDLE - LH, ASSY- DASHBOARD STRUCTURE | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - RH | ASSY - DOOR CARD - RH
ASSY - DOOR CARD - LH | DOORS | BODYWORK | INTERIOR | Sunswift |  | Yaheng Li | 3 weeks |  | ASSY- OCUPANT CELL SPIDER,ASSY- OCUUPANT CELL TUB ,ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE, ASSY - DOOR AUDIO - LH |  | ASSY - INNER DOOR HANDLE - LH, ASSY- DASHBOARD STRUCTURE | ASSY - OCCUPANT CELL SPIDER | ASSY - OCCUPANT CELL TUB | ASSY - DOOR SHELL - LH | ASSY - DOOR CARD - LH
ASSY - DOOR AUDIO - RH | AUDIO | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 8 Weeks |  |  |  | ASSY - DOOR SHELL - RH
ASSY - DOOR AUDIO - LH | AUDIO | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 8 Weeks |  |  |  | ASSY - DOOR SHELL - LH
ASSY - DOOR ACTUATOR BOARD - RH | DOORS | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 5 Weeks |  | N/A |  | N/A | ASSY - DOOR SHELL - RH | ASSY - DOOR ACTUATOR BOARD - RH
ASSY - DOOR ACTUATOR BOARD - LH | DOORS | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Sebastian Moore | 5 Weeks |  | N/A |  | N/A | ASSY - DOOR SHELL - LH | ASSY - DOOR ACTUATOR BOARD - LH
ASSY - DC-DC CONVERTERS | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS | Unknown | 8 weeks | Darren Paradhen | 2 weeks |  | ASSY - AUX BATTERY
ASSY - DASHBOARD STRUCTURE | DASHBOARD | DASHBOARD | INTERIOR | Sunswift/Mconaghy |  | Elisa Wong | 6 weeks |  | ASSY - OCCUPANT CELL TUB, ASSY-DOOR CARD, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR) |  |  | ASSY - OCCUPANT CELL TUB |  | Driver's display
ASSY - CYBERSECURITY MVP | CYBERSECURITY | SECURITY | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | N/A
ASSY - CYBERSECURITY | CYBERSECURITY | SECURITY | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - CONTROL LOGIC | ENERGY CONTROL SYSTEMS | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | Vincet Younes | 3 weeks |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING,
ASSY - CHASSIS VENTILATION | VENTILATION | CHASSIS | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Peleg Mondry Cohen | 8 Weeks |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS |  | ASSY - FRONT CLAMSHELL | ASSY - FRONT FLUID MANAGEMENT | ASSY - REAR FLUID MANAGEMENT | ASSY - THERMAL BOX | ASSY - FRONT CRASH STRUCTURE
ASSY - CHASSIS SUBFRAME | SUBFRAMES | CHASSIS | CHASSIS & BODYWORK | Divergent | 8 weeks | Aditya Bansal | 4 Weeks |  | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH |  | ASSY - OCCUPANT CELL TUB | ASSY - MOTOR UNIT - LH | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - LH | ASSY - GEARBOX - RH | ASSY - AXLE CV - LH | ASSY - AXLE CV - RH
ASSY - CENTRAL STOPLAMP CONTROLLER | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Maria Lee | 3 Weeks |  | ASSY - CENTRAL STOPLAMP
ASSY - CENTRAL STOPLAMP CASING | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Hitesh Bhuta | 4 Weeks |  | ASSY - CENTRAL STOPLAMP
ASSY - CENTRAL STOPLAMP | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Maria Lee | 3 Weeks |  | N/A |  | ASSY - CENTRAL STOPLAMP CASING, ASSY - CENTRAL STOPLAMP CONTROLLER
ASSY - CENTRAL STOP LAMP PCB | CENTRAL STOP LAMP | LIGHTS | EMBEDDED SYSTEMS | Sunswift |  | Maria Lee | 4 Weeks (once started) |  | ASSY - CENTRAL STOP LAMP |  |  | ASSY - CENTRAL STOP LAMP PCB
ASSY - CENTRAL STOP LAMP | CENTRAL STOP LAMP | LIGHTS | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Sharifa Husna | 3 weeks |  |  |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT | ASSY - REAR BOOT | ASSY - CENTRAL STOP LAMP PCB | ASSY - CENTRAL STOP LAMP
ASSY - CENTRAL DISPLAY | CENTRAL DISPLAY | DASHBOARD | INTERIOR | Espresso conversation | 0 | Anubhav Sharma | 2 weeks |  |  |  | ASSY - DASHBOARD STRUCTURE
ASSY - CEILING | CEILING | INTERIOR | INTERIOR | Sunswift |  | Jason Jin | 4 weeks |  | ASSY - REAR VISION CAMERA (mount), ASSY - SUN VISOR LH, ASSY - SUN VISOR RH, ASSY - OCCUPANT CELL SPIDER |  |  | ASSY - OCCUPANT CELL SPIDER | ASSY - CEILING
ASSY - C-V2X PCB | C-V2X | V2X | EMBEDDED SYSTEMS | Sunswift |  | N/A | 2 Months |  | N/A |  | N/A | ASSY - C-V2V ANTENNA | ASSY - C-V2V RADAR/LiDAR
ASSY - C-V2V RADAR/LiDAR | C-V2X | V2X | EMBEDDED SYSTEMS |  |  | N/A | 3 Months + |  |  |  | ASSY - FRONT CLAMSHELL | ASSY - FRONT BODY STRUCTURE | ASSY - C-V2V RADAR/LiDAR
ASSY - C-V2V ANTENNA | C-V2X | V2X | EMBEDDED SYSTEMS | Sunswift |  | N/A | 3 Weeks |  | N/A |  | N/A | ASSY - C-V2V ANTENNA
ASSY - BRAKE PEDAL | PEDALS | PEDALS | INTERIOR | Sunswift |  | Ray He | 1 week |  |  |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER | ASSY - FRONT MASTER CYLINDER | ASSY - BRAKE PEDAL
ASSY - BOOT LOCKING BOARD | BOOT | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 4 Weeks |  | ASSY - BOOT |  | N/A
ASSY - BOOT | BOOT | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader, Colan and Stabillus | 1 week | Luca (PQ) Nguyen | 5 Weeks |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH |  | ASSY - BOOT LOCKING BOARD | ASSY - SOLAR BOOT ASSAY | ASSY - CENTRAL STOP LAMP | ASSY - PRESSURE VESSEL SHELL | Hydrogen venting | ASSY - BOOT LOCKING BOARD | ASSY - REAR QUARTER PANEL - LH | ASSY - REAR QUARTER PANEL - RH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- LH | ASSY - TAILLIGHT/INDICATOR EXTERIOR- RH | ASSY - CENTRAL STOP LAMP
ASSY - BONNET LOCKING BOARD | BONNET | BODYWORK | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 4 Weeks |  | ASSY - BONNET |  | N/A | ASSY - BONNET | ASSY - BONNET LOCKING BOARD
ASSY - BONNET | BONNET | BODYWORK | CHASSIS & BODYWORK | McConaghy, Scott Bader and Colan | 0 | Luca (PQ) Nguyen | 4 Weeks |  | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAMSHELL |  | ASSY - BONNET LOCKING BOARD | ASSY - SOLAR BONNET ARRAY | ASSY - FRONT BODY STRUCTURE
ASSY - BMS WIRING | BATTERY | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | David Thirugnanaraj | 3 weeks |  | ASSY - BATTERY PACK |  | ASSY - CONTROL LOGIC
ASSY - BLUETOOTH CONNECTIVITY MVP | BLUETOOTH CONNECTIVITY | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - INFOTAINMENT MVP |  | ASSY - APPLE & ANDROID COMPATABILITY MVP, ASSY - SUNSWIFT PHONE APP MVP
ASSY - BLUETOOTH CONNECTIVITY | BLUETOOTH CONNECTIVITY | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - BLINDSPOT MONITORING SENSOR - RH | BLIND SPOT MONITORING | ADAS | EMBEDDED SYSTEMS | Sunswift |  | EMB Member | 4 Weeks |  | ASSY - SIDE CAMERA - RH, ASSY - SENSOR MOTHERBOARD - FL ASSY - SENSOR MOTHERBOARD- FR ASSY - SENSOR MOTHERBOARD - BL ASSY - SENSOR MOTHERBOARD- BR |  | N/A
ASSY - BLINDSPOT MONITORING SENSOR - LH | BLIND SPOT MONITORING | ADAS | EMBEDDED SYSTEMS | Sunswift |  | EMB Member | 4 Weeks |  | ASSY - SIDE CAMERA - LH, ASSY - SENSOR MOTHERBOARD - FL ASSY - SENSOR MOTHERBOARD- FR ASSY - SENSOR MOTHERBOARD - BL ASSY - SENSOR MOTHERBOARD- BR |  | N/A
ASSY - BATTERY PACK | BATTERY | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks |  | ASSY - BATTERY MODULES |  | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING
ASSY - BATTERY MODULES | BATTERY | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | David Thirugnanaraj | 4 weeks |  | - |  | ASSY - BATTERY PACK
ASSY - BATTERY LV WIRING | BATTERY | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks |  | ASSY - BATTERY PACK |  | -
ASSY - BATTERY HV WIRING | BATTERY | BATTERY | ENERGY SYSTEMS | Unknown | 8 weeks | David Thirugnanaraj | 2 weeks |  | ASSY - BATTERY PACK |  | -
ASSY - AXLE CV - RH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Ricardo/Unknown | 8 weeks | Jack Lawson | 6 weeks |  | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - CV AXLES | ASSY - MOTOR UNIT - RH | ASSY - GEARBOX - RH | ASSY - AXLE CV - RH
ASSY - AXLE CV - LH | TRANSMISSION | TRANSMISSION | POWERTRAIN | Ricardo/Unknown | 8 weeks | Jack Lawson | 6 weeks |  | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | ASSY - MOTOR UNIT - LH | ASSY - GEARBOX - LH | ASSY - AXLE CV - LH
ASSY - AUXILLARY POWER WIRING | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS | Unknown | 8 weeks | Darren Paradhen | 2 weeks |  | ASSY - AUX BATTERY
ASSY - AUX BATTERY | AUXILLARY POWER DISTRIBUTION | AUXILLARY POWER DISTRIBUTION | ENERGY SYSTEMS | Unknown | 8 weeks | Darren Paradhen | 2 weeks |  | - |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING
ASSY - AUDIO CONTROL SYSTEM | AUDIO | AUDIO | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 2 Months |  | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER |  | N/A | ASSY - DOOR AUDIO - LH | ASSY - DOOR AUDIO - RH | ASSY - SUBWOOFER | ASSY - AUDIO CONTROL SYSTEM
ASSY - APPLE & ANDROID COMPATABILITY MVP | APPLE & ANDROID COMPATABILITY | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - BLUETOOTH CONNECTIVITY MVP |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - APPLE & ANDROID COMPATABILITY | APPLE & ANDROID COMPATABILITY | HMI | TECHNICAL SUPPORT SYSTEMS | Sunswift |  | Nathan Nguyen |  |  | ASSY - SUNSWIFT PHONE APP MVP
ASSY - ACTIVE AERO MOTORS | ACTIVE AERO | AERO | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Melissa Thein | 2 weeks
ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ACTIVE AERO | AERO | CHASSIS & BODYWORK | Sunswift | 0 Wekes | Melissa Thein | 3 weeks |  |  |  |  | ASSY - ACTIVE AERO MOTORS | ASSY - CHASSIS VENTILATION | ASSY - FRONT BODY STRUCTURE
ASSY - ACTIVE AERO CONTROL PCB | ACTIVE AERO | AERO | EMBEDDED SYSTEMS | Sunswift |  | Hamish Hunter | 6 Weeks (when started) |  | ASSY - ACTIVE AERO MOTORS |  | N/A | ASSY - ACTIVE AERO MOTORS | ASSY-ACTIVE AERO CONTROLI PCB
ASSY - ABS BRAKES CONTROL SYSTEM | ABS BRAKES | ADAS | EMBEDDED SYSTEMS | Bosch, or just Sunswift | 0 | Hamish Hunter | 4 Weeks |  | ASSY - EMBEDDED HIGH LEVEL SOFTWARE, ASSY - DRIVE CONTROL UNIT |  | N/A
ASSY - SENSOR MOTHERBOARD - FR | SENSORS | SENSORS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 3 Months + |  | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - FR
ASSY - SENSOR MOTHERBOARD - BR | SENSORS | SENSORS | EMBEDDED SYSTEMS | Sunswift |  | Angus Macdonald | 3 Months + |  | N/A |  | N/A | ASSY - SENSOR MOTHERBOARD - BR
ASSY - HORN PCB CODE | HORN | HORN | EMBEDDED SYSTEMS | Sunswift |  |  | 2 Weeks |  | N/A |  | N/A | ASSY - HORN PCB CODE
COLOUR CODING
Added in by project management but unordered
Added in by project management, ordered under correct project | [6 empty] | Needs accurate timeframe (added in with 14 days timeframe) |  | Needs dependencies added (added in with none)
Added in by Systems but unordered
Added in by Systems, ordered under project
Added in by ELT as new assembly
Needs Clarification
IF THERE ARE NO DEPENDENCIES, WRITE N/A OR "-"
Note on A60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please Check
Note on A78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete all red assemblies relating to ALT
Note on A119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove all red ALT assemblies
Note on J132: Henry Jiang: Any dependencies from other assemblies/projects?
Note on A166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reservoir assembly repeated twice -> check if just cylinder dependencies are the same
Note on A173: Henry Jiang: Assuming clamshell means fenders + bumper in one so adding to front bumper project
Note on L178: Andy Danis: