## data_input
ID | Description | Department | Partners | PartnerWeight | EdgeWeight | Duration | Predecessors | Successors | PredecessorIDs | Pre | PreIds | PreDiff | SuccessorIDs | Suc | SucIds | SucDiff | Parallel | ParallelIDs | Par | ParIDs | ParDiff
1 | ASSY - OCCUPANT CELL SPIDER | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH | ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD | 27,28,144 | 3 | 3 | 0 | 38,46,49,100 | 4 | 4 | 0 | ASSY - OCCUPANT CELL TUB | 2 | 1 | 1 | 0
2 | ASSY - OCCUPANT CELL TUB | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEAT BELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEAT BELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULES, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - DOOR CARD - LH, ASSY - FRONT CLAM SHELL | 3,4,5,7,8,11,12,14,15,29,30,50,52,53,54,55,56,57,60,61,87,88,91,108,110,112,113,114,115,126,127,128,175,181 | 34 | 34 | 0 | 16,17,18,38 | 4 | 4 | 0 | ASSY - OCCUPANT CELL SPIDER | 1 | 1 | 1 | 0
3 | ASSY - STEERING COLUMN MOUNT | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 2 | 2 | ASSY - STEERING COLUMN | ASSY - OCCUPANT CELL TUB | 87 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
4 | ASSY - FRONT CRASH STRUCTURE | CHASSIS AND BODYWORK | Calm Aluminium | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - REAR CRASH STRUCTURE | 5 | 1 | 1 | 0
5 | ASSY - REAR CRASH STRUCTURE | CHASSIS AND BODYWORK | Calm Aluminium | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - FRONT CRASH STRUCTURE | 4 | 1 | 1 | 0
6 | ASSY - CHASSIS VENTILATION | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 8 | 8 | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ASSY - FRONT CLAM SHELL | 11,43 | 2 | 2 | 0 | 16 | 1 | 1 | 0 |  |  | 0 | 0 | 0
7 | ASSY - CHASSIS SUBFRAME | CHASSIS AND BODYWORK | Divergent | 8 | 4 | 12 | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB | 114,115,116,117,124,125,126,127 | 8 | 8 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
8 | ASSY - HVAC BOX | CHASSIS AND BODYWORK | AutoFrost | 0 | 8 | 8 | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING | 9 | 1 | 1 | 0 | 2,10,11 | 3 | 3 | 0 | ASSY - HVAC PIPING | 10 | 1 | 1 | 0
9 | ASSY - THERMAL BOX | CHASSIS AND BODYWORK | AutoFrost, PWR | 3 | 6 | 9 |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX |  | 0 | 0 | 0 | 8,10,11,12 | 4 | 4 | 0 |  |  | 0 | 0 | 0
10 | ASSY - HVAC PIPING | CHASSIS AND BODYWORK | Unknown | 3 | 7 | 10 | ASSY - THERMAL BOX, ASSY - HVAC BOX | ASSY - FRONT FLUID MANAGEMENT | 8,9 | 2 | 2 | 0 | 11 | 1 | 1 | 0 | ASSY - HVAC BOX | 8 | 1 | 1 | 0
11 | ASSY - FRONT FLUID MANAGEMENT | CHASSIS AND BODYWORK | Unknown | 3 | 4 | 7 | ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX | ASSY - CHASSIS VENTILATION, ASSY - OCCUPANT CELL TUB | 8,9,10 | 3 | 3 | 0 | 2,6 | 2 | 2 | 0 |  |  | 0 | 0 | 0
12 | ASSY - REAR FLUID MANAGEMENT | CHASSIS AND BODYWORK | Unknown | 3 | 5 | 8 | ASSY - THERMAL BOX, ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH, ASSY - HYDROGEN COOLING SYSTEM | ASSY - OCCUPANT CELL TUB | 9,114,115,189 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
13 | ASSY - REAR BUMPER | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 6 | 6 | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE | 14,15,169,170 | 4 | 4 | 0 | 17,18 | 2 | 2 | 0 |  |  | 0 | 0 | 0
14 | ASSY - REAR QUARTER PANEL - LH | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH |  | 0 | 0 | 0 | 2,13,17,18,19,24 | 6 | 6 | 0 |  |  | 0 | 0 | 0
15 | ASSY - REAR QUARTER PANEL - RH | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH |  | 0 | 0 | 0 | 2,13,17,18,19,23 | 6 | 6 | 0 |  |  | 0 | 0 | 0
16 | ASSY - FRONT CLAM SHELL | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 7 | 7 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LiDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB | ASSY - BONNET | 2,6,27,28,43,45,93,94,155,156,157,158,161,195 | 14 | 14 | 0 | 21 | 1 | 1 | 0 |  |  | 0 | 0 | 0
17 | ASSY - REAR FLOOR | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
18 | ASSY - REAR SUPPORT STRUCTURE | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
19 | ASSY - BOOT | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan, Stabillus | 1 | 5 | 6 | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT LOCKING BOARD | 14,15,18,145,148,149,150,151,152,153,154,235 | 11 | 12 | -1 | 20 | 1 | 1 | 0 |  |  | 0 | 0 | 0
20 | ASSY - BOOT LOCKING BOARD | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - BOOT |  | 19 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
21 | ASSY - BONNET | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 4 | 4 | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAM SHELL | ASSY - BONNET LOCKING BOARD | 16,49,146 | 3 | 3 | 0 | 22 | 1 | 1 | 0 |  |  | 0 | 0 | 0
22 | ASSY - BONNET LOCKING BOARD | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - BONNET |  | 21 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
23 | ASSY - OUTER DOOR HANDLE - RH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - RH |  | 29 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
24 | ASSY - OUTER DOOR HANDLE - LH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - LH |  | 30 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
25 | ASSY - INNER DOOR HANDLE - RH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - RH |  | 37 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
26 | ASSY - INNER DOOR HANDLE - LH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - LH |  | 38 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
27 | ASSY - DOOR SHELL - RH | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - RH, ASSY - REAR QUARTER PANEL - RH | 31,39,42,160 | 4 | 4 | 0 | 1,15,16,37 | 4 | 4 | 0 |  |  | 0 | 0 | 0
28 | ASSY - DOOR SHELL - LH | CHASSIS AND BODYWORK | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - LH, ASSY - REAR QUARTER PANEL - LH | 32,40,41,159 | 4 | 4 | 0 | 1,14,16,38 | 4 | 4 | 0 |  |  | 0 | 0 | 0
29 | ASSY - DOOR LATCH - RH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,23 | 2 | 2 | 0 |  |  | 0 | 0 | 0
30 | ASSY - DOOR LATCH - LH | CHASSIS AND BODYWORK | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,24 | 2 | 2 | 0 |  |  | 0 | 0 | 0
31 | ASSY - DOOR HINGE - RH | CHASSIS AND BODYWORK | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD - RH |  | 0 | 0 | 0 | 27,37 | 2 | 2 | 0 |  |  | 0 | 0 | 0
32 | ASSY - DOOR HINGE - LH | CHASSIS AND BODYWORK | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH |  | 0 | 0 | 0 | 28,38 | 2 | 2 | 0 |  |  | 0 | 0 | 0
33 | ASSY - DOOR CONTROL BOARD - RH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 | ASSY - DOOR CONTROL BOARD - RH |  | 34 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
34 | ASSY - DOOR CONTROL BOARD - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 5 | 5 | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH |  | 27,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
35 | ASSY - DOOR CONTROL BOARD - LH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 | ASSY - DOOR CONTROL BOARD - LH |  | 36 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
36 | ASSY - DOOR CONTROL BOARD - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 5 | 5 | ASSY - DOOR HINGE - LH , ASSY - DOOR SHELL - LH |  | 28,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
37 | ASSY - DOOR CARD - RH | INTERIOR | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - RH, ASSY - DOOR AUDIO - RH | ASSY - INNER DOOR HANDLE - RH, ASSY - DASHBOARD STRUCTURE | 1,2,27,31,39 | 5 | 5 | 0 | 25,103 | 2 | 2 | 0 |  |  | 0 | 0 | 0
38 | ASSY - DOOR CARD - LH | INTERIOR | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE - LH, ASSY - DOOR AUDIO - LH | ASSY - INNER DOOR HANDLE - LH, ASSY - DASHBOARD STRUCTURE | 1,2,28,32,40 | 5 | 5 | 0 | 26,103 | 2 | 2 | 0 |  |  | 0 | 0 | 0
39 | ASSY - DOOR AUDIO - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
40 | ASSY - DOOR AUDIO - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
41 | ASSY - ELECTRIC WINDOWS - LH | CHASSIS AND BODYWORK | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
42 | ASSY - ELECTRIC WINDOWS - RH | CHASSIS AND BODYWORK | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
43 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
44 | ASSY - ACTIVE AERO MOTORS | CHASSIS AND BODYWORK | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
45 | ASSY - ACTIVE AERO CONTROL PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 6 | 6 | ASSY - ACTIVE AERO MOTORS |  | 44 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
46 | ASSY - WINDSCREEN | CHASSIS AND BODYWORK | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
47 | ASSY - WINDSCREEN WIPER | CHASSIS AND BODYWORK | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
48 | ASSY - WINDSCREEN WASHER | CHASSIS AND BODYWORK | Unknown | 4 | 2 | 6 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
49 | ASSY - WINDSCREEN WIPER AERO GUARD | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
50 | ASSY - WINDSCREEN WIPER MOTOR | CHASSIS AND BODYWORK | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
51 | ASSY - WINDSCREEN WIPER CONTROL PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - WINDSCREEN WIPER MOTOR |  | 50 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
52 | ASSY - FRONT TOP WISHBONE - LH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 62 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
53 | ASSY - FRONT TOP WISHBONE - RH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 62 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
54 | ASSY - FRONT LOWER WISHBONE - LH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 62 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
55 | ASSY - FRONT LOWER WISHBONE - RH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 62 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
56 | ASSY - FRONT TIEROD - LH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - LH, ASSY - FRONT DAMPER - LH, ASSY - FRONT CALIPER - LH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 58,60,73,77 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
57 | ASSY - FRONT TIEROD - RH | VEHICLE DYNAMICS | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - RH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 59,61,74,77 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
58 | ASSY - FRONT UPRIGHT - LH | VEHICLE DYNAMICS | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 62 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
59 | ASSY - FRONT UPRIGHT - RH | VEHICLE DYNAMICS | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 62 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
60 | ASSY - FRONT DAMPER - LH | VEHICLE DYNAMICS | Bilstein | 0 | 2 | 2 | ASSY - FRONT WHEEL |  | 62 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
61 | ASSY - FRONT DAMPER - RH | VEHICLE DYNAMICS | Bilstein | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
62 | ASSY - FRONT WHEEL | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC |  | 0 | 0 | 0 | 2,52,53,56,57,58,59,60,61,73,74,75,77 | 13 | 13 | 0 |  |  | 0 | 0 | 0
63 | ASSY - REAR TOP WISHBONE - LH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 72 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
64 | ASSY - REAR TOP WISHBONE - RH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 72 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
65 | ASSY - REAR LOWER WISHBONE - LH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 72 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
66 | ASSY - REAR LOWER WISHBONE - RH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 72 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
67 | ASSY - REAR TOELINK | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH |  | 2,63,64,65,66 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
68 | ASSY - REAR UPRIGHT - LH | VEHICLE DYNAMICS | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - LH | 72 | 1 | 1 | 0 | 70 | 1 | 1 | 0 |  |  | 0 | 0 | 0
69 | ASSY - REAR UPRIGHT - RH | VEHICLE DYNAMICS | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - RH | 72 | 1 | 1 | 0 | 71 | 1 | 1 | 0 |  |  | 0 | 0 | 0
70 | ASSY - REAR DAMPER - LH | VEHICLE DYNAMICS | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - LH |  | 68,72 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
71 | ASSY - REAR DAMPER - RH | VEHICLE DYNAMICS | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - RH |  | 69,72 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
72 | ASSY - REAR WHEEL | VEHICLE DYNAMICS | Sunswift | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE |  | 0 | 0 | 0 | 2,14,15,18,63,64,65,66,67,68,69,70,71,80,81,82,83,84,85,86 | 20 | 20 | 0 |  |  | 0 | 0 | 0
73 | ASSY - FRONT CALIPER - LH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 62,77 | 2 | 2 | 0 | 2,78 | 2 | 2 | 0 |  |  | 0 | 0 | 0
74 | ASSY - FRONT CALIPER - RH | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 62,77 | 2 | 2 | 0 | 2,78 | 2 | 2 | 0 |  |  | 0 | 0 | 0
75 | ASSY - FRONT MASTER CYLINDER RESERVOIR | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | 2,4,52,53,54,55,56,57,58,59,88,95,97 | 13 | 13 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
76 | ASSY - FRONT MASTER CYLINDER | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
77 | ASSY - FRONT BRAKE DISC | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT WHEEL | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH | 62 | 1 | 1 | 0 | 58,59,73,74 | 4 | 4 | 0 |  |  | 0 | 0 | 0
78 | ASSY - FRONT BRAKE LINE | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
79 | ASSY CHASSIS BRAKE LINE | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
80 | ASSY - REAR BRAKE CALIPER - LH | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 72,84 | 2 | 2 | 0 | 85 | 1 | 1 | 0 |  |  | 0 | 0 | 0
81 | ASSY - REAR BRAKE CALIPER - RH | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 72,84 | 2 | 2 | 0 | 85 | 1 | 1 | 0 |  |  | 0 | 0 | 0
82 | ASSY - REAR MASTER CYLINDER | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
83 | ASSY - REAR MASTER CYLINDER RESERVOIR | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
84 | ASSY - REAR BRAKE DISC | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | 72 | 1 | 1 | 0 | 80,81,85,86 | 4 | 4 | 0 |  |  | 0 | 0 | 0
85 | ASSY - REAR BRAKE LINE | VEHICLE DYNAMICS | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,52,53,54,55,56,57,58,59,88,95,97 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
86 | ASSY - HAND BRAKE | VEHICLE DYNAMICS | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY CHASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE | 72,84 | 2 | 2 | 0 | 79,103 | 2 | 2 | 0 |  |  | 0 | 0 | 0
87 | ASSY - STEERING COLUMN | VEHICLE DYNAMICS | Flaming River | 4 | 2 | 6 | ASSY - STEERING WHEEL, ASSY - STEERING RACK | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE | 88,89 | 2 | 2 | 0 | 3,4 | 2 | 2 | 0 |  |  | 0 | 0 | 0
88 | ASSY - STEERING RACK | VEHICLE DYNAMICS | Flaming River | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - STEERING COLUMN |  | 0 | 0 | 0 | 2,56,57,87 | 4 | 4 | 0 |  |  | 0 | 0 | 0
89 | ASSY - STEERING WHEEL | INTERIOR | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB | ASSY - DRIVER DISPLAY, ASSY - STEERING COLUMN | 90 | 1 | 1 | 0 | 87,105 | 2 | 2 | 0 |  |  | 0 | 0 | 0
90 | ASSY - STEERING WHEEL PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 6 | 6 |  | ASSY - STEERING WHEEL |  | 0 | 0 | 0 | 89 | 1 | 1 | 0 |  |  | 0 | 0 | 0
91 | ASSY - INTERIOR LIGHTS PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 6 | 6 |  | ASSY - OCCUPANT CELL SPIDER, ASSY - CEILING |  | 0 | 0 | 0 | 1,100 | 2 | 2 | 0 |  |  | 0 | 0 | 0
92 | ASSY - REAR VISION CAMERA | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
93 | ASSY - SIDE CAMERA - LH | EMBEDDED SYSTEMS | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 0 | 0 | 0 | 149 | 1 | 1 | 0 |  |  | 0 | 0 | 0
94 | ASSY - SIDE CAMERA - RH | EMBEDDED SYSTEMS | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 0 | 0 | 0 | 150 | 1 | 1 | 0 |  |  | 0 | 0 | 0
95 | ASSY - PEDAL BOX | INTERIOR | Sunswift | 0 | 2 | 2 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR | ASSY - OCCUPANT CELL TUB | 96,97,98,99 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
96 | ASSY - THROTTLE PEDAL | INTERIOR | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 76,82,99 | 3 | 3 | 0 |  |  | 0 | 0 | 0
97 | ASSY - BRAKE PEDAL | INTERIOR | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 76,78,82,99 | 4 | 4 | 0 |  |  | 0 | 0 | 0
98 | ASSY - PEDAL BOX CONTROLLER | EMBEDDED SYSTEMS | Sunswift | 0 | 2 | 2 | ASSY - PEDAL PRESS SENSOR |  | 99 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
99 | ASSY - PEDAL PRESS SENSOR | EMBEDDED SYSTEMS | Sunswift | 0 | 1 | 1 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL |  | 96,97 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
100 | ASSY - CEILING | INTERIOR | Sunswift | 0 | 4 | 4 | ASSY - REAR VISION CAMERA, ASSY - SUN VISOR - LH, ASSY - SUN VISOR - RH, ASSY - OCCUPANT CELL SPIDER |  | 1,92,101,102 | 4 | 4 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
101 | ASSY - SUN VISOR - LH | INTERIOR | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 100 | 1 | 1 | 0 |  |  | 0 | 0 | 0
102 | ASSY - SUN VISOR - RH | INTERIOR | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 100 | 1 | 1 | 0 |  |  | 0 | 0 | 0
103 | ASSY - DASHBOARD STRUCTURE | INTERIOR | Sunswift/Mconaghy | 0 | 6 | 6 | ASSY - OCCUPANT CELL TUB, ASSY - DOOR CARD - LH, ASSY - DOOR CARD - RH, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR) |  | 2,37,38,104,105,106 | 7 | 6 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
104 | ASSY - CENTRAL DISPLAY | INTERIOR | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 103 | 1 | 1 | 0 |  |  | 0 | 0 | 0
105 | ASSY - DRIVER DISPLAY | INTERIOR | Espresso conversation | 0 | 2 | 2 | ASSY - STEERING WHEEL | ASSY - DASHBOARD STRUCTURE | 89 | 1 | 1 | 0 | 103 | 1 | 1 | 0 |  |  | 0 | 0 | 0
106 | ASSY - HEADS-UP DISPLAY | INTERIOR | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 103 | 1 | 1 | 0 |  |  | 0 | 0 | 0
107 | ASSY - FRONT SEAT RAIL DRIVER | INTERIOR | Bride Racing | 0 | 4 | 4 | ASSY - FRONT SEAT DRIVER |  | 108 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
108 | ASSY - FRONT SEAT DRIVER | INTERIOR | Sunswift | 0 | 4 | 4 |  | ASSY - FRONT SEAT RAIL DRIVER |  | 0 | 0 | 0 | 107 | 1 | 1 | 0 |  |  | 0 | 0 | 0
109 | ASSY - FRONT SEAT MOUNT DRIVER | INTERIOR | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER, ASSY - FRONT SEAT BELT DRIVER |  | 0 | 0 | 0 | 2,108,112 | 3 | 3 | 0 |  |  | 0 | 0 | 0
110 | ASSY - FRONT SEAT PASSENGER | INTERIOR | Sunswift | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER |  | 0 | 0 | 0 | 2,111 | 2 | 2 | 0 |  |  | 0 | 0 | 0
111 | ASSY - FRONT SEAT MOUNT PASSENGER | INTERIOR | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER |  | 0 | 0 | 0 | 2,113 | 2 | 2 | 0 |  |  | 0 | 0 | 0
112 | ASSY - FRONT SEAT BELT DRIVER | INTERIOR | Unknown | 1 | 1 | 2 | ASSY - FRONT SEAT DRIVER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 108 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
113 | ASSY - FRONT SEAT BELT PASSENGER | INTERIOR | Unknown | 0 | 1 | 1 | ASSY - FRONT SEAT PASSENGER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 110 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
114 | ASSY - MOTOR UNIT - LH | POWERTRAIN | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - INVERTER - LH, ASSY - INVERTER MOUNTING FRAME - LH, ASSY - PWT HV WIRING - LH, ASSY - GEARBOX - LH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,116,118,120,122,124,126 | 9 | 8 | 1 |  |  | 0 | 0 | 0
115 | ASSY - MOTOR UNIT - RH | POWERTRAIN | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - INVERTER - RH, ASSY - INVERTER MOUNTING FRAME - RH, ASSY - PWT HV WIRING - RH, ASSY - GEARBOX - RH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,117,119,121,123,125,126 | 9 | 8 | 1 |  |  | 0 | 0 | 0
116 | ASSY - MOTOR MOUNTING FRAME - LH | POWERTRAIN | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | 114,124 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
117 | ASSY - MOTOR MOUNTING FRAME - RH | POWERTRAIN | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | 115,125 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
118 | ASSY - INVERTER - LH | POWERTRAIN | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - LH | ASSY - HYDROGEN COOLING SYSTEM | 114 | 1 | 1 | 0 | 189 | 1 | 1 | 0 |  |  | 0 | 0 | 0
119 | ASSY - INVERTER - RH | POWERTRAIN | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - RH | ASSY - HYDROGEN COOLING SYSTEM | 115 | 1 | 1 | 0 | 189 | 1 | 1 | 0 |  |  | 0 | 0 | 0
120 | ASSY - INVERTER MOUNTING FRAME - LH | POWERTRAIN | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 114,118 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
121 | ASSY - INVERTER MOUNTING FRAME - RH | POWERTRAIN | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 115,119 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
122 | ASSY - PWT HV WIRING - LH | POWERTRAIN | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 114,118 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
123 | ASSY - PWT HV WIRING - RH | POWERTRAIN | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 115,119 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
124 | ASSY - GEARBOX - LH | POWERTRAIN | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - LH | 114 | 1 | 1 | 0 | 2,7,126 | 3 | 3 | 0 |  |  | 0 | 0 | 0
125 | ASSY - GEARBOX - RH | POWERTRAIN | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - RH | 115 | 1 | 1 | 0 | 2,7,127 | 3 | 3 | 0 |  |  | 0 | 0 | 0
126 | ASSY - AXLE CV - LH | POWERTRAIN | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 114,124 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
127 | ASSY - AXLE CV - RH | POWERTRAIN | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 115,125 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
128 | ASSY - BATTERY MODULES | ENERGY SYSTEMS | Sunswift | 8 | 4 | 12 |  | ASSY - BATTERY PACK |  | 0 | 0 | 0 | 129 | 1 | 1 | 0 |  |  | 0 | 0 | 0
129 | ASSY - BATTERY PACK | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - BATTERY MODULES | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING | 128 | 1 | 1 | 0 | 130,131,132 | 3 | 3 | 0 |  |  | 0 | 0 | 0
130 | ASSY - BMS WIRING | ENERGY SYSTEMS | Sunswift | 8 | 3 | 11 | ASSY - BATTERY PACK | ASSY - CONTROL LOGIC | 129 | 1 | 1 | 0 | 138 | 1 | 1 | 0 |  |  | 0 | 0 | 0
131 | ASSY - BATTERY HV WIRING | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 129 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
132 | ASSY - BATTERY LV WIRING | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 129 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
133 | ASSY - AUXILLARY POWER WIRING | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 135 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
134 | ASSY - DC-DC CONVERTERS | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 135 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
135 | ASSY - AUX BATTERY | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING |  | 0 | 0 | 0 | 133,134 | 2 | 2 | 0 |  |  | 0 | 0 | 0
136 | ASSY - ECS HV WIRING | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 129 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
137 | ASSY - ECS LV WIRING | ENERGY SYSTEMS | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 129 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
138 | ASSY - CONTROL LOGIC | ENERGY SYSTEMS | Sunswift | 8 | 3 | 11 | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING |  | 136,137 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
139 | ASSY - ECS MODULE | ENERGY SYSTEMS | Sunswift | 8 | 3 | 11 |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC |  | 0 | 0 | 0 | 136,137,138 | 3 | 3 | 0 |  |  | 0 | 0 | 0
140 | ASSY - ONBOARD CHARGING WIRING | ENERGY SYSTEMS | Sunswift | 0 | 2 | 2 | ASSY - ONBOARD CHARGER INSTALLATION |  | 141 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
141 | ASSY - ONBOARD CHARGER INSTALLATION | ENERGY SYSTEMS | Sunswift | 0 | 3 | 3 |  | ASSY - ONBOARD CHARGING WIRING |  | 0 | 0 | 0 | 140 | 1 | 1 | 0 |  |  | 0 | 0 | 0
142 | ASSY - MPPT JUNCTION BOX | ENERGY SYSTEMS | Sunswift | 0 | 2 | 2 | ASSY - MPPT | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC | 143 | 1 | 1 | 0 | 136,138 | 2 | 2 | 0 |  |  | 0 | 0 | 0
143 | ASSY - MPPT | ENERGY SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - occupant cell spider | 144,145,146,148 | 4 | 4 | 0 | 1 | 1 | 1 | 0 |  |  | 0 | 0 | 0
144 | ASSY - SOLAR ROOF ARRAY | ENERGY SYSTEMS | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - occupant cell spider, ASSY - occupant cell tub, ASSY - ceiling, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 1,2,100,143,147 | 5 | 5 | 0 |  |  | 0 | 0 | 0
145 | ASSY - SOLAR BOOT ARRAY | ENERGY SYSTEMS | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,143,147 | 3 | 3 | 0 |  |  | 0 | 0 | 0
146 | ASSY - SOLAR BONNET ARRAY | ENERGY SYSTEMS | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - bonnet, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 21,143,147 | 3 | 3 | 0 |  |  | 0 | 0 | 0
147 | ASSY - MC4 Cabling | ENERGY SYSTEMS | None, by off sheld, maybe SunDrive | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - Occupant cell spider, ASSY - boot, ASSY - Bonnet, ASSY - MPPT | 144,145,146,148 | 4 | 4 | 0 | 1,19,21,143 | 4 | 4 | 0 |  |  | 0 | 0 | 0
148 | Assy - Shingled Matrix Panels | ENERGY SYSTEMS | M10 | 0 | 12 | 12 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,143,147 | 3 | 3 | 0 |  |  | 0 | 0 | 0
149 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
150 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
151 | ASSY - TAILLIGHT/INDICATOR PCB - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 149 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
152 | ASSY - TAILLIGHT/INDICATOR PCB - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 150 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
153 | ASSY - CENTRAL STOP LAMP | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT |  | 0 | 0 | 0 | 19,154 | 2 | 2 | 0 |  |  | 0 | 0 | 0
154 | ASSY - CENTRAL STOP LAMP PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOP LAMP |  | 153,235 | 1 | 2 | -1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
155 | ASSY - HEADLIGHT EXTERIOR - LH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
156 | ASSY - HEADLIGHT EXTERIOR - RH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
157 | ASSY - HEADLIGHT/INDICATOR PCB - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - LH |  | 0 | 0 | 0 | 155 | 1 | 1 | 0 |  |  | 0 | 0 | 0
158 | ASSY - HEADLIGHT/INDICATOR PCB - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - RH |  | 0 | 0 | 0 | 156 | 1 | 1 | 0 |  |  | 0 | 0 | 0
159 | ASSY - SIDE INDICATOR EXTERIOR - LH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
160 | ASSY - SIDE INDICATOR EXTERIOR - RH | CHASSIS AND BODYWORK | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
161 | ASSY - HORN | EMBEDDED SYSTEMS | Sunswift | 0 | 1 | 1 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
162 | ASSY - HORN PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
163 | ASSY - DRIVE CONTROL UNIT | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH |  | 114,115 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
164 | ASSY - SENSOR MOTHERBOARD - FL | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
165 | ASSY - SENSOR MOTHERBOARD - FR | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
166 | ASSY - SENSOR MOTHERBOARD - BL | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
167 | ASSY - SENSOR MOTHERBOARD - BR | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
168 | ASSY - FATIGUE MONITORING SYSTEM | EMBEDDED SYSTEMS | Sunswift | 0 | 0 | 0 | ASSY - OCCUPANT CELL TUB |  | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
169 | ASSY - BLINDSPOT MONITORING SENSOR - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - SIDE CAMERA - LH, ASSY - SENSOR MOTHERBOARD - FL, ASSY - SENSOR MOTHERBOARD - FR, ASSY - SENSOR MOTHERBOARD - BL, ASSY - SENSOR MOTHERBOARD - BR |  | 93,164,165,166,167 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
170 | ASSY - BLINDSPOT MONITORING SENSOR - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - SIDE CAMERA - RH, ASSY - SENSOR MOTHERBOARD - FL, ASSY - SENSOR MOTHERBOARD - FR, ASSY - SENSOR MOTHERBOARD - BL, ASSY - SENSOR MOTHERBOARD - BR |  | 94,164,165,166,167 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
171 | ASSY - C-V2V ANTENNA | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
172 | ASSY - C-V2X PCB | EMBEDDED SYSTEMS | Sunswift | 0 | 8 | 8 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
173 | ASSY - SUBWOOFER | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
174 | ASSY - AUDIO CONTROL SYSTEM | EMBEDDED SYSTEMS | Sunswift | 0 | 8 | 8 | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER |  | 39,40,173 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
175 | ASSY - PRESSURE VESSEL SHELL | ALTERNATIVE ENERGIES | Coregas, Swagelok | 6 | 0 | 6 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY | 176 | 1 | 1 | 0 | 177,178 | 2 | 2 | 0 |  |  | 0 | 0 | 0
176 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL |  | 0 | 0 | 0 | 2,17,175,177,178 | 5 | 5 | 0 |  |  | 0 | 0 | 0
177 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR | 175,176 | 2 | 2 | 0 | 181,182 | 2 | 2 | 0 |  |  | 0 | 0 | 0
178 | ASSY - PRESSURE REGULATION & SAFETY | ALTERNATIVE ENERGIES | Swagelok | 12 | 0 | 12 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 175,176 | 2 | 2 | 0 | 179,186,191 | 3 | 3 | 0 |  |  | 0 | 0 | 0
179 | ASSY - HYDROGEN SUPPLY LINE | ALTERNATIVE ENERGIES | Swagelok | 6 | 0 | 6 | ASSY - PRESSURE REGULATION & SAFETY | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - SENSOR ARRAY | 178 | 1 | 1 | 0 | 180 | 2 | 1 | 1 |  |  | 0 | 0 | 0
180 | ASSY - HYDROGEN PURGE MANAGEMENT | ALTERNATIVE ENERGIES | Siltrax, Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE | ASSY - P&ID HYDROGEN RECYCLE STREAM | 179,188 | 2 | 2 | 0 | 183 | 1 | 1 | 0 |  |  | 0 | 0 | 0
181 | ASSY - HYDROGEN COMPARTMENT VENTILATION | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - P&ID AIR SUPPLY LINE, ASSY - REARWHEEL HUB AIR INTAKE | 177 | 1 | 1 | 0 | 192,193 | 2 | 2 | 0 |  |  | 0 | 0 | 0
182 | ASSY - OCCUPANT CELL HYDROGEN SENSOR | ALTERNATIVE ENERGIES | Gas detection supplier (Honeywell/CityTech etc.) | 10 | 0 | 10 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 177 | 1 | 1 | 0 | 185,190 | 2 | 2 | 0 |  |  | 0 | 0 | 0
183 | ASSY - P&ID HYDROGEN RECYCLE STREAM | ALTERNATIVE ENERGIES | Siltrax | 6 | 0 | 6 | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK | ASSY - HYDROGEN SENSOR ARRAY | 180,188 | 2 | 2 | 0 | 186 | 1 | 1 | 0 |  |  | 0 | 0 | 0
184 | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY |  | 186,190 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
185 | ASSY - OCCUPANT CELL SHUTDOWN VALVE | ALTERNATIVE ENERGIES | Swagelok | 6 | 0 | 6 | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC |  | 182,187 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
186 | ASSY - HYDROGEN SENSOR ARRAY | ALTERNATIVE ENERGIES | External Supplier (TBA) | 10 | 0 | 10 | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 178,179,188 | 3 | 3 | 0 | 184,187 | 2 | 2 | 0 |  |  | 0 | 0 | 0
187 | ASSY - HYDROGEN CONTROL LOGIC | ALTERNATIVE ENERGIES | External Supplier (TBA) | 16 | 0 | 16 | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL SYSTEM | 186,188 | 2 | 2 | 0 | 194 | 1 | 1 | 0 |  |  | 0 | 0 | 0
188 | ASSY - FUEL CELL STACK | ALTERNATIVE ENERGIES | Siltrax | 6 | 0 | 6 | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE | 129 | 2 | 1 | 1 | 177,179,186,189,194 | 5 | 5 | 0 |  |  | 0 | 0 | 0
189 | ASSY - HYDROGEN COOLING SYSTEM | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT | 188 | 1 | 1 | 0 | 12,190,191 | 3 | 3 | 0 |  |  | 0 | 0 | 0
190 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | ALTERNATIVE ENERGIES | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 188 | 1 | 1 | 0 | 184 | 1 | 1 | 0 |  |  | 0 | 0 | 0
191 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE | ALTERNATIVE ENERGIES | Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT | ASSY - P&ID AIR SUPPLY LINE | 179,180,188 | 3 | 3 | 0 | 192 | 1 | 1 | 0 |  |  | 0 | 0 | 0
192 | ASSY - P&ID AIR SUPPLY LINE | ALTERNATIVE ENERGIES | Beswick, Swagelok | 8 | 0 | 8 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - OCCUPANT CELL SHUTDOWN VALVE | 193 | 2 | 1 | 1 | 185 | 1 | 1 | 0 |  |  | 0 | 0 | 0
193 | ASSY - REARWHEEL HUB AIR INTAKE | ALTERNATIVE ENERGIES | Sunswift |  | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN CONTROL LOGIC | 177 | 1 | 1 | 0 | 187 | 1 | 1 | 0 |  |  | 0 | 0 | 0
194 | ASSY - HYDROGEN CONTROL SYSTEM | ALTERNATIVE ENERGIES | Ballard or Intelligent Energy | 12 | 0 | 12 | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS MODULE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS |  | 139,187,190 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
195 | ASSY - C-V2V RADAR/LiDAR | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 |  | ASSY - FRONT CLAM SHELL |  | 0 | 0 | 0 | 16 | 1 | 1 | 0 |  |  | 0 | 0 | 0
196 | ASSY - INTERNAL EMBEDDED NETWORK WIRING | EMBEDDED SYSTEMS | Sunswift | 0 | 2 | 2 | ASSY - HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP, ASSY - STEERING WHEEL, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LiDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM, ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - BOOT, ASSY - BONNET |  | 2,3,4,5,6,13,14,15,16,17,18,19,21,39,40,89,98,104,105,151,152,153,157,158,162,163,171,172,173,174,195,225,235 | 33 | 33 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
219 | ASSY - DRIVE CONTROL UNIT SOFTWARE | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 | ASSY - DRIVE CONTROL UNIT |  | 163 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
220 | ASSY - HEADLAMP/INDICATOR PCB - LH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
221 | ASSY - HEADLAMP/INDICATOR PCB - RH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
222 | ASSY - TAILLIGHT/INDICATOR PCB - LH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
223 | ASSY - TAILLIGHT/INDICATOR PCB - RH - CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
224 | ASSY - HORN PCB CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
225 | ASSY - MAIN COMPUTER | EMBEDDED SYSTEMS | Adlink | 8 | 1 | 9 |  | ASSY - INTERNAL EMBEDDED NETWORK WIRING |  | 0 | 0 | 0 | 196 | 1 | 1 | 0 |  |  | 0 | 0 | 0
226 | ASSY - STEERING WHEEL PCB CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB |  | 90 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
227 | ASSY - INTERIOR LIGHTS PCB CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
228 | ASSY - DOOR ACTUATOR BOARD - RH | EMBEDDED SYSTEMS | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
229 | ASSY - DOOR ACTUATOR BOARD - LH | EMBEDDED SYSTEMS | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
230 | ASSY - WINDSCREEN WIPER CONTROL PCB CODE | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
231 | ASSY - EMBEDDED HIGH LEVEL SOFTWARE | EMBEDDED SYSTEMS | Sunswift | 0 | 12 | 12 | ASSY - MAIN COMPUTER |  | 225 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
232 | ASSY - SIDE INDICATOR - LH | CHASSIS AND BODYWORK | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - LH |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 |  |  | 0 | 0 | 0
233 | ASSY - SIDE INDICATOR - RH | CHASSIS AND BODYWORK | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - RH |  | 0 | 0 | 0 | 94 | 1 | 1 | 0 |  |  | 0 | 0 | 0
234 | ASSY - ABS BRAKES CONTROL SYSTEM | EMBEDDED SYSTEMS | Bosch | 0 | 4 | 4 | ASSY - EMBEDDED HIGH LEVEL SOFTWARE, ASSY - DRIVE CONTROL UNIT |  | 163,231 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
235 | ASSY - CENTRAL STOP LAMP | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOP LAMP CASING, ASSY - CENTRAL STOP LAMP CONTROLLER |  | 0 | 0 | 0 | 236,237 | 2 | 2 | 0 |  |  | 0 | 0 | 0
236 | ASSY - CENTRAL STOP LAMP CASING | EMBEDDED SYSTEMS | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOP LAMP |  | 153,235 | 1 | 2 | -1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
237 | ASSY - CENTRAL STOP LAMP CONTROLLER | EMBEDDED SYSTEMS | Sunswift | 0 | 3 | 3 | ASSY - CENTRAL STOP LAMP |  | 153,235 | 1 | 2 | -1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0

## Cycles_Named
Cycle | Cycle_Named