## data_input
ID | Description | Partners | PartnerWeight | EdgeWeight | Duration | Predecessors | Successors | PredecessorIDs | Pre | PreIds | PreDiff | SuccessorIDs | Suc | SucIds | SucDiff | Parallel | ParallelIDs | Par | ParIDs | ParDiff
1 | ASSY - OCCUPANT CELL SPIDER | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH | ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD | 27,28,142 | 3 | 3 | 0 | 36,44,47,98 | 4 | 4 | 0 | ASSY - OCCUPANT CELL TUB | 2 | 1 | 1 | 0
2 | ASSY - OCCUPANT CELL TUB | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEAT BELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEAT BELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULES, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - DOOR CARD - LH, ASSY - FRONT CLAM SHELL | 3,4,5,7,8,11,12,14,15,29,30,48,50,51,52,53,54,55,58,59,85,86,89,106,108,110,111,112,113,124,125,126,168,174 | 34 | 34 | 0 | 16,17,18,36 | 4 | 4 | 0 | ASSY - OCCUPANT CELL SPIDER | 1 | 1 | 1 | 0
3 | ASSY - STEERING COLUMN MOUNT | McConaghy, Scott Bader, Colan | 0 | 2 | 2 | ASSY - STEERING COLUMN | ASSY - OCCUPANT CELL TUB | 85 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
4 | ASSY - FRONT CRASH STRUCTURE | Calm Aluminium | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - REAR CRASH STRUCTURE | 5 | 1 | 1 | 0
5 | ASSY - REAR CRASH STRUCTURE | Calm Aluminium | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - FRONT CRASH STRUCTURE | 4 | 1 | 1 | 0
6 | ASSY - CHASSIS VENTILATION | McConaghy, Scott Bader, Colan | 0 | 8 | 8 | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ASSY - FRONT CLAM SHELL | 11,41 | 2 | 2 | 0 | 16 | 1 | 1 | 0 |  |  | 0 | 0 | 0
7 | ASSY - CHASSIS SUBFRAME | Divergent | 8 | 4 | 12 | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB | 112,113,114,115,122,123,124,125 | 8 | 8 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
8 | ASSY - HVAC BOX | AutoFrost | 0 | 8 | 8 | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING | 9 | 1 | 1 | 0 | 2,10,11 | 3 | 3 | 0 | ASSY - HVAC PIPING | 10 | 1 | 1 | 0
9 | ASSY - THERMAL BOX | AutoFrost, PWR | 3 | 6 | 9 |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX |  | 0 | 0 | 0 | 8,10,11,12 | 4 | 4 | 0 |  |  | 0 | 0 | 0
10 | ASSY - HVAC PIPING | Unknown | 3 | 7 | 10 | ASSY - THERMAL BOX, ASSY - HVAC BOX | ASSY - FRONT FLUID MANAGEMENT | 8,9 | 2 | 2 | 0 | 11 | 1 | 1 | 0 | ASSY - HVAC BOX | 8 | 1 | 1 | 0
11 | ASSY - FRONT FLUID MANAGEMENT | Unknown | 3 | 4 | 7 | ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX | ASSY - CHASSIS VENTILATION, ASSY - REAR FLUID MANAGEMENT, ASSY - BATTERY MODULES, ASSY - OCCUPANT CELL TUB | 8,9,10 | 3 | 3 | 0 | 2,6,12,126 | 4 | 4 | 0 |  |  | 0 | 0 | 0
12 | ASSY - REAR FLUID MANAGEMENT | Unknown | 3 | 5 | 8 | ASSY - THERMAL BOX, ASSY - FRONT FLUID MANAGEMENT, ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH, ASSY - HYDROGEN COOLING SYSTEM | ASSY - OCCUPANT CELL TUB | 9,11,112,113,182 | 5 | 5 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
13 | ASSY - REAR BUMPER | McConaghy, Scott Bader, Colan | 0 | 6 | 6 | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE | 14,15 | 4 | 2 | 2 | 17,18 | 2 | 2 | 0 |  |  | 0 | 0 | 0
14 | ASSY - REAR QUARTER PANEL - LH | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH |  | 0 | 0 | 0 | 2,13,17,18,19,24 | 6 | 6 | 0 |  |  | 0 | 0 | 0
15 | ASSY - REAR QUARTER PANEL - RH | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH |  | 0 | 0 | 0 | 2,13,17,18,19,23 | 6 | 6 | 0 |  |  | 0 | 0 | 0
16 | ASSY - FRONT CLAM SHELL | McConaghy, Scott Bader, Colan | 0 | 7 | 7 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LiDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB | ASSY - BONNET | 2,6,27,28,41,43,91,92,153,154,155,156,159 | 14 | 13 | 1 | 21 | 1 | 1 | 0 |  |  | 0 | 0 | 0
17 | ASSY - REAR FLOOR | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
18 | ASSY - REAR SUPPORT STRUCTURE | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
19 | ASSY - BOOT | McConaghy, Scott Bader, Colan, Stabillus | 1 | 5 | 6 | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT LOCKING BOARD | 14,15,18,143,146,147,148,149,150,151,152 | 11 | 11 | 0 | 20 | 1 | 1 | 0 |  |  | 0 | 0 | 0
20 | ASSY - BOOT LOCKING BOARD | Sunswift | 0 | 4 | 4 | ASSY - BOOT |  | 19 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
21 | ASSY - BONNET | McConaghy, Scott Bader, Colan | 0 | 4 | 4 | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAM SHELL | ASSY - BONNET LOCKING BOARD | 16,47,144 | 3 | 3 | 0 | 22 | 1 | 1 | 0 |  |  | 0 | 0 | 0
22 | ASSY - BONNET LOCKING BOARD | Sunswift | 0 | 4 | 4 | ASSY - BONNET |  | 21 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
23 | ASSY - OUTER DOOR HANDLE - RH | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - RH |  | 29 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
24 | ASSY - OUTER DOOR HANDLE - LH | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - LH |  | 30 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
25 | ASSY - INNER DOOR HANDLE - RH | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - RH |  | 35 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
26 | ASSY - INNER DOOR HANDLE - LH | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - LH |  | 36 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
27 | ASSY - DOOR SHELL - RH | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - RH, ASSY - REAR QUARTER PANEL - RH | 31,37,40,158 | 4 | 4 | 0 | 1,15,16,35 | 4 | 4 | 0 |  |  | 0 | 0 | 0
28 | ASSY - DOOR SHELL - LH | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - LH, ASSY - REAR QUARTER PANEL - LH | 32,38,39,157 | 4 | 4 | 0 | 1,14,16,36 | 4 | 4 | 0 |  |  | 0 | 0 | 0
29 | ASSY - DOOR LATCH - RH | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,23 | 2 | 2 | 0 |  |  | 0 | 0 | 0
30 | ASSY - DOOR LATCH - LH | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,24 | 2 | 2 | 0 |  |  | 0 | 0 | 0
31 | ASSY - DOOR HINGE - RH | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD - RH |  | 0 | 0 | 0 | 27,35 | 2 | 2 | 0 |  |  | 0 | 0 | 0
32 | ASSY - DOOR HINGE - LH | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH |  | 0 | 0 | 0 | 28,36 | 2 | 2 | 0 |  |  | 0 | 0 | 0
33 | ASSY - DOOR CONTROL BOARD - RH | Sunswift | 0 | 5 | 5 | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH |  | 27,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
34 | ASSY - DOOR CONTROL BOARD - LH | Sunswift | 0 | 5 | 5 | ASSY - DOOR HINGE - LH , ASSY - DOOR SHELL - LH |  | 28,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
35 | ASSY - DOOR CARD - RH | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - RH, ASSY - DOOR AUDIO - RH | ASSY - INNER DOOR HANDLE - RH, ASSY - DASHBOARD STRUCTURE | 1,2,27,31,37 | 5 | 5 | 0 | 25,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
36 | ASSY - DOOR CARD - LH | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE - LH, ASSY - DOOR AUDIO - LH | ASSY - INNER DOOR HANDLE - LH, ASSY - DASHBOARD STRUCTURE | 1,2,28,32,38 | 5 | 5 | 0 | 26,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
37 | ASSY - DOOR AUDIO - RH | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
38 | ASSY - DOOR AUDIO - LH | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
39 | ASSY - ELECTRIC WINDOWS - LH | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
40 | ASSY - ELECTRIC WINDOWS - RH | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
41 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
42 | ASSY - ACTIVE AERO MOTORS | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
43 | ASSY - ACTIVE AERO CONTROL PCB | Sunswift | 0 | 6 | 6 | ASSY - ACTIVE AERO MOTORS |  | 42 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
44 | ASSY - WINDSCREEN | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
45 | ASSY - WINDSCREEN WIPER | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
46 | ASSY - WINDSCREEN WASHER | Unknown | 4 | 2 | 6 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
47 | ASSY - WINDSCREEN WIPER AERO GUARD | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
48 | ASSY - WINDSCREEN WIPER MOTOR | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
49 | ASSY - WINDSCREEN WIPER CONTROL PCB | Sunswift | 0 | 4 | 4 | ASSY - WINDSCREEN WIPER MOTOR |  | 48 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
50 | ASSY - FRONT TOP WISHBONE - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
51 | ASSY - FRONT TOP WISHBONE - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
52 | ASSY - FRONT LOWER WISHBONE - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
53 | ASSY - FRONT LOWER WISHBONE - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
54 | ASSY - FRONT TIEROD - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - LH, ASSY - FRONT DAMPER - LH, ASSY - FRONT CALIPER - LH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 56,58,71,75 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
55 | ASSY - FRONT TIEROD - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - RH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 57,59,72,75 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
56 | ASSY - FRONT UPRIGHT - LH | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
57 | ASSY - FRONT UPRIGHT - RH | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
58 | ASSY - FRONT DAMPER - LH | Bilstein | 0 | 2 | 2 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
59 | ASSY - FRONT DAMPER - RH | Bilstein | 0 | 2 | 2 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
60 | ASSY - FRONT WHEEL | Sunswift | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC |  | 0 | 0 | 0 | 2,50,51,54,55,56,57,58,59,71,72,73,75 | 13 | 13 | 0 |  |  | 0 | 0 | 0
61 | ASSY - REAR TOP WISHBONE - LH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
62 | ASSY - REAR TOP WISHBONE - RH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
63 | ASSY - REAR LOWER WISHBONE - LH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
64 | ASSY - REAR LOWER WISHBONE - RH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
65 | ASSY - REAR TOELINK | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH |  | 2,61,62,63,64 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
66 | ASSY - REAR UPRIGHT - LH | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - LH | 70 | 1 | 1 | 0 | 68 | 1 | 1 | 0 |  |  | 0 | 0 | 0
67 | ASSY - REAR UPRIGHT - RH | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - RH | 70 | 1 | 1 | 0 | 69 | 1 | 1 | 0 |  |  | 0 | 0 | 0
68 | ASSY - REAR DAMPER - LH | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - LH |  | 66,70 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
69 | ASSY - REAR DAMPER - RH | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - RH |  | 67,70 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
70 | ASSY - REAR WHEEL | Sunswift | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE |  | 0 | 0 | 0 | 2,14,15,18,61,62,63,64,65,66,67,68,69,78,79,80,81,82,83,84 | 20 | 20 | 0 |  |  | 0 | 0 | 0
71 | ASSY - FRONT CALIPER - LH | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 60,75 | 2 | 2 | 0 | 2,76 | 2 | 2 | 0 |  |  | 0 | 0 | 0
72 | ASSY - FRONT CALIPER - RH | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 60,75 | 2 | 2 | 0 | 2,76 | 2 | 2 | 0 |  |  | 0 | 0 | 0
73 | ASSY - FRONT MASTER CYLINDER RESERVOIR | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | 2,4,50,51,52,53,54,55,56,57,86,93,95 | 13 | 13 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
74 | ASSY - FRONT MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
75 | ASSY - FRONT BRAKE DISC | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT WHEEL | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH | 60 | 1 | 1 | 0 | 56,57,71,72 | 4 | 4 | 0 |  |  | 0 | 0 | 0
76 | ASSY - FRONT BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
77 | ASSY CHASSIS BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
78 | ASSY - REAR BRAKE CALIPER - LH | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 70,82 | 2 | 2 | 0 | 83 | 1 | 1 | 0 |  |  | 0 | 0 | 0
79 | ASSY - REAR BRAKE CALIPER - RH | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 70,82 | 2 | 2 | 0 | 83 | 1 | 1 | 0 |  |  | 0 | 0 | 0
80 | ASSY - REAR MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
81 | ASSY - REAR MASTER CYLINDER RESERVOIR | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
82 | ASSY - REAR BRAKE DISC | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | 70 | 1 | 1 | 0 | 78,79,83,84 | 4 | 4 | 0 |  |  | 0 | 0 | 0
83 | ASSY - REAR BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
84 | ASSY - HAND BRAKE | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY CHASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE | 70,82 | 2 | 2 | 0 | 77,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
85 | ASSY - STEERING COLUMN | Flaming River | 4 | 2 | 6 | ASSY - STEERING WHEEL, ASSY - STEERING RACK | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE | 86,87 | 2 | 2 | 0 | 3,4 | 2 | 2 | 0 |  |  | 0 | 0 | 0
86 | ASSY - STEERING RACK | Flaming River | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - STEERING COLUMN |  | 0 | 0 | 0 | 2,54,55,85 | 4 | 4 | 0 |  |  | 0 | 0 | 0
87 | ASSY - STEERING WHEEL | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB | ASSY - DRIVER DISPLAY, ASSY - STEERING COLUMN | 88 | 1 | 1 | 0 | 85,103 | 2 | 2 | 0 |  |  | 0 | 0 | 0
88 | ASSY - STEERING WHEEL PCB | Sunswift | 0 | 6 | 6 |  | ASSY - STEERING WHEEL |  | 0 | 0 | 0 | 87 | 1 | 1 | 0 |  |  | 0 | 0 | 0
89 | ASSY - INTERIOR LIGHTS PCB | Sunswift | 0 | 6 | 6 |  | ASSY - OCCUPANT CELL SPIDER, ASSY - CEILING |  | 0 | 0 | 0 | 1,98 | 2 | 2 | 0 |  |  | 0 | 0 | 0
90 | ASSY - REAR VISION CAMERA | Sunswift | 0 | 4 | 4 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
91 | ASSY - SIDE CAMERA - LH | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 0 | 0 | 0 | 147 | 1 | 1 | 0 |  |  | 0 | 0 | 0
92 | ASSY - SIDE CAMERA - RH | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 0 | 0 | 0 | 148 | 1 | 1 | 0 |  |  | 0 | 0 | 0
93 | ASSY - PEDAL BOX | Sunswift | 0 | 2 | 2 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR | ASSY - OCCUPANT CELL TUB | 94,95,96,97 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
94 | ASSY - THROTTLE PEDAL | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 74,80,97 | 3 | 3 | 0 |  |  | 0 | 0 | 0
95 | ASSY - BRAKE PEDAL | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 74,76,80,97 | 4 | 4 | 0 |  |  | 0 | 0 | 0
96 | ASSY - PEDAL BOX CONTROLLER | Sunswift | 0 | 2 | 2 | ASSY - PEDAL PRESS SENSOR |  | 97 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
97 | ASSY - PEDAL PRESS SENSOR | Sunswift | 0 | 1 | 1 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL |  | 94,95 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
98 | ASSY - CEILING | Sunswift | 0 | 4 | 4 | ASSY - REAR VISION CAMERA, ASSY - SUN VISOR - LH, ASSY - SUN VISOR - RH, ASSY - OCCUPANT CELL SPIDER |  | 1,90,99,100 | 4 | 4 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
99 | ASSY - SUN VISOR - LH | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 98 | 1 | 1 | 0 |  |  | 0 | 0 | 0
100 | ASSY - SUN VISOR - RH | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 98 | 1 | 1 | 0 |  |  | 0 | 0 | 0
101 | ASSY - DASHBOARD STRUCTURE | Sunswift/Mconaghy | 0 | 6 | 6 | ASSY - OCCUPANT CELL TUB, ASSY - DOOR CARD - LH, ASSY - DOOR CARD - RH, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR) |  | 2,35,36,102,103,104 | 7 | 6 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
102 | ASSY - CENTRAL DISPLAY | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
103 | ASSY - DRIVER DISPLAY | Espresso conversation | 0 | 2 | 2 | ASSY - STEERING WHEEL | ASSY - DASHBOARD STRUCTURE | 87 | 1 | 1 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
104 | ASSY - HEADS-UP DISPLAY | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
105 | ASSY - FRONT SEAT RAIL DRIVER | Bride Racing | 0 | 4 | 4 | ASSY - FRONT SEAT DRIVER |  | 106 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
106 | ASSY - FRONT SEAT DRIVER | Sunswift | 0 | 4 | 4 |  | ASSY - FRONT SEAT RAIL DRIVER |  | 0 | 0 | 0 | 105 | 1 | 1 | 0 |  |  | 0 | 0 | 0
107 | ASSY - FRONT SEAT MOUNT DRIVER | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER, ASSY - FRONT SEAT BELT DRIVER |  | 0 | 0 | 0 | 2,106,110 | 3 | 3 | 0 |  |  | 0 | 0 | 0
108 | ASSY - FRONT SEAT PASSENGER | Sunswift | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER |  | 0 | 0 | 0 | 2,109 | 2 | 2 | 0 |  |  | 0 | 0 | 0
109 | ASSY - FRONT SEAT MOUNT PASSENGER | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER |  | 0 | 0 | 0 | 2,111 | 2 | 2 | 0 |  |  | 0 | 0 | 0
110 | ASSY - FRONT SEAT BELT DRIVER | Unknown | 1 | 1 | 2 | ASSY - FRONT SEAT DRIVER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 106 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
111 | ASSY - FRONT SEAT BELT PASSENGER | Unknown | 0 | 1 | 1 | ASSY - FRONT SEAT PASSENGER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 108 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
112 | ASSY - MOTOR UNIT - LH | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - INVERTER - LH, ASSY - INVERTER MOUNTING FRAME - LH, ASSY - PWT HV WIRING - LH, ASSY - GEARBOX - LH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,114,116,118,120,122,124 | 9 | 8 | 1 |  |  | 0 | 0 | 0
113 | ASSY - MOTOR UNIT - RH | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - INVERTER - RH, ASSY - INVERTER MOUNTING FRAME - RH, ASSY - PWT HV WIRING - RH, ASSY - GEARBOX - RH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,115,117,119,121,123,124 | 9 | 8 | 1 |  |  | 0 | 0 | 0
114 | ASSY - MOTOR MOUNTING FRAME - LH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | 112,122 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
115 | ASSY - MOTOR MOUNTING FRAME - RH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | 113,123 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
116 | ASSY - INVERTER - LH | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - LH | ASSY - HYDROGEN COOLING SYSTEM | 112 | 1 | 1 | 0 | 182 | 1 | 1 | 0 |  |  | 0 | 0 | 0
117 | ASSY - INVERTER - RH | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - RH | ASSY - HYDROGEN COOLING SYSTEM | 113 | 1 | 1 | 0 | 182 | 1 | 1 | 0 |  |  | 0 | 0 | 0
118 | ASSY - INVERTER MOUNTING FRAME - LH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 112,116 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
119 | ASSY - INVERTER MOUNTING FRAME - RH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 113,117 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
120 | ASSY - PWT HV WIRING - LH | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 112,116 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
121 | ASSY - PWT HV WIRING - RH | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 113,117 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
122 | ASSY - GEARBOX - LH | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - LH | 112 | 1 | 1 | 0 | 2,7,124 | 3 | 3 | 0 |  |  | 0 | 0 | 0
123 | ASSY - GEARBOX - RH | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - RH | 113 | 1 | 1 | 0 | 2,7,125 | 3 | 3 | 0 |  |  | 0 | 0 | 0
124 | ASSY - AXLE CV - LH | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 112,122 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
125 | ASSY - AXLE CV - RH | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 113,123 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
126 | ASSY - BATTERY MODULES | Sunswift | 8 | 4 | 12 |  | ASSY - BATTERY PACK |  | 0 | 0 | 0 | 127 | 1 | 1 | 0 |  |  | 0 | 0 | 0
127 | ASSY - BATTERY PACK | Sunswift | 8 | 2 | 10 | ASSY - BATTERY MODULES | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING | 126 | 1 | 1 | 0 | 128,129,130 | 3 | 3 | 0 |  |  | 0 | 0 | 0
128 | ASSY - BMS WIRING | Sunswift | 8 | 3 | 11 | ASSY - BATTERY PACK | ASSY - CONTROL LOGIC | 127 | 1 | 1 | 0 | 136 | 1 | 1 | 0 |  |  | 0 | 0 | 0
129 | ASSY - BATTERY HV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
130 | ASSY - BATTERY LV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
131 | ASSY - AUXILLARY POWER WIRING | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 133 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
132 | ASSY - DC-DC CONVERTERS | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 133 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
133 | ASSY - AUX BATTERY | Sunswift | 8 | 2 | 10 |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING |  | 0 | 0 | 0 | 131,132 | 2 | 2 | 0 |  |  | 0 | 0 | 0
134 | ASSY - ECS HV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
135 | ASSY - ECS LV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
136 | ASSY - CONTROL LOGIC | Sunswift | 8 | 3 | 11 | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING |  | 134,135 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
137 | ASSY - ECS MODULE | Sunswift | 8 | 3 | 11 |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC |  | 0 | 0 | 0 | 134,135,136 | 3 | 3 | 0 |  |  | 0 | 0 | 0
138 | ASSY - ONBOARD CHARGING WIRING | Sunswift | 0 | 2 | 2 | ASSY - ONBOARD CHARGER INSTALLATION |  | 139 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
139 | ASSY - ONBOARD CHARGER INSTALLATION | Sunswift | 0 | 3 | 3 |  | ASSY - ONBOARD CHARGING WIRING |  | 0 | 0 | 0 | 138 | 1 | 1 | 0 |  |  | 0 | 0 | 0
140 | ASSY - MPPT JUNCTION BOX | Sunswift | 0 | 2 | 2 | ASSY - MPPT | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC | 141 | 1 | 1 | 0 | 134,136 | 2 | 2 | 0 |  |  | 0 | 0 | 0
141 | ASSY - MPPT | Sunswift | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - occupant cell spider | 142,143,144,146 | 4 | 4 | 0 | 1 | 1 | 1 | 0 |  |  | 0 | 0 | 0
142 | ASSY - SOLAR ROOF ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - occupant cell spider, ASSY - occupant cell tub, ASSY - ceiling, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 1,2,98,141,145 | 5 | 5 | 0 |  |  | 0 | 0 | 0
143 | ASSY - SOLAR BOOT ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
144 | ASSY - SOLAR BONNET ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - bonnet, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 21,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
145 | ASSY - MC4 Cabling | None, by off sheld, maybe SunDrive | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - Occupant cell spider, ASSY - boot, ASSY - Bonnet, ASSY - MPPT | 142,143,144,146 | 4 | 4 | 0 | 1,19,21,141 | 4 | 4 | 0 |  |  | 0 | 0 | 0
146 | Assy - Shingled Matrix Panels | M10 | 0 | 12 | 12 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
147 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
148 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
149 | ASSY - TAILLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 147 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
150 | ASSY - TAILLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 148 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
151 | ASSY - CENTRAL STOP LAMP | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT |  | 0 | 0 | 0 | 19,152 | 2 | 2 | 0 |  |  | 0 | 0 | 0
152 | ASSY - CENTRAL STOP LAMP PCB | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOP LAMP |  | 151 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
153 | ASSY - HEADLIGHT EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
154 | ASSY - HEADLIGHT EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
155 | ASSY - HEADLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - LH |  | 0 | 0 | 0 | 153 | 1 | 1 | 0 |  |  | 0 | 0 | 0
156 | ASSY - HEADLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - RH |  | 0 | 0 | 0 | 154 | 1 | 1 | 0 |  |  | 0 | 0 | 0
157 | ASSY - SIDE INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
158 | ASSY - SIDE INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
159 | ASSY - HORN | Sunswift | 0 | 1 | 1 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
160 | ASSY - HORN PCB | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
161 | ASSY - DRIVE CONTROL UNIT | Sunswift | 0 | 12 | 12 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH |  | 112,113 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
162 | ASSY - SENSOR MOTHERBOARD - FL | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
163 | ASSY - SENSOR MOTHERBOARD - FR | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
164 | ASSY - SENSOR MOTHERBOARD - BL | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
165 | ASSY - SENSOR MOTHERBOARD - BR | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
166 | ASSY - SUBWOOFER | Sunswift | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
167 | ASSY - AUDIO CONTROL SYSTEM | Sunswift | 0 | 8 | 8 | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER |  | 37,38,166 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
168 | ASSY - PRESSURE VESSEL SHELL | Coregas, Swagelok | 6 | 0 | 6 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY | 169 | 1 | 1 | 0 | 170,171 | 2 | 2 | 0 |  |  | 0 | 0 | 0
169 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | Sunswift | 0 | 0 | 0 |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL |  | 0 | 0 | 0 | 2,17,168,170,171 | 5 | 5 | 0 |  |  | 0 | 0 | 0
170 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | Sunswift | 0 | 0 | 0 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR | 168,169 | 2 | 2 | 0 | 174,175 | 2 | 2 | 0 |  |  | 0 | 0 | 0
171 | ASSY - PRESSURE REGULATION & SAFETY | Swagelok | 12 | 0 | 12 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 168,169 | 2 | 2 | 0 | 172,179,184 | 3 | 3 | 0 |  |  | 0 | 0 | 0
172 | ASSY - HYDROGEN SUPPLY LINE | Swagelok | 6 | 0 | 6 | ASSY - PRESSURE REGULATION & SAFETY | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - SENSOR ARRAY | 171 | 1 | 1 | 0 | 173 | 2 | 1 | 1 |  |  | 0 | 0 | 0
173 | ASSY - HYDROGEN PURGE MANAGEMENT | Siltrax, Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE | ASSY - P&ID HYDROGEN RECYCLE STREAM | 172,181 | 2 | 2 | 0 | 176 | 1 | 1 | 0 |  |  | 0 | 0 | 0
174 | ASSY - HYDROGEN COMPARTMENT VENTILATION | Sunswift | 0 | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - P&ID AIR SUPPLY LINE, ASSY - REARWHEEL HUB AIR INTAKE | 170 | 1 | 1 | 0 | 185,186 | 2 | 2 | 0 |  |  | 0 | 0 | 0
175 | ASSY - OCCUPANT CELL HYDROGEN SENSOR | Gas detection supplier (Honeywell/CityTech etc.) | 10 | 0 | 10 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 170 | 1 | 1 | 0 | 178,183 | 2 | 2 | 0 |  |  | 0 | 0 | 0
176 | ASSY - P&ID HYDROGEN RECYCLE STREAM | Siltrax | 6 | 0 | 6 | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK | ASSY - HYDROGEN SENSOR ARRAY | 173,181 | 2 | 2 | 0 | 179 | 1 | 1 | 0 |  |  | 0 | 0 | 0
177 | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY |  | 179,183 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
178 | ASSY - OCCUPANT CELL SHUTDOWN VALVE | Swagelok | 6 | 0 | 6 | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC |  | 175,180 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
179 | ASSY - HYDROGEN SENSOR ARRAY | External Supplier (TBA) | 10 | 0 | 10 | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 171,172,181 | 3 | 3 | 0 | 177,180 | 2 | 2 | 0 |  |  | 0 | 0 | 0
180 | ASSY - HYDROGEN CONTROL LOGIC | External Supplier (TBA) | 16 | 0 | 16 | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL SYSTEM | 179,181 | 2 | 2 | 0 | 187 | 1 | 1 | 0 |  |  | 0 | 0 | 0
181 | ASSY - FUEL CELL STACK | Siltrax | 6 | 0 | 6 | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE | 127 | 2 | 1 | 1 | 170,172,179,182,187 | 5 | 5 | 0 |  |  | 0 | 0 | 0
182 | ASSY - HYDROGEN COOLING SYSTEM | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT | 181 | 1 | 1 | 0 | 12,183,184 | 3 | 3 | 0 |  |  | 0 | 0 | 0
183 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 181 | 1 | 1 | 0 | 177 | 1 | 1 | 0 |  |  | 0 | 0 | 0
184 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE | Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT | ASSY - P&ID AIR SUPPLY LINE | 172,173,181 | 3 | 3 | 0 | 185 | 1 | 1 | 0 |  |  | 0 | 0 | 0
185 | ASSY - P&ID AIR SUPPLY LINE | Beswick, Swagelok | 8 | 0 | 8 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - OCCUPANT CELL SHUTDOWN VALVE | 186 | 2 | 1 | 1 | 178 | 1 | 1 | 0 |  |  | 0 | 0 | 0
186 | ASSY - REARWHEEL HUB AIR INTAKE | Sunswift |  | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN CONTROL LOGIC | 170 | 1 | 1 | 0 | 180 | 1 | 1 | 0 |  |  | 0 | 0 | 0
187 | ASSY - HYDROGEN CONTROL SYSTEM | Ballard or Intelligent Energy | 12 | 0 | 12 | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS MODULE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS |  | 137,180,183 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
188 | ASSY - INTERNAL EMBEDDED NETWORK WIRING | Sunswift | 0 | 2 | 2 | ASSY - HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP, ASSY - STEERING WHEEL, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LiDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM, ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - BOOT, ASSY - BONNET |  | 2,3,4,5,6,13,14,15,16,17,18,19,21,37,38,87,96,102,103,149,150,151,155,156,160,161,166,167,190 | 33 | 29 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
189 | ASSY - INTRANET | Sunswift | 0 | 0 | 0 | ASSY - SUNSWIFT PHONE APP |  |  | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
190 | ASSY - MAIN COMPUTER | Adlink | 8 | 1 | 9 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH, ASSY - DRIVE CONTROL UNIT | ASSY - INTERNAL EMBEDDED NETWORK WIRING | 112,113,161 | 3 | 3 | 0 | 188 | 1 | 1 | 0 |  |  | 0 | 0 | 0
191 | ASSY - STEERING WHEEL PCB CODE | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB |  | 88 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
192 | ASSY - DOOR ACTUATOR BOARD - RH | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
193 | ASSY - DOOR ACTUATOR BOARD - LH | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
194 | ASSY - SIDE INDICATOR - LH | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - LH |  | 0 | 0 | 0 | 91 | 1 | 1 | 0 |  |  | 0 | 0 | 0
195 | ASSY - SIDE INDICATOR - RH | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - RH |  | 0 | 0 | 0 | 92 | 1 | 1 | 0 |  |  | 0 | 0 | 0
196 | ASSY - CENTRAL STOPLAMP | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOPLAMP CASING, ASSY - CENTRAL STOPLAMP CONTROLLER |  | 0 | 0 | 0 | 197,198 | 2 | 2 | 0 |  |  | 0 | 0 | 0
197 | ASSY - CENTRAL STOPLAMP CASING | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOPLAMP |  | 196 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
198 | ASSY - CENTRAL STOPLAMP CONTROLLER | Sunswift | 0 | 3 | 3 | ASSY - CENTRAL STOPLAMP |  | 196 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0

## Cycles_Named
Cycle | Cycle_Named