## Raw_Tasks
ID | Description | Partners | PartnerWeight | EdgeWeight | Duration | Predecessors | Successors | PredecessorIDs | Pre | PreIds | PreDiff | SuccessorIDs | Suc | SucIds | SucDiff | Parallel | ParallelIDs | Par | ParIDs | ParDiff
1 | ASSY - OCCUPANT CELL SPIDER | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - SOLAR ROOF ARRAY, ASSY - DOOR SHELL - LH, ASSY - DOOR SHELL - RH | ASSY - WINDSCREEN, ASSY - CEILING, ASSY - DOOR CARD - LH, ASSY - WINDSCREEN WIPER AERO GUARD | 27,28,142 | 3 | 3 | 0 | 36,44,47,98 | 4 | 4 | 0 | ASSY - OCCUPANT CELL TUB | 2 | 1 | 1 | 0
2 | ASSY - OCCUPANT CELL TUB | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - FRONT FLUID MANAGEMENT, ASSY - HVAC BOX, ASSY - FRONT CRASH STRUCTURE, ASSY - STEERING COLUMN, ASSY - FRONT SEAT BELT DRIVER, ASSY - AXLE CV - LH, ASSY - CHASSIS SUBFRAME, ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - WINDSCREEN WIPER MOTOR, ASSY - STEERING COLUMN MOUNT, ASSY - REAR FLUID MANAGEMENT, ASSY - FRONT DAMPER - LH, ASSY - FRONT SEAT PASSENGER, ASSY - MOTOR UNIT - RH, ASSY - STEERING RACK, ASSY - REAR CRASH STRUCTURE, ASSY - DOOR LATCH - RH, ASSY - INTERIOR LIGHTS PCB, ASSY - MOTOR UNIT - LH, ASSY - FRONT SEAT BELT PASSENGER, ASSY - AXLE CV - RH, ASSY - FRONT TOP WISHBONE - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - PRESSURE VESSEL SHELL, ASSY - FRONT LOWER WISHBONE - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - DOOR LATCH - LH, ASSY - BATTERY MODULES, ASSY - FRONT SEAT DRIVER, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT TIEROD - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - DOOR CARD - LH, ASSY - FRONT CLAM SHELL | 3,4,5,7,8,11,12,14,15,29,30,48,50,51,52,53,54,55,58,59,85,86,89,106,108,110,111,112,113,124,125,126,168,174 | 34 | 34 | 0 | 16,17,18,36 | 4 | 4 | 0 | ASSY - OCCUPANT CELL SPIDER | 1 | 1 | 1 | 0
3 | ASSY - STEERING COLUMN MOUNT | McConaghy, Scott Bader, Colan | 0 | 2 | 2 | ASSY - STEERING COLUMN | ASSY - OCCUPANT CELL TUB | 85 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
4 | ASSY - FRONT CRASH STRUCTURE | Calm Aluminium | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - REAR CRASH STRUCTURE | 5 | 1 | 1 | 0
5 | ASSY - REAR CRASH STRUCTURE | Calm Aluminium | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | ASSY - FRONT CRASH STRUCTURE | 4 | 1 | 1 | 0
6 | ASSY - CHASSIS VENTILATION | McConaghy, Scott Bader, Colan | 0 | 8 | 8 | ASSY - FRONT FLUID MANAGEMENT, ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | ASSY - FRONT CLAM SHELL | 11,41 | 2 | 2 | 0 | 16 | 1 | 1 | 0 |  |  | 0 | 0 | 0
7 | ASSY - CHASSIS SUBFRAME | Divergent | 8 | 4 | 12 | ASSY - GEARBOX - RH, ASSY - MOTOR UNIT - LH, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - AXLE CV - LH, ASSY - AXLE CV - RH, ASSY - GEARBOX - LH, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB | 112,113,114,115,122,123,124,125 | 8 | 8 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
8 | ASSY - HVAC BOX | AutoFrost | 0 | 8 | 8 | ASSY - THERMAL BOX | ASSY - FRONT FLUID MANAGEMENT, ASSY - OCCUPANT CELL TUB, ASSY - HVAC PIPING | 9 | 1 | 1 | 0 | 2,10,11 | 3 | 3 | 0 | ASSY - HVAC PIPING | 10 | 1 | 1 | 0
9 | ASSY - THERMAL BOX | AutoFrost, PWR | 3 | 6 | 9 |  | ASSY - FRONT FLUID MANAGEMENT, ASSY - REAR FLUID MANAGEMENT, ASSY - HVAC PIPING, ASSY - HVAC BOX |  | 0 | 0 | 0 | 8,10,11,12 | 4 | 4 | 0 |  |  | 0 | 0 | 0
10 | ASSY - HVAC PIPING | Unknown | 3 | 7 | 10 | ASSY - THERMAL BOX, ASSY - HVAC BOX | ASSY - FRONT FLUID MANAGEMENT | 8,9 | 2 | 2 | 0 | 11 | 1 | 1 | 0 | ASSY - HVAC BOX | 8 | 1 | 1 | 0
11 | ASSY - FRONT FLUID MANAGEMENT | Unknown | 3 | 4 | 7 | ASSY - HVAC PIPING, ASSY - HVAC BOX, ASSY - THERMAL BOX | ASSY - CHASSIS VENTILATION, ASSY - REAR FLUID MANAGEMENT, ASSY - BATTERY MODULES, ASSY - OCCUPANT CELL TUB | 8,9,10 | 3 | 3 | 0 | 2,6,12,126 | 4 | 4 | 0 |  |  | 0 | 0 | 0
12 | ASSY - REAR FLUID MANAGEMENT | Unknown | 3 | 5 | 8 | ASSY - THERMAL BOX, ASSY - FRONT FLUID MANAGEMENT, ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH, ASSY - HYDROGEN COOLING SYSTEM | ASSY - OCCUPANT CELL TUB | 9,11,112,113,182 | 5 | 5 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
13 | ASSY - REAR BUMPER | McConaghy, Scott Bader, Colan | 0 | 6 | 6 | ASSY - BLINDSPOT MONITORING SENSOR - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - BLINDSPOT MONITORING SENSOR - LH | ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE | 14,15 | 4 | 2 | 2 | 17,18 | 2 | 2 | 0 |  |  | 0 | 0 | 0
14 | ASSY - REAR QUARTER PANEL - LH | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - LH |  | 0 | 0 | 0 | 2,13,17,18,19,24 | 6 | 6 | 0 |  |  | 0 | 0 | 0
15 | ASSY - REAR QUARTER PANEL - RH | McConaghy, Scott Bader, Colan | 0 | 2 | 2 |  | ASSY - REAR BUMPER, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - BOOT, ASSY - REAR SUPPORT STRUCTURE, ASSY - OUTER DOOR HANDLE - RH |  | 0 | 0 | 0 | 2,13,17,18,19,23 | 6 | 6 | 0 |  |  | 0 | 0 | 0
16 | ASSY - FRONT CLAM SHELL | McConaghy, Scott Bader, Colan | 0 | 7 | 7 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - DOOR SHELL - LH, ASSY - C-V2V RADAR/LiDAR, ASSY - HEADLIGHT EXTERIOR - RH, ASSY - ACTIVE AERO CONTROL PCB, ASSY - SIDE CAMERA - LH, ASSY - DOOR SHELL - RH, ASSY - CHASSIS VENTILATION, ASSY - HEADLIGHT EXTERIOR - LH, ASSY - HORN, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - SIDE CAMERA - RH, ASSY - OCCUPANT CELL TUB | ASSY - BONNET | 2,6,27,28,41,43,91,92,153,154,155,156,159 | 14 | 13 | 1 | 21 | 1 | 1 | 0 |  |  | 0 | 0 | 0
17 | ASSY - REAR FLOOR | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
18 | ASSY - REAR SUPPORT STRUCTURE | McConaghy, Scott Bader, Colan | 0 | 5 | 5 | ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR BUMPER, ASSY - OCCUPANT CELL TUB | ASSY - BOOT | 2,13,14,15 | 4 | 4 | 0 | 19 | 1 | 1 | 0 |  |  | 0 | 0 | 0
19 | ASSY - BOOT | McConaghy, Scott Bader, Colan, Stabillus | 1 | 5 | 6 | ASSY - CENTRAL STOP LAMP PCB, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH, ASSY - REAR SUPPORT STRUCTURE, ASSY - CENTRAL STOP LAMP, ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH, ASSY - SHINGLED MATRIX PANELS, ASSY - SOLAR BOOT ARRAY, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR QUARTER PANEL - LH | ASSY - BOOT LOCKING BOARD | 14,15,18,143,146,147,148,149,150,151,152 | 11 | 11 | 0 | 20 | 1 | 1 | 0 |  |  | 0 | 0 | 0
20 | ASSY - BOOT LOCKING BOARD | Sunswift | 0 | 4 | 4 | ASSY - BOOT |  | 19 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
21 | ASSY - BONNET | McConaghy, Scott Bader, Colan | 0 | 4 | 4 | ASSY - SOLAR BONNET ARRAY, ASSY - WINDSCREEN WIPER AERO GUARD, ASSY - FRONT CLAM SHELL | ASSY - BONNET LOCKING BOARD | 16,47,144 | 3 | 3 | 0 | 22 | 1 | 1 | 0 |  |  | 0 | 0 | 0
22 | ASSY - BONNET LOCKING BOARD | Sunswift | 0 | 4 | 4 | ASSY - BONNET |  | 21 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
23 | ASSY - OUTER DOOR HANDLE - RH | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - RH |  | 29 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
24 | ASSY - OUTER DOOR HANDLE - LH | Chevalier | 4 | 2 | 6 | ASSY - DOOR LATCH - LH |  | 30 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
25 | ASSY - INNER DOOR HANDLE - RH | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - RH |  | 35 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
26 | ASSY - INNER DOOR HANDLE - LH | Chevalier | 4 | 2 | 6 | ASSY - DOOR CARD - LH |  | 36 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
27 | ASSY - DOOR SHELL - RH | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - RH, ASSY - SIDE INDICATOR EXTERIOR - RH, ASSY - DOOR AUDIO - RH, ASSY - DOOR HINGE - RH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - RH, ASSY - REAR QUARTER PANEL - RH | 31,37,40,158 | 4 | 4 | 0 | 1,15,16,35 | 4 | 4 | 0 |  |  | 0 | 0 | 0
28 | ASSY - DOOR SHELL - LH | McConaghy, Scott Bader, Colan | 0 | 3 | 3 | ASSY - ELECTRIC WINDOWS - LH, ASSY - SIDE INDICATOR EXTERIOR - LH, ASSY - DOOR AUDIO - LH, ASSY - DOOR HINGE - LH | ASSY - OCCUPANT CELL SPIDER, ASSY - FRONT CLAM SHELL, ASSY - DOOR CARD - LH, ASSY - REAR QUARTER PANEL - LH | 32,38,39,157 | 4 | 4 | 0 | 1,14,16,36 | 4 | 4 | 0 |  |  | 0 | 0 | 0
29 | ASSY - DOOR LATCH - RH | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - RH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,23 | 2 | 2 | 0 |  |  | 0 | 0 | 0
30 | ASSY - DOOR LATCH - LH | Chevalier | 4 | 2 | 6 |  | ASSY - OUTER DOOR HANDLE - LH, ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2,24 | 2 | 2 | 0 |  |  | 0 | 0 | 0
31 | ASSY - DOOR HINGE - RH | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - RH, ASSY - DOOR CARD - RH |  | 0 | 0 | 0 | 27,35 | 2 | 2 | 0 |  |  | 0 | 0 | 0
32 | ASSY - DOOR HINGE - LH | Stabillus | 1 | 3 | 4 |  | ASSY - DOOR SHELL - LH, ASSY - DOOR CARD - LH |  | 0 | 0 | 0 | 28,36 | 2 | 2 | 0 |  |  | 0 | 0 | 0
33 | ASSY - DOOR CONTROL BOARD - RH | Sunswift | 0 | 5 | 5 | ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - LH |  | 27,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
34 | ASSY - DOOR CONTROL BOARD - LH | Sunswift | 0 | 5 | 5 | ASSY - DOOR HINGE - LH , ASSY - DOOR SHELL - LH |  | 28,32 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
35 | ASSY - DOOR CARD - RH | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - RH, ASSY - DOOR HINGE - RH, ASSY - DOOR AUDIO - RH | ASSY - INNER DOOR HANDLE - RH, ASSY - DASHBOARD STRUCTURE | 1,2,27,31,37 | 5 | 5 | 0 | 25,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
36 | ASSY - DOOR CARD - LH | Sunswift | 0 | 3 | 3 | ASSY - OCCUPANT CELL SPIDER, ASSY - OCCUPANT CELL TUB, ASSY - DOOR SHELL - LH, ASSY - DOOR HINGE - LH, ASSY - DOOR AUDIO - LH | ASSY - INNER DOOR HANDLE - LH, ASSY - DASHBOARD STRUCTURE | 1,2,28,32,38 | 5 | 5 | 0 | 26,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
37 | ASSY - DOOR AUDIO - RH | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
38 | ASSY - DOOR AUDIO - LH | Sunswift | 0 | 8 | 8 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
39 | ASSY - ELECTRIC WINDOWS - LH | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - LH |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 |  |  | 0 | 0 | 0
40 | ASSY - ELECTRIC WINDOWS - RH | Unknown | 4 | 2 | 6 |  | ASSY - DOOR SHELL - RH |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 |  |  | 0 | 0 | 0
41 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
42 | ASSY - ACTIVE AERO MOTORS | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
43 | ASSY - ACTIVE AERO CONTROL PCB | Sunswift | 0 | 6 | 6 | ASSY - ACTIVE AERO MOTORS |  | 42 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
44 | ASSY - WINDSCREEN | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
45 | ASSY - WINDSCREEN WIPER | Unknown | 4 | 3 | 7 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
46 | ASSY - WINDSCREEN WASHER | Unknown | 4 | 2 | 6 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
47 | ASSY - WINDSCREEN WIPER AERO GUARD | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
48 | ASSY - WINDSCREEN WIPER MOTOR | Sunswift | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
49 | ASSY - WINDSCREEN WIPER CONTROL PCB | Sunswift | 0 | 4 | 4 | ASSY - WINDSCREEN WIPER MOTOR |  | 48 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
50 | ASSY - FRONT TOP WISHBONE - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
51 | ASSY - FRONT TOP WISHBONE - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
52 | ASSY - FRONT LOWER WISHBONE - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
53 | ASSY - FRONT LOWER WISHBONE - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT WHEEL | ASSY - OCCUPANT CELL TUB | 60 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
54 | ASSY - FRONT TIEROD - LH | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - LH, ASSY - FRONT DAMPER - LH, ASSY - FRONT CALIPER - LH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 56,58,71,75 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
55 | ASSY - FRONT TIEROD - RH | Sunswift | 2 | 2 | 4 | ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - RH, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB | 57,59,72,75 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
56 | ASSY - FRONT UPRIGHT - LH | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
57 | ASSY - FRONT UPRIGHT - RH | Sunswift | 4 | 2 | 6 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
58 | ASSY - FRONT DAMPER - LH | Bilstein | 0 | 2 | 2 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
59 | ASSY - FRONT DAMPER - RH | Bilstein | 0 | 2 | 2 | ASSY - FRONT WHEEL |  | 60 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
60 | ASSY - FRONT WHEEL | Sunswift | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - FRONT DAMPER - LH, ASSY - FRONT DAMPER - RH, ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT MASTER CYLINDER RESERVOIR, ASSY - FRONT BRAKE DISC |  | 0 | 0 | 0 | 2,50,51,54,55,56,57,58,59,71,72,73,75 | 13 | 13 | 0 |  |  | 0 | 0 | 0
61 | ASSY - REAR TOP WISHBONE - LH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
62 | ASSY - REAR TOP WISHBONE - RH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
63 | ASSY - REAR LOWER WISHBONE - LH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
64 | ASSY - REAR LOWER WISHBONE - RH | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - OCCUPANT CELL TUB | 70 | 1 | 1 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
65 | ASSY - REAR TOELINK | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH |  | 2,61,62,63,64 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
66 | ASSY - REAR UPRIGHT - LH | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - LH | 70 | 1 | 1 | 0 | 68 | 1 | 1 | 0 |  |  | 0 | 0 | 0
67 | ASSY - REAR UPRIGHT - RH | Sunswift | 4 | 2 | 6 | ASSY - REAR WHEEL | ASSY - REAR DAMPER - RH | 70 | 1 | 1 | 0 | 69 | 1 | 1 | 0 |  |  | 0 | 0 | 0
68 | ASSY - REAR DAMPER - LH | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - LH |  | 66,70 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
69 | ASSY - REAR DAMPER - RH | Bilstein | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR UPRIGHT - RH |  | 67,70 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
70 | ASSY - REAR WHEEL | Sunswift | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - REAR SUPPORT STRUCTURE, ASSY - REAR TOP WISHBONE - LH, ASSY - REAR TOP WISHBONE - RH, ASSY - REAR LOWER WISHBONE - LH, ASSY - REAR LOWER WISHBONE - RH, ASSY - REAR TOELINK, ASSY - REAR UPRIGHT - LH, ASSY - REAR UPRIGHT - RH, ASSY - REAR DAMPER - LH, ASSY - REAR DAMPER - RH, ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR MASTER CYLINDER, ASSY - REAR MASTER CYLINDER RESERVOIR, ASSY - REAR BRAKE DISC, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE |  | 0 | 0 | 0 | 2,14,15,18,61,62,63,64,65,66,67,68,69,78,79,80,81,82,83,84 | 20 | 20 | 0 |  |  | 0 | 0 | 0
71 | ASSY - FRONT CALIPER - LH | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 60,75 | 2 | 2 | 0 | 2,76 | 2 | 2 | 0 |  |  | 0 | 0 | 0
72 | ASSY - FRONT CALIPER - RH | Sunswift | 0 | 2 | 2 | ASSY - FRONT WHEEL, ASSY - FRONT BRAKE DISC | ASSY - OCCUPANT CELL TUB, ASSY - FRONT BRAKE LINE | 60,75 | 2 | 2 | 0 | 2,76 | 2 | 2 | 0 |  |  | 0 | 0 | 0
73 | ASSY - FRONT MASTER CYLINDER RESERVOIR | Sunswift | 0 | 2 | 2 | ASSY - OCCUPANT CELL TUB, ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL |  | 2,4,50,51,52,53,54,55,56,57,86,93,95 | 13 | 13 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
74 | ASSY - FRONT MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
75 | ASSY - FRONT BRAKE DISC | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT WHEEL | ASSY - FRONT CALIPER - LH, ASSY - FRONT CALIPER - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH | 60 | 1 | 1 | 0 | 56,57,71,72 | 4 | 4 | 0 |  |  | 0 | 0 | 0
76 | ASSY - FRONT BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
77 | ASSY CHASSIS BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
78 | ASSY - REAR BRAKE CALIPER - LH | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 70,82 | 2 | 2 | 0 | 83 | 1 | 1 | 0 |  |  | 0 | 0 | 0
79 | ASSY - REAR BRAKE CALIPER - RH | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY - REAR BRAKE LINE | 70,82 | 2 | 2 | 0 | 83 | 1 | 1 | 0 |  |  | 0 | 0 | 0
80 | ASSY - REAR MASTER CYLINDER | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
81 | ASSY - REAR MASTER CYLINDER RESERVOIR | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
82 | ASSY - REAR BRAKE DISC | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - REAR WHEEL | ASSY - REAR BRAKE CALIPER - LH, ASSY - REAR BRAKE CALIPER - RH, ASSY - REAR BRAKE LINE, ASSY - HAND BRAKE | 70 | 1 | 1 | 0 | 78,79,83,84 | 4 | 4 | 0 |  |  | 0 | 0 | 0
83 | ASSY - REAR BRAKE LINE | Compfriction/AP Racing | 0 | 2 | 2 | ASSY - FRONT CRASH STRUCTURE, ASSY - FRONT TOP WISHBONE - LH, ASSY - FRONT TOP WISHBONE - RH, ASSY - FRONT LOWER WISHBONE - LH, ASSY - FRONT LOWER WISHBONE - RH, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - FRONT UPRIGHT - LH, ASSY - FRONT UPRIGHT - RH, ASSY - STEERING RACK, ASSY - PEDAL BOX, ASSY - BRAKE PEDAL | ASSY - OCCUPANT CELL TUB | 4,50,51,52,53,54,55,56,57,86,93,95 | 12 | 12 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
84 | ASSY - HAND BRAKE | Sunswift | 0 | 2 | 2 | ASSY - REAR WHEEL, ASSY - REAR BRAKE DISC | ASSY CHASSIS BRAKE LINE, ASSY - DASHBOARD STRUCTURE | 70,82 | 2 | 2 | 0 | 77,101 | 2 | 2 | 0 |  |  | 0 | 0 | 0
85 | ASSY - STEERING COLUMN | Flaming River | 4 | 2 | 6 | ASSY - STEERING WHEEL, ASSY - STEERING RACK | ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE | 86,87 | 2 | 2 | 0 | 3,4 | 2 | 2 | 0 |  |  | 0 | 0 | 0
86 | ASSY - STEERING RACK | Flaming River | 4 | 2 | 6 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT TIEROD - LH, ASSY - FRONT TIEROD - RH, ASSY - STEERING COLUMN |  | 0 | 0 | 0 | 2,54,55,85 | 4 | 4 | 0 |  |  | 0 | 0 | 0
87 | ASSY - STEERING WHEEL | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB | ASSY - DRIVER DISPLAY, ASSY - STEERING COLUMN | 88 | 1 | 1 | 0 | 85,103 | 2 | 2 | 0 |  |  | 0 | 0 | 0
88 | ASSY - STEERING WHEEL PCB | Sunswift | 0 | 6 | 6 |  | ASSY - STEERING WHEEL |  | 0 | 0 | 0 | 87 | 1 | 1 | 0 |  |  | 0 | 0 | 0
89 | ASSY - INTERIOR LIGHTS PCB | Sunswift | 0 | 6 | 6 |  | ASSY - OCCUPANT CELL SPIDER, ASSY - CEILING |  | 0 | 0 | 0 | 1,98 | 2 | 2 | 0 |  |  | 0 | 0 | 0
90 | ASSY - REAR VISION CAMERA | Sunswift | 0 | 4 | 4 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
91 | ASSY - SIDE CAMERA - LH | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 0 | 0 | 0 | 147 | 1 | 1 | 0 |  |  | 0 | 0 | 0
92 | ASSY - SIDE CAMERA - RH | Unknown | 4 | 6 | 10 |  | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 0 | 0 | 0 | 148 | 1 | 1 | 0 |  |  | 0 | 0 | 0
93 | ASSY - PEDAL BOX | Sunswift | 0 | 2 | 2 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL, ASSY - PEDAL BOX CONTROLLER, ASSY - PEDAL PRESS SENSOR | ASSY - OCCUPANT CELL TUB | 94,95,96,97 | 4 | 4 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
94 | ASSY - THROTTLE PEDAL | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 74,80,97 | 3 | 3 | 0 |  |  | 0 | 0 | 0
95 | ASSY - BRAKE PEDAL | Sunswift | 0 | 1 | 1 |  | ASSY - PEDAL PRESS SENSOR, ASSY - FRONT MASTER CYLINDER, ASSY - FRONT BRAKE LINE, ASSY - REAR MASTER CYLINDER |  | 0 | 0 | 0 | 74,76,80,97 | 4 | 4 | 0 |  |  | 0 | 0 | 0
96 | ASSY - PEDAL BOX CONTROLLER | Sunswift | 0 | 2 | 2 | ASSY - PEDAL PRESS SENSOR |  | 97 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
97 | ASSY - PEDAL PRESS SENSOR | Sunswift | 0 | 1 | 1 | ASSY - THROTTLE PEDAL, ASSY - BRAKE PEDAL |  | 94,95 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
98 | ASSY - CEILING | Sunswift | 0 | 4 | 4 | ASSY - REAR VISION CAMERA, ASSY - SUN VISOR - LH, ASSY - SUN VISOR - RH, ASSY - OCCUPANT CELL SPIDER |  | 1,90,99,100 | 4 | 4 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
99 | ASSY - SUN VISOR - LH | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 98 | 1 | 1 | 0 |  |  | 0 | 0 | 0
100 | ASSY - SUN VISOR - RH | Sunswift | 0 | 3 | 3 |  | ASSY - CEILING |  | 0 | 0 | 0 | 98 | 1 | 1 | 0 |  |  | 0 | 0 | 0
101 | ASSY - DASHBOARD STRUCTURE | Sunswift/Mconaghy | 0 | 6 | 6 | ASSY - OCCUPANT CELL TUB, ASSY - DOOR CARD - LH, ASSY - DOOR CARD - RH, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - HEADS-UP DISPLAY, ASSY - SIDE VISION (MONITOR) |  | 2,35,36,102,103,104 | 7 | 6 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
102 | ASSY - CENTRAL DISPLAY | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
103 | ASSY - DRIVER DISPLAY | Espresso conversation | 0 | 2 | 2 | ASSY - STEERING WHEEL | ASSY - DASHBOARD STRUCTURE | 87 | 1 | 1 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
104 | ASSY - HEADS-UP DISPLAY | Espresso conversation | 0 | 2 | 2 |  | ASSY - DASHBOARD STRUCTURE |  | 0 | 0 | 0 | 101 | 1 | 1 | 0 |  |  | 0 | 0 | 0
105 | ASSY - FRONT SEAT RAIL DRIVER | Bride Racing | 0 | 4 | 4 | ASSY - FRONT SEAT DRIVER |  | 106 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
106 | ASSY - FRONT SEAT DRIVER | Sunswift | 0 | 4 | 4 |  | ASSY - FRONT SEAT RAIL DRIVER |  | 0 | 0 | 0 | 105 | 1 | 1 | 0 |  |  | 0 | 0 | 0
107 | ASSY - FRONT SEAT MOUNT DRIVER | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT DRIVER, ASSY - FRONT SEAT BELT DRIVER |  | 0 | 0 | 0 | 2,106,110 | 3 | 3 | 0 |  |  | 0 | 0 | 0
108 | ASSY - FRONT SEAT PASSENGER | Sunswift | 0 | 4 | 4 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT MOUNT PASSENGER |  | 0 | 0 | 0 | 2,109 | 2 | 2 | 0 |  |  | 0 | 0 | 0
109 | ASSY - FRONT SEAT MOUNT PASSENGER | Bride Racing | 1 | 4 | 5 |  | ASSY - OCCUPANT CELL TUB, ASSY - FRONT SEAT BELT PASSENGER |  | 0 | 0 | 0 | 2,111 | 2 | 2 | 0 |  |  | 0 | 0 | 0
110 | ASSY - FRONT SEAT BELT DRIVER | Unknown | 1 | 1 | 2 | ASSY - FRONT SEAT DRIVER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 106 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
111 | ASSY - FRONT SEAT BELT PASSENGER | Unknown | 0 | 1 | 1 | ASSY - FRONT SEAT PASSENGER | ASSY - OCCUPANT CELL TUB, ASSY - OCCUPANT CELL SPIDER | 108 | 1 | 1 | 0 | 1,2 | 2 | 2 | 0 |  |  | 0 | 0 | 0
112 | ASSY - MOTOR UNIT - LH | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - LH, ASSY - INVERTER - LH, ASSY - INVERTER MOUNTING FRAME - LH, ASSY - PWT HV WIRING - LH, ASSY - GEARBOX - LH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,114,116,118,120,122,124 | 9 | 8 | 1 |  |  | 0 | 0 | 0
113 | ASSY - MOTOR UNIT - RH | Schaeffler | 0 | 2 | 2 |  | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - MOTOR MOUNTING FRAME - RH, ASSY - INVERTER - RH, ASSY - INVERTER MOUNTING FRAME - RH, ASSY - PWT HV WIRING - RH, ASSY - GEARBOX - RH, ASSY - AXLE CV - LH, ASSY - ENERGY CONTROL SYSTEM |  | 0 | 0 | 0 | 2,7,115,117,119,121,123,124 | 9 | 8 | 1 |  |  | 0 | 0 | 0
114 | ASSY - MOTOR MOUNTING FRAME - LH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH |  | 112,122 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
115 | ASSY - MOTOR MOUNTING FRAME - RH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH |  | 113,123 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
116 | ASSY - INVERTER - LH | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - LH | ASSY - HYDROGEN COOLING SYSTEM | 112 | 1 | 1 | 0 | 182 | 1 | 1 | 0 |  |  | 0 | 0 | 0
117 | ASSY - INVERTER - RH | Schaeffler | 0 | 2 | 2 | ASSY - MOTOR UNIT - RH | ASSY - HYDROGEN COOLING SYSTEM | 113 | 1 | 1 | 0 | 182 | 1 | 1 | 0 |  |  | 0 | 0 | 0
118 | ASSY - INVERTER MOUNTING FRAME - LH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 112,116 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
119 | ASSY - INVERTER MOUNTING FRAME - RH | Sunswift | 0 | 6 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 113,117 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
120 | ASSY - PWT HV WIRING - LH | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - LH, ASSY - INVERTER - LH |  | 112,116 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
121 | ASSY - PWT HV WIRING - RH | Unknown | 4 | 2 | 6 | ASSY - MOTOR UNIT - RH, ASSY - INVERTER - RH |  | 113,117 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
122 | ASSY - GEARBOX - LH | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - LH | 112 | 1 | 1 | 0 | 2,7,124 | 3 | 3 | 0 |  |  | 0 | 0 | 0
123 | ASSY - GEARBOX - RH | Ricardo | 8 | 3 | 11 | ASSY - MOTOR UNIT - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME, ASSY - AXLE CV - RH | 113 | 1 | 1 | 0 | 2,7,125 | 3 | 3 | 0 |  |  | 0 | 0 | 0
124 | ASSY - AXLE CV - LH | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - LH, ASSY - GEARBOX - LH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 112,122 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
125 | ASSY - AXLE CV - RH | Ricardo | 8 | 6 | 14 | ASSY - MOTOR UNIT - RH, ASSY - GEARBOX - RH | ASSY - OCCUPANT CELL TUB, ASSY - CHASSIS SUBFRAME | 113,123 | 2 | 2 | 0 | 2,7 | 2 | 2 | 0 |  |  | 0 | 0 | 0
126 | ASSY - BATTERY MODULES | Sunswift | 8 | 4 | 12 |  | ASSY - BATTERY PACK |  | 0 | 0 | 0 | 127 | 1 | 1 | 0 |  |  | 0 | 0 | 0
127 | ASSY - BATTERY PACK | Sunswift | 8 | 2 | 10 | ASSY - BATTERY MODULES | ASSY - BMS WIRING, ASSY - BATTERY HV WIRING, ASSY - BATTERY LV WIRING | 126 | 1 | 1 | 0 | 128,129,130 | 3 | 3 | 0 |  |  | 0 | 0 | 0
128 | ASSY - BMS WIRING | Sunswift | 8 | 3 | 11 | ASSY - BATTERY PACK | ASSY - CONTROL LOGIC | 127 | 1 | 1 | 0 | 136 | 1 | 1 | 0 |  |  | 0 | 0 | 0
129 | ASSY - BATTERY HV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
130 | ASSY - BATTERY LV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
131 | ASSY - AUXILLARY POWER WIRING | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 133 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
132 | ASSY - DC-DC CONVERTERS | Sunswift | 8 | 2 | 10 | ASSY - AUX BATTERY |  | 133 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
133 | ASSY - AUX BATTERY | Sunswift | 8 | 2 | 10 |  | ASSY - DC-DC CONVERTERS, ASSY - AUXILLARY POWER WIRING |  | 0 | 0 | 0 | 131,132 | 2 | 2 | 0 |  |  | 0 | 0 | 0
134 | ASSY - ECS HV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
135 | ASSY - ECS LV WIRING | Sunswift | 8 | 2 | 10 | ASSY - BATTERY PACK |  | 127 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
136 | ASSY - CONTROL LOGIC | Sunswift | 8 | 3 | 11 | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING |  | 134,135 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
137 | ASSY - ECS MODULE | Sunswift | 8 | 3 | 11 |  | ASSY - ECS HV WIRING, ASSY - ECS LV WIRING, ASSY - CONTROL LOGIC |  | 0 | 0 | 0 | 134,135,136 | 3 | 3 | 0 |  |  | 0 | 0 | 0
138 | ASSY - ONBOARD CHARGING WIRING | Sunswift | 0 | 2 | 2 | ASSY - ONBOARD CHARGER INSTALLATION |  | 139 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
139 | ASSY - ONBOARD CHARGER INSTALLATION | Sunswift | 0 | 3 | 3 |  | ASSY - ONBOARD CHARGING WIRING |  | 0 | 0 | 0 | 138 | 1 | 1 | 0 |  |  | 0 | 0 | 0
140 | ASSY - MPPT JUNCTION BOX | Sunswift | 0 | 2 | 2 | ASSY - MPPT | ASSY - ECS HV WIRING, ASSY - CONTROL LOGIC | 141 | 1 | 1 | 0 | 134,136 | 2 | 2 | 0 |  |  | 0 | 0 | 0
141 | ASSY - MPPT | Sunswift | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - occupant cell spider | 142,143,144,146 | 4 | 4 | 0 | 1 | 1 | 1 | 0 |  |  | 0 | 0 | 0
142 | ASSY - SOLAR ROOF ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - occupant cell spider, ASSY - occupant cell tub, ASSY - ceiling, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 1,2,98,141,145 | 5 | 5 | 0 |  |  | 0 | 0 | 0
143 | ASSY - SOLAR BOOT ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
144 | ASSY - SOLAR BONNET ARRAY | Sundrive, Corning, McCognaughy, REOO | 12 | 8 | 20 |  | ASSY - bonnet, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 21,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
145 | ASSY - MC4 Cabling | None, by off sheld, maybe SunDrive | 0 | 4 | 4 | ASSY - SOLAR Roof array, ASSY - SOLAR boot array, ASSY - SOLAR bonnet array, ASSY - Shingled Matrix Panels | ASSY - Occupant cell spider, ASSY - boot, ASSY - Bonnet, ASSY - MPPT | 142,143,144,146 | 4 | 4 | 0 | 1,19,21,141 | 4 | 4 | 0 |  |  | 0 | 0 | 0
146 | Assy - Shingled Matrix Panels | M10 | 0 | 12 | 12 |  | ASSY - boot, ASSY - MPPT, ASSY - MC4 Cabling |  | 0 | 0 | 0 | 19,141,145 | 3 | 3 | 0 |  |  | 0 | 0 | 0
147 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
148 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
149 | ASSY - TAILLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH |  | 147 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
150 | ASSY - TAILLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 6 | 6 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH |  | 148 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
151 | ASSY - CENTRAL STOP LAMP | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOP LAMP PCB, ASSY - BOOT |  | 0 | 0 | 0 | 19,152 | 2 | 2 | 0 |  |  | 0 | 0 | 0
152 | ASSY - CENTRAL STOP LAMP PCB | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOP LAMP |  | 151 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
153 | ASSY - HEADLIGHT EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
154 | ASSY - HEADLIGHT EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
155 | ASSY - HEADLIGHT/INDICATOR PCB - LH | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - LH |  | 0 | 0 | 0 | 153 | 1 | 1 | 0 |  |  | 0 | 0 | 0
156 | ASSY - HEADLIGHT/INDICATOR PCB - RH | Sunswift | 0 | 2 | 2 |  | ASSY - HEADLIGHT EXTERIOR - RH |  | 0 | 0 | 0 | 154 | 1 | 1 | 0 |  |  | 0 | 0 | 0
157 | ASSY - SIDE INDICATOR EXTERIOR - LH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
158 | ASSY - SIDE INDICATOR EXTERIOR - RH | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
159 | ASSY - HORN | Sunswift | 0 | 1 | 1 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
160 | ASSY - HORN PCB | Sunswift | 0 | 3 | 3 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
161 | ASSY - DRIVE CONTROL UNIT | Sunswift | 0 | 12 | 12 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH |  | 112,113 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
162 | ASSY - SENSOR MOTHERBOARD - FL | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
163 | ASSY - SENSOR MOTHERBOARD - FR | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
164 | ASSY - SENSOR MOTHERBOARD - BL | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
165 | ASSY - SENSOR MOTHERBOARD - BR | Sunswift | 0 | 12 | 12 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
166 | ASSY - SUBWOOFER | Sunswift | 0 | 3 | 3 |  | ASSY - OCCUPANT CELL TUB |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 |  |  | 0 | 0 | 0
167 | ASSY - AUDIO CONTROL SYSTEM | Sunswift | 0 | 8 | 8 | ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER |  | 37,38,166 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
168 | ASSY - PRESSURE VESSEL SHELL | Coregas, Swagelok | 6 | 0 | 6 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY | 169 | 1 | 1 | 0 | 170,171 | 2 | 2 | 0 |  |  | 0 | 0 | 0
169 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | Sunswift | 0 | 0 | 0 |  | ASSY - HYDROGEN COMPARTMENT STRUCTURE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - REAR FLOOR, ASSY - OCCUPANT CELL TUB, ASSY - PRESSURE VESSEL SHELL |  | 0 | 0 | 0 | 2,17,168,170,171 | 5 | 5 | 0 |  |  | 0 | 0 | 0
170 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | Sunswift | 0 | 0 | 0 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN COMPARTMENT VENTILATION, ASSY - OCCUPANT CELL HYDROGEN SENSOR | 168,169 | 2 | 2 | 0 | 174,175 | 2 | 2 | 0 |  |  | 0 | 0 | 0
171 | ASSY - PRESSURE REGULATION & SAFETY | Swagelok | 12 | 0 | 12 | ASSY - PRESSURE VESSEL SHELL, ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN SENSOR ARRAY, ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 168,169 | 2 | 2 | 0 | 172,179,184 | 3 | 3 | 0 |  |  | 0 | 0 | 0
172 | ASSY - HYDROGEN SUPPLY LINE | Swagelok | 6 | 0 | 6 | ASSY - PRESSURE REGULATION & SAFETY | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - SENSOR ARRAY | 171 | 1 | 1 | 0 | 173 | 2 | 1 | 1 |  |  | 0 | 0 | 0
173 | ASSY - HYDROGEN PURGE MANAGEMENT | Siltrax, Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE | ASSY - P&ID HYDROGEN RECYCLE STREAM | 172,181 | 2 | 2 | 0 | 176 | 1 | 1 | 0 |  |  | 0 | 0 | 0
174 | ASSY - HYDROGEN COMPARTMENT VENTILATION | Sunswift | 0 | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - P&ID AIR SUPPLY LINE, ASSY - REARWHEEL HUB AIR INTAKE | 170 | 1 | 1 | 0 | 185,186 | 2 | 2 | 0 |  |  | 0 | 0 | 0
175 | ASSY - OCCUPANT CELL HYDROGEN SENSOR | Gas detection supplier (Honeywell/CityTech etc.) | 10 | 0 | 10 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - OCCUPANT CELL SHUTDOWN VALVE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 170 | 1 | 1 | 0 | 178,183 | 2 | 2 | 0 |  |  | 0 | 0 | 0
176 | ASSY - P&ID HYDROGEN RECYCLE STREAM | Siltrax | 6 | 0 | 6 | ASSY - HYDROGEN PURGE MANAGEMENT, ASSY - FUEL CELL STACK | ASSY - HYDROGEN SENSOR ARRAY | 173,181 | 2 | 2 | 0 | 179 | 1 | 1 | 0 |  |  | 0 | 0 | 0
177 | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - HYDROGEN SENSOR ARRAY |  | 179,183 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
178 | ASSY - OCCUPANT CELL SHUTDOWN VALVE | Swagelok | 6 | 0 | 6 | ASSY - OCCUPANT CELL HYDROGEN SENSOR, ASSY - HYDROGEN CONTROL LOGIC |  | 175,180 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
179 | ASSY - HYDROGEN SENSOR ARRAY | External Supplier (TBA) | 10 | 0 | 10 | ASSY - HYDROGEN SUPPLY LINE, ASSY - PRESSURE REGULATION & SAFETY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL LOGIC, ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 171,172,181 | 3 | 3 | 0 | 177,180 | 2 | 2 | 0 |  |  | 0 | 0 | 0
180 | ASSY - HYDROGEN CONTROL LOGIC | External Supplier (TBA) | 16 | 0 | 16 | ASSY - HYDROGEN SENSOR ARRAY, ASSY - FUEL CELL STACK | ASSY - HYDROGEN CONTROL SYSTEM | 179,181 | 2 | 2 | 0 | 187 | 1 | 1 | 0 |  |  | 0 | 0 | 0
181 | ASSY - FUEL CELL STACK | Siltrax | 6 | 0 | 6 | ASSY - BATTERY PACK, ASSY - FUEL SENSOR ARRAY | ASSY - HYDROGEN SENSOR ARRAY, ASSY - HYDROGEN CONTROL SYSTEM, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN COOLING SYSTEM, ASSY - HYDROGEN COMPARTMENT STRUCTURE | 127 | 2 | 1 | 1 | 170,172,179,182,187 | 5 | 5 | 0 |  |  | 0 | 0 | 0
182 | ASSY - HYDROGEN COOLING SYSTEM | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - P&ID HYDROGEN DOWNSTREAM LINE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS, ASSY - REAR FLUID MANAGEMENT | 181 | 1 | 1 | 0 | 12,183,184 | 3 | 3 | 0 |  |  | 0 | 0 | 0
183 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | Sunswift | 0 | 0 | 0 | ASSY - FUEL CELL STACK | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 181 | 1 | 1 | 0 | 177 | 1 | 1 | 0 |  |  | 0 | 0 | 0
184 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE | Swagelok | 6 | 0 | 6 | ASSY - FUEL CELL STACK, ASSY - HYDROGEN SUPPLY LINE, ASSY - HYDROGEN PURGE MANAGEMENT | ASSY - P&ID AIR SUPPLY LINE | 172,173,181 | 3 | 3 | 0 | 185 | 1 | 1 | 0 |  |  | 0 | 0 | 0
185 | ASSY - P&ID AIR SUPPLY LINE | Beswick, Swagelok | 8 | 0 | 8 | ASSY - REARWHEEL HUB AIR INTAKE, ASSY - AIR SOURCE | ASSY - OCCUPANT CELL SHUTDOWN VALVE | 186 | 2 | 1 | 1 | 178 | 1 | 1 | 0 |  |  | 0 | 0 | 0
186 | ASSY - REARWHEEL HUB AIR INTAKE | Sunswift |  | 0 | 0 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | ASSY - HYDROGEN CONTROL LOGIC | 170 | 1 | 1 | 0 | 180 | 1 | 1 | 0 |  |  | 0 | 0 | 0
187 | ASSY - HYDROGEN CONTROL SYSTEM | Ballard or Intelligent Energy | 12 | 0 | 12 | ASSY - HYDROGEN CONTROL LOGIC, ASSY - ECS MODULE, ASSY - FUEL CELL ELECTRICAL CONNECTIONS |  | 137,180,183 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
188 | ASSY - INTERNAL EMBEDDED NETWORK WIRING | Sunswift | 0 | 2 | 2 | ASSY - HORN PCB, ASSY - HEADLIGHT/INDICATOR PCB - RH, ASSY - HEADLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - LH, ASSY - TAILLIGHT/INDICATOR PCB - RH, ASSY - CENTRAL STOP LAMP, ASSY - STEERING WHEEL, ASSY - CENTRAL DISPLAY, ASSY - DRIVER DISPLAY, ASSY - PEDAL BOX CONTROLLER, ASSY - DRIVE CONTROL UNIT, ASSY - MAIN COMPUTER, ASSY - SUBWOOFER, ASSY - C-V2V RADAR/LiDAR, ASSY - C-V2V ANTENNA, ASSY - C-V2X PCB, ASSY - DOOR AUDIO - LH, ASSY - DOOR AUDIO - RH, ASSY - SUBWOOFER, ASSY - AUDIO CONTROL SYSTEM, ASSY - OCCUPANT CELL TUB, ASSY - STEERING COLUMN MOUNT, ASSY - FRONT CRASH STRUCTURE, ASSY - REAR CRASH STRUCTURE, ASSY - CHASSIS VENTILATION, ASSY - REAR BUMPER, ASSY - REAR QUARTER PANEL - LH, ASSY - REAR QUARTER PANEL - RH, ASSY - FRONT CLAM SHELL, ASSY - REAR FLOOR, ASSY - REAR SUPPORT STRUCTURE, ASSY - BOOT, ASSY - BONNET |  | 2,3,4,5,6,13,14,15,16,17,18,19,21,37,38,87,96,102,103,149,150,151,155,156,160,161,166,167,190 | 33 | 29 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
189 | ASSY - INTRANET | Sunswift | 0 | 0 | 0 | ASSY - SUNSWIFT PHONE APP |  |  | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
190 | ASSY - MAIN COMPUTER | Adlink | 8 | 1 | 9 | ASSY - MOTOR UNIT - LH, ASSY - MOTOR UNIT - RH, ASSY - DRIVE CONTROL UNIT | ASSY - INTERNAL EMBEDDED NETWORK WIRING | 112,113,161 | 3 | 3 | 0 | 188 | 1 | 1 | 0 |  |  | 0 | 0 | 0
191 | ASSY - STEERING WHEEL PCB CODE | Sunswift | 0 | 4 | 4 | ASSY - STEERING WHEEL PCB |  | 88 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
192 | ASSY - DOOR ACTUATOR BOARD - RH | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
193 | ASSY - DOOR ACTUATOR BOARD - LH | Sunswift | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
194 | ASSY - SIDE INDICATOR - LH | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - LH |  | 0 | 0 | 0 | 91 | 1 | 1 | 0 |  |  | 0 | 0 | 0
195 | ASSY - SIDE INDICATOR - RH | Sunswift | 0 | 4 | 4 |  | ASSY - SIDE CAMERA - RH |  | 0 | 0 | 0 | 92 | 1 | 1 | 0 |  |  | 0 | 0 | 0
196 | ASSY - CENTRAL STOPLAMP | Sunswift | 0 | 3 | 3 |  | ASSY - CENTRAL STOPLAMP CASING, ASSY - CENTRAL STOPLAMP CONTROLLER |  | 0 | 0 | 0 | 197,198 | 2 | 2 | 0 |  |  | 0 | 0 | 0
197 | ASSY - CENTRAL STOPLAMP CASING | Sunswift | 0 | 4 | 4 | ASSY - CENTRAL STOPLAMP |  | 196 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
198 | ASSY - CENTRAL STOPLAMP CONTROLLER | Sunswift | 0 | 3 | 3 | ASSY - CENTRAL STOPLAMP |  | 196 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0

## Edges
Edge | Description | Weight
0->Divergent-7 | Source->Divergent for 7 | 0
0->AutoFrost, PWR-9 | Source->AutoFrost, PWR for 9 | 0
0->Unknown-10 | Source->Unknown for 10 | 0
0->Unknown-11 | Source->Unknown for 11 | 0
0->Unknown-12 | Source->Unknown for 12 | 0
0->McConaghy, Scott Bader, Colan, Stabillus-19 | Source->McConaghy, Scott Bader, Colan, Stabillus for 19 | 0
0->Chevalier-23 | Source->Chevalier for 23 | 0
0->Chevalier-24 | Source->Chevalier for 24 | 0
0->Chevalier-25 | Source->Chevalier for 25 | 0
0->Chevalier-26 | Source->Chevalier for 26 | 0
0->Chevalier-29 | Source->Chevalier for 29 | 0
0->Chevalier-30 | Source->Chevalier for 30 | 0
0->Stabillus-31 | Source->Stabillus for 31 | 0
0->Stabillus-32 | Source->Stabillus for 32 | 0
0->Unknown-39 | Source->Unknown for 39 | 0
0->Unknown-40 | Source->Unknown for 40 | 0
0->Unknown-44 | Source->Unknown for 44 | 0
0->Unknown-45 | Source->Unknown for 45 | 0
0->Unknown-46 | Source->Unknown for 46 | 0
0->Sunswift-50 | Source->Sunswift for 50 | 0
0->Sunswift-51 | Source->Sunswift for 51 | 0
0->Sunswift-52 | Source->Sunswift for 52 | 0
0->Sunswift-53 | Source->Sunswift for 53 | 0
0->Sunswift-54 | Source->Sunswift for 54 | 0
0->Sunswift-55 | Source->Sunswift for 55 | 0
0->Sunswift-56 | Source->Sunswift for 56 | 0
0->Sunswift-57 | Source->Sunswift for 57 | 0
0->Sunswift-66 | Source->Sunswift for 66 | 0
0->Sunswift-67 | Source->Sunswift for 67 | 0
0->Sunswift-70 | Source->Sunswift for 70 | 0
0->Flaming River-85 | Source->Flaming River for 85 | 0
0->Flaming River-86 | Source->Flaming River for 86 | 0
0->Unknown-91 | Source->Unknown for 91 | 0
0->Unknown-92 | Source->Unknown for 92 | 0
0->Bride Racing-107 | Source->Bride Racing for 107 | 0
0->Bride Racing-109 | Source->Bride Racing for 109 | 0
0->Unknown-110 | Source->Unknown for 110 | 0
0->Unknown-120 | Source->Unknown for 120 | 0
0->Unknown-121 | Source->Unknown for 121 | 0
0->Ricardo-122 | Source->Ricardo for 122 | 0
0->Ricardo-123 | Source->Ricardo for 123 | 0
0->Ricardo-124 | Source->Ricardo for 124 | 0
0->Ricardo-125 | Source->Ricardo for 125 | 0
0->Sunswift-126 | Source->Sunswift for 126 | 0
0->Sunswift-127 | Source->Sunswift for 127 | 0
0->Sunswift-128 | Source->Sunswift for 128 | 0
0->Sunswift-129 | Source->Sunswift for 129 | 0
0->Sunswift-130 | Source->Sunswift for 130 | 0
0->Sunswift-131 | Source->Sunswift for 131 | 0
0->Sunswift-132 | Source->Sunswift for 132 | 0
0->Sunswift-133 | Source->Sunswift for 133 | 0
0->Sunswift-134 | Source->Sunswift for 134 | 0
0->Sunswift-135 | Source->Sunswift for 135 | 0
0->Sunswift-136 | Source->Sunswift for 136 | 0
0->Sunswift-137 | Source->Sunswift for 137 | 0
0->Sundrive, Corning, McCognaughy, REOO-142 | Source->Sundrive, Corning, McCognaughy, REOO for 142 | 0
0->Sundrive, Corning, McCognaughy, REOO-143 | Source->Sundrive, Corning, McCognaughy, REOO for 143 | 0
0->Sundrive, Corning, McCognaughy, REOO-144 | Source->Sundrive, Corning, McCognaughy, REOO for 144 | 0
0->Coregas, Swagelok-168 | Source->Coregas, Swagelok for 168 | 0
0->Swagelok-171 | Source->Swagelok for 171 | 0
0->Swagelok-172 | Source->Swagelok for 172 | 0
0->Siltrax, Swagelok-173 | Source->Siltrax, Swagelok for 173 | 0
0->Gas detection supplier (Honeywell/CityTech etc.)-175 | Source->Gas detection supplier (Honeywell/CityTech etc.) for 175 | 0
0->Siltrax-176 | Source->Siltrax for 176 | 0
0->Swagelok-178 | Source->Swagelok for 178 | 0
0->External Supplier (TBA)-179 | Source->External Supplier (TBA) for 179 | 0
0->External Supplier (TBA)-180 | Source->External Supplier (TBA) for 180 | 0
0->Siltrax-181 | Source->Siltrax for 181 | 0
0->Swagelok-184 | Source->Swagelok for 184 | 0
0->Beswick, Swagelok-185 | Source->Beswick, Swagelok for 185 | 0
0->Ballard or Intelligent Energy-187 | Source->Ballard or Intelligent Energy for 187 | 0
0->Adlink-190 | Source->Adlink for 190 | 0
0->5 | Source->ASSY - REAR CRASH STRUCTURE | 0
0->37 | Source->ASSY - DOOR AUDIO - RH | 0
0->38 | Source->ASSY - DOOR AUDIO - LH | 0
0->41 | Source->ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | 0
0->42 | Source->ASSY - ACTIVE AERO MOTORS | 0
0->48 | Source->ASSY - WINDSCREEN WIPER MOTOR | 0
0->60 | Source->ASSY - FRONT WHEEL | 0
0->88 | Source->ASSY - STEERING WHEEL PCB | 0
0->89 | Source->ASSY - INTERIOR LIGHTS PCB | 0
0->90 | Source->ASSY - REAR VISION CAMERA | 0
0->94 | Source->ASSY - THROTTLE PEDAL | 0
0->95 | Source->ASSY - BRAKE PEDAL | 0
0->99 | Source->ASSY - SUN VISOR - LH | 0
0->100 | Source->ASSY - SUN VISOR - RH | 0
0->102 | Source->ASSY - CENTRAL DISPLAY | 0
0->104 | Source->ASSY - HEADS-UP DISPLAY | 0
0->108 | Source->ASSY - FRONT SEAT PASSENGER | 0
0->112 | Source->ASSY - MOTOR UNIT - LH | 0
0->113 | Source->ASSY - MOTOR UNIT - RH | 0
0->139 | Source->ASSY - ONBOARD CHARGER INSTALLATION | 0
0->146 | Source->Assy - Shingled Matrix Panels | 0
0->151 | Source->ASSY - CENTRAL STOP LAMP | 0
0->155 | Source->ASSY - HEADLIGHT/INDICATOR PCB - LH | 0
0->156 | Source->ASSY - HEADLIGHT/INDICATOR PCB - RH | 0
0->157 | Source->ASSY - SIDE INDICATOR EXTERIOR - LH | 0
0->158 | Source->ASSY - SIDE INDICATOR EXTERIOR - RH | 0
0->159 | Source->ASSY - HORN | 0
0->160 | Source->ASSY - HORN PCB | 0
0->162 | Source->ASSY - SENSOR MOTHERBOARD - FL | 0
0->163 | Source->ASSY - SENSOR MOTHERBOARD - FR | 0
0->164 | Source->ASSY - SENSOR MOTHERBOARD - BL | 0
0->165 | Source->ASSY - SENSOR MOTHERBOARD - BR | 0
0->166 | Source->ASSY - SUBWOOFER | 0
0->169 | Source->ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | 0
0->189 | Source->ASSY - INTRANET | 0
0->192 | Source->ASSY - DOOR ACTUATOR BOARD - RH | 0
0->193 | Source->ASSY - DOOR ACTUATOR BOARD - LH | 0
0->194 | Source->ASSY - SIDE INDICATOR - LH | 0
0->195 | Source->ASSY - SIDE INDICATOR - RH | 0
0->196 | Source->ASSY - CENTRAL STOPLAMP | 0
1->35 | ASSY - OCCUPANT CELL SPIDER->ASSY - DOOR CARD - RH | 5
1->36 | ASSY - OCCUPANT CELL SPIDER->ASSY - DOOR CARD - LH | 5
1->98 | ASSY - OCCUPANT CELL SPIDER->ASSY - CEILING | 5
1->44 | ASSY - OCCUPANT CELL SPIDER->ASSY - WINDSCREEN | 5
1->47 | ASSY - OCCUPANT CELL SPIDER->ASSY - WINDSCREEN WIPER AERO GUARD | 5
2->16 | ASSY - OCCUPANT CELL TUB->ASSY - FRONT CLAM SHELL | 5
2->17 | ASSY - OCCUPANT CELL TUB->ASSY - REAR FLOOR | 5
2->18 | ASSY - OCCUPANT CELL TUB->ASSY - REAR SUPPORT STRUCTURE | 5
2->35 | ASSY - OCCUPANT CELL TUB->ASSY - DOOR CARD - RH | 5
2->36 | ASSY - OCCUPANT CELL TUB->ASSY - DOOR CARD - LH | 5
2->65 | ASSY - OCCUPANT CELL TUB->ASSY - REAR TOELINK | 5
2->73 | ASSY - OCCUPANT CELL TUB->ASSY - FRONT MASTER CYLINDER RESERVOIR | 5
2->101 | ASSY - OCCUPANT CELL TUB->ASSY - DASHBOARD STRUCTURE | 5
2->188 | ASSY - OCCUPANT CELL TUB->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 5
3->2 | ASSY - STEERING COLUMN MOUNT->ASSY - OCCUPANT CELL TUB | 2
3->188 | ASSY - STEERING COLUMN MOUNT->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
4->2 | ASSY - FRONT CRASH STRUCTURE->ASSY - OCCUPANT CELL TUB | 4
4->73 | ASSY - FRONT CRASH STRUCTURE->ASSY - FRONT MASTER CYLINDER RESERVOIR | 4
4->74 | ASSY - FRONT CRASH STRUCTURE->ASSY - FRONT MASTER CYLINDER | 4
4->76 | ASSY - FRONT CRASH STRUCTURE->ASSY - FRONT BRAKE LINE | 4
4->77 | ASSY - FRONT CRASH STRUCTURE->ASSY CHASSIS BRAKE LINE | 4
4->80 | ASSY - FRONT CRASH STRUCTURE->ASSY - REAR MASTER CYLINDER | 4
4->81 | ASSY - FRONT CRASH STRUCTURE->ASSY - REAR MASTER CYLINDER RESERVOIR | 4
4->83 | ASSY - FRONT CRASH STRUCTURE->ASSY - REAR BRAKE LINE | 4
4->188 | ASSY - FRONT CRASH STRUCTURE->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 4
5->2 | ASSY - REAR CRASH STRUCTURE->ASSY - OCCUPANT CELL TUB | 3
5->188 | ASSY - REAR CRASH STRUCTURE->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 3
6->16 | ASSY - CHASSIS VENTILATION->ASSY - FRONT CLAM SHELL | 8
6->188 | ASSY - CHASSIS VENTILATION->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 8
7->2 | ASSY - CHASSIS SUBFRAME->ASSY - OCCUPANT CELL TUB | 4
Divergent-7->7 | Divergent for 7->ASSY - CHASSIS SUBFRAME | 8
8->2 | ASSY - HVAC BOX->ASSY - OCCUPANT CELL TUB | 8
8->10 | ASSY - HVAC BOX->ASSY - HVAC PIPING | 8
8->11 | ASSY - HVAC BOX->ASSY - FRONT FLUID MANAGEMENT | 8
9->8 | ASSY - THERMAL BOX->ASSY - HVAC BOX | 6
9->10 | ASSY - THERMAL BOX->ASSY - HVAC PIPING | 6
9->11 | ASSY - THERMAL BOX->ASSY - FRONT FLUID MANAGEMENT | 6
9->12 | ASSY - THERMAL BOX->ASSY - REAR FLUID MANAGEMENT | 6
AutoFrost, PWR-9->9 | AutoFrost, PWR for 9->ASSY - THERMAL BOX | 3
10->11 | ASSY - HVAC PIPING ->ASSY - FRONT FLUID MANAGEMENT | 7
Unknown-10->10 | Unknown for 10->ASSY - HVAC PIPING | 3
11->2 | ASSY - FRONT FLUID MANAGEMENT->ASSY - OCCUPANT CELL TUB | 4
11->6 | ASSY - FRONT FLUID MANAGEMENT->ASSY - CHASSIS VENTILATION | 4
11->12 | ASSY - FRONT FLUID MANAGEMENT->ASSY - REAR FLUID MANAGEMENT | 4
11->126 | ASSY - FRONT FLUID MANAGEMENT->ASSY - BATTERY MODULES | 4
Unknown-11->11 | Unknown for 11->ASSY - FRONT FLUID MANAGEMENT | 3
12->2 | ASSY - REAR FLUID MANAGEMENT->ASSY - OCCUPANT CELL TUB | 5
Unknown-12->12 | Unknown for 12->ASSY - REAR FLUID MANAGEMENT | 3
13->17 | ASSY - REAR BUMPER->ASSY - REAR FLOOR | 6
13->18 | ASSY - REAR BUMPER->ASSY - REAR SUPPORT STRUCTURE | 6
13->188 | ASSY - REAR BUMPER->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 6
14->2 | ASSY - REAR QUARTER PANEL - LH->ASSY - OCCUPANT CELL TUB | 2
14->13 | ASSY - REAR QUARTER PANEL - LH->ASSY - REAR BUMPER | 2
14->17 | ASSY - REAR QUARTER PANEL - LH->ASSY - REAR FLOOR | 2
14->18 | ASSY - REAR QUARTER PANEL - LH->ASSY - REAR SUPPORT STRUCTURE | 2
14->19 | ASSY - REAR QUARTER PANEL - LH->ASSY - BOOT | 2
14->188 | ASSY - REAR QUARTER PANEL - LH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
14->24 | ASSY - REAR QUARTER PANEL - LH->ASSY - OUTER DOOR HANDLE - LH | 2
15->2 | ASSY - REAR QUARTER PANEL - RH->ASSY - OCCUPANT CELL TUB | 2
15->13 | ASSY - REAR QUARTER PANEL - RH->ASSY - REAR BUMPER | 2
15->17 | ASSY - REAR QUARTER PANEL - RH->ASSY - REAR FLOOR | 2
15->18 | ASSY - REAR QUARTER PANEL - RH->ASSY - REAR SUPPORT STRUCTURE | 2
15->19 | ASSY - REAR QUARTER PANEL - RH->ASSY - BOOT | 2
15->188 | ASSY - REAR QUARTER PANEL - RH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
15->23 | ASSY - REAR QUARTER PANEL - RH->ASSY - OUTER DOOR HANDLE - RH | 2
16->21 | ASSY - FRONT CLAM SHELL->ASSY - BONNET | 7
16->188 | ASSY - FRONT CLAM SHELL->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 7
17->188 | ASSY - REAR FLOOR->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 3
17->19 | ASSY - REAR FLOOR->ASSY - BOOT | 3
18->19 | ASSY - REAR SUPPORT STRUCTURE->ASSY - BOOT | 5
18->188 | ASSY - REAR SUPPORT STRUCTURE->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 5
19->20 | ASSY - BOOT->ASSY - BOOT LOCKING BOARD | 5
19->188 | ASSY - BOOT->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 5
McConaghy, Scott Bader, Colan, Stabillus-19->19 | McConaghy, Scott Bader, Colan, Stabillus for 19->ASSY - BOOT | 1
20->199 | ASSY - BOOT LOCKING BOARD->Sink | 4
21->22 | ASSY - BONNET->ASSY - BONNET LOCKING BOARD | 4
21->188 | ASSY - BONNET->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 4
22->199 | ASSY - BONNET LOCKING BOARD->Sink | 4
23->199 | ASSY - OUTER DOOR HANDLE - RH->Sink | 2
Chevalier-23->23 | Chevalier for 23->ASSY - OUTER DOOR HANDLE - RH | 4
24->199 | ASSY - OUTER DOOR HANDLE - LH->Sink | 2
Chevalier-24->24 | Chevalier for 24->ASSY - OUTER DOOR HANDLE - LH | 4
25->199 | ASSY - INNER DOOR HANDLE - RH->Sink | 2
Chevalier-25->25 | Chevalier for 25->ASSY - INNER DOOR HANDLE - RH | 4
26->199 | ASSY - INNER DOOR HANDLE - LH->Sink | 2
Chevalier-26->26 | Chevalier for 26->ASSY - INNER DOOR HANDLE - LH | 4
27->1 | ASSY - DOOR SHELL - RH->ASSY - OCCUPANT CELL SPIDER | 3
27->16 | ASSY - DOOR SHELL - RH->ASSY - FRONT CLAM SHELL | 3
27->33 | ASSY - DOOR SHELL - RH->ASSY - DOOR CONTROL BOARD - RH | 3
27->35 | ASSY - DOOR SHELL - RH->ASSY - DOOR CARD - RH | 3
27->15 | ASSY - DOOR SHELL - RH->ASSY - REAR QUARTER PANEL - RH | 3
28->1 | ASSY - DOOR SHELL - LH->ASSY - OCCUPANT CELL SPIDER | 3
28->16 | ASSY - DOOR SHELL - LH->ASSY - FRONT CLAM SHELL | 3
28->34 | ASSY - DOOR SHELL - LH->ASSY - DOOR CONTROL BOARD - LH | 3
28->36 | ASSY - DOOR SHELL - LH->ASSY - DOOR CARD - LH | 3
28->14 | ASSY - DOOR SHELL - LH->ASSY - REAR QUARTER PANEL - LH | 3
29->2 | ASSY - DOOR LATCH - RH->ASSY - OCCUPANT CELL TUB | 2
29->23 | ASSY - DOOR LATCH - RH->ASSY - OUTER DOOR HANDLE - RH | 2
Chevalier-29->29 | Chevalier for 29->ASSY - DOOR LATCH - RH | 4
30->2 | ASSY - DOOR LATCH - LH->ASSY - OCCUPANT CELL TUB | 2
30->24 | ASSY - DOOR LATCH - LH->ASSY - OUTER DOOR HANDLE - LH | 2
Chevalier-30->30 | Chevalier for 30->ASSY - DOOR LATCH - LH | 4
31->27 | ASSY - DOOR HINGE - RH ->ASSY - DOOR SHELL - RH | 3
31->35 | ASSY - DOOR HINGE - RH ->ASSY - DOOR CARD - RH | 3
Stabillus-31->31 | Stabillus for 31->ASSY - DOOR HINGE - RH | 1
32->28 | ASSY - DOOR HINGE - LH ->ASSY - DOOR SHELL - LH | 3
32->33 | ASSY - DOOR HINGE - LH ->ASSY - DOOR CONTROL BOARD - RH | 3
32->34 | ASSY - DOOR HINGE - LH ->ASSY - DOOR CONTROL BOARD - LH | 3
32->36 | ASSY - DOOR HINGE - LH ->ASSY - DOOR CARD - LH | 3
Stabillus-32->32 | Stabillus for 32->ASSY - DOOR HINGE - LH | 1
33->199 | ASSY - DOOR CONTROL BOARD - RH->Sink | 5
34->199 | ASSY - DOOR CONTROL BOARD - LH->Sink | 5
35->25 | ASSY - DOOR CARD - RH ->ASSY - INNER DOOR HANDLE - RH | 3
35->101 | ASSY - DOOR CARD - RH ->ASSY - DASHBOARD STRUCTURE | 3
36->26 | ASSY - DOOR CARD - LH->ASSY - INNER DOOR HANDLE - LH | 3
36->101 | ASSY - DOOR CARD - LH->ASSY - DASHBOARD STRUCTURE | 3
37->27 | ASSY - DOOR AUDIO - RH->ASSY - DOOR SHELL - RH | 8
37->35 | ASSY - DOOR AUDIO - RH->ASSY - DOOR CARD - RH | 8
37->167 | ASSY - DOOR AUDIO - RH->ASSY - AUDIO CONTROL SYSTEM | 8
37->188 | ASSY - DOOR AUDIO - RH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 8
38->28 | ASSY - DOOR AUDIO - LH->ASSY - DOOR SHELL - LH | 8
38->36 | ASSY - DOOR AUDIO - LH->ASSY - DOOR CARD - LH | 8
38->167 | ASSY - DOOR AUDIO - LH->ASSY - AUDIO CONTROL SYSTEM | 8
38->188 | ASSY - DOOR AUDIO - LH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 8
39->28 | ASSY - ELECTRIC WINDOWS - LH ->ASSY - DOOR SHELL - LH | 2
Unknown-39->39 | Unknown for 39->ASSY - ELECTRIC WINDOWS - LH | 4
40->27 | ASSY - ELECTRIC WINDOWS - RH ->ASSY - DOOR SHELL - RH | 2
Unknown-40->40 | Unknown for 40->ASSY - ELECTRIC WINDOWS - RH | 4
41->6 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS->ASSY - CHASSIS VENTILATION | 3
41->16 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS->ASSY - FRONT CLAM SHELL | 3
42->43 | ASSY - ACTIVE AERO MOTORS->ASSY - ACTIVE AERO CONTROL PCB | 2
43->16 | ASSY - ACTIVE AERO CONTROL PCB->ASSY - FRONT CLAM SHELL | 6
44->199 | ASSY - WINDSCREEN->Sink | 3
Unknown-44->44 | Unknown for 44->ASSY - WINDSCREEN | 4
45->199 | ASSY - WINDSCREEN WIPER->Sink | 3
Unknown-45->45 | Unknown for 45->ASSY - WINDSCREEN WIPER | 4
46->199 | ASSY - WINDSCREEN WASHER ->Sink | 2
Unknown-46->46 | Unknown for 46->ASSY - WINDSCREEN WASHER | 4
47->21 | ASSY - WINDSCREEN WIPER AERO GUARD->ASSY - BONNET | 3
48->2 | ASSY - WINDSCREEN WIPER MOTOR->ASSY - OCCUPANT CELL TUB | 2
48->49 | ASSY - WINDSCREEN WIPER MOTOR->ASSY - WINDSCREEN WIPER CONTROL PCB | 2
49->199 | ASSY - WINDSCREEN WIPER CONTROL PCB->Sink | 4
50->2 | ASSY - FRONT TOP WISHBONE - LH->ASSY - OCCUPANT CELL TUB | 2
50->73 | ASSY - FRONT TOP WISHBONE - LH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
50->74 | ASSY - FRONT TOP WISHBONE - LH->ASSY - FRONT MASTER CYLINDER | 2
50->76 | ASSY - FRONT TOP WISHBONE - LH->ASSY - FRONT BRAKE LINE | 2
50->77 | ASSY - FRONT TOP WISHBONE - LH->ASSY CHASSIS BRAKE LINE | 2
50->80 | ASSY - FRONT TOP WISHBONE - LH->ASSY - REAR MASTER CYLINDER | 2
50->81 | ASSY - FRONT TOP WISHBONE - LH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
50->83 | ASSY - FRONT TOP WISHBONE - LH->ASSY - REAR BRAKE LINE | 2
Sunswift-50->50 | Sunswift for 50->ASSY - FRONT TOP WISHBONE - LH | 2
51->2 | ASSY - FRONT TOP WISHBONE - RH->ASSY - OCCUPANT CELL TUB | 2
51->73 | ASSY - FRONT TOP WISHBONE - RH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
51->74 | ASSY - FRONT TOP WISHBONE - RH->ASSY - FRONT MASTER CYLINDER | 2
51->76 | ASSY - FRONT TOP WISHBONE - RH->ASSY - FRONT BRAKE LINE | 2
51->77 | ASSY - FRONT TOP WISHBONE - RH->ASSY CHASSIS BRAKE LINE | 2
51->80 | ASSY - FRONT TOP WISHBONE - RH->ASSY - REAR MASTER CYLINDER | 2
51->81 | ASSY - FRONT TOP WISHBONE - RH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
51->83 | ASSY - FRONT TOP WISHBONE - RH->ASSY - REAR BRAKE LINE | 2
Sunswift-51->51 | Sunswift for 51->ASSY - FRONT TOP WISHBONE - RH | 2
52->2 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - OCCUPANT CELL TUB | 2
52->73 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
52->74 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - FRONT MASTER CYLINDER | 2
52->76 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - FRONT BRAKE LINE | 2
52->77 | ASSY - FRONT LOWER WISHBONE - LH->ASSY CHASSIS BRAKE LINE | 2
52->80 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - REAR MASTER CYLINDER | 2
52->81 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
52->83 | ASSY - FRONT LOWER WISHBONE - LH->ASSY - REAR BRAKE LINE | 2
Sunswift-52->52 | Sunswift for 52->ASSY - FRONT LOWER WISHBONE - LH | 2
53->2 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - OCCUPANT CELL TUB | 2
53->73 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
53->74 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - FRONT MASTER CYLINDER | 2
53->76 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - FRONT BRAKE LINE | 2
53->77 | ASSY - FRONT LOWER WISHBONE - RH->ASSY CHASSIS BRAKE LINE | 2
53->80 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - REAR MASTER CYLINDER | 2
53->81 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
53->83 | ASSY - FRONT LOWER WISHBONE - RH->ASSY - REAR BRAKE LINE | 2
Sunswift-53->53 | Sunswift for 53->ASSY - FRONT LOWER WISHBONE - RH | 2
54->2 | ASSY - FRONT TIEROD - LH->ASSY - OCCUPANT CELL TUB | 2
54->73 | ASSY - FRONT TIEROD - LH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
54->74 | ASSY - FRONT TIEROD - LH->ASSY - FRONT MASTER CYLINDER | 2
54->76 | ASSY - FRONT TIEROD - LH->ASSY - FRONT BRAKE LINE | 2
54->77 | ASSY - FRONT TIEROD - LH->ASSY CHASSIS BRAKE LINE | 2
54->80 | ASSY - FRONT TIEROD - LH->ASSY - REAR MASTER CYLINDER | 2
54->81 | ASSY - FRONT TIEROD - LH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
54->83 | ASSY - FRONT TIEROD - LH->ASSY - REAR BRAKE LINE | 2
Sunswift-54->54 | Sunswift for 54->ASSY - FRONT TIEROD - LH | 2
55->2 | ASSY - FRONT TIEROD - RH->ASSY - OCCUPANT CELL TUB | 2
55->73 | ASSY - FRONT TIEROD - RH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
55->74 | ASSY - FRONT TIEROD - RH->ASSY - FRONT MASTER CYLINDER | 2
55->76 | ASSY - FRONT TIEROD - RH->ASSY - FRONT BRAKE LINE | 2
55->77 | ASSY - FRONT TIEROD - RH->ASSY CHASSIS BRAKE LINE | 2
55->80 | ASSY - FRONT TIEROD - RH->ASSY - REAR MASTER CYLINDER | 2
55->81 | ASSY - FRONT TIEROD - RH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
55->83 | ASSY - FRONT TIEROD - RH->ASSY - REAR BRAKE LINE | 2
Sunswift-55->55 | Sunswift for 55->ASSY - FRONT TIEROD - RH | 2
56->54 | ASSY - FRONT UPRIGHT - LH->ASSY - FRONT TIEROD - LH | 2
56->73 | ASSY - FRONT UPRIGHT - LH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
56->74 | ASSY - FRONT UPRIGHT - LH->ASSY - FRONT MASTER CYLINDER | 2
56->76 | ASSY - FRONT UPRIGHT - LH->ASSY - FRONT BRAKE LINE | 2
56->77 | ASSY - FRONT UPRIGHT - LH->ASSY CHASSIS BRAKE LINE | 2
56->80 | ASSY - FRONT UPRIGHT - LH->ASSY - REAR MASTER CYLINDER | 2
56->81 | ASSY - FRONT UPRIGHT - LH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
56->83 | ASSY - FRONT UPRIGHT - LH->ASSY - REAR BRAKE LINE | 2
Sunswift-56->56 | Sunswift for 56->ASSY - FRONT UPRIGHT - LH | 4
57->55 | ASSY - FRONT UPRIGHT - RH->ASSY - FRONT TIEROD - RH | 2
57->73 | ASSY - FRONT UPRIGHT - RH->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
57->74 | ASSY - FRONT UPRIGHT - RH->ASSY - FRONT MASTER CYLINDER | 2
57->76 | ASSY - FRONT UPRIGHT - RH->ASSY - FRONT BRAKE LINE | 2
57->77 | ASSY - FRONT UPRIGHT - RH->ASSY CHASSIS BRAKE LINE | 2
57->80 | ASSY - FRONT UPRIGHT - RH->ASSY - REAR MASTER CYLINDER | 2
57->81 | ASSY - FRONT UPRIGHT - RH->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
57->83 | ASSY - FRONT UPRIGHT - RH->ASSY - REAR BRAKE LINE | 2
Sunswift-57->57 | Sunswift for 57->ASSY - FRONT UPRIGHT - RH | 4
58->2 | ASSY - FRONT DAMPER - LH->ASSY - OCCUPANT CELL TUB | 2
58->54 | ASSY - FRONT DAMPER - LH->ASSY - FRONT TIEROD - LH | 2
59->2 | ASSY - FRONT DAMPER - RH->ASSY - OCCUPANT CELL TUB | 2
59->55 | ASSY - FRONT DAMPER - RH->ASSY - FRONT TIEROD - RH | 2
60->50 | ASSY - FRONT WHEEL->ASSY - FRONT TOP WISHBONE - LH | 2
60->51 | ASSY - FRONT WHEEL->ASSY - FRONT TOP WISHBONE - RH | 2
60->52 | ASSY - FRONT WHEEL->ASSY - FRONT LOWER WISHBONE - LH | 2
60->53 | ASSY - FRONT WHEEL->ASSY - FRONT LOWER WISHBONE - RH | 2
60->56 | ASSY - FRONT WHEEL->ASSY - FRONT UPRIGHT - LH | 2
60->57 | ASSY - FRONT WHEEL->ASSY - FRONT UPRIGHT - RH | 2
60->58 | ASSY - FRONT WHEEL->ASSY - FRONT DAMPER - LH | 2
60->59 | ASSY - FRONT WHEEL->ASSY - FRONT DAMPER - RH | 2
60->71 | ASSY - FRONT WHEEL->ASSY - FRONT CALIPER - LH | 2
60->72 | ASSY - FRONT WHEEL->ASSY - FRONT CALIPER - RH | 2
60->75 | ASSY - FRONT WHEEL->ASSY - FRONT BRAKE DISC | 2
60->2 | ASSY - FRONT WHEEL->ASSY - OCCUPANT CELL TUB | 2
60->54 | ASSY - FRONT WHEEL->ASSY - FRONT TIEROD - LH | 2
60->55 | ASSY - FRONT WHEEL->ASSY - FRONT TIEROD - RH | 2
60->73 | ASSY - FRONT WHEEL->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
61->65 | ASSY - REAR TOP WISHBONE - LH->ASSY - REAR TOELINK | 2
61->2 | ASSY - REAR TOP WISHBONE - LH->ASSY - OCCUPANT CELL TUB | 2
62->65 | ASSY - REAR TOP WISHBONE - RH->ASSY - REAR TOELINK | 2
62->2 | ASSY - REAR TOP WISHBONE - RH->ASSY - OCCUPANT CELL TUB | 2
63->65 | ASSY - REAR LOWER WISHBONE - LH->ASSY - REAR TOELINK | 2
63->2 | ASSY - REAR LOWER WISHBONE - LH->ASSY - OCCUPANT CELL TUB | 2
64->65 | ASSY - REAR LOWER WISHBONE - RH->ASSY - REAR TOELINK | 2
64->2 | ASSY - REAR LOWER WISHBONE - RH->ASSY - OCCUPANT CELL TUB | 2
65->199 | ASSY - REAR TOELINK->Sink | 2
66->68 | ASSY - REAR UPRIGHT - LH->ASSY - REAR DAMPER - LH | 2
Sunswift-66->66 | Sunswift for 66->ASSY - REAR UPRIGHT - LH | 4
67->69 | ASSY - REAR UPRIGHT - RH->ASSY - REAR DAMPER - RH | 2
Sunswift-67->67 | Sunswift for 67->ASSY - REAR UPRIGHT - RH | 4
68->199 | ASSY - REAR DAMPER - LH->Sink | 2
69->199 | ASSY - REAR DAMPER - RH->Sink | 2
70->61 | ASSY - REAR WHEEL->ASSY - REAR TOP WISHBONE - LH | 2
70->62 | ASSY - REAR WHEEL->ASSY - REAR TOP WISHBONE - RH | 2
70->63 | ASSY - REAR WHEEL->ASSY - REAR LOWER WISHBONE - LH | 2
70->64 | ASSY - REAR WHEEL->ASSY - REAR LOWER WISHBONE - RH | 2
70->66 | ASSY - REAR WHEEL->ASSY - REAR UPRIGHT - LH | 2
70->67 | ASSY - REAR WHEEL->ASSY - REAR UPRIGHT - RH | 2
70->68 | ASSY - REAR WHEEL->ASSY - REAR DAMPER - LH | 2
70->69 | ASSY - REAR WHEEL->ASSY - REAR DAMPER - RH | 2
70->78 | ASSY - REAR WHEEL->ASSY - REAR BRAKE CALIPER - LH | 2
70->79 | ASSY - REAR WHEEL->ASSY - REAR BRAKE CALIPER - RH | 2
70->82 | ASSY - REAR WHEEL->ASSY - REAR BRAKE DISC | 2
70->84 | ASSY - REAR WHEEL->ASSY - HAND BRAKE | 2
70->2 | ASSY - REAR WHEEL->ASSY - OCCUPANT CELL TUB | 2
70->14 | ASSY - REAR WHEEL->ASSY - REAR QUARTER PANEL - LH | 2
70->15 | ASSY - REAR WHEEL->ASSY - REAR QUARTER PANEL - RH | 2
70->18 | ASSY - REAR WHEEL->ASSY - REAR SUPPORT STRUCTURE | 2
70->65 | ASSY - REAR WHEEL->ASSY - REAR TOELINK | 2
70->80 | ASSY - REAR WHEEL->ASSY - REAR MASTER CYLINDER | 2
70->81 | ASSY - REAR WHEEL->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
70->83 | ASSY - REAR WHEEL->ASSY - REAR BRAKE LINE | 2
Sunswift-70->70 | Sunswift for 70->ASSY - REAR WHEEL | 4
71->54 | ASSY - FRONT CALIPER - LH->ASSY - FRONT TIEROD - LH | 2
71->2 | ASSY - FRONT CALIPER - LH->ASSY - OCCUPANT CELL TUB | 2
71->76 | ASSY - FRONT CALIPER - LH->ASSY - FRONT BRAKE LINE | 2
72->55 | ASSY - FRONT CALIPER - RH->ASSY - FRONT TIEROD - RH | 2
72->2 | ASSY - FRONT CALIPER - RH->ASSY - OCCUPANT CELL TUB | 2
72->76 | ASSY - FRONT CALIPER - RH->ASSY - FRONT BRAKE LINE | 2
73->199 | ASSY - FRONT MASTER CYLINDER RESERVOIR->Sink | 2
74->2 | ASSY - FRONT MASTER CYLINDER->ASSY - OCCUPANT CELL TUB | 2
75->54 | ASSY - FRONT BRAKE DISC->ASSY - FRONT TIEROD - LH | 2
75->55 | ASSY - FRONT BRAKE DISC->ASSY - FRONT TIEROD - RH | 2
75->71 | ASSY - FRONT BRAKE DISC->ASSY - FRONT CALIPER - LH | 2
75->72 | ASSY - FRONT BRAKE DISC->ASSY - FRONT CALIPER - RH | 2
75->56 | ASSY - FRONT BRAKE DISC->ASSY - FRONT UPRIGHT - LH | 2
75->57 | ASSY - FRONT BRAKE DISC->ASSY - FRONT UPRIGHT - RH | 2
76->2 | ASSY - FRONT BRAKE LINE->ASSY - OCCUPANT CELL TUB | 2
77->2 | ASSY CHASSIS BRAKE LINE->ASSY - OCCUPANT CELL TUB | 2
78->83 | ASSY - REAR BRAKE CALIPER - LH->ASSY - REAR BRAKE LINE | 2
79->83 | ASSY - REAR BRAKE CALIPER - RH->ASSY - REAR BRAKE LINE | 2
80->2 | ASSY - REAR MASTER CYLINDER->ASSY - OCCUPANT CELL TUB | 2
81->2 | ASSY - REAR MASTER CYLINDER RESERVOIR->ASSY - OCCUPANT CELL TUB | 2
82->78 | ASSY - REAR BRAKE DISC->ASSY - REAR BRAKE CALIPER - LH | 2
82->79 | ASSY - REAR BRAKE DISC->ASSY - REAR BRAKE CALIPER - RH | 2
82->84 | ASSY - REAR BRAKE DISC->ASSY - HAND BRAKE | 2
82->83 | ASSY - REAR BRAKE DISC->ASSY - REAR BRAKE LINE | 2
83->2 | ASSY - REAR BRAKE LINE->ASSY - OCCUPANT CELL TUB | 2
84->77 | ASSY - HAND BRAKE ->ASSY CHASSIS BRAKE LINE | 2
84->101 | ASSY - HAND BRAKE ->ASSY - DASHBOARD STRUCTURE | 2
85->2 | ASSY - STEERING COLUMN->ASSY - OCCUPANT CELL TUB | 2
85->3 | ASSY - STEERING COLUMN->ASSY - STEERING COLUMN MOUNT | 2
85->4 | ASSY - STEERING COLUMN->ASSY - FRONT CRASH STRUCTURE | 2
Flaming River-85->85 | Flaming River for 85->ASSY - STEERING COLUMN | 4
86->2 | ASSY - STEERING RACK->ASSY - OCCUPANT CELL TUB | 2
86->73 | ASSY - STEERING RACK->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
86->74 | ASSY - STEERING RACK->ASSY - FRONT MASTER CYLINDER | 2
86->76 | ASSY - STEERING RACK->ASSY - FRONT BRAKE LINE | 2
86->77 | ASSY - STEERING RACK->ASSY CHASSIS BRAKE LINE | 2
86->80 | ASSY - STEERING RACK->ASSY - REAR MASTER CYLINDER | 2
86->81 | ASSY - STEERING RACK->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
86->83 | ASSY - STEERING RACK->ASSY - REAR BRAKE LINE | 2
86->85 | ASSY - STEERING RACK->ASSY - STEERING COLUMN | 2
86->54 | ASSY - STEERING RACK->ASSY - FRONT TIEROD - LH | 2
86->55 | ASSY - STEERING RACK->ASSY - FRONT TIEROD - RH | 2
Flaming River-86->86 | Flaming River for 86->ASSY - STEERING RACK | 4
87->85 | ASSY - STEERING WHEEL->ASSY - STEERING COLUMN | 4
87->103 | ASSY - STEERING WHEEL->ASSY - DRIVER DISPLAY | 4
87->188 | ASSY - STEERING WHEEL->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 4
88->87 | ASSY - STEERING WHEEL PCB->ASSY - STEERING WHEEL | 6
88->191 | ASSY - STEERING WHEEL PCB->ASSY - STEERING WHEEL PCB CODE | 6
89->2 | ASSY - INTERIOR LIGHTS PCB->ASSY - OCCUPANT CELL TUB | 6
89->1 | ASSY - INTERIOR LIGHTS PCB->ASSY - OCCUPANT CELL SPIDER | 6
89->98 | ASSY - INTERIOR LIGHTS PCB->ASSY - CEILING | 6
90->98 | ASSY - REAR VISION CAMERA->ASSY - CEILING | 4
91->16 | ASSY - SIDE CAMERA - LH->ASSY - FRONT CLAM SHELL | 6
91->147 | ASSY - SIDE CAMERA - LH->ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | 6
Unknown-91->91 | Unknown for 91->ASSY - SIDE CAMERA - LH | 4
92->16 | ASSY - SIDE CAMERA - RH->ASSY - FRONT CLAM SHELL | 6
92->148 | ASSY - SIDE CAMERA - RH->ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | 6
Unknown-92->92 | Unknown for 92->ASSY - SIDE CAMERA - RH | 4
93->73 | ASSY - PEDAL BOX->ASSY - FRONT MASTER CYLINDER RESERVOIR | 2
93->74 | ASSY - PEDAL BOX->ASSY - FRONT MASTER CYLINDER | 2
93->76 | ASSY - PEDAL BOX->ASSY - FRONT BRAKE LINE | 2
93->77 | ASSY - PEDAL BOX->ASSY CHASSIS BRAKE LINE | 2
93->80 | ASSY - PEDAL BOX->ASSY - REAR MASTER CYLINDER | 2
93->81 | ASSY - PEDAL BOX->ASSY - REAR MASTER CYLINDER RESERVOIR | 2
93->83 | ASSY - PEDAL BOX->ASSY - REAR BRAKE LINE | 2
93->2 | ASSY - PEDAL BOX->ASSY - OCCUPANT CELL TUB | 2
94->93 | ASSY - THROTTLE PEDAL->ASSY - PEDAL BOX | 1
94->97 | ASSY - THROTTLE PEDAL->ASSY - PEDAL PRESS SENSOR | 1
94->74 | ASSY - THROTTLE PEDAL->ASSY - FRONT MASTER CYLINDER | 1
94->80 | ASSY - THROTTLE PEDAL->ASSY - REAR MASTER CYLINDER | 1
95->73 | ASSY - BRAKE PEDAL->ASSY - FRONT MASTER CYLINDER RESERVOIR | 1
95->74 | ASSY - BRAKE PEDAL->ASSY - FRONT MASTER CYLINDER | 1
95->76 | ASSY - BRAKE PEDAL->ASSY - FRONT BRAKE LINE | 1
95->77 | ASSY - BRAKE PEDAL->ASSY CHASSIS BRAKE LINE | 1
95->80 | ASSY - BRAKE PEDAL->ASSY - REAR MASTER CYLINDER | 1
95->81 | ASSY - BRAKE PEDAL->ASSY - REAR MASTER CYLINDER RESERVOIR | 1
95->83 | ASSY - BRAKE PEDAL->ASSY - REAR BRAKE LINE | 1
95->93 | ASSY - BRAKE PEDAL->ASSY - PEDAL BOX | 1
95->97 | ASSY - BRAKE PEDAL->ASSY - PEDAL PRESS SENSOR | 1
96->93 | ASSY - PEDAL BOX CONTROLLER->ASSY - PEDAL BOX | 2
96->188 | ASSY - PEDAL BOX CONTROLLER->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
97->93 | ASSY - PEDAL PRESS SENSOR->ASSY - PEDAL BOX | 1
97->96 | ASSY - PEDAL PRESS SENSOR->ASSY - PEDAL BOX CONTROLLER | 1
98->199 | ASSY - CEILING->Sink | 4
99->98 | ASSY - SUN VISOR - LH->ASSY - CEILING | 3
100->98 | ASSY - SUN VISOR - RH->ASSY - CEILING | 3
101->199 | ASSY - DASHBOARD STRUCTURE->Sink | 6
102->101 | ASSY - CENTRAL DISPLAY->ASSY - DASHBOARD STRUCTURE | 2
102->188 | ASSY - CENTRAL DISPLAY->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
103->101 | ASSY - DRIVER DISPLAY->ASSY - DASHBOARD STRUCTURE | 2
103->188 | ASSY - DRIVER DISPLAY->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
104->101 | ASSY - HEADS-UP DISPLAY->ASSY - DASHBOARD STRUCTURE | 2
105->199 | ASSY - FRONT SEAT RAIL DRIVER->Sink | 4
106->2 | ASSY - FRONT SEAT DRIVER->ASSY - OCCUPANT CELL TUB | 4
106->105 | ASSY - FRONT SEAT DRIVER->ASSY - FRONT SEAT RAIL DRIVER | 4
106->110 | ASSY - FRONT SEAT DRIVER->ASSY - FRONT SEAT BELT DRIVER | 4
107->2 | ASSY - FRONT SEAT MOUNT DRIVER->ASSY - OCCUPANT CELL TUB | 4
107->106 | ASSY - FRONT SEAT MOUNT DRIVER->ASSY - FRONT SEAT DRIVER | 4
107->110 | ASSY - FRONT SEAT MOUNT DRIVER->ASSY - FRONT SEAT BELT DRIVER | 4
Bride Racing-107->107 | Bride Racing for 107->ASSY - FRONT SEAT MOUNT DRIVER | 1
108->2 | ASSY - FRONT SEAT PASSENGER->ASSY - OCCUPANT CELL TUB | 4
108->111 | ASSY - FRONT SEAT PASSENGER->ASSY - FRONT SEAT BELT PASSENGER | 4
108->109 | ASSY - FRONT SEAT PASSENGER->ASSY - FRONT SEAT MOUNT PASSENGER | 4
109->2 | ASSY - FRONT SEAT MOUNT PASSENGER->ASSY - OCCUPANT CELL TUB | 4
109->111 | ASSY - FRONT SEAT MOUNT PASSENGER->ASSY - FRONT SEAT BELT PASSENGER | 4
Bride Racing-109->109 | Bride Racing for 109->ASSY - FRONT SEAT MOUNT PASSENGER | 1
110->2 | ASSY - FRONT SEAT BELT DRIVER->ASSY - OCCUPANT CELL TUB | 1
110->1 | ASSY - FRONT SEAT BELT DRIVER->ASSY - OCCUPANT CELL SPIDER | 1
Unknown-110->110 | Unknown for 110->ASSY - FRONT SEAT BELT DRIVER | 1
111->2 | ASSY - FRONT SEAT BELT PASSENGER->ASSY - OCCUPANT CELL TUB | 1
111->1 | ASSY - FRONT SEAT BELT PASSENGER->ASSY - OCCUPANT CELL SPIDER | 1
112->2 | ASSY - MOTOR UNIT - LH->ASSY - OCCUPANT CELL TUB | 2
112->7 | ASSY - MOTOR UNIT - LH->ASSY - CHASSIS SUBFRAME | 2
112->12 | ASSY - MOTOR UNIT - LH->ASSY - REAR FLUID MANAGEMENT | 2
112->114 | ASSY - MOTOR UNIT - LH->ASSY - MOTOR MOUNTING FRAME - LH | 2
112->116 | ASSY - MOTOR UNIT - LH->ASSY - INVERTER - LH | 2
112->118 | ASSY - MOTOR UNIT - LH->ASSY - INVERTER MOUNTING FRAME - LH | 2
112->120 | ASSY - MOTOR UNIT - LH->ASSY - PWT HV WIRING - LH | 2
112->122 | ASSY - MOTOR UNIT - LH->ASSY - GEARBOX - LH | 2
112->124 | ASSY - MOTOR UNIT - LH->ASSY - AXLE CV - LH | 2
112->161 | ASSY - MOTOR UNIT - LH->ASSY - DRIVE CONTROL UNIT | 2
112->190 | ASSY - MOTOR UNIT - LH->ASSY - MAIN COMPUTER | 2
113->2 | ASSY - MOTOR UNIT - RH->ASSY - OCCUPANT CELL TUB | 2
113->7 | ASSY - MOTOR UNIT - RH->ASSY - CHASSIS SUBFRAME | 2
113->12 | ASSY - MOTOR UNIT - RH->ASSY - REAR FLUID MANAGEMENT | 2
113->115 | ASSY - MOTOR UNIT - RH->ASSY - MOTOR MOUNTING FRAME - RH | 2
113->117 | ASSY - MOTOR UNIT - RH->ASSY - INVERTER - RH | 2
113->119 | ASSY - MOTOR UNIT - RH->ASSY - INVERTER MOUNTING FRAME - RH | 2
113->121 | ASSY - MOTOR UNIT - RH->ASSY - PWT HV WIRING - RH | 2
113->123 | ASSY - MOTOR UNIT - RH->ASSY - GEARBOX - RH | 2
113->125 | ASSY - MOTOR UNIT - RH->ASSY - AXLE CV - RH | 2
113->161 | ASSY - MOTOR UNIT - RH->ASSY - DRIVE CONTROL UNIT | 2
113->190 | ASSY - MOTOR UNIT - RH->ASSY - MAIN COMPUTER | 2
113->124 | ASSY - MOTOR UNIT - RH->ASSY - AXLE CV - LH | 2
114->7 | ASSY - MOTOR MOUNTING FRAME - LH->ASSY - CHASSIS SUBFRAME | 6
115->7 | ASSY - MOTOR MOUNTING FRAME - RH->ASSY - CHASSIS SUBFRAME | 6
116->118 | ASSY - INVERTER - LH->ASSY - INVERTER MOUNTING FRAME - LH | 2
116->120 | ASSY - INVERTER - LH->ASSY - PWT HV WIRING - LH | 2
116->182 | ASSY - INVERTER - LH->ASSY - HYDROGEN COOLING SYSTEM | 2
117->119 | ASSY - INVERTER - RH->ASSY - INVERTER MOUNTING FRAME - RH | 2
117->121 | ASSY - INVERTER - RH->ASSY - PWT HV WIRING - RH | 2
117->182 | ASSY - INVERTER - RH->ASSY - HYDROGEN COOLING SYSTEM | 2
118->199 | ASSY - INVERTER MOUNTING FRAME - LH->Sink | 6
119->199 | ASSY - INVERTER MOUNTING FRAME - RH->Sink | 6
120->199 | ASSY - PWT HV WIRING - LH->Sink | 2
Unknown-120->120 | Unknown for 120->ASSY - PWT HV WIRING - LH | 4
121->199 | ASSY - PWT HV WIRING - RH->Sink | 2
Unknown-121->121 | Unknown for 121->ASSY - PWT HV WIRING - RH | 4
122->7 | ASSY - GEARBOX - LH->ASSY - CHASSIS SUBFRAME | 3
122->114 | ASSY - GEARBOX - LH->ASSY - MOTOR MOUNTING FRAME - LH | 3
122->124 | ASSY - GEARBOX - LH->ASSY - AXLE CV - LH | 3
122->2 | ASSY - GEARBOX - LH->ASSY - OCCUPANT CELL TUB | 3
Ricardo-122->122 | Ricardo for 122->ASSY - GEARBOX - LH | 8
123->7 | ASSY - GEARBOX - RH->ASSY - CHASSIS SUBFRAME | 3
123->115 | ASSY - GEARBOX - RH->ASSY - MOTOR MOUNTING FRAME - RH | 3
123->125 | ASSY - GEARBOX - RH->ASSY - AXLE CV - RH | 3
123->2 | ASSY - GEARBOX - RH->ASSY - OCCUPANT CELL TUB | 3
Ricardo-123->123 | Ricardo for 123->ASSY - GEARBOX - RH | 8
124->2 | ASSY - AXLE CV - LH->ASSY - OCCUPANT CELL TUB | 6
124->7 | ASSY - AXLE CV - LH->ASSY - CHASSIS SUBFRAME | 6
Ricardo-124->124 | Ricardo for 124->ASSY - AXLE CV - LH | 8
125->2 | ASSY - AXLE CV - RH->ASSY - OCCUPANT CELL TUB | 6
125->7 | ASSY - AXLE CV - RH->ASSY - CHASSIS SUBFRAME | 6
Ricardo-125->125 | Ricardo for 125->ASSY - AXLE CV - RH | 8
126->2 | ASSY - BATTERY MODULES->ASSY - OCCUPANT CELL TUB | 4
126->127 | ASSY - BATTERY MODULES->ASSY - BATTERY PACK | 4
Sunswift-126->126 | Sunswift for 126->ASSY - BATTERY MODULES | 8
127->128 | ASSY - BATTERY PACK->ASSY - BMS WIRING | 2
127->129 | ASSY - BATTERY PACK->ASSY - BATTERY HV WIRING | 2
127->130 | ASSY - BATTERY PACK->ASSY - BATTERY LV WIRING | 2
127->134 | ASSY - BATTERY PACK->ASSY - ECS HV WIRING | 2
127->135 | ASSY - BATTERY PACK->ASSY - ECS LV WIRING | 2
127->181 | ASSY - BATTERY PACK->ASSY - FUEL CELL STACK | 2
Sunswift-127->127 | Sunswift for 127->ASSY - BATTERY PACK | 8
128->136 | ASSY - BMS WIRING->ASSY - CONTROL LOGIC | 3
Sunswift-128->128 | Sunswift for 128->ASSY - BMS WIRING | 8
129->199 | ASSY - BATTERY HV WIRING->Sink | 2
Sunswift-129->129 | Sunswift for 129->ASSY - BATTERY HV WIRING | 8
130->199 | ASSY - BATTERY LV WIRING->Sink | 2
Sunswift-130->130 | Sunswift for 130->ASSY - BATTERY LV WIRING | 8
131->199 | ASSY - AUXILLARY POWER WIRING->Sink | 2
Sunswift-131->131 | Sunswift for 131->ASSY - AUXILLARY POWER WIRING | 8
132->199 | ASSY - DC-DC CONVERTERS->Sink | 2
Sunswift-132->132 | Sunswift for 132->ASSY - DC-DC CONVERTERS | 8
133->131 | ASSY - AUX BATTERY->ASSY - AUXILLARY POWER WIRING | 2
133->132 | ASSY - AUX BATTERY->ASSY - DC-DC CONVERTERS | 2
Sunswift-133->133 | Sunswift for 133->ASSY - AUX BATTERY | 8
134->136 | ASSY - ECS HV WIRING->ASSY - CONTROL LOGIC | 2
Sunswift-134->134 | Sunswift for 134->ASSY - ECS HV WIRING | 8
135->136 | ASSY - ECS LV WIRING->ASSY - CONTROL LOGIC | 2
Sunswift-135->135 | Sunswift for 135->ASSY - ECS LV WIRING | 8
136->199 | ASSY - CONTROL LOGIC->Sink | 3
Sunswift-136->136 | Sunswift for 136->ASSY - CONTROL LOGIC | 8
137->187 | ASSY - ECS MODULE->ASSY - HYDROGEN CONTROL SYSTEM | 3
137->134 | ASSY - ECS MODULE->ASSY - ECS HV WIRING | 3
137->135 | ASSY - ECS MODULE->ASSY - ECS LV WIRING | 3
137->136 | ASSY - ECS MODULE->ASSY - CONTROL LOGIC | 3
Sunswift-137->137 | Sunswift for 137->ASSY - ECS MODULE | 8
138->199 | ASSY - ONBOARD CHARGING WIRING->Sink | 2
139->138 | ASSY - ONBOARD CHARGER INSTALLATION->ASSY - ONBOARD CHARGING WIRING | 3
140->134 | ASSY - MPPT JUNCTION BOX->ASSY - ECS HV WIRING | 2
140->136 | ASSY - MPPT JUNCTION BOX->ASSY - CONTROL LOGIC | 2
141->140 | ASSY - MPPT->ASSY - MPPT JUNCTION BOX | 4
141->1 | ASSY - MPPT->ASSY - OCCUPANT CELL SPIDER | 4
142->1 | ASSY - SOLAR ROOF ARRAY->ASSY - OCCUPANT CELL SPIDER | 8
142->141 | ASSY - SOLAR ROOF ARRAY->ASSY - MPPT | 8
142->145 | ASSY - SOLAR ROOF ARRAY->ASSY - MC4 Cabling | 8
142->2 | ASSY - SOLAR ROOF ARRAY->ASSY - OCCUPANT CELL TUB | 8
142->98 | ASSY - SOLAR ROOF ARRAY->ASSY - CEILING | 8
Sundrive, Corning, McCognaughy, REOO-142->142 | Sundrive, Corning, McCognaughy, REOO for 142->ASSY - SOLAR ROOF ARRAY | 12
143->19 | ASSY - SOLAR BOOT ARRAY->ASSY - BOOT | 8
143->141 | ASSY - SOLAR BOOT ARRAY->ASSY - MPPT | 8
143->145 | ASSY - SOLAR BOOT ARRAY->ASSY - MC4 Cabling | 8
Sundrive, Corning, McCognaughy, REOO-143->143 | Sundrive, Corning, McCognaughy, REOO for 143->ASSY - SOLAR BOOT ARRAY | 12
144->21 | ASSY - SOLAR BONNET ARRAY->ASSY - BONNET | 8
144->141 | ASSY - SOLAR BONNET ARRAY->ASSY - MPPT | 8
144->145 | ASSY - SOLAR BONNET ARRAY->ASSY - MC4 Cabling | 8
Sundrive, Corning, McCognaughy, REOO-144->144 | Sundrive, Corning, McCognaughy, REOO for 144->ASSY - SOLAR BONNET ARRAY | 12
145->1 | ASSY - MC4 Cabling->ASSY - OCCUPANT CELL SPIDER | 4
145->19 | ASSY - MC4 Cabling->ASSY - BOOT | 4
145->21 | ASSY - MC4 Cabling->ASSY - BONNET | 4
145->141 | ASSY - MC4 Cabling->ASSY - MPPT | 4
146->19 | Assy - Shingled Matrix Panels->ASSY - BOOT | 12
146->141 | Assy - Shingled Matrix Panels->ASSY - MPPT | 12
146->145 | Assy - Shingled Matrix Panels->ASSY - MC4 Cabling | 12
147->19 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH->ASSY - BOOT | 3
147->149 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH->ASSY - TAILLIGHT/INDICATOR PCB - LH | 3
148->19 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH->ASSY - BOOT | 3
148->150 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH->ASSY - TAILLIGHT/INDICATOR PCB - RH | 3
149->19 | ASSY - TAILLIGHT/INDICATOR PCB - LH->ASSY - BOOT | 6
149->188 | ASSY - TAILLIGHT/INDICATOR PCB - LH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 6
150->19 | ASSY - TAILLIGHT/INDICATOR PCB - RH->ASSY - BOOT | 6
150->188 | ASSY - TAILLIGHT/INDICATOR PCB - RH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 6
151->19 | ASSY - CENTRAL STOP LAMP->ASSY - BOOT | 3
151->152 | ASSY - CENTRAL STOP LAMP->ASSY - CENTRAL STOP LAMP PCB | 3
151->188 | ASSY - CENTRAL STOP LAMP->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 3
152->19 | ASSY - CENTRAL STOP LAMP PCB->ASSY - BOOT | 4
153->16 | ASSY - HEADLIGHT EXTERIOR - LH->ASSY - FRONT CLAM SHELL | 3
154->16 | ASSY - HEADLIGHT EXTERIOR - RH->ASSY - FRONT CLAM SHELL | 3
155->16 | ASSY - HEADLIGHT/INDICATOR PCB - LH->ASSY - FRONT CLAM SHELL | 2
155->188 | ASSY - HEADLIGHT/INDICATOR PCB - LH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
155->153 | ASSY - HEADLIGHT/INDICATOR PCB - LH->ASSY - HEADLIGHT EXTERIOR - LH | 2
156->16 | ASSY - HEADLIGHT/INDICATOR PCB - RH->ASSY - FRONT CLAM SHELL | 2
156->188 | ASSY - HEADLIGHT/INDICATOR PCB - RH->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2
156->154 | ASSY - HEADLIGHT/INDICATOR PCB - RH->ASSY - HEADLIGHT EXTERIOR - RH | 2
157->28 | ASSY - SIDE INDICATOR EXTERIOR - LH->ASSY - DOOR SHELL - LH | 3
158->27 | ASSY - SIDE INDICATOR EXTERIOR - RH->ASSY - DOOR SHELL - RH | 3
159->16 | ASSY - HORN->ASSY - FRONT CLAM SHELL | 1
160->188 | ASSY - HORN PCB->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 3
161->188 | ASSY - DRIVE CONTROL UNIT->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 12
161->190 | ASSY - DRIVE CONTROL UNIT->ASSY - MAIN COMPUTER | 12
162->199 | ASSY - SENSOR MOTHERBOARD - FL->Sink | 12
163->199 | ASSY - SENSOR MOTHERBOARD - FR->Sink | 12
164->199 | ASSY - SENSOR MOTHERBOARD - BL->Sink | 12
165->199 | ASSY - SENSOR MOTHERBOARD - BR->Sink | 12
166->167 | ASSY - SUBWOOFER->ASSY - AUDIO CONTROL SYSTEM | 3
166->188 | ASSY - SUBWOOFER->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 3
166->2 | ASSY - SUBWOOFER->ASSY - OCCUPANT CELL TUB | 3
167->188 | ASSY - AUDIO CONTROL SYSTEM->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 8
168->2 | ASSY - PRESSURE VESSEL SHELL->ASSY - OCCUPANT CELL TUB | 0
168->170 | ASSY - PRESSURE VESSEL SHELL->ASSY - HYDROGEN COMPARTMENT STRUCTURE | 0
168->171 | ASSY - PRESSURE VESSEL SHELL->ASSY - PRESSURE REGULATION & SAFETY | 0
Coregas, Swagelok-168->168 | Coregas, Swagelok for 168->ASSY - PRESSURE VESSEL SHELL | 6
169->168 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE->ASSY - PRESSURE VESSEL SHELL | 0
169->170 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE->ASSY - HYDROGEN COMPARTMENT STRUCTURE | 0
169->171 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE->ASSY - PRESSURE REGULATION & SAFETY | 0
169->2 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE->ASSY - OCCUPANT CELL TUB | 0
169->17 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE->ASSY - REAR FLOOR | 0
170->174 | ASSY - HYDROGEN COMPARTMENT STRUCTURE->ASSY - HYDROGEN COMPARTMENT VENTILATION | 0
170->175 | ASSY - HYDROGEN COMPARTMENT STRUCTURE->ASSY - OCCUPANT CELL HYDROGEN SENSOR | 0
170->186 | ASSY - HYDROGEN COMPARTMENT STRUCTURE->ASSY - REARWHEEL HUB AIR INTAKE | 0
171->172 | ASSY - PRESSURE REGULATION & SAFETY->ASSY - HYDROGEN SUPPLY LINE | 0
171->179 | ASSY - PRESSURE REGULATION & SAFETY->ASSY - HYDROGEN SENSOR ARRAY | 0
171->184 | ASSY - PRESSURE REGULATION & SAFETY->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0
Swagelok-171->171 | Swagelok for 171->ASSY - PRESSURE REGULATION & SAFETY | 12
172->173 | ASSY - HYDROGEN SUPPLY LINE->ASSY - HYDROGEN PURGE MANAGEMENT | 0
172->179 | ASSY - HYDROGEN SUPPLY LINE->ASSY - HYDROGEN SENSOR ARRAY | 0
172->184 | ASSY - HYDROGEN SUPPLY LINE->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0
Swagelok-172->172 | Swagelok for 172->ASSY - HYDROGEN SUPPLY LINE | 6
173->176 | ASSY - HYDROGEN PURGE MANAGEMENT->ASSY - P&ID HYDROGEN RECYCLE STREAM | 0
173->184 | ASSY - HYDROGEN PURGE MANAGEMENT->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0
Siltrax, Swagelok-173->173 | Siltrax, Swagelok for 173->ASSY - HYDROGEN PURGE MANAGEMENT | 6
174->2 | ASSY - HYDROGEN COMPARTMENT VENTILATION->ASSY - OCCUPANT CELL TUB | 0
174->185 | ASSY - HYDROGEN COMPARTMENT VENTILATION->ASSY - P&ID AIR SUPPLY LINE | 0
174->186 | ASSY - HYDROGEN COMPARTMENT VENTILATION->ASSY - REARWHEEL HUB AIR INTAKE | 0
175->178 | ASSY - OCCUPANT CELL HYDROGEN SENSOR->ASSY - OCCUPANT CELL SHUTDOWN VALVE | 0
175->183 | ASSY - OCCUPANT CELL HYDROGEN SENSOR->ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 0
Gas detection supplier (Honeywell/CityTech etc.)-175->175 | Gas detection supplier (Honeywell/CityTech etc.) for 175->ASSY - OCCUPANT CELL HYDROGEN SENSOR | 10
176->179 | ASSY - P&ID HYDROGEN RECYCLE STREAM->ASSY - HYDROGEN SENSOR ARRAY | 0
Siltrax-176->176 | Siltrax for 176->ASSY - P&ID HYDROGEN RECYCLE STREAM | 6
177->199 | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY ->Sink | 0
178->199 | ASSY - OCCUPANT CELL SHUTDOWN VALVE->Sink | 0
Swagelok-178->178 | Swagelok for 178->ASSY - OCCUPANT CELL SHUTDOWN VALVE | 6
179->177 | ASSY - HYDROGEN SENSOR ARRAY->ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 0
179->180 | ASSY - HYDROGEN SENSOR ARRAY->ASSY - HYDROGEN CONTROL LOGIC | 0
External Supplier (TBA)-179->179 | External Supplier (TBA) for 179->ASSY - HYDROGEN SENSOR ARRAY | 10
180->178 | ASSY - HYDROGEN CONTROL LOGIC->ASSY - OCCUPANT CELL SHUTDOWN VALVE | 0
180->187 | ASSY - HYDROGEN CONTROL LOGIC->ASSY - HYDROGEN CONTROL SYSTEM | 0
External Supplier (TBA)-180->180 | External Supplier (TBA) for 180->ASSY - HYDROGEN CONTROL LOGIC | 16
181->173 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN PURGE MANAGEMENT | 0
181->176 | ASSY - FUEL CELL STACK->ASSY - P&ID HYDROGEN RECYCLE STREAM | 0
181->179 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN SENSOR ARRAY | 0
181->180 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN CONTROL LOGIC | 0
181->182 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN COOLING SYSTEM | 0
181->183 | ASSY - FUEL CELL STACK->ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 0
181->184 | ASSY - FUEL CELL STACK->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0
181->170 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN COMPARTMENT STRUCTURE | 0
181->172 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN SUPPLY LINE | 0
181->187 | ASSY - FUEL CELL STACK->ASSY - HYDROGEN CONTROL SYSTEM | 0
Siltrax-181->181 | Siltrax for 181->ASSY - FUEL CELL STACK | 6
182->12 | ASSY - HYDROGEN COOLING SYSTEM->ASSY - REAR FLUID MANAGEMENT | 0
182->183 | ASSY - HYDROGEN COOLING SYSTEM->ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 0
182->184 | ASSY - HYDROGEN COOLING SYSTEM->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0
183->177 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS->ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 0
183->187 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS->ASSY - HYDROGEN CONTROL SYSTEM | 0
184->185 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE->ASSY - P&ID AIR SUPPLY LINE | 0
Swagelok-184->184 | Swagelok for 184->ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 6
185->178 | ASSY - P&ID AIR SUPPLY LINE ->ASSY - OCCUPANT CELL SHUTDOWN VALVE | 0
Beswick, Swagelok-185->185 | Beswick, Swagelok for 185->ASSY - P&ID AIR SUPPLY LINE | 8
186->185 | ASSY - REARWHEEL HUB AIR INTAKE ->ASSY - P&ID AIR SUPPLY LINE | 0
186->180 | ASSY - REARWHEEL HUB AIR INTAKE ->ASSY - HYDROGEN CONTROL LOGIC | 0
187->199 | ASSY - HYDROGEN CONTROL SYSTEM->Sink | 0
Ballard or Intelligent Energy-187->187 | Ballard or Intelligent Energy for 187->ASSY - HYDROGEN CONTROL SYSTEM | 12
188->199 | ASSY - INTERNAL EMBEDDED NETWORK WIRING->Sink | 2
189->199 | ASSY - INTRANET->Sink | 0
190->188 | ASSY - MAIN COMPUTER->ASSY - INTERNAL EMBEDDED NETWORK WIRING | 1
Adlink-190->190 | Adlink for 190->ASSY - MAIN COMPUTER | 8
191->199 | ASSY - STEERING WHEEL PCB CODE->Sink | 4
192->199 | ASSY - DOOR ACTUATOR BOARD - RH->Sink | 5
193->199 | ASSY - DOOR ACTUATOR BOARD - LH->Sink | 5
194->91 | ASSY - SIDE INDICATOR - LH->ASSY - SIDE CAMERA - LH | 4
195->92 | ASSY - SIDE INDICATOR - RH->ASSY - SIDE CAMERA - RH | 4
196->197 | ASSY - CENTRAL STOPLAMP ->ASSY - CENTRAL STOPLAMP CASING | 3
196->198 | ASSY - CENTRAL STOPLAMP ->ASSY - CENTRAL STOPLAMP CONTROLLER | 3
197->199 | ASSY - CENTRAL STOPLAMP CASING->Sink | 4
198->199 | ASSY - CENTRAL STOPLAMP CONTROLLER->Sink | 3

## Scheduled_Results
ID | Description | Duration | ES | EF | LS | LF | Slack | Critical
0 | Source | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Divergent-7 | Divergent for 7 | 8 | 0 | 8 | 27 | 35 | 27 | FALSE
AutoFrost, PWR-9 | AutoFrost, PWR for 9 | 3 | 0 | 3 | 0 | 3 | 0 | TRUE
Unknown-10 | Unknown for 10 | 3 | 0 | 3 | 14 | 17 | 14 | FALSE
Unknown-11 | Unknown for 11 | 3 | 0 | 3 | 21 | 24 | 21 | FALSE
Unknown-12 | Unknown for 12 | 3 | 0 | 3 | 31 | 34 | 31 | FALSE
McConaghy, Scott Bader, Colan, Stabillus-19 | McConaghy, Scott Bader, Colan, Stabillus for 19 | 1 | 0 | 1 | 49 | 50 | 49 | FALSE
Chevalier-23 | Chevalier for 23 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Chevalier-24 | Chevalier for 24 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Chevalier-25 | Chevalier for 25 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Chevalier-26 | Chevalier for 26 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Chevalier-29 | Chevalier for 29 | 4 | 0 | 4 | 33 | 37 | 33 | FALSE
Chevalier-30 | Chevalier for 30 | 4 | 0 | 4 | 33 | 37 | 33 | FALSE
Stabillus-31 | Stabillus for 31 | 1 | 0 | 1 | 30 | 31 | 30 | FALSE
Stabillus-32 | Stabillus for 32 | 1 | 0 | 1 | 30 | 31 | 30 | FALSE
Unknown-39 | Unknown for 39 | 4 | 0 | 4 | 28 | 32 | 28 | FALSE
Unknown-40 | Unknown for 40 | 4 | 0 | 4 | 28 | 32 | 28 | FALSE
Unknown-44 | Unknown for 44 | 4 | 0 | 4 | 52 | 56 | 52 | FALSE
Unknown-45 | Unknown for 45 | 4 | 0 | 4 | 52 | 56 | 52 | FALSE
Unknown-46 | Unknown for 46 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Sunswift-50 | Sunswift for 50 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-51 | Sunswift for 51 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-52 | Sunswift for 52 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-53 | Sunswift for 53 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-54 | Sunswift for 54 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-55 | Sunswift for 55 | 2 | 0 | 2 | 33 | 35 | 33 | FALSE
Sunswift-56 | Sunswift for 56 | 4 | 0 | 4 | 29 | 33 | 29 | FALSE
Sunswift-57 | Sunswift for 57 | 4 | 0 | 4 | 29 | 33 | 29 | FALSE
Sunswift-66 | Sunswift for 66 | 4 | 0 | 4 | 51 | 55 | 51 | FALSE
Sunswift-67 | Sunswift for 67 | 4 | 0 | 4 | 51 | 55 | 51 | FALSE
Sunswift-70 | Sunswift for 70 | 4 | 0 | 4 | 27 | 31 | 27 | FALSE
Flaming River-85 | Flaming River for 85 | 4 | 0 | 4 | 27 | 31 | 27 | FALSE
Flaming River-86 | Flaming River for 86 | 4 | 0 | 4 | 25 | 29 | 25 | FALSE
Unknown-91 | Unknown for 91 | 4 | 0 | 4 | 31 | 35 | 31 | FALSE
Unknown-92 | Unknown for 92 | 4 | 0 | 4 | 31 | 35 | 31 | FALSE
Bride Racing-107 | Bride Racing for 107 | 1 | 0 | 1 | 29 | 30 | 29 | FALSE
Bride Racing-109 | Bride Racing for 109 | 1 | 0 | 1 | 33 | 34 | 33 | FALSE
Unknown-110 | Unknown for 110 | 1 | 0 | 1 | 37 | 38 | 37 | FALSE
Unknown-120 | Unknown for 120 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Unknown-121 | Unknown for 121 | 4 | 0 | 4 | 53 | 57 | 53 | FALSE
Ricardo-122 | Ricardo for 122 | 8 | 0 | 8 | 18 | 26 | 18 | FALSE
Ricardo-123 | Ricardo for 123 | 8 | 0 | 8 | 18 | 26 | 18 | FALSE
Ricardo-124 | Ricardo for 124 | 8 | 0 | 8 | 21 | 29 | 21 | FALSE
Ricardo-125 | Ricardo for 125 | 8 | 0 | 8 | 21 | 29 | 21 | FALSE
Sunswift-126 | Sunswift for 126 | 8 | 0 | 8 | 20 | 28 | 20 | FALSE
Sunswift-127 | Sunswift for 127 | 8 | 0 | 8 | 24 | 32 | 24 | FALSE
Sunswift-128 | Sunswift for 128 | 8 | 0 | 8 | 45 | 53 | 45 | FALSE
Sunswift-129 | Sunswift for 129 | 8 | 0 | 8 | 49 | 57 | 49 | FALSE
Sunswift-130 | Sunswift for 130 | 8 | 0 | 8 | 49 | 57 | 49 | FALSE
Sunswift-131 | Sunswift for 131 | 8 | 0 | 8 | 49 | 57 | 49 | FALSE
Sunswift-132 | Sunswift for 132 | 8 | 0 | 8 | 49 | 57 | 49 | FALSE
Sunswift-133 | Sunswift for 133 | 8 | 0 | 8 | 47 | 55 | 47 | FALSE
Sunswift-134 | Sunswift for 134 | 8 | 0 | 8 | 46 | 54 | 46 | FALSE
Sunswift-135 | Sunswift for 135 | 8 | 0 | 8 | 46 | 54 | 46 | FALSE
Sunswift-136 | Sunswift for 136 | 8 | 0 | 8 | 48 | 56 | 48 | FALSE
Sunswift-137 | Sunswift for 137 | 8 | 0 | 8 | 43 | 51 | 43 | FALSE
Sundrive, Corning, McCognaughy, REOO-142 | Sundrive, Corning, McCognaughy, REOO for 142 | 12 | 0 | 12 | 15 | 27 | 15 | FALSE
Sundrive, Corning, McCognaughy, REOO-143 | Sundrive, Corning, McCognaughy, REOO for 143 | 12 | 0 | 12 | 15 | 27 | 15 | FALSE
Sundrive, Corning, McCognaughy, REOO-144 | Sundrive, Corning, McCognaughy, REOO for 144 | 12 | 0 | 12 | 15 | 27 | 15 | FALSE
Coregas, Swagelok-168 | Coregas, Swagelok for 168 | 6 | 0 | 6 | 33 | 39 | 33 | FALSE
Swagelok-171 | Swagelok for 171 | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
Swagelok-172 | Swagelok for 172 | 6 | 0 | 6 | 53 | 59 | 53 | FALSE
Siltrax, Swagelok-173 | Siltrax, Swagelok for 173 | 6 | 0 | 6 | 53 | 59 | 53 | FALSE
Gas detection supplier (Honeywell/CityTech etc.)-175 | Gas detection supplier (Honeywell/CityTech etc.) for 175 | 10 | 0 | 10 | 49 | 59 | 49 | FALSE
Siltrax-176 | Siltrax for 176 | 6 | 0 | 6 | 53 | 59 | 53 | FALSE
Swagelok-178 | Swagelok for 178 | 6 | 0 | 6 | 53 | 59 | 53 | FALSE
External Supplier (TBA)-179 | External Supplier (TBA) for 179 | 10 | 0 | 10 | 49 | 59 | 49 | FALSE
External Supplier (TBA)-180 | External Supplier (TBA) for 180 | 16 | 0 | 16 | 43 | 59 | 43 | FALSE
Siltrax-181 | Siltrax for 181 | 6 | 0 | 6 | 28 | 34 | 28 | FALSE
Swagelok-184 | Swagelok for 184 | 6 | 0 | 6 | 53 | 59 | 53 | FALSE
Beswick, Swagelok-185 | Beswick, Swagelok for 185 | 8 | 0 | 8 | 51 | 59 | 51 | FALSE
Ballard or Intelligent Energy-187 | Ballard or Intelligent Energy for 187 | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
Adlink-190 | Adlink for 190 | 8 | 0 | 8 | 48 | 56 | 48 | FALSE
5 | ASSY - REAR CRASH STRUCTURE | 3 | 0 | 3 | 36 | 39 | 36 | FALSE
37 | ASSY - DOOR AUDIO - RH | 8 | 0 | 8 | 26 | 34 | 26 | FALSE
38 | ASSY - DOOR AUDIO - LH | 8 | 0 | 8 | 26 | 34 | 26 | FALSE
41 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS | 3 | 0 | 3 | 33 | 36 | 33 | FALSE
42 | ASSY - ACTIVE AERO MOTORS | 2 | 0 | 2 | 36 | 38 | 36 | FALSE
48 | ASSY - WINDSCREEN WIPER MOTOR | 2 | 0 | 2 | 37 | 39 | 37 | FALSE
60 | ASSY - FRONT WHEEL | 2 | 0 | 2 | 29 | 31 | 29 | FALSE
88 | ASSY - STEERING WHEEL PCB | 6 | 0 | 6 | 21 | 27 | 21 | FALSE
89 | ASSY - INTERIOR LIGHTS PCB | 6 | 0 | 6 | 33 | 39 | 33 | FALSE
90 | ASSY - REAR VISION CAMERA | 4 | 0 | 4 | 51 | 55 | 51 | FALSE
94 | ASSY - THROTTLE PEDAL | 1 | 0 | 1 | 31 | 32 | 31 | FALSE
95 | ASSY - BRAKE PEDAL | 1 | 0 | 1 | 31 | 32 | 31 | FALSE
99 | ASSY - SUN VISOR - LH | 3 | 0 | 3 | 52 | 55 | 52 | FALSE
100 | ASSY - SUN VISOR - RH | 3 | 0 | 3 | 52 | 55 | 52 | FALSE
102 | ASSY - CENTRAL DISPLAY | 2 | 0 | 2 | 51 | 53 | 51 | FALSE
104 | ASSY - HEADS-UP DISPLAY | 2 | 0 | 2 | 51 | 53 | 51 | FALSE
108 | ASSY - FRONT SEAT PASSENGER | 4 | 0 | 4 | 30 | 34 | 30 | FALSE
112 | ASSY - MOTOR UNIT - LH | 2 | 0 | 2 | 24 | 26 | 24 | FALSE
113 | ASSY - MOTOR UNIT - RH | 2 | 0 | 2 | 24 | 26 | 24 | FALSE
139 | ASSY - ONBOARD CHARGER INSTALLATION | 3 | 0 | 3 | 54 | 57 | 54 | FALSE
146 | Assy - Shingled Matrix Panels | 12 | 0 | 12 | 23 | 35 | 23 | FALSE
151 | ASSY - CENTRAL STOP LAMP | 3 | 0 | 3 | 43 | 46 | 43 | FALSE
155 | ASSY - HEADLIGHT/INDICATOR PCB - LH | 2 | 0 | 2 | 39 | 41 | 39 | FALSE
156 | ASSY - HEADLIGHT/INDICATOR PCB - RH | 2 | 0 | 2 | 39 | 41 | 39 | FALSE
157 | ASSY - SIDE INDICATOR EXTERIOR - LH | 3 | 0 | 3 | 31 | 34 | 31 | FALSE
158 | ASSY - SIDE INDICATOR EXTERIOR - RH | 3 | 0 | 3 | 31 | 34 | 31 | FALSE
159 | ASSY - HORN | 1 | 0 | 1 | 43 | 44 | 43 | FALSE
160 | ASSY - HORN PCB | 3 | 0 | 3 | 54 | 57 | 54 | FALSE
162 | ASSY - SENSOR MOTHERBOARD - FL | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
163 | ASSY - SENSOR MOTHERBOARD - FR | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
164 | ASSY - SENSOR MOTHERBOARD - BL | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
165 | ASSY - SENSOR MOTHERBOARD - BR | 12 | 0 | 12 | 47 | 59 | 47 | FALSE
166 | ASSY - SUBWOOFER | 3 | 0 | 3 | 36 | 39 | 36 | FALSE
169 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE | 0 | 0 | 0 | 39 | 39 | 39 | FALSE
189 | ASSY - INTRANET | 0 | 0 | 0 | 59 | 59 | 59 | FALSE
192 | ASSY - DOOR ACTUATOR BOARD - RH | 5 | 0 | 5 | 54 | 59 | 54 | FALSE
193 | ASSY - DOOR ACTUATOR BOARD - LH | 5 | 0 | 5 | 54 | 59 | 54 | FALSE
194 | ASSY - SIDE INDICATOR - LH | 4 | 0 | 4 | 31 | 35 | 31 | FALSE
195 | ASSY - SIDE INDICATOR - RH | 4 | 0 | 4 | 31 | 35 | 31 | FALSE
196 | ASSY - CENTRAL STOPLAMP | 3 | 0 | 3 | 52 | 55 | 52 | FALSE
9 | ASSY - THERMAL BOX | 6 | 3 | 9 | 3 | 9 | 0 | TRUE
29 | ASSY - DOOR LATCH - RH | 2 | 4 | 6 | 37 | 39 | 33 | FALSE
30 | ASSY - DOOR LATCH - LH | 2 | 4 | 6 | 37 | 39 | 33 | FALSE
31 | ASSY - DOOR HINGE - RH | 3 | 1 | 4 | 31 | 34 | 30 | FALSE
32 | ASSY - DOOR HINGE - LH | 3 | 1 | 4 | 31 | 34 | 30 | FALSE
39 | ASSY - ELECTRIC WINDOWS - LH | 2 | 4 | 6 | 32 | 34 | 28 | FALSE
40 | ASSY - ELECTRIC WINDOWS - RH | 2 | 4 | 6 | 32 | 34 | 28 | FALSE
45 | ASSY - WINDSCREEN WIPER | 3 | 4 | 7 | 56 | 59 | 52 | FALSE
46 | ASSY - WINDSCREEN WASHER | 2 | 4 | 6 | 57 | 59 | 53 | FALSE
70 | ASSY - REAR WHEEL | 2 | 4 | 6 | 31 | 33 | 27 | FALSE
86 | ASSY - STEERING RACK | 2 | 4 | 6 | 29 | 31 | 25 | FALSE
107 | ASSY - FRONT SEAT MOUNT DRIVER | 4 | 1 | 5 | 30 | 34 | 29 | FALSE
133 | ASSY - AUX BATTERY | 2 | 8 | 10 | 55 | 57 | 47 | FALSE
137 | ASSY - ECS MODULE | 3 | 8 | 11 | 51 | 54 | 43 | FALSE
142 | ASSY - SOLAR ROOF ARRAY | 8 | 12 | 20 | 27 | 35 | 15 | FALSE
143 | ASSY - SOLAR BOOT ARRAY | 8 | 12 | 20 | 27 | 35 | 15 | FALSE
144 | ASSY - SOLAR BONNET ARRAY | 8 | 12 | 20 | 27 | 35 | 15 | FALSE
43 | ASSY - ACTIVE AERO CONTROL PCB | 6 | 2 | 8 | 38 | 44 | 36 | FALSE
49 | ASSY - WINDSCREEN WIPER CONTROL PCB | 4 | 2 | 6 | 55 | 59 | 53 | FALSE
50 | ASSY - FRONT TOP WISHBONE - LH | 2 | 2 | 4 | 35 | 37 | 33 | FALSE
51 | ASSY - FRONT TOP WISHBONE - RH | 2 | 2 | 4 | 35 | 37 | 33 | FALSE
52 | ASSY - FRONT LOWER WISHBONE - LH | 2 | 2 | 4 | 35 | 37 | 33 | FALSE
53 | ASSY - FRONT LOWER WISHBONE - RH | 2 | 2 | 4 | 35 | 37 | 33 | FALSE
58 | ASSY - FRONT DAMPER - LH | 2 | 2 | 4 | 33 | 35 | 31 | FALSE
59 | ASSY - FRONT DAMPER - RH | 2 | 2 | 4 | 33 | 35 | 31 | FALSE
75 | ASSY - FRONT BRAKE DISC | 2 | 2 | 4 | 31 | 33 | 29 | FALSE
87 | ASSY - STEERING WHEEL | 4 | 6 | 10 | 27 | 31 | 21 | FALSE
191 | ASSY - STEERING WHEEL PCB CODE | 4 | 6 | 10 | 55 | 59 | 49 | FALSE
97 | ASSY - PEDAL PRESS SENSOR | 1 | 1 | 2 | 32 | 33 | 31 | FALSE
109 | ASSY - FRONT SEAT MOUNT PASSENGER | 4 | 4 | 8 | 34 | 38 | 30 | FALSE
116 | ASSY - INVERTER - LH | 2 | 2 | 4 | 32 | 34 | 30 | FALSE
122 | ASSY - GEARBOX - LH | 3 | 8 | 11 | 26 | 29 | 18 | FALSE
117 | ASSY - INVERTER - RH | 2 | 2 | 4 | 32 | 34 | 30 | FALSE
123 | ASSY - GEARBOX - RH | 3 | 8 | 11 | 26 | 29 | 18 | FALSE
161 | ASSY - DRIVE CONTROL UNIT | 12 | 2 | 14 | 44 | 56 | 42 | FALSE
138 | ASSY - ONBOARD CHARGING WIRING | 2 | 3 | 5 | 57 | 59 | 54 | FALSE
152 | ASSY - CENTRAL STOP LAMP PCB | 4 | 3 | 7 | 46 | 50 | 43 | FALSE
153 | ASSY - HEADLIGHT EXTERIOR - LH | 3 | 2 | 5 | 41 | 44 | 39 | FALSE
154 | ASSY - HEADLIGHT EXTERIOR - RH | 3 | 2 | 5 | 41 | 44 | 39 | FALSE
167 | ASSY - AUDIO CONTROL SYSTEM | 8 | 8 | 16 | 49 | 57 | 41 | FALSE
168 | ASSY - PRESSURE VESSEL SHELL | 0 | 6 | 6 | 39 | 39 | 33 | FALSE
91 | ASSY - SIDE CAMERA - LH | 6 | 4 | 10 | 35 | 41 | 31 | FALSE
92 | ASSY - SIDE CAMERA - RH | 6 | 4 | 10 | 35 | 41 | 31 | FALSE
197 | ASSY - CENTRAL STOPLAMP CASING | 4 | 3 | 7 | 55 | 59 | 52 | FALSE
198 | ASSY - CENTRAL STOPLAMP CONTROLLER | 3 | 3 | 6 | 56 | 59 | 53 | FALSE
8 | ASSY - HVAC BOX | 8 | 9 | 17 | 9 | 17 | 0 | TRUE
28 | ASSY - DOOR SHELL - LH | 3 | 8 | 11 | 34 | 37 | 26 | FALSE
27 | ASSY - DOOR SHELL - RH | 3 | 8 | 11 | 34 | 37 | 26 | FALSE
61 | ASSY - REAR TOP WISHBONE - LH | 2 | 6 | 8 | 37 | 39 | 31 | FALSE
62 | ASSY - REAR TOP WISHBONE - RH | 2 | 6 | 8 | 37 | 39 | 31 | FALSE
63 | ASSY - REAR LOWER WISHBONE - LH | 2 | 6 | 8 | 37 | 39 | 31 | FALSE
64 | ASSY - REAR LOWER WISHBONE - RH | 2 | 6 | 8 | 37 | 39 | 31 | FALSE
66 | ASSY - REAR UPRIGHT - LH | 2 | 6 | 8 | 55 | 57 | 49 | FALSE
67 | ASSY - REAR UPRIGHT - RH | 2 | 6 | 8 | 55 | 57 | 49 | FALSE
82 | ASSY - REAR BRAKE DISC | 2 | 6 | 8 | 33 | 35 | 27 | FALSE
106 | ASSY - FRONT SEAT DRIVER | 4 | 5 | 9 | 34 | 38 | 29 | FALSE
131 | ASSY - AUXILLARY POWER WIRING | 2 | 10 | 12 | 57 | 59 | 47 | FALSE
132 | ASSY - DC-DC CONVERTERS | 2 | 10 | 12 | 57 | 59 | 47 | FALSE
145 | ASSY - MC4 Cabling | 4 | 20 | 24 | 35 | 39 | 15 | FALSE
71 | ASSY - FRONT CALIPER - LH | 2 | 4 | 6 | 33 | 35 | 29 | FALSE
72 | ASSY - FRONT CALIPER - RH | 2 | 4 | 6 | 33 | 35 | 29 | FALSE
56 | ASSY - FRONT UPRIGHT - LH | 2 | 4 | 6 | 33 | 35 | 29 | FALSE
57 | ASSY - FRONT UPRIGHT - RH | 2 | 4 | 6 | 33 | 35 | 29 | FALSE
85 | ASSY - STEERING COLUMN | 2 | 10 | 12 | 31 | 33 | 21 | FALSE
103 | ASSY - DRIVER DISPLAY | 2 | 10 | 12 | 51 | 53 | 41 | FALSE
96 | ASSY - PEDAL BOX CONTROLLER | 2 | 2 | 4 | 33 | 35 | 31 | FALSE
111 | ASSY - FRONT SEAT BELT PASSENGER | 1 | 8 | 9 | 38 | 39 | 30 | FALSE
118 | ASSY - INVERTER MOUNTING FRAME - LH | 6 | 4 | 10 | 53 | 59 | 49 | FALSE
120 | ASSY - PWT HV WIRING - LH | 2 | 4 | 6 | 57 | 59 | 53 | FALSE
114 | ASSY - MOTOR MOUNTING FRAME - LH | 6 | 11 | 17 | 29 | 35 | 18 | FALSE
124 | ASSY - AXLE CV - LH | 6 | 11 | 17 | 29 | 35 | 18 | FALSE
119 | ASSY - INVERTER MOUNTING FRAME - RH | 6 | 4 | 10 | 53 | 59 | 49 | FALSE
121 | ASSY - PWT HV WIRING - RH | 2 | 4 | 6 | 57 | 59 | 53 | FALSE
115 | ASSY - MOTOR MOUNTING FRAME - RH | 6 | 11 | 17 | 29 | 35 | 18 | FALSE
125 | ASSY - AXLE CV - RH | 6 | 11 | 17 | 29 | 35 | 18 | FALSE
190 | ASSY - MAIN COMPUTER | 1 | 14 | 15 | 56 | 57 | 42 | FALSE
171 | ASSY - PRESSURE REGULATION & SAFETY | 0 | 12 | 12 | 59 | 59 | 47 | FALSE
147 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH | 3 | 10 | 13 | 41 | 44 | 31 | FALSE
148 | ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH | 3 | 10 | 13 | 41 | 44 | 31 | FALSE
10 | ASSY - HVAC PIPING | 7 | 17 | 24 | 17 | 24 | 0 | TRUE
34 | ASSY - DOOR CONTROL BOARD - LH | 5 | 11 | 16 | 54 | 59 | 43 | FALSE
14 | ASSY - REAR QUARTER PANEL - LH | 2 | 11 | 13 | 37 | 39 | 26 | FALSE
33 | ASSY - DOOR CONTROL BOARD - RH | 5 | 11 | 16 | 54 | 59 | 43 | FALSE
15 | ASSY - REAR QUARTER PANEL - RH | 2 | 11 | 13 | 37 | 39 | 26 | FALSE
68 | ASSY - REAR DAMPER - LH | 2 | 8 | 10 | 57 | 59 | 49 | FALSE
69 | ASSY - REAR DAMPER - RH | 2 | 8 | 10 | 57 | 59 | 49 | FALSE
78 | ASSY - REAR BRAKE CALIPER - LH | 2 | 8 | 10 | 35 | 37 | 27 | FALSE
79 | ASSY - REAR BRAKE CALIPER - RH | 2 | 8 | 10 | 35 | 37 | 27 | FALSE
84 | ASSY - HAND BRAKE | 2 | 8 | 10 | 35 | 37 | 27 | FALSE
105 | ASSY - FRONT SEAT RAIL DRIVER | 4 | 9 | 13 | 55 | 59 | 46 | FALSE
110 | ASSY - FRONT SEAT BELT DRIVER | 1 | 9 | 10 | 38 | 39 | 29 | FALSE
141 | ASSY - MPPT | 4 | 24 | 28 | 39 | 43 | 15 | FALSE
54 | ASSY - FRONT TIEROD - LH | 2 | 6 | 8 | 35 | 37 | 29 | FALSE
55 | ASSY - FRONT TIEROD - RH | 2 | 6 | 8 | 35 | 37 | 29 | FALSE
3 | ASSY - STEERING COLUMN MOUNT | 2 | 12 | 14 | 37 | 39 | 25 | FALSE
4 | ASSY - FRONT CRASH STRUCTURE | 4 | 12 | 16 | 33 | 37 | 21 | FALSE
93 | ASSY - PEDAL BOX | 2 | 4 | 6 | 35 | 37 | 31 | FALSE
7 | ASSY - CHASSIS SUBFRAME | 4 | 17 | 21 | 35 | 39 | 18 | FALSE
149 | ASSY - TAILLIGHT/INDICATOR PCB - LH | 6 | 13 | 19 | 44 | 50 | 31 | FALSE
150 | ASSY - TAILLIGHT/INDICATOR PCB - RH | 6 | 13 | 19 | 44 | 50 | 31 | FALSE
11 | ASSY - FRONT FLUID MANAGEMENT | 4 | 24 | 28 | 24 | 28 | 0 | TRUE
24 | ASSY - OUTER DOOR HANDLE - LH | 2 | 13 | 15 | 57 | 59 | 44 | FALSE
13 | ASSY - REAR BUMPER | 6 | 13 | 19 | 39 | 45 | 26 | FALSE
23 | ASSY - OUTER DOOR HANDLE - RH | 2 | 13 | 15 | 57 | 59 | 44 | FALSE
140 | ASSY - MPPT JUNCTION BOX | 2 | 28 | 30 | 52 | 54 | 24 | FALSE
1 | ASSY - OCCUPANT CELL SPIDER | 5 | 28 | 33 | 43 | 48 | 15 | FALSE
74 | ASSY - FRONT MASTER CYLINDER | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
76 | ASSY - FRONT BRAKE LINE | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
77 | ASSY CHASSIS BRAKE LINE | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
80 | ASSY - REAR MASTER CYLINDER | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
81 | ASSY - REAR MASTER CYLINDER RESERVOIR | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
83 | ASSY - REAR BRAKE LINE | 2 | 16 | 18 | 37 | 39 | 21 | FALSE
6 | ASSY - CHASSIS VENTILATION | 8 | 28 | 36 | 36 | 44 | 8 | FALSE
126 | ASSY - BATTERY MODULES | 4 | 28 | 32 | 28 | 32 | 0 | TRUE
98 | ASSY - CEILING | 4 | 33 | 37 | 55 | 59 | 22 | FALSE
44 | ASSY - WINDSCREEN | 3 | 33 | 36 | 56 | 59 | 23 | FALSE
47 | ASSY - WINDSCREEN WIPER AERO GUARD | 3 | 33 | 36 | 48 | 51 | 15 | FALSE
127 | ASSY - BATTERY PACK | 2 | 32 | 34 | 32 | 34 | 0 | TRUE
128 | ASSY - BMS WIRING | 3 | 34 | 37 | 53 | 56 | 19 | FALSE
129 | ASSY - BATTERY HV WIRING | 2 | 34 | 36 | 57 | 59 | 23 | FALSE
130 | ASSY - BATTERY LV WIRING | 2 | 34 | 36 | 57 | 59 | 23 | FALSE
134 | ASSY - ECS HV WIRING | 2 | 34 | 36 | 54 | 56 | 20 | FALSE
135 | ASSY - ECS LV WIRING | 2 | 34 | 36 | 54 | 56 | 20 | FALSE
181 | ASSY - FUEL CELL STACK | 0 | 34 | 34 | 34 | 34 | 0 | TRUE
136 | ASSY - CONTROL LOGIC | 3 | 37 | 40 | 56 | 59 | 19 | FALSE
182 | ASSY - HYDROGEN COOLING SYSTEM | 0 | 34 | 34 | 34 | 34 | 0 | TRUE
170 | ASSY - HYDROGEN COMPARTMENT STRUCTURE | 0 | 34 | 34 | 39 | 39 | 5 | FALSE
172 | ASSY - HYDROGEN SUPPLY LINE | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
12 | ASSY - REAR FLUID MANAGEMENT | 5 | 34 | 39 | 34 | 39 | 0 | TRUE
174 | ASSY - HYDROGEN COMPARTMENT VENTILATION | 0 | 34 | 34 | 39 | 39 | 5 | FALSE
175 | ASSY - OCCUPANT CELL HYDROGEN SENSOR | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
173 | ASSY - HYDROGEN PURGE MANAGEMENT | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
2 | ASSY - OCCUPANT CELL TUB | 5 | 39 | 44 | 39 | 44 | 0 | TRUE
186 | ASSY - REARWHEEL HUB AIR INTAKE | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
183 | ASSY - FUEL CELL ELECTRICAL CONNECTIONS | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
176 | ASSY - P&ID HYDROGEN RECYCLE STREAM | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
184 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
16 | ASSY - FRONT CLAM SHELL | 7 | 44 | 51 | 44 | 51 | 0 | TRUE
17 | ASSY - REAR FLOOR | 3 | 44 | 47 | 47 | 50 | 3 | FALSE
18 | ASSY - REAR SUPPORT STRUCTURE | 5 | 44 | 49 | 45 | 50 | 1 | FALSE
35 | ASSY - DOOR CARD - RH | 3 | 44 | 47 | 50 | 53 | 6 | FALSE
36 | ASSY - DOOR CARD - LH | 3 | 44 | 47 | 50 | 53 | 6 | FALSE
65 | ASSY - REAR TOELINK | 2 | 44 | 46 | 57 | 59 | 13 | FALSE
73 | ASSY - FRONT MASTER CYLINDER RESERVOIR | 2 | 44 | 46 | 57 | 59 | 13 | FALSE
179 | ASSY - HYDROGEN SENSOR ARRAY | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
185 | ASSY - P&ID AIR SUPPLY LINE | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
21 | ASSY - BONNET | 4 | 51 | 55 | 51 | 55 | 0 | TRUE
19 | ASSY - BOOT | 5 | 49 | 54 | 50 | 55 | 1 | FALSE
25 | ASSY - INNER DOOR HANDLE - RH | 2 | 47 | 49 | 57 | 59 | 10 | FALSE
26 | ASSY - INNER DOOR HANDLE - LH | 2 | 47 | 49 | 57 | 59 | 10 | FALSE
101 | ASSY - DASHBOARD STRUCTURE | 6 | 47 | 53 | 53 | 59 | 6 | FALSE
177 | ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
180 | ASSY - HYDROGEN CONTROL LOGIC | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
22 | ASSY - BONNET LOCKING BOARD | 4 | 55 | 59 | 55 | 59 | 0 | TRUE
20 | ASSY - BOOT LOCKING BOARD | 4 | 54 | 58 | 55 | 59 | 1 | FALSE
188 | ASSY - INTERNAL EMBEDDED NETWORK WIRING | 2 | 55 | 57 | 57 | 59 | 2 | FALSE
178 | ASSY - OCCUPANT CELL SHUTDOWN VALVE | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
187 | ASSY - HYDROGEN CONTROL SYSTEM | 0 | 34 | 34 | 59 | 59 | 25 | FALSE
199 | Sink | 0 | 59 | 59 | 59 | 59 | 0 | TRUE

## Critical_and_Disjoint_Paths
Path_ID | Task_IDs | Descriptions | Total_Duration | Is_Critical
b871a2e1-96fc-464a-8a39-53f96ad044ce | 9,8,10,11,126,127,181,182,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 59 | TRUE
99bbc5d6-4107-4632-8a32-0f29f8ffa1cc | 162 | ASSY - SENSOR MOTHERBOARD - FL (12) | 12 | FALSE
3d4fa973-5507-4785-9ea7-a8c0745a8d8e | 163 | ASSY - SENSOR MOTHERBOARD - FR (12) | 12 | FALSE
47b9e161-d282-4e1b-8805-f6a419a832ec | 164 | ASSY - SENSOR MOTHERBOARD - BL (12) | 12 | FALSE
f7abc0c2-dd9d-4016-9dba-8eb0b4000959 | 165 | ASSY - SENSOR MOTHERBOARD - BR (12) | 12 | FALSE
0c5c7d14-ffe7-4438-9116-2892ef97551b | 189 | ASSY - INTRANET (0) | 0 | FALSE
8a2dc806-aba0-4287-ac04-f02b2f8dd2b6 | 192 | ASSY - DOOR ACTUATOR BOARD - RH (5) | 5 | FALSE
28b50c04-0690-4688-907e-87a091bd387b | 193 | ASSY - DOOR ACTUATOR BOARD - LH (5) | 5 | FALSE
08a1c759-fa60-4d53-8add-367abbf12912 | 48,49 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - WINDSCREEN WIPER CONTROL PCB (4) | 6 | FALSE
a8b21f31-1134-4849-b11d-eda73b7fdce2 | 60,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
0cb54f89-dc7e-496c-a90d-55ed690f0c81 | 89,98 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - CEILING (4) | 10 | FALSE
48fc2baf-1e42-4b77-8172-62993f2378aa | 102,101 | ASSY - CENTRAL DISPLAY (2) -> ASSY - DASHBOARD STRUCTURE (6) | 8 | FALSE
785107ef-5a9a-4893-b522-15cc3424bd56 | 112,118 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER MOUNTING FRAME - LH (6) | 8 | FALSE
8d0c36cc-cc4c-46e9-95a1-b4296aba617c | 113,119 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER MOUNTING FRAME - RH (6) | 8 | FALSE
6b79cdbb-a838-43ca-9b29-5d35e19eb4aa | 139,138 | ASSY - ONBOARD CHARGER INSTALLATION (3) -> ASSY - ONBOARD CHARGING WIRING (2) | 5 | FALSE
1ee93b97-8cc1-4ba1-8852-28e162cc98f8 | 5,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
50dbe411-6dd0-49cc-b672-6f8a71845a95 | 88,191 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL PCB CODE (4) | 10 | FALSE
6058bd08-b559-4e60-b331-ea96bcf04b6e | 196,197 | ASSY - CENTRAL STOPLAMP (3) -> ASSY - CENTRAL STOPLAMP CASING (4) | 7 | FALSE
ae1dfc3f-b28d-4063-82ba-b737a928845e | 37,27,33 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 16 | FALSE
21f74590-efef-4787-97cf-2cbb4bd8578f | 38,28,34 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 16 | FALSE
daa3ffad-65cc-4940-a013-51dfbad5e1bb | 108,2,65 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
d678871b-4087-4caf-a017-08b635c31ecc | 146,19,20 | Assy - Shingled Matrix Panels (12) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
0bb1e471-1df5-4f30-a9e9-0e663fb855a4 | 41,16,21,22 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 18 | FALSE
c52a4ba7-560d-4758-a1ae-b8e373ec3531 | 169,170,175,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE

## All_Paths
Path_ID | Task_IDs | Descriptions | Total_Duration | Is_Critical
bbd1ac46-f8e2-4265-939b-cebc545e4a34 | 7,2,16,21,22 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
47cb1d93-23c4-49fb-8ee9-19518a0e07a7 | 7,2,16,21,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
345f8d09-480a-48dc-93de-bd54b64ff238 | 7,2,16,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
be02d2d9-06bd-46c9-a608-a31119472798 | 7,2,17,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
9b72712b-7965-4b46-9c78-5e7e422900a7 | 7,2,17,19,20 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6ecf36be-3652-4dad-97ca-b9699794bfa7 | 7,2,17,19,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
877a418a-9ffc-4417-8597-f7df6b2a9c38 | 7,2,18,19,20 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2d0fb5c3-5b2b-4297-adc2-9418d0269f10 | 7,2,18,19,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3c1535af-af81-4a77-a6dc-f10c602d738c | 7,2,18,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a46f8594-5d7b-471f-a08c-0f14b88c080a | 7,2,35,25 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
aeea9edc-256f-4f36-8a19-55113ec0b0e1 | 7,2,35,101 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
846c1eb8-c07f-4c25-aa82-271d71d87f34 | 7,2,36,26 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
3dd68d4b-e30a-48ba-9d9e-4c632195d8bb | 7,2,36,101 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4573a442-42d7-4a56-bece-14da9d1b526b | 7,2,65 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
4d6bf304-023a-4d05-8a4f-5479cfa9c312 | 7,2,73 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
8e320ef7-c2a6-4cc5-9cd0-2eb3fd2557d0 | 7,2,101 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
35b8eb95-6ae0-4b07-a184-929d636ba8fa | 7,2,188 | ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
3b145614-ee8c-47c0-95cc-806bab4a71ad | 9,8,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 34 | FALSE
e88a9eff-92dc-48a0-9a6f-4a70c5fc27ca | 9,8,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
70ddff05-c226-4cf5-9a70-0007a188b37f | 9,8,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
dd29f42a-5de8-433b-8aba-65318659d059 | 9,8,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
545854d9-24ff-4155-b93c-a299b522c0b0 | 9,8,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
4632ee1d-7c12-424c-860d-6d77b1985cad | 9,8,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
2459b9ab-3425-4a4c-859a-75c381a2e83c | 9,8,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
6387c805-f309-40e8-a015-26fe8169a8e9 | 9,8,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
c9992148-c8cb-4ecf-b62a-e00a11ecaab7 | 9,8,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0824e28a-ccf9-4f1b-a033-482f659c96e4 | 9,8,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 24 | FALSE
52c62f40-459b-44da-a243-93b31d0063f1 | 9,8,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
f6d62e65-12fe-4fd1-a812-13433e07fe97 | 9,8,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 24 | FALSE
3aef0dca-8eda-4882-9ee7-837f8f77c143 | 9,8,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
149d5428-5953-4e6b-b25f-0dee22f78a5c | 9,8,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 21 | FALSE
8b012b92-df3f-4b48-97d3-1752af76d4ab | 9,8,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 21 | FALSE
5296dcdf-fd98-4bdb-b9ba-2e636be7a64c | 9,8,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
2a8984aa-9dbe-4ed0-8f12-31d86426d20a | 9,8,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
716666a7-58b2-4927-b13d-e0030cc036dc | 9,8,10,11,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 45 | FALSE
62682f27-ec99-45d2-ac4e-1e8eca02f381 | 9,8,10,11,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
eba15c5e-c00e-43d0-9325-e53fbea11189 | 9,8,10,11,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
72ef98b8-089d-4ba7-9961-7dbf7e6c88e8 | 9,8,10,11,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
93eff171-e367-4299-8ecd-f03a73b25073 | 9,8,10,11,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 42 | FALSE
001f9257-9c47-46ca-8ef2-311bef754db5 | 9,8,10,11,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
18e33725-8681-407d-b742-68902f389d26 | 9,8,10,11,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 44 | FALSE
ed89b78b-58d5-4644-8689-fd95a16ecd47 | 9,8,10,11,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 42 | FALSE
ecf10070-eb2d-4083-acf6-1ac6d10651f8 | 9,8,10,11,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
e5362ce4-f416-4777-aca1-7ab516c9f3cd | 9,8,10,11,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 35 | FALSE
6455e089-4118-425a-89b8-f2a07ea15b1d | 9,8,10,11,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 39 | FALSE
ccbc24e3-682c-49f9-9256-96147bd00b85 | 9,8,10,11,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 35 | FALSE
16f67f2d-0240-40ca-933b-4097068e73cf | 9,8,10,11,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 39 | FALSE
a75de4cb-9edf-4025-92ed-be5c1a9194d6 | 9,8,10,11,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 32 | FALSE
668a60f6-2318-4215-b9fd-c60217067938 | 9,8,10,11,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 32 | FALSE
f70b1f26-555b-4669-8f65-de4e234aa243 | 9,8,10,11,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
7efdaf3e-ab07-49c6-b06e-dca49b5e70f4 | 9,8,10,11,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
0ff2a87c-7eda-4916-a445-b4eacee9f4a6 | 9,8,10,11,6,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 48 | FALSE
bae30141-703d-4f7f-93fc-dc39355850c8 | 9,8,10,11,6,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
478c4bec-8d6a-4b38-9028-1dc3e8f17f9d | 9,8,10,11,6,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 42 | FALSE
f2d71139-0eae-465f-b6f4-83f0c756e53e | 9,8,10,11,6,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
2144a0ce-06f6-4a36-bea7-87d6d0b07d6b | 9,8,10,11,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 50 | FALSE
f684bbed-f1bf-402b-bdaa-b7a1dd16f34b | 9,8,10,11,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 48 | FALSE
04b03693-09b8-4391-8896-7cbf302b364b | 9,8,10,11,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 44 | FALSE
ebedc654-3392-4d51-8831-809618e6b1e4 | 9,8,10,11,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
df9e3a0b-530e-43e2-bdfe-8c4711987272 | 9,8,10,11,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 47 | FALSE
6af5c9b5-9527-468d-b8d8-f3d72ee052f4 | 9,8,10,11,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 45 | FALSE
804889ec-5628-4eb5-b69c-1c3a46be2446 | 9,8,10,11,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 49 | FALSE
159c004c-8824-4991-b7cb-86541c3c1c2b | 9,8,10,11,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 47 | FALSE
0ebc9d3a-d39f-4cd7-8924-b3098086902a | 9,8,10,11,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 42 | FALSE
5339e067-9a72-41c3-a854-a573bff0332e | 9,8,10,11,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 40 | FALSE
29fb1ea2-6ead-4051-a978-e115b045bb26 | 9,8,10,11,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 44 | FALSE
9f539786-93f8-4866-81ff-38b9d431fa45 | 9,8,10,11,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 40 | FALSE
8fbcb593-491b-4f04-b0ba-23eb84652d13 | 9,8,10,11,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 44 | FALSE
52c3b5cd-6891-435d-a13c-83c57ac2ca07 | 9,8,10,11,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 37 | FALSE
c8510ede-3d42-426d-b0d7-54e4371330e5 | 9,8,10,11,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 37 | FALSE
139c64f5-f293-465b-9435-b75a2615365c | 9,8,10,11,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 41 | FALSE
321480f0-1f89-477c-97a6-8ea0140ddb52 | 9,8,10,11,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
4fb24eda-fe78-4f61-96a5-a3748dbbd81f | 9,8,10,11,126,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 49 | FALSE
f23aefd8-5517-4a73-a3de-838a30b90579 | 9,8,10,11,126,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 47 | FALSE
588536cb-be42-4b99-a35c-2a8b19c8087f | 9,8,10,11,126,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
95b7b32d-a11f-49c2-abe9-a558442a777d | 9,8,10,11,126,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
614f9259-6217-48fc-b84d-21871b1ab867 | 9,8,10,11,126,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 46 | FALSE
d0e8aabd-75b8-48db-9f38-8dd177c49431 | 9,8,10,11,126,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 44 | FALSE
f487544e-1b99-4d3c-aba9-8b1061f5aa22 | 9,8,10,11,126,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 48 | FALSE
4e88476b-bb00-4781-a11a-7c82f990b7a3 | 9,8,10,11,126,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
aad511c1-0670-418a-a2f8-1a14627f00cd | 9,8,10,11,126,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
afa051c9-79df-4cdc-ac3d-9e612000a8ba | 9,8,10,11,126,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 39 | FALSE
fc04ae36-7741-4801-bff2-a94537235d35 | 9,8,10,11,126,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 43 | FALSE
84dc48b1-e407-4411-9ed4-a8542a5332cc | 9,8,10,11,126,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 39 | FALSE
719df18e-e464-4cd4-85d7-8fa8930ebca8 | 9,8,10,11,126,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 43 | FALSE
3df15104-5e6b-4a77-b8cd-f49c4e5c1157 | 9,8,10,11,126,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 36 | FALSE
6127a11f-e883-4f3e-908e-d093613b8892 | 9,8,10,11,126,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 36 | FALSE
21d714d6-62c3-473a-8baf-3aab3f68854b | 9,8,10,11,126,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 40 | FALSE
65ead528-4d11-4fc9-9ff4-030e1c638f50 | 9,8,10,11,126,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
329642d6-fd66-4d7a-b370-5e137379d182 | 9,8,10,11,126,127,128,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 37 | FALSE
da6f74eb-2dc1-465b-a10d-df1b61104126 | 9,8,10,11,126,127,129 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 33 | FALSE
d55423da-3ac7-4f6a-93d2-e0ebb431fa6b | 9,8,10,11,126,127,130 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 33 | FALSE
30a289a8-fe9f-4d9f-b325-b4c24b048a89 | 9,8,10,11,126,127,134,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 36 | FALSE
2e5b4bfa-1af6-4270-bd2e-a63bd16f0408 | 9,8,10,11,126,127,135,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 36 | FALSE
881fd556-821b-40cc-97a2-1c51f9ae79ab | 9,8,10,11,126,127,181,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
0a309885-823e-44bd-bbd3-ff69015036da | 9,8,10,11,126,127,181,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
3a58ce97-d0f0-43b7-af59-b4aed6388830 | 9,8,10,11,126,127,181,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
06de577d-426e-455a-9b3f-af776fcd7430 | 9,8,10,11,126,127,181,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
8c2e1578-206e-476a-b5d5-ac897d641505 | 9,8,10,11,126,127,181,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
6a531137-493b-485a-9021-d5c6a92fe600 | 9,8,10,11,126,127,181,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
e16f695b-5930-4742-a247-6a080802ddbd | 9,8,10,11,126,127,181,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
9b8e8304-6d16-476d-adcd-4ed1bf6e1606 | 9,8,10,11,126,127,181,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
2a9c66f2-da2f-4029-a25b-31f6b7fddb85 | 9,8,10,11,126,127,181,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
f2f66a0e-9d6b-4b79-96af-392b3dfde309 | 9,8,10,11,126,127,181,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
981f3549-3adc-4000-8b53-e26ef4339f9e | 9,8,10,11,126,127,181,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
9790880d-85cd-481b-8296-ab0254f01f14 | 9,8,10,11,126,127,181,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
b17a9b11-70ce-49a9-afad-f6a3cee82199 | 9,8,10,11,126,127,181,182,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 56 | FALSE
92b39191-ddb6-43ce-a66e-2ecd62eaa252 | 9,8,10,11,126,127,181,182,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 54 | FALSE
4dec0837-cc84-483a-b3b0-2c27a6e6b3b3 | 9,8,10,11,126,127,181,182,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 50 | FALSE
5cc63113-803b-46bc-9a9a-72987fd8b195 | 9,8,10,11,126,127,181,182,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
3a98e083-9fac-4c34-9fb7-919c417f71e6 | 9,8,10,11,126,127,181,182,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 53 | FALSE
e3f5b2a2-26d4-41e1-8e93-3a3ec9107173 | 9,8,10,11,126,127,181,182,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 51 | FALSE
e4598ac4-7fd5-42b4-92ad-4303e5e00cb6 | 9,8,10,11,126,127,181,182,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 55 | FALSE
e401433b-b472-474e-ab41-4bf03907bb90 | 9,8,10,11,126,127,181,182,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 53 | FALSE
195259c6-4a98-4d73-a533-da73c651992d | 9,8,10,11,126,127,181,182,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 48 | FALSE
948d98c4-9a23-43c4-97df-e83916fc08b7 | 9,8,10,11,126,127,181,182,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 46 | FALSE
3845862a-1699-4506-90e0-54fd53183671 | 9,8,10,11,126,127,181,182,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 50 | FALSE
8376ff28-0dca-4436-aefd-332c3da2bb31 | 9,8,10,11,126,127,181,182,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 46 | FALSE
e877b729-4d30-4a2a-9d23-cd9652078598 | 9,8,10,11,126,127,181,182,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 50 | FALSE
2ee7c7ee-3cb1-41b6-847e-86df386fe2b4 | 9,8,10,11,126,127,181,182,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 43 | FALSE
d03a7529-0bdb-4921-8390-650920886445 | 9,8,10,11,126,127,181,182,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 43 | FALSE
ca0824cd-3799-43c8-b639-ef2fe033035d | 9,8,10,11,126,127,181,182,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 47 | FALSE
287000c6-b644-4f86-881c-088f1c2bf44a | 9,8,10,11,126,127,181,182,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
53576b6d-fb64-4092-9248-e41e6e03582b | 9,8,10,11,126,127,181,182,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
efee69e1-b337-4075-8718-740a548970d3 | 9,8,10,11,126,127,181,182,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
a68e83ff-cdee-49cf-a08b-e88cc263777a | 9,8,10,11,126,127,181,182,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
3208a096-12ac-424c-bdbf-7cf02124a0b9 | 9,8,10,11,126,127,181,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
cdeef6d7-f42e-44b7-a2fd-0e7627e66721 | 9,8,10,11,126,127,181,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
edbc701d-e552-4dbd-974f-36b4e4f41ea5 | 9,8,10,11,126,127,181,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
40817663-09c7-40f1-9610-111ce7a4d589 | 9,8,10,11,126,127,181,170,174,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 51 | FALSE
3e6b5ac7-8490-4b4b-8fc6-a0347d516bb4 | 9,8,10,11,126,127,181,170,174,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 49 | FALSE
f91b4b06-5638-408b-9be8-c7eaa8fb7f65 | 9,8,10,11,126,127,181,170,174,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 45 | FALSE
0e027690-c284-44da-bdbe-39b95daba240 | 9,8,10,11,126,127,181,170,174,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
575be695-dccb-4775-aedd-9d09604bedd9 | 9,8,10,11,126,127,181,170,174,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 48 | FALSE
77c1573b-de53-4632-a478-c90272a0d47e | 9,8,10,11,126,127,181,170,174,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
498406b5-6ec8-4ebe-918e-0ed5bb8874ca | 9,8,10,11,126,127,181,170,174,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 50 | FALSE
a766ad1b-e465-48a1-acaf-8fb502e708bd | 9,8,10,11,126,127,181,170,174,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 48 | FALSE
37aff1d9-b135-4812-bbe4-7df8689788d0 | 9,8,10,11,126,127,181,170,174,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
e66bded7-9815-42de-996a-ec55992d51d4 | 9,8,10,11,126,127,181,170,174,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 41 | FALSE
97f597b8-3838-4036-9333-fa980a091865 | 9,8,10,11,126,127,181,170,174,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 45 | FALSE
a4bd8e57-5e91-481a-a5d4-fffba403e31f | 9,8,10,11,126,127,181,170,174,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 41 | FALSE
228a75ff-e334-4638-90df-fd33cc225528 | 9,8,10,11,126,127,181,170,174,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 45 | FALSE
7ab38143-79d5-44c3-b55f-daecff5bd891 | 9,8,10,11,126,127,181,170,174,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 38 | FALSE
ab093c7f-2cb9-496c-9dea-9bafc2a9be68 | 9,8,10,11,126,127,181,170,174,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 38 | FALSE
1d64b244-16cc-45d2-9f7e-7f111dcb1c27 | 9,8,10,11,126,127,181,170,174,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 42 | FALSE
fc717184-b32a-492a-a5fa-7eaad154aa6d | 9,8,10,11,126,127,181,170,174,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
f0abbba8-ae15-42dd-a5ed-6b61762dbf59 | 9,8,10,11,126,127,181,170,174,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
37451e31-9519-46d1-bab8-853ccf76a8c7 | 9,8,10,11,126,127,181,170,174,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
ecc760ef-320b-4f74-8818-27462be54fe4 | 9,8,10,11,126,127,181,170,174,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
13247892-7301-443a-98ce-9e56e8b1b11c | 9,8,10,11,126,127,181,170,174,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
2e9bdf30-de19-4057-99bb-0a45ec008f32 | 9,8,10,11,126,127,181,170,175,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
aad57ba5-0578-40df-b903-fe0285f96625 | 9,8,10,11,126,127,181,170,175,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
f975439e-803c-474a-8593-7e9fb19a3a37 | 9,8,10,11,126,127,181,170,175,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
e6f00e6b-b300-4b0e-8ed6-05bbb4af55ab | 9,8,10,11,126,127,181,170,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
7e286be6-c847-4e5c-9c52-d5e7a520d021 | 9,8,10,11,126,127,181,170,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
2bfdb82e-a60f-47b2-a161-ca515f20bafa | 9,8,10,11,126,127,181,170,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
1ea29f6f-74d4-4901-b784-9580e6e3defc | 9,8,10,11,126,127,181,172,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
d12c13ee-8314-4895-8529-2ebcc8ca9f0a | 9,8,10,11,126,127,181,172,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
a2337631-3a87-4dbd-87b8-c2260ab05005 | 9,8,10,11,126,127,181,172,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
d6a58a5e-a87e-4496-9f0e-e8823bbccf05 | 9,8,10,11,126,127,181,172,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
c26a2409-2126-468f-9619-af1d2b6a9a51 | 9,8,10,11,126,127,181,172,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 31 | FALSE
599db48e-d76d-4381-bf8a-be394d89ecff | 9,8,10,11,126,127,181,172,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
50f2932c-03ac-4df3-8212-fa2df8360296 | 9,8,10,11,126,127,181,172,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
bd36bedf-2e61-4c7e-817a-cc05223c51b0 | 9,8,10,11,126,127,181,172,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 31 | FALSE
53e2f351-170c-4893-bae5-fd6f1020cb9b | 9,8,10,11,126,127,181,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 31 | FALSE
e977cf92-0abb-4dd2-8585-57243281abea | 9,8,11,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
f65d9287-2a54-4c09-bf0b-7a2ae87c760e | 9,8,11,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
33bb82e2-feca-433f-af58-d3f89224e63f | 9,8,11,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
32fcccbf-575d-446a-918f-65488e8b64aa | 9,8,11,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
7953f71e-f3e0-4b56-b1b9-6e74382f878c | 9,8,11,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
cdb617d2-cdf4-4046-9734-9b7d5767280d | 9,8,11,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
cf49bd3e-c087-40d9-9244-77c6bf1350ee | 9,8,11,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
52624c44-6ae9-4ecc-94a9-3ada365a1a51 | 9,8,11,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
bd3caa16-6d88-4ecc-98e8-531ddf31286a | 9,8,11,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
8aa74134-94c2-4eec-a9ee-f7640bbd3147 | 9,8,11,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
a3d93533-c61e-46c3-8081-4f19bbdf61d2 | 9,8,11,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
9308c4e7-37ca-44b6-9874-36cdc7292acc | 9,8,11,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
c1a1462c-1a12-4ded-b38f-c3b07755554a | 9,8,11,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
9022b304-caa1-459d-a2ae-1ec8a02670f3 | 9,8,11,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
8e907cec-dfcb-4582-a806-c4d9d8c15fd5 | 9,8,11,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
88df4f97-4e34-40eb-90dd-e031b6ff9036 | 9,8,11,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
f37ac9c9-4fb9-43c7-88d2-5b8ec6d35c2a | 9,8,11,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a30219a3-6373-40f7-a1ef-4cfed096e112 | 9,8,11,6,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 41 | FALSE
ee613410-d999-4983-aa02-e2fd41093244 | 9,8,11,6,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
a506cad2-843d-4b35-af2c-e13faf626cd3 | 9,8,11,6,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
a39938e2-0f26-4563-8bcb-104edaa68367 | 9,8,11,6,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
d780f200-61d4-4f14-8aa2-73ae059026b5 | 9,8,11,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 43 | FALSE
1dc5e5c1-92ac-4224-9b61-13126aba517f | 9,8,11,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
7ec19f10-c5a9-433a-b02d-a940c4e68762 | 9,8,11,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
221b6cf5-0af7-4e99-8da1-d49062d97717 | 9,8,11,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
70fffd8b-fb0f-44a6-8a8f-058247caf6b1 | 9,8,11,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 40 | FALSE
74f91263-8a7e-40db-9d5e-9c67f04784e6 | 9,8,11,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
f48c5de0-566c-4f76-b06a-4751fecb29a4 | 9,8,11,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 42 | FALSE
ce16d73d-a9ef-411b-9ea5-7354bc524f2a | 9,8,11,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
33005d94-db9d-4fd5-96ad-e4a51c442c87 | 9,8,11,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
2e743f59-8de4-4fbd-b910-a2b35c12f3ce | 9,8,11,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 33 | FALSE
cf917146-747a-4aa2-8ad2-3fb51b7de7c3 | 9,8,11,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 37 | FALSE
eb5c4ae5-9776-4130-9cdb-8d71dc1fd68a | 9,8,11,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 33 | FALSE
6e335b67-1a31-4666-976a-6ef448a0b135 | 9,8,11,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 37 | FALSE
534a35a5-c92f-4a6a-aa88-e85424633738 | 9,8,11,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 30 | FALSE
2a7ee259-42e2-4f41-a4a1-ed2dcd61f52c | 9,8,11,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 30 | FALSE
ab294871-b7cc-450b-b2a0-434a8dccc6f9 | 9,8,11,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 34 | FALSE
2b5ec541-ca1f-49dc-9bd2-507e600e5aff | 9,8,11,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
751b2830-44db-499a-a34b-75afce20c417 | 9,8,11,126,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 42 | FALSE
ef62de17-f9d8-41c4-a54f-61a14e166409 | 9,8,11,126,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
a162897b-07e2-4876-8d24-13b20d581384 | 9,8,11,126,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
69e9117b-5bd8-4add-aab2-dbc0ea94e2f3 | 9,8,11,126,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
cd4e6d7f-1aa4-4d99-b453-3c57d910d716 | 9,8,11,126,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 39 | FALSE
a8ee8d70-3ff2-43b3-ad29-caff96145458 | 9,8,11,126,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
b06dc0ce-2440-476a-ac5b-891f9e53f506 | 9,8,11,126,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 41 | FALSE
4e16bf6d-b322-4aef-9626-5452a72bf8af | 9,8,11,126,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
c50f18a9-10fb-4227-a286-f2411eab18b0 | 9,8,11,126,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
4e5dc4d2-9311-47bd-b7a7-478d8dd673da | 9,8,11,126,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 32 | FALSE
ba47cb6e-a3c3-4074-8d37-301d7e6b308e | 9,8,11,126,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
22c38dea-d0f2-4dcb-a491-058f5d1a7795 | 9,8,11,126,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 32 | FALSE
a913bd2c-68f9-4a5e-9d96-f0d350bdadf7 | 9,8,11,126,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
e832183d-8099-4565-ad75-36200c7eb90f | 9,8,11,126,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 29 | FALSE
ef0f8f75-3ec6-48d9-a7d0-02e5704d63b7 | 9,8,11,126,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 29 | FALSE
56b72812-8f05-427e-bd19-dd82a0a82545 | 9,8,11,126,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 33 | FALSE
25a24ac9-8084-4229-b759-9544505c4e0a | 9,8,11,126,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
126af87d-dca6-494d-a2cd-59421f21df3b | 9,8,11,126,127,128,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 30 | FALSE
786d820f-6704-4b1d-8775-759a3ff799aa | 9,8,11,126,127,129 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 26 | FALSE
6bd5f5f3-c88d-4ee4-b888-227950273136 | 9,8,11,126,127,130 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 26 | FALSE
c615fe54-24d1-43b0-8270-6cb79f2421b7 | 9,8,11,126,127,134,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 29 | FALSE
eaaae31a-d876-4ef6-af20-a0d0013dbdc5 | 9,8,11,126,127,135,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 29 | FALSE
538b5e32-d11f-47c6-8fe4-e64a71c82244 | 9,8,11,126,127,181,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
69dfb106-e3c2-4bde-a087-cec239d6731c | 9,8,11,126,127,181,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
8f3e7ab0-7827-40f2-8984-fae542008a80 | 9,8,11,126,127,181,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
8ee26bb6-f327-4707-9a16-a30f7a8af459 | 9,8,11,126,127,181,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
ed233ca8-d026-440f-994a-c020ed2ca15d | 9,8,11,126,127,181,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
f24fbffd-b731-4d9e-b9e0-e2300fc33a69 | 9,8,11,126,127,181,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
458361ed-b674-4dbc-8d5e-791eabb6019a | 9,8,11,126,127,181,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
2b0e1163-bfa0-4a1d-9747-ed75eeb4ae96 | 9,8,11,126,127,181,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
61e8f114-0cdc-4bb0-af35-f292cef8c2db | 9,8,11,126,127,181,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
92219120-6363-401a-b04b-680c7792fb01 | 9,8,11,126,127,181,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
65216b6c-a937-47b0-be7c-c9a4fe49db78 | 9,8,11,126,127,181,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
e2cba703-2016-4360-bc56-c322c9a2af1e | 9,8,11,126,127,181,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
66a631e7-3733-4335-be5a-075ba687db6e | 9,8,11,126,127,181,182,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 49 | FALSE
67f204b7-776c-4bfe-9132-564c0cb2e33c | 9,8,11,126,127,181,182,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 47 | FALSE
9489b9d4-6aaa-43a4-a201-ac79ae0c1e91 | 9,8,11,126,127,181,182,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
54ba5c23-fef7-4a18-83c2-b568d0cb9788 | 9,8,11,126,127,181,182,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
08ad3fed-0e0a-4f32-aefc-b31ae6776161 | 9,8,11,126,127,181,182,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 46 | FALSE
a723dc44-65d6-40b8-ab20-dd3e2a70f52a | 9,8,11,126,127,181,182,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 44 | FALSE
4815ad03-a3ee-4971-bc81-2a50811cc05f | 9,8,11,126,127,181,182,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 48 | FALSE
6c25f998-b7eb-4b74-bf5c-63c332330883 | 9,8,11,126,127,181,182,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
80038b25-37a0-47e7-b8cc-f391d2e02d2a | 9,8,11,126,127,181,182,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
62958771-6f32-41c2-8f46-1992223d7a88 | 9,8,11,126,127,181,182,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 39 | FALSE
8134e10b-f02a-44ba-b9c6-233cb2bb617d | 9,8,11,126,127,181,182,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 43 | FALSE
d351a29d-72e5-44f8-89d2-53c949628f51 | 9,8,11,126,127,181,182,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 39 | FALSE
cf100855-70fa-4aac-aec0-65e68ef47261 | 9,8,11,126,127,181,182,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 43 | FALSE
3924ee82-d823-429b-b82b-68201faae531 | 9,8,11,126,127,181,182,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 36 | FALSE
41275af1-a9cd-4d38-913d-c4ab44319177 | 9,8,11,126,127,181,182,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 36 | FALSE
aff4caef-6147-4ce7-a091-96cf5d3ce3fc | 9,8,11,126,127,181,182,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 40 | FALSE
5c869f6f-9c01-4c25-8f96-703569a71f32 | 9,8,11,126,127,181,182,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
fb747e98-f753-4634-a137-16ae177273cb | 9,8,11,126,127,181,182,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
9eb69c31-2b77-458d-b351-8ff57d6ffe5f | 9,8,11,126,127,181,182,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
292de234-dfec-4723-8691-d2fcab36a606 | 9,8,11,126,127,181,182,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
ba062cec-12ef-4e8e-83c2-068c22a93fd8 | 9,8,11,126,127,181,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
883700d1-88fc-44e2-a927-c83cfaea2f83 | 9,8,11,126,127,181,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
6a21cf8b-39c9-4a1b-b464-9d16a615698b | 9,8,11,126,127,181,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
937016a1-a3d0-49aa-bd22-a57be36a9e6d | 9,8,11,126,127,181,170,174,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 44 | FALSE
e53ef1c5-41c9-4a34-8c96-f428f686c6d2 | 9,8,11,126,127,181,170,174,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 42 | FALSE
f8c81445-34bd-4598-9cb4-7b852d55188e | 9,8,11,126,127,181,170,174,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
0b35bc30-fa74-4a15-ab6e-6296f4222909 | 9,8,11,126,127,181,170,174,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
9a5cf472-0899-42c3-839d-d32fed5b50ba | 9,8,11,126,127,181,170,174,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 41 | FALSE
afe21762-ff57-4d90-82f4-c9be708d430d | 9,8,11,126,127,181,170,174,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
676a1c89-ff9a-41dd-8c0b-03b449f920d3 | 9,8,11,126,127,181,170,174,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 43 | FALSE
70898e8e-1177-4fd5-9ca2-5e36e7b58f37 | 9,8,11,126,127,181,170,174,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
a758a7f6-ec35-46d9-99e7-9baeb4e4f425 | 9,8,11,126,127,181,170,174,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
ee60f833-8771-4f7d-a7e9-0911c01fb112 | 9,8,11,126,127,181,170,174,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 34 | FALSE
d79a7199-1ff3-4b1d-82fa-186768f38139 | 9,8,11,126,127,181,170,174,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 38 | FALSE
cd47f272-6324-48b5-b66b-e980f1251746 | 9,8,11,126,127,181,170,174,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 34 | FALSE
f4c817e9-e28c-4127-a5ed-a87eae2ed812 | 9,8,11,126,127,181,170,174,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 38 | FALSE
daa9f5d5-2bc3-42fa-a8b7-894fff47513d | 9,8,11,126,127,181,170,174,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 31 | FALSE
087a2f87-8bca-4c89-8de7-a96f77092ce3 | 9,8,11,126,127,181,170,174,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 31 | FALSE
aac96d2c-413f-4455-a7ba-1815b1c0297c | 9,8,11,126,127,181,170,174,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 35 | FALSE
95ff218b-2e3e-48c2-a64a-acea038af27c | 9,8,11,126,127,181,170,174,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
f37dbf74-931c-4254-8d89-d8c5fa2671cf | 9,8,11,126,127,181,170,174,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
5c595a87-5a50-43cb-a727-5c851096fa2d | 9,8,11,126,127,181,170,174,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
298a7197-00c2-44df-968c-fbec859d994f | 9,8,11,126,127,181,170,174,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
ee0cf834-1173-401a-bcb1-a922f3ea706e | 9,8,11,126,127,181,170,174,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
62d56f87-70ce-4197-beaf-df0701408802 | 9,8,11,126,127,181,170,175,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
a23c2058-8226-4c3b-8b59-cd7325ab5e7f | 9,8,11,126,127,181,170,175,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
0d1560bb-f8f2-46d2-923f-67622dffb533 | 9,8,11,126,127,181,170,175,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
35f58dea-0773-47eb-9caa-e1fd2d8dbef9 | 9,8,11,126,127,181,170,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
f3f9fe17-6eba-4d85-a876-4f66237287f3 | 9,8,11,126,127,181,170,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
0ceb67e4-c7a4-4428-a73c-f341e041b1be | 9,8,11,126,127,181,170,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
f851a161-7973-434a-937d-c5325e23dc6c | 9,8,11,126,127,181,172,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
5da9d4e3-6ee8-4685-b334-18b013e81868 | 9,8,11,126,127,181,172,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
13d27053-a486-45cb-8f1d-38423d1be2de | 9,8,11,126,127,181,172,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
e0c8da6f-2e0a-4c68-9656-000e5889660e | 9,8,11,126,127,181,172,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
e5bbd505-69ad-445a-8457-94abbac9bb02 | 9,8,11,126,127,181,172,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 24 | FALSE
c07e4a18-576d-495e-945b-b83285c066fd | 9,8,11,126,127,181,172,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
15e87f88-7e33-45c1-b8f4-b2b864a9f071 | 9,8,11,126,127,181,172,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
dd2a5248-227f-4b53-b640-31c5ab83c91a | 9,8,11,126,127,181,172,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 24 | FALSE
9cfdfe01-b913-4e6d-bf24-d1785ba9bf97 | 9,8,11,126,127,181,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC BOX (8) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 24 | FALSE
567d2132-f0e8-4c90-aa93-fbec37780067 | 9,10,11,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 37 | FALSE
800bb34c-01af-4763-a7b8-718fc0674555 | 9,10,11,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
cc3eadd7-b3de-443a-81b8-57d742cb3789 | 9,10,11,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
77b5399e-a9dc-4bc3-833c-a58e58572698 | 9,10,11,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
d9e8da95-646f-407c-ad09-a9c6e759fd25 | 9,10,11,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
b473eaad-5f9b-4df6-9131-8bf985a8091b | 9,10,11,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
9b363acf-6cfc-4b46-92c9-f1df07b10e15 | 9,10,11,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 36 | FALSE
a5cb344f-d68f-4482-99f2-b9bbfb82c537 | 9,10,11,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
1eea0191-83ff-4ace-9060-e7fa152dc6cb | 9,10,11,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
6ea15ee6-64c4-4ebc-bcd4-f00264f82043 | 9,10,11,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 27 | FALSE
6666b002-17ab-4af5-b578-ee1e2a399fa9 | 9,10,11,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 31 | FALSE
a51ca260-dbc9-4446-b735-07f06e8cd6dd | 9,10,11,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 27 | FALSE
0f881ce0-4e23-4c42-bedb-2ebcb09208b2 | 9,10,11,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 31 | FALSE
0f75c728-e9ac-4cd2-a88f-d2a80c00c11a | 9,10,11,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 24 | FALSE
e6c08e7a-5eb2-40ba-85b4-93526d549bc3 | 9,10,11,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 24 | FALSE
dcc839ed-e9d9-4f02-8024-eaa86a520d61 | 9,10,11,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
345bd750-21e7-4925-a5d6-64eebe1e5c22 | 9,10,11,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
bf730ef0-9784-4f7e-934a-dd1705c03a43 | 9,10,11,6,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 40 | FALSE
38ee8559-e716-4eb7-b77c-376a20bcc84f | 9,10,11,6,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
94116abd-e227-47c4-a383-be3afa7a2a9b | 9,10,11,6,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
baea14c6-dcae-4bb0-861d-1852594030dc | 9,10,11,6,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
0d1f17ff-f526-4f78-8828-eb34c3948395 | 9,10,11,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 42 | FALSE
b7bd7130-7120-4e09-ad77-cf103567594d | 9,10,11,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
7cd5402c-c0ba-461a-bb3b-3beb1d8a2d21 | 9,10,11,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
dd344a85-5c48-4d53-a49d-bd22421bb4e8 | 9,10,11,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
3ff9f3e5-87d4-453d-9ab2-4f13f6f8033e | 9,10,11,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 39 | FALSE
1cf70436-3422-4ec1-b395-8ac482c5fb87 | 9,10,11,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
d3b16e0f-ec02-4481-866e-d82d72176aa2 | 9,10,11,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 41 | FALSE
3dfb4ec2-e24e-4025-a14b-813262f67875 | 9,10,11,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
9b922ef1-75ff-4a6a-a7ad-fad2ff90f020 | 9,10,11,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
99cf3e0e-53f7-42ad-a77b-75c7ee5a178d | 9,10,11,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 32 | FALSE
300035fe-66fa-46ba-912d-b61022aa327b | 9,10,11,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
f02cf8f9-b0b2-40a8-b816-74030ac03799 | 9,10,11,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 32 | FALSE
15fb2cd4-c3c5-4317-99e1-5db064c7fb6a | 9,10,11,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
fe1546ea-0589-4701-9b3d-b178876fd760 | 9,10,11,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 29 | FALSE
b745b05b-ba4c-49bd-b35b-0fff6b860a11 | 9,10,11,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 29 | FALSE
e7069ad2-7d0e-476f-bc37-9bd29638c76f | 9,10,11,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 33 | FALSE
25382eca-db05-4202-8ebe-ba4b9d0decb2 | 9,10,11,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
ca4bfd50-dabc-4454-a392-65f2076137c0 | 9,10,11,126,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 41 | FALSE
c4b199ba-0c3e-42e6-8eb4-103c6fe8fba1 | 9,10,11,126,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
99dd18bb-4c53-4160-8515-b8aa446e9a30 | 9,10,11,126,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
cc104d41-e73b-4ce1-93d3-1e6fae9474d2 | 9,10,11,126,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
3e35c5f3-387f-425e-b209-223014d02c4f | 9,10,11,126,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 38 | FALSE
a56502d0-e79c-4083-9a93-11c49797f910 | 9,10,11,126,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
65d76d6d-6d51-4389-9b31-29597955b9e3 | 9,10,11,126,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 40 | FALSE
9cb425dc-c216-4b7d-a6cb-2a263618edba | 9,10,11,126,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
64e91ef2-e2d0-4086-a249-e41a14579f70 | 9,10,11,126,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
2ccfaef5-0c32-4c40-8b4f-d45d885470a8 | 9,10,11,126,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 31 | FALSE
097ab517-b460-4b0b-b852-45c37c050189 | 9,10,11,126,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 35 | FALSE
463b910c-0760-43ea-a4f1-5aacbed95663 | 9,10,11,126,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 31 | FALSE
225e38ad-de7f-4248-9c7a-23268dbd6385 | 9,10,11,126,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 35 | FALSE
e9d86686-412e-4aec-aabd-b689eb272917 | 9,10,11,126,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 28 | FALSE
77a11cec-716b-4877-8517-17c8d9bd819f | 9,10,11,126,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 28 | FALSE
559bced3-9b11-4c44-8075-834c4f738264 | 9,10,11,126,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
ceae03f1-fd99-43de-844f-bfb02e453ff3 | 9,10,11,126,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
8a4ada00-e741-4962-98ee-a260a1d38917 | 9,10,11,126,127,128,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 29 | FALSE
837ab043-8d2f-48d0-b4ba-35a4b840e741 | 9,10,11,126,127,129 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 25 | FALSE
c3ad91f5-5780-4a3e-ab88-bc41ad3825fc | 9,10,11,126,127,130 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 25 | FALSE
9bc70d19-ef81-437d-9d7e-93601ade827a | 9,10,11,126,127,134,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 28 | FALSE
c01fc990-2aaa-44bd-9328-fe58f08c781b | 9,10,11,126,127,135,136 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 28 | FALSE
52ae2744-990d-447a-be40-319710d4b29e | 9,10,11,126,127,181,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
f7abb497-bbdb-481c-b059-b97e9b1b663a | 9,10,11,126,127,181,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
fc857147-6065-4a70-88c2-d05e105c280e | 9,10,11,126,127,181,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
b1674bb3-8805-48b3-bfd5-4f8ae844acbd | 9,10,11,126,127,181,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
e42b0c6f-0c6c-4256-afa4-8fbe40fb5908 | 9,10,11,126,127,181,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
13263757-c55f-46a0-8176-71573d3dd67e | 9,10,11,126,127,181,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
224bb8e6-7501-4282-bd61-b06db30d17a8 | 9,10,11,126,127,181,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
b549f44d-84ce-43e8-9baf-852db58d5971 | 9,10,11,126,127,181,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
8a8add13-ae22-41b5-880c-72743e1564e3 | 9,10,11,126,127,181,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
c98d63ab-4552-43d3-b71e-4acc1be48ac7 | 9,10,11,126,127,181,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
caa05173-a19e-4265-8371-2115ef5ca1a9 | 9,10,11,126,127,181,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
188dec61-8e58-4c4e-b748-66f7ead69e37 | 9,10,11,126,127,181,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
ade9601a-1b10-461e-bd7a-74149e8fb80a | 9,10,11,126,127,181,182,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 48 | FALSE
31707448-df54-482c-bfee-dc78a59d6bb6 | 9,10,11,126,127,181,182,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 46 | FALSE
3b3ce55c-5514-4f9d-875e-7c52d19c3289 | 9,10,11,126,127,181,182,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 42 | FALSE
93425219-273d-4741-8c19-bd8abb38f435 | 9,10,11,126,127,181,182,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
cefcd9a7-c5d8-4970-9c82-f790549271b3 | 9,10,11,126,127,181,182,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 45 | FALSE
70a20bd7-1b46-48bb-9904-4b4b430b8f2f | 9,10,11,126,127,181,182,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 43 | FALSE
b2057639-f317-430b-af2a-f6d9d3c0c915 | 9,10,11,126,127,181,182,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 47 | FALSE
948cf977-3a63-4073-872c-1127d0e6ffa9 | 9,10,11,126,127,181,182,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 45 | FALSE
6eae3a69-17c9-47d3-a099-37948402e666 | 9,10,11,126,127,181,182,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
9ae78073-b276-4202-82dc-08d5764cca45 | 9,10,11,126,127,181,182,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 38 | FALSE
ba346199-dfe2-4eb0-9da1-9c2d7c8a583d | 9,10,11,126,127,181,182,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 42 | FALSE
fbd3a777-1312-4ca1-9616-6214f61ac4ce | 9,10,11,126,127,181,182,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 38 | FALSE
b5dfc972-f0d0-4bf5-b789-cbabbb9e749a | 9,10,11,126,127,181,182,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 42 | FALSE
1144ed27-ba15-46be-a50f-c0a63ada95f3 | 9,10,11,126,127,181,182,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 35 | FALSE
f8bd5f8d-6e75-41fd-91c8-00e6b3455edd | 9,10,11,126,127,181,182,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 35 | FALSE
17a438d0-499f-4f5f-a389-1ecf8deb9547 | 9,10,11,126,127,181,182,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 39 | FALSE
34103ba2-7b55-45bb-869b-e7d1df1fbb46 | 9,10,11,126,127,181,182,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
8e0e5705-ccdd-4ae2-af73-8a830bd730f8 | 9,10,11,126,127,181,182,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
5189aed8-25ed-4850-a7e0-50a70d45bdde | 9,10,11,126,127,181,182,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
4d2cd9c3-c972-48de-a596-06972473f464 | 9,10,11,126,127,181,182,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
b426b604-5a2e-44e1-ac77-73f8a74a7262 | 9,10,11,126,127,181,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
f7b8ade5-4f8c-4df7-91dc-619c013bd066 | 9,10,11,126,127,181,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
330936cc-8938-4318-842a-063810edaf4c | 9,10,11,126,127,181,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
9799b38d-f577-4dc5-a976-cd4352f87b5a | 9,10,11,126,127,181,170,174,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 43 | FALSE
a288b4ea-8e6a-4de8-a60a-b691e4dafcb0 | 9,10,11,126,127,181,170,174,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 41 | FALSE
04775191-9fbd-4975-b097-630843d801da | 9,10,11,126,127,181,170,174,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
29679924-52b9-46fd-9a23-5a30ffcfff53 | 9,10,11,126,127,181,170,174,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
dee66d64-fa2a-4ad9-9b21-0310270f5137 | 9,10,11,126,127,181,170,174,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 40 | FALSE
9a9056c2-cbb2-43d7-b9cf-b433405ec8f4 | 9,10,11,126,127,181,170,174,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
9de635b4-3d55-460a-9f62-d157d618519d | 9,10,11,126,127,181,170,174,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 42 | FALSE
1f8aed01-7de5-4fa5-b3a6-70c20a1066a0 | 9,10,11,126,127,181,170,174,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
ab418cad-bf3f-4fcc-ab30-abca0b450171 | 9,10,11,126,127,181,170,174,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
73d3fadb-b8c9-4389-ae6a-ed2eda7572b3 | 9,10,11,126,127,181,170,174,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 33 | FALSE
0ed031e4-c5cc-4429-876e-1a70b8da56df | 9,10,11,126,127,181,170,174,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 37 | FALSE
01b4f599-fdb6-439b-a299-c57e35edeefd | 9,10,11,126,127,181,170,174,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 33 | FALSE
dc89fa93-a30f-4a6c-a374-74fa2606b272 | 9,10,11,126,127,181,170,174,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 37 | FALSE
3d52b9e2-2cb2-4f5b-877e-f3f5fd239379 | 9,10,11,126,127,181,170,174,2,65 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 30 | FALSE
6f47e681-0f8a-4263-b892-05f5efa431c4 | 9,10,11,126,127,181,170,174,2,73 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 30 | FALSE
ebc6f11b-164c-4eb0-98be-4e805ce9bed8 | 9,10,11,126,127,181,170,174,2,101 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 34 | FALSE
6e6b0a52-3585-4e24-8ce4-2c242f161853 | 9,10,11,126,127,181,170,174,2,188 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
74c41902-233e-4afd-a4ed-5c3d886e702a | 9,10,11,126,127,181,170,174,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
43d61876-e559-49f2-b36d-05cdf840b98e | 9,10,11,126,127,181,170,174,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
38d9470c-7724-4c56-9251-7ec8dd0a44cf | 9,10,11,126,127,181,170,174,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
89fa5e39-50ae-4b6b-9d95-4c9db21c9801 | 9,10,11,126,127,181,170,174,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
c850d195-d477-4bdc-81f8-7950a44249c2 | 9,10,11,126,127,181,170,175,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
aaf2a0bb-096f-4485-8a0c-043e778f6e64 | 9,10,11,126,127,181,170,175,183,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
11f1b454-4084-40c8-8336-df933be65929 | 9,10,11,126,127,181,170,175,183,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
96c2069f-72f2-4a0a-aeaf-32f4fc13eb22 | 9,10,11,126,127,181,170,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
64597f7b-d3dc-4b5e-aacf-c9407c140715 | 9,10,11,126,127,181,170,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
bd39be1b-c83b-49bc-9710-7987d7d7efe9 | 9,10,11,126,127,181,170,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
23a9dc8f-99be-458f-bb2c-af004906034a | 9,10,11,126,127,181,172,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
0ea49822-2c99-45e6-bd9b-a1fdc29481bb | 9,10,11,126,127,181,172,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
339fcd41-fd36-43a2-a237-691cace9bc5f | 9,10,11,126,127,181,172,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
21e29dca-8e4f-4acc-ae0b-455a59753a3e | 9,10,11,126,127,181,172,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
87f976c5-3fb0-4fd8-9f5c-3b559f0d5ca7 | 9,10,11,126,127,181,172,179,177 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 23 | FALSE
cf3c2c87-6a17-4ec3-b1ed-359a7224e565 | 9,10,11,126,127,181,172,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
80588dd3-a33a-497d-a021-76b1cc21d31d | 9,10,11,126,127,181,172,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
cb472703-b348-42fb-8d32-0db375a79d89 | 9,10,11,126,127,181,172,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 23 | FALSE
01d16770-8404-4fae-ad90-8f2132cb7690 | 9,10,11,126,127,181,187 | ASSY - THERMAL BOX (6) -> ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 23 | FALSE
032874fa-ccef-4933-b9cc-651c5c1976a0 | 9,11,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
4a48df93-80af-4633-ab1e-3a9897bd1a59 | 9,11,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
bbbe62c9-3981-446c-81ec-85648fb52fbb | 9,11,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2898af92-7b83-4a42-a363-99f0c21eedb5 | 9,11,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
82a93900-1d0f-4cb8-bb3a-ac1ce8338458 | 9,11,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
21196bcc-5271-41ad-a1bf-265b441bda41 | 9,11,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
f3f175e6-7819-4660-ab9c-63be818770ce | 9,11,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
84e5124f-7dde-4066-aefa-24090291eab2 | 9,11,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
b16f7759-c418-4ea2-b404-107fe5f30958 | 9,11,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
67fedaa3-f53b-4724-97c7-f60bbcf2fb2b | 9,11,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
a86f7a11-ae5d-4f6f-8f5f-c888b9445f2f | 9,11,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
c59cfa94-b413-435c-bf2a-ea255b313675 | 9,11,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
1cda5d40-80d1-4a04-ba1a-a93a373d0b14 | 9,11,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
c72f4572-006f-4f9c-8283-836aa596670d | 9,11,2,65 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
2faff2b0-14da-4501-9733-d5cb51634ae0 | 9,11,2,73 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
0bf8ed33-f4f8-497f-b4b8-3daf345dcc7f | 9,11,2,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
b7c28d6e-4b4e-46d1-b835-bf8d467ce6f0 | 9,11,2,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
994e384f-5830-4303-a823-a512c8250328 | 9,11,6,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
b1864eb2-5d2e-4683-9b2d-b166150ee5f9 | 9,11,6,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
e0bc78a5-da83-4956-9d02-1b01b27debec | 9,11,6,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
99a04ee5-f71c-4c1a-bf4a-b9878cdf974e | 9,11,6,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c5191ecc-c9ce-4a08-9a33-655800fd5ef4 | 9,11,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
e6688bad-f0d6-44b4-bce1-0731a0f47719 | 9,11,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
4e193f6f-648c-46a8-96a3-b6bfd88845ec | 9,11,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
0998534e-c92c-483a-a291-df667ca3db56 | 9,11,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
020954ba-83d7-454d-9458-ea49ac077779 | 9,11,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
959339d4-f707-4d63-a555-71adad010c27 | 9,11,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
b3fc56dd-64c5-4ad9-8d56-a6538ec7c9c1 | 9,11,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
f1b7ed5d-a251-4fcc-a337-b318eea65d54 | 9,11,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
91febef5-4714-4889-945f-5e8aac1f1c23 | 9,11,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
501e6772-8265-415b-b177-03b188836588 | 9,11,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
9611d6cd-a9eb-4798-aa05-5481adc152ab | 9,11,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
d0ce4723-d098-42a0-9e6f-91fb64cac7a2 | 9,11,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
829d6780-ffe0-43d5-baf8-c0ad60afae71 | 9,11,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
5db3cad7-a404-46a4-bdc0-aef185315cbe | 9,11,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
53ed119a-e237-4e7d-bae6-62b26a5abe9e | 9,11,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
b0fefe27-50e9-4fd6-9d22-07cb2cf7d4ad | 9,11,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
0e16ce87-3df2-40fe-9462-c8f2100d09c1 | 9,11,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
dc5779e7-41eb-496d-9739-4bbbcc139f28 | 9,11,126,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 34 | FALSE
abd72162-76d5-4e7c-91ea-a2fc72c80f17 | 9,11,126,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
ae647d87-304c-4cd0-9f93-ea5e61c453fa | 9,11,126,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
d4a817b1-6e1d-4652-9f94-c1f66cdd4c8a | 9,11,126,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c48a380b-a912-484d-a8f4-c6a9b4cace5d | 9,11,126,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
595e8813-4aaa-49c8-9925-6f9e5dd9a92e | 9,11,126,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
9c391963-3e11-4f13-96b6-360ff0268dff | 9,11,126,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
57674942-474a-4a68-a380-867b5a8931bb | 9,11,126,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
636b16a3-afe0-4b47-84cc-79a87c03a651 | 9,11,126,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b4c27906-f186-450a-84f9-60a6dfdcca21 | 9,11,126,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 24 | FALSE
bdf6dab3-beef-4fb8-a1c5-fac11be64a59 | 9,11,126,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
ab1bce20-9159-436f-8d13-938dfbb62347 | 9,11,126,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 24 | FALSE
53e5bd12-af49-44dc-b5cc-e58bf11f7a4b | 9,11,126,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
378a5633-1ba0-4a82-8192-225f21997603 | 9,11,126,2,65 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 21 | FALSE
de3b42bf-0654-4541-9ca6-70f86429fe8f | 9,11,126,2,73 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 21 | FALSE
3e73c128-18c5-4620-8f72-184c8ba249a2 | 9,11,126,2,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
e41a9b10-8dad-4665-ab7a-782f4b4657ad | 9,11,126,2,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
43268361-6c44-4c42-b112-3ec8dc57ae2a | 9,11,126,127,128,136 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 22 | FALSE
0e10b663-58ab-4be1-9073-8662bc4cb7ed | 9,11,126,127,129 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 18 | FALSE
30286546-c225-4937-bcf0-7b3c9e3b89e1 | 9,11,126,127,130 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 18 | FALSE
8e34039f-5975-4deb-870e-2b98d4d559f4 | 9,11,126,127,134,136 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
873f101c-1d74-4405-a9bd-a524bc3f993e | 9,11,126,127,135,136 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
bf887a69-f250-4aa8-bb49-c9353056cc5b | 9,11,126,127,181,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
381a36dd-14ac-42de-bce7-ef6df87b3f9e | 9,11,126,127,181,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
7787e91d-2f07-40ff-83b7-3a8dd3621d2e | 9,11,126,127,181,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
c97fd622-c8ab-43ac-bc26-2f33b07192b6 | 9,11,126,127,181,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
4b4198f7-3164-41f1-bca8-f45aca4b557e | 9,11,126,127,181,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
d3a01688-901e-4ba4-92e2-ad9ba616cd8c | 9,11,126,127,181,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
cafea781-ee7c-4b2e-89e0-54c3b4814229 | 9,11,126,127,181,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
386ac6f8-741c-4b73-b0c9-cfe706577bef | 9,11,126,127,181,179,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
d684ebde-9661-4a88-8733-17926247d45e | 9,11,126,127,181,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
9b00b1ec-de32-4a45-96c9-a39269b32914 | 9,11,126,127,181,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
ba82187f-51d7-4176-99f0-34c8fc8ee569 | 9,11,126,127,181,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
89e9cbf0-e8e2-4496-8ae1-aa4607de46f9 | 9,11,126,127,181,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
9f5c54d0-df5b-41d1-aac3-933308f168b2 | 9,11,126,127,181,182,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 41 | FALSE
e11af05f-0a4c-4a52-b23f-9226e44e2aae | 9,11,126,127,181,182,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
bd77cadc-55bf-43e2-81e0-38c2f2b992b0 | 9,11,126,127,181,182,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
1d42d0d3-26eb-49a2-abdd-375e90b8a7b0 | 9,11,126,127,181,182,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
baa932ff-4a62-4831-9ea6-3d48d6659b09 | 9,11,126,127,181,182,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 38 | FALSE
5aca8542-5bee-4bf4-8b9c-0b02b121f0f4 | 9,11,126,127,181,182,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
7bf865b4-e254-4668-857c-41ead21eae06 | 9,11,126,127,181,182,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 40 | FALSE
430f67db-d2fa-40d1-909f-6244fbe7383d | 9,11,126,127,181,182,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 38 | FALSE
f60c3f30-1a25-4ef0-94a0-fa4c8581dd15 | 9,11,126,127,181,182,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
6194ff91-8456-4140-9712-076660c9de96 | 9,11,126,127,181,182,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 31 | FALSE
faa722a2-e570-4ec7-9c3c-22dc1246f780 | 9,11,126,127,181,182,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 35 | FALSE
143c4a0a-fa64-4661-96c2-c6f0d7d0fded | 9,11,126,127,181,182,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 31 | FALSE
89a89990-f0a7-475d-9bbc-0fa132ef1bd6 | 9,11,126,127,181,182,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 35 | FALSE
12f05051-4a30-4f92-a87d-6ee811123851 | 9,11,126,127,181,182,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 28 | FALSE
93ef0142-d0c2-4dcb-9f38-eb9afa89bea1 | 9,11,126,127,181,182,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 28 | FALSE
30ce9ab2-1465-4191-bdf9-732aa31ff5d1 | 9,11,126,127,181,182,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
6939a2a8-5a06-4ca5-8a48-c1440adb18c3 | 9,11,126,127,181,182,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
2b798603-6a24-4b31-b301-9ef9c4257118 | 9,11,126,127,181,182,183,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
0d27cf6a-c50d-44d0-a6bc-69fc39608bea | 9,11,126,127,181,182,183,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
050c18f5-3f27-4384-9e96-b1193a5e286e | 9,11,126,127,181,182,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
e9aefd04-c641-4eb3-90c9-032c1d97ce5f | 9,11,126,127,181,183,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
620c110b-758e-43a0-9284-3f5c2baf4995 | 9,11,126,127,181,183,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
7d226c92-b6e6-48c7-8dc2-8e9b1a9ba43f | 9,11,126,127,181,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
1088fa2b-e951-4059-981d-faaa21eb93e0 | 9,11,126,127,181,170,174,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 36 | FALSE
3afcab88-7d0e-4f05-a752-4bb0af1db032 | 9,11,126,127,181,170,174,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
d8703686-c4d3-4d56-bf19-48a3942cb5c9 | 9,11,126,127,181,170,174,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
1005941d-9b1c-45f0-84a4-250897737d86 | 9,11,126,127,181,170,174,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8a78198b-d5a6-4ec7-89a4-8eda797468c0 | 9,11,126,127,181,170,174,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
b15bb3c3-3703-44f1-a26e-bd4624415fd4 | 9,11,126,127,181,170,174,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
d585767a-e009-493b-a959-2421d9e258d0 | 9,11,126,127,181,170,174,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
877e60ac-cb03-4758-8b88-0ab3a44eb3ce | 9,11,126,127,181,170,174,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
1eace425-6f7e-4e3a-88d7-0d2539374101 | 9,11,126,127,181,170,174,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
59d6f4e9-f41a-4705-ba57-68bb225729a1 | 9,11,126,127,181,170,174,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
dfaaadf9-3fd3-4bbd-bebe-f2cd2798c26e | 9,11,126,127,181,170,174,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
8a5febae-3a8c-474a-9aa4-f2ab98377f2c | 9,11,126,127,181,170,174,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
387c431c-71d4-4165-b8e0-fe98996a6924 | 9,11,126,127,181,170,174,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
81ad6b05-3266-47cf-bdd4-bd3b504b03d6 | 9,11,126,127,181,170,174,2,65 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 23 | FALSE
0b261b5f-5015-4abc-892a-945f0c2b142f | 9,11,126,127,181,170,174,2,73 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 23 | FALSE
109edb5d-b73a-43a3-b2f1-6b9be793a4e0 | 9,11,126,127,181,170,174,2,101 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
769e1cce-edd9-46d1-adf8-033b81f8b2a7 | 9,11,126,127,181,170,174,2,188 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
71953236-7ddc-4ab6-9e94-9aa5b894d770 | 9,11,126,127,181,170,174,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
30379e15-9ae9-490a-a831-fd1b6c10f0a0 | 9,11,126,127,181,170,174,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
eefc9562-46b1-4a11-a712-127410089a35 | 9,11,126,127,181,170,174,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
ebd651e9-c96f-407f-be03-5434e9f28625 | 9,11,126,127,181,170,174,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
160c2604-a86e-4072-abec-6d0dbfbf5c18 | 9,11,126,127,181,170,175,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
64f4bf59-7c55-426b-a485-2e60ac54b5fc | 9,11,126,127,181,170,175,183,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
eaa3227e-e734-48f3-b6ce-854ba3dace31 | 9,11,126,127,181,170,175,183,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
ee8494a9-c9db-406b-993e-96ca67fd1c14 | 9,11,126,127,181,170,186,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
d53c9b4a-8d73-423b-986b-c5583c8eeea2 | 9,11,126,127,181,170,186,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
c266e3e8-5220-4aea-9123-bd7c7dc122c8 | 9,11,126,127,181,170,186,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
f591600a-08df-44e1-84f9-c380007c9874 | 9,11,126,127,181,172,173,176,179,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
f313a004-7f49-4756-883a-ddb8e7868443 | 9,11,126,127,181,172,173,176,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
2fc19061-d07a-454f-b264-f5bc5adae509 | 9,11,126,127,181,172,173,176,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
2cf0b87c-0feb-4ded-b5d4-517645557b4a | 9,11,126,127,181,172,173,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
14cb7193-9455-4e0c-8c1e-ed158fef7460 | 9,11,126,127,181,172,179,177 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 16 | FALSE
3bdf6f00-ebb1-4ab2-9693-f81f9d55f423 | 9,11,126,127,181,172,179,180,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
f015e033-c026-4b3c-921c-c62997bb9ecb | 9,11,126,127,181,172,179,180,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
8a9499f3-ea5e-4274-aa51-9c56a512ece3 | 9,11,126,127,181,172,184,185,178 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 16 | FALSE
85c13961-ce7b-462c-977b-7409e75dc7e5 | 9,11,126,127,181,187 | ASSY - THERMAL BOX (6) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 16 | FALSE
219af597-2c2b-4807-9345-930328f7b57b | 9,12,2,16,21,22 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 31 | FALSE
3e046f0b-b769-49ad-a9da-6c848996441e | 9,12,2,16,21,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
0efe1f79-41ee-4da0-93e2-6ec31ad5a4ab | 9,12,2,16,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
aa9951f4-7e12-48e6-a682-3079574aa3ba | 9,12,2,17,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e8c692ea-bad4-41ae-bf49-ed7f735bb306 | 9,12,2,17,19,20 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
dc4f627c-8b61-49c0-a0e2-6ae644de6a43 | 9,12,2,17,19,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
c0263c44-c26e-49dd-8f7f-d815230c8d42 | 9,12,2,18,19,20 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
03e2249b-08a2-4030-9cda-89f32fdd1277 | 9,12,2,18,19,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
bd138c5d-6c3d-4fac-9d7b-049d8830debc | 9,12,2,18,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8a0780b7-a803-4fd6-875a-0ea538c77969 | 9,12,2,35,25 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
a9036680-e23d-4061-af5f-66c75a92f434 | 9,12,2,35,101 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
e396ce39-58a8-4fd2-9277-4fee4d8eb616 | 9,12,2,36,26 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
16513cc9-9230-4a26-90f3-dce5ab6ff13f | 9,12,2,36,101 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
2b43b88f-ce1e-4e0a-bfdb-d4d5c54edf75 | 9,12,2,65 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 18 | FALSE
9cc0f767-8b56-4de5-be74-87ac1a3a00e0 | 9,12,2,73 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
cd0a0411-1c35-4e76-bba3-e40939a07710 | 9,12,2,101 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
69c60617-aad2-4b06-ac82-f43332673ba7 | 9,12,2,188 | ASSY - THERMAL BOX (6) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c9d74342-63c5-4e62-9708-dfb03707e9ab | 10,11,2,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 31 | FALSE
22f57ad6-ef04-48f5-b2d4-75cdb880e76f | 10,11,2,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
3c02d0bb-36bc-48b1-a4bf-505f36211599 | 10,11,2,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
907fa5b9-378a-4949-ae32-7e4044cdfb0d | 10,11,2,17,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d682bdd4-734a-46c1-93b7-23c5ce8869a0 | 10,11,2,17,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
72bbe02a-a8df-43bc-a597-63d80a125a3b | 10,11,2,17,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
80fb75cb-7769-40f9-bd9d-9d174c9dad7e | 10,11,2,18,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
65cb3da6-c962-429b-9014-cf08ca8065c7 | 10,11,2,18,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
5fc2a1c0-8366-4a97-b21d-0003ea407590 | 10,11,2,18,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
55c5030b-f3ae-41c8-ac04-0987e7da19d9 | 10,11,2,35,25 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
40db69f3-9a37-4f5c-83cd-b92058b54d3f | 10,11,2,35,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
8fbbbe2e-ff83-4d93-9fc7-826b43d0c2f3 | 10,11,2,36,26 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
7c07b7f7-be20-48ee-8532-06e65683590f | 10,11,2,36,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
1bf70245-fa12-45fe-b02c-f4206449a007 | 10,11,2,65 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 18 | FALSE
21dcc41d-ad72-4349-b35c-53afa0488da6 | 10,11,2,73 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
e1365f0e-0bc3-4318-81ac-2b650863cc58 | 10,11,2,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
3270b25c-7ef8-47e9-9d69-3c27596fa7c3 | 10,11,2,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
18e68aeb-655e-4173-bdbd-b6710b082115 | 10,11,6,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 34 | FALSE
eb58669e-e78d-44ac-a058-ed95e6f7b654 | 10,11,6,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
072aa6fc-d777-4c33-88c9-54107fc122f9 | 10,11,6,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
c416fb78-b09c-4633-80e6-81408b9587f3 | 10,11,6,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
51727315-ac23-4cba-9aed-9a5c2aebd4f5 | 10,11,12,2,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 36 | FALSE
ead2ce9f-33a8-462a-90d7-abce0e549083 | 10,11,12,2,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
3d0c804e-4646-4a55-9ac0-8bba94efa1ad | 10,11,12,2,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
904cf59f-1a6b-468d-af7c-99fc0c40dab4 | 10,11,12,2,17,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4b1244b6-898f-44cb-a7e3-b416d7715621 | 10,11,12,2,17,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
1a693f35-d290-4cce-b875-53e8324e794d | 10,11,12,2,17,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
69af5553-556d-4994-9f40-db50f89a1676 | 10,11,12,2,18,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
3ec4b318-1fb9-478a-9458-f0bd9425fff5 | 10,11,12,2,18,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
203d0820-b011-4530-aac6-065430f5ad52 | 10,11,12,2,18,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
c33229c4-dd39-4dd6-8ec8-31bd153891ed | 10,11,12,2,35,25 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
cafc5e69-67f1-499e-9979-ba2c298fc59b | 10,11,12,2,35,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
a34ca419-3347-4077-8bf8-409b72af8d7b | 10,11,12,2,36,26 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
f5ec4eda-0361-4045-9cc3-c94c3ba790d1 | 10,11,12,2,36,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
1fae6763-79bd-41de-93e2-667f5fb0345d | 10,11,12,2,65 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 23 | FALSE
955aac07-65d8-418c-81db-e1ede42ed9ef | 10,11,12,2,73 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 23 | FALSE
49b0d2e1-2660-4bb9-a3e5-43a7649e2efa | 10,11,12,2,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
424ff4ba-7947-4292-84db-25209fba4fc6 | 10,11,12,2,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
4990719c-1156-4b53-b997-24551ec70c76 | 10,11,126,2,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
f4b6e9db-40b7-416f-87ee-596b9bbdca79 | 10,11,126,2,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
27817427-b65c-4d3c-96aa-db724c9abee6 | 10,11,126,2,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
f943abb6-7974-4787-bbfb-5de99ff244ce | 10,11,126,2,17,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c5dd1b25-feb8-40db-8f6e-0b37c74fd93c | 10,11,126,2,17,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
e31c368f-d080-4181-8361-6340fd476184 | 10,11,126,2,17,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
6de359b3-2275-4917-a36c-9d67b198fb70 | 10,11,126,2,18,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
4e60015b-95a6-4815-82f8-6e32277bbb86 | 10,11,126,2,18,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
fb7bcde7-e92b-4c83-b80c-2c6f3cb34829 | 10,11,126,2,18,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
efb32983-cb6e-4024-89f1-fe419fdb456d | 10,11,126,2,35,25 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
2bd31e0e-410c-45fc-8a25-cf8b2e52be85 | 10,11,126,2,35,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
760ac999-2572-451d-83f1-a101ddcd43dd | 10,11,126,2,36,26 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
312646f6-1317-4978-9f48-3c0623ff6c68 | 10,11,126,2,36,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
a945405b-21b0-401d-b2cf-9f155bdcd508 | 10,11,126,2,65 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
17290440-817c-44f9-919c-934e6e6085c5 | 10,11,126,2,73 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
f34470f5-79aa-4773-b196-27e5a0fc1626 | 10,11,126,2,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
9dc4c55f-8ee5-44ff-8acc-f74d3b0c01fc | 10,11,126,2,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8f645844-e428-41a6-aa40-f52083145bfc | 10,11,126,127,128,136 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 23 | FALSE
109ae6a9-6ce7-4bcf-98d3-a6547b4022c5 | 10,11,126,127,129 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 19 | FALSE
561b0f4f-a8fc-47a2-9487-4fb4c2369877 | 10,11,126,127,130 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 19 | FALSE
3e15e94c-4e01-498c-96fb-ab02839c507a | 10,11,126,127,134,136 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 22 | FALSE
c311e7e9-41ad-45f2-9e37-78c717873e18 | 10,11,126,127,135,136 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 22 | FALSE
8d3a2c37-abef-4b81-9def-6663ef7ae111 | 10,11,126,127,181,173,176,179,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
38e1b790-102e-43b8-a764-3f36d39074e1 | 10,11,126,127,181,173,176,179,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
99182186-4eb8-4eee-bf12-0abf6448f54a | 10,11,126,127,181,173,176,179,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
137c9f86-1f65-42d0-96cf-860808f6af0b | 10,11,126,127,181,173,184,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
7bf1c6d7-2538-4a4c-98f0-fcaab48ddb4f | 10,11,126,127,181,176,179,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
29a6efbc-b975-4255-bac8-2cec5ed2cca7 | 10,11,126,127,181,176,179,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
2bea5ce7-67f9-43d0-9477-021a2f478b5e | 10,11,126,127,181,176,179,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
6d9bedb2-d191-474a-9c43-9024332bef11 | 10,11,126,127,181,179,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
50bc4d98-e708-46bb-8b2c-08f176056947 | 10,11,126,127,181,179,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
f613b5a3-efc5-4ecd-bc08-a163a563954a | 10,11,126,127,181,179,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
e5853861-5ec1-448a-a492-dc3fd5d7d3dd | 10,11,126,127,181,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
986a2298-4850-4494-9883-3519c3c8a8ab | 10,11,126,127,181,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
01d7b50f-ea25-4d31-b65a-a179386218f7 | 10,11,126,127,181,182,12,2,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 42 | FALSE
44bf3cae-9a49-4abf-ac82-6b2667d9679a | 10,11,126,127,181,182,12,2,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 40 | FALSE
34e83d46-00f3-4fab-9b48-c3185538138d | 10,11,126,127,181,182,12,2,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
48d1a26b-f5fc-4c9b-8368-c383d3c236d3 | 10,11,126,127,181,182,12,2,17,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
8c1278ee-6842-4a9a-9156-8aa2a2e2efe6 | 10,11,126,127,181,182,12,2,17,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 39 | FALSE
cab1d09d-cbe9-4073-be2d-2cc7ba7bacf0 | 10,11,126,127,181,182,12,2,17,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 37 | FALSE
f8a8ce05-b131-4bbf-a76a-b149deb24a9e | 10,11,126,127,181,182,12,2,18,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 41 | FALSE
1b11bd69-3aa4-4dfc-a22f-55e642baf1b8 | 10,11,126,127,181,182,12,2,18,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 39 | FALSE
308e3a3b-d0e4-4ccf-acaa-dea86d1a182c | 10,11,126,127,181,182,12,2,18,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
ad490618-aa7c-4b02-b0ab-b3a3eba891f5 | 10,11,126,127,181,182,12,2,35,25 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 32 | FALSE
c779209a-7b4d-4499-87b4-a1f16c383109 | 10,11,126,127,181,182,12,2,35,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
77114538-10fa-44ef-b093-b3e428aa6865 | 10,11,126,127,181,182,12,2,36,26 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 32 | FALSE
76c76e0c-6355-4306-8fb8-e157d832c509 | 10,11,126,127,181,182,12,2,36,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 36 | FALSE
32aba471-7a01-40d9-836a-b206b06a53bf | 10,11,126,127,181,182,12,2,65 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 29 | FALSE
b3c6e2a9-e867-47d9-9b2a-061e1412d69e | 10,11,126,127,181,182,12,2,73 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 29 | FALSE
178f93c0-d95b-45ce-8823-266eeff310ee | 10,11,126,127,181,182,12,2,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 33 | FALSE
7c78fc79-7acc-464b-a96b-866aa0ba7aae | 10,11,126,127,181,182,12,2,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
4b8a48a0-e0f5-4267-bc57-2fbae936aabb | 10,11,126,127,181,182,183,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
aa63fe3d-dbd1-47b9-96cf-ae7f0b172677 | 10,11,126,127,181,182,183,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
294ff3be-b13b-4863-a662-326ce0ccddfe | 10,11,126,127,181,182,184,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
74a32c9e-fdb4-403d-a7fe-ba24fa635208 | 10,11,126,127,181,183,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
6a4e4b23-9362-4f44-9fcf-89284dda7115 | 10,11,126,127,181,183,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
4c9dd0ca-1ace-4f25-9538-a0e3f717002c | 10,11,126,127,181,184,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
b3f55ffb-7c03-497c-a66c-517193f0651c | 10,11,126,127,181,170,174,2,16,21,22 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 37 | FALSE
657caa15-c28d-451f-9e58-b3cea36cefaa | 10,11,126,127,181,170,174,2,16,21,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
88d6cd71-8b66-4ae4-ab56-8a8a0e0cd112 | 10,11,126,127,181,170,174,2,16,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
8993b571-23dd-4dc1-b0a6-0a6b6b9838a1 | 10,11,126,127,181,170,174,2,17,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
4f1ee623-1bbe-4e02-aa4d-ed41a41dc5cf | 10,11,126,127,181,170,174,2,17,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
325f85d5-ad1f-4f5e-b6f3-2b6e9344263f | 10,11,126,127,181,170,174,2,17,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
7258e015-00b6-4514-adf3-30b9958562f5 | 10,11,126,127,181,170,174,2,18,19,20 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 36 | FALSE
aed977d4-390e-4025-8ff0-41e69c01cccd | 10,11,126,127,181,170,174,2,18,19,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
d17ea3c4-29ef-4935-9ac1-73b1e4580a4a | 10,11,126,127,181,170,174,2,18,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
0174fb63-3cc2-4d38-86fc-39f84e0ff0e0 | 10,11,126,127,181,170,174,2,35,25 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 27 | FALSE
2ee6456a-ebe6-4e54-8605-7e05be8147b6 | 10,11,126,127,181,170,174,2,35,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 31 | FALSE
5fb2bd48-1148-4aca-b60a-d337d2e71be7 | 10,11,126,127,181,170,174,2,36,26 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 27 | FALSE
52f2f968-0915-4663-abb1-aaf308b92800 | 10,11,126,127,181,170,174,2,36,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 31 | FALSE
bf484d1e-7599-426e-8842-d42e66e220bd | 10,11,126,127,181,170,174,2,65 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 24 | FALSE
1a470913-ca9c-41ad-ae91-1d3982eed9c4 | 10,11,126,127,181,170,174,2,73 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 24 | FALSE
5ac8e8aa-1a43-42eb-a27c-175414359f40 | 10,11,126,127,181,170,174,2,101 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
80c9d072-69cd-42a4-83c6-7d89cf58c51a | 10,11,126,127,181,170,174,2,188 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
1b33fd7f-67e0-4572-85e8-a161f156dde3 | 10,11,126,127,181,170,174,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
560fbcd2-8d1e-4b44-be73-f973ea8da59c | 10,11,126,127,181,170,174,186,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
51091014-9917-444a-bf27-3d3508ee6958 | 10,11,126,127,181,170,174,186,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
c1ca6e3d-220c-4230-8042-67c292682925 | 10,11,126,127,181,170,174,186,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
3dd89150-48f9-4e34-9c5e-311f80966a2b | 10,11,126,127,181,170,175,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
045bcc3b-f12f-4d99-bf16-e9351a799a32 | 10,11,126,127,181,170,175,183,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
df836711-2255-484a-84b5-c9ef75f65238 | 10,11,126,127,181,170,175,183,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
5509ddca-0676-4a87-b915-ff4f13d8389a | 10,11,126,127,181,170,186,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
c1e73400-ecbd-4437-85d5-5e7b4e25853e | 10,11,126,127,181,170,186,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
b66a3d67-54c2-46b0-9148-da0925d20ee5 | 10,11,126,127,181,170,186,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
8ff6a99e-7012-4ab1-a74d-b8835a797b13 | 10,11,126,127,181,172,173,176,179,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
482f1a7a-fabb-4850-b703-5afa75ce56c8 | 10,11,126,127,181,172,173,176,179,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
85760597-1236-46ea-8b73-3170a85f3bb0 | 10,11,126,127,181,172,173,176,179,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
c8a64e33-50f5-47b5-8d23-3b54cf1f8222 | 10,11,126,127,181,172,173,184,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
02c531ca-6c0f-448d-b815-8a763d82d0df | 10,11,126,127,181,172,179,177 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 17 | FALSE
5057548b-990f-4a24-b2ab-54e6ec79baeb | 10,11,126,127,181,172,179,180,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
a7b61629-cf1a-4076-ad1e-0fc0259a1cfc | 10,11,126,127,181,172,179,180,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
47538f11-b231-4f79-a3d1-8cea6bf014d6 | 10,11,126,127,181,172,184,185,178 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 17 | FALSE
8733866d-ffbb-4d09-8e1c-b5c58359da27 | 10,11,126,127,181,187 | ASSY - HVAC PIPING (7) -> ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 17 | FALSE
8c0deda5-d524-46d8-9a6c-159c2cf111e4 | 11,2,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
0eb9f9ce-e454-4206-81b9-839df0e7399b | 11,2,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9273335d-c175-455c-8941-266b004865c3 | 11,2,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
136193cf-1b84-4076-ada0-c4134202bfce | 11,2,17,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
c196998d-83a9-4b4d-87cd-7ab13cb79343 | 11,2,17,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
d461f3ec-aa0c-4c36-ad3e-3984924ffcbb | 11,2,17,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d5715761-08c9-49ae-a1f8-a77ae54cf0e8 | 11,2,18,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f9ba7387-901f-4bc9-8f72-fa7117b72c2b | 11,2,18,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e4bc646c-8cdf-4b2f-8be2-325fdd6756b1 | 11,2,18,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
0d1a86a8-bb08-480d-a415-6a6eb1bb99c8 | 11,2,35,25 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
0a03c657-78bd-4ffb-bf09-a513d2f772ca | 11,2,35,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
79515d26-ce74-4755-8340-3b612b72f168 | 11,2,36,26 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
5ae4886c-b3fe-4217-af7b-07c17fa5d008 | 11,2,36,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
6bcdbd76-88fb-4cc4-abff-eaa2eb6a94b3 | 11,2,65 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
5857c313-826b-4d5a-a1cf-0ee0b047f139 | 11,2,73 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
c18bb1ab-f34d-40c6-971b-df0fcbab93b2 | 11,2,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
db4a086a-5659-477a-8442-42a39caf77b6 | 11,2,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
75fe2416-ff57-4840-9801-e573a98ee685 | 11,6,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
3cc5dd37-e9e6-4ce7-977a-4e602a714d1c | 11,6,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5363cc60-e459-4cf6-8d62-2a40917413d9 | 11,6,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
0ef043c5-da81-4be3-9ecc-7c2d163d5784 | 11,6,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e5347571-53f2-483b-ae64-64848f8d0d41 | 11,12,2,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
888b2da5-a82a-44dc-827f-d52e18410d2f | 11,12,2,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
2bcf8c5b-d631-41a1-82e6-ff547de60533 | 11,12,2,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
358f4c72-54fa-4598-a324-39c09be6b82b | 11,12,2,17,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
48de6456-9591-49f1-b1ba-5a5226d8d79a | 11,12,2,17,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
632e1518-f79c-48df-bec8-a7bb429d6600 | 11,12,2,17,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
48865720-a997-4803-a20a-fbeda0186e26 | 11,12,2,18,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
8f769cfc-5d16-40b6-977a-7de269aba4f3 | 11,12,2,18,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5d4a5466-d2e8-4096-8052-3972ac7a339a | 11,12,2,18,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d28b0966-0fbd-4e29-9afe-6894aa876d1b | 11,12,2,35,25 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
2c859170-d4f4-47c9-a860-649e48d048fb | 11,12,2,35,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
cb5e20eb-2c18-4dd2-981a-4c28178c3342 | 11,12,2,36,26 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
ab0b80ee-2434-45d8-9f4d-2b16679a595b | 11,12,2,36,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
4bbf1005-25e9-4901-8c9f-0d74a73c30f7 | 11,12,2,65 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
ba307ee8-644f-44f9-93f5-48f98611ae26 | 11,12,2,73 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
6084d630-96d4-46d2-8f94-222137bccac9 | 11,12,2,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
f8d553f4-7ffa-4c6a-9094-bb6af6251436 | 11,12,2,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e20d458e-dee2-4371-96cc-5b72bb401827 | 11,126,2,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
585fcc4b-16be-40d8-b371-a13418a6847c | 11,126,2,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b46ef56f-0a82-438f-b8c0-06c85c47fc1f | 11,126,2,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f5eb4fed-a113-44b3-b60d-2dcd689097da | 11,126,2,17,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7287264e-d2f3-4d4e-8b82-57c6804983dc | 11,126,2,17,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d28d8271-2bf8-48ab-88ed-aac0247368ba | 11,126,2,17,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
23113da5-edd6-499b-b6e9-bad87a3f3e92 | 11,126,2,18,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2d4caf7d-5330-4a6b-8cbe-1b9bb15863fd | 11,126,2,18,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ebc9a931-915a-4c38-bb52-28f81f08e75c | 11,126,2,18,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
871d5b73-f601-46f3-9646-ec14197a20ca | 11,126,2,35,25 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
03642490-f31d-4594-b3df-5d6a395c2b13 | 11,126,2,35,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a0cab2fd-dbea-4dd6-a242-10044fca0dea | 11,126,2,36,26 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
5278cb08-effd-40c8-bff8-514a7cc3c3b4 | 11,126,2,36,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2f9ef4f5-b2c5-47ac-95d9-8b576bebdf0d | 11,126,2,65 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
fa0d1795-b15c-4760-912c-0798b430a7ae | 11,126,2,73 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e8f6c96f-a5d5-4b6c-bcd0-5359411c4127 | 11,126,2,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
081b4a69-bba6-48a5-934d-816ce8d7d273 | 11,126,2,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ba83dbfb-f6eb-4653-b17f-074735a2dd90 | 11,126,127,128,136 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 16 | FALSE
38813256-d897-4747-9e88-3bbc921c5b4a | 11,126,127,129 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 12 | FALSE
0a89e68c-27ff-49a0-a73e-0ccd6c700141 | 11,126,127,130 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 12 | FALSE
ea4dddfa-1eab-4f8d-817f-ae9caf93064a | 11,126,127,134,136 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 15 | FALSE
d334b4a5-27db-41d2-89e7-d7e91488215f | 11,126,127,135,136 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 15 | FALSE
8cbfd9f9-d8c7-4bad-bf51-df127a82db3d | 11,126,127,181,173,176,179,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
999810a0-8f4e-4178-bd9a-0a789be6956c | 11,126,127,181,173,176,179,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
29218957-bf4d-408e-96f3-e3b7f61b291f | 11,126,127,181,173,176,179,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
ba5809dd-474f-4ec6-a81b-9561073fa9cb | 11,126,127,181,173,184,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
ce23a8c2-999f-4dfb-9581-04995816bc57 | 11,126,127,181,176,179,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
49710a48-707f-4351-84f2-6b183d11865f | 11,126,127,181,176,179,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
5d68692e-c1bc-430a-b702-bc1a557a169e | 11,126,127,181,176,179,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
28f17d77-005b-4c6b-a9c6-3b997d7124e1 | 11,126,127,181,179,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
eb3fc5ad-a8ae-4a09-8b7b-853f9af56ad1 | 11,126,127,181,179,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
bc3db2d0-757d-4b0c-9ba8-7a81944b9b6d | 11,126,127,181,179,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
f094496e-6c77-49c7-b4fc-05c88cb9ac31 | 11,126,127,181,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
302de15d-b160-40ee-bee0-5dd4793e2a81 | 11,126,127,181,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
2e3f1538-caa1-4021-8117-1639354d7c38 | 11,126,127,181,182,12,2,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
c56e8650-ae0b-4529-8481-d3005c022bad | 11,126,127,181,182,12,2,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
ab4b40bb-9537-4fdd-a511-1e4e8a74ee7f | 11,126,127,181,182,12,2,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
2f0873bc-4d58-4a31-b3d2-e0b8cb09fb3c | 11,126,127,181,182,12,2,17,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8be8f52c-40c3-4ab7-8cc5-c8b205229569 | 11,126,127,181,182,12,2,17,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
2964c59d-7df9-4cfc-9b89-25eba567acd0 | 11,126,127,181,182,12,2,17,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
f4fb9433-f7ef-4b3e-b51c-b3c7cc42eeb0 | 11,126,127,181,182,12,2,18,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
e165be5c-6bf1-4cf5-bb42-843eb31149ac | 11,126,127,181,182,12,2,18,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
4a3c2888-8691-444c-a5bc-01198d82bed2 | 11,126,127,181,182,12,2,18,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
a17f5aac-54c5-49bc-8d1d-d153bd9f45bb | 11,126,127,181,182,12,2,35,25 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
f9191487-5303-45ae-b665-e2fb21bcc15c | 11,126,127,181,182,12,2,35,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
7bffcdae-16e0-472b-a385-91f779bd59cc | 11,126,127,181,182,12,2,36,26 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
b4955a6b-f975-47c0-b020-07b90d058cc8 | 11,126,127,181,182,12,2,36,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
d858b2e8-527c-4e13-b60e-0a6df7139059 | 11,126,127,181,182,12,2,65 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
cbcbc577-dcfc-48ec-9c72-dac604637c6c | 11,126,127,181,182,12,2,73 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
16aa0ab0-949b-41fb-bb00-fac1b5322128 | 11,126,127,181,182,12,2,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
3d684a59-f96f-4fbe-95ba-6a095bb82393 | 11,126,127,181,182,12,2,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9c55c84e-0c21-4dcd-86ff-62113bc51ae7 | 11,126,127,181,182,183,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
0667c663-84b1-4cc3-b168-23784f4e538d | 11,126,127,181,182,183,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
e829667c-9264-4bca-ab32-d0568f185b55 | 11,126,127,181,182,184,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
019b82f8-89ff-4515-91e6-b84889d70b7a | 11,126,127,181,183,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
1f60d72c-0942-4dd1-ae9f-1597a15bd4a3 | 11,126,127,181,183,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
ee47af5d-c604-44d3-8368-0e97f3a40d89 | 11,126,127,181,184,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
52e6aa3a-dfab-41f4-997e-d8f223790560 | 11,126,127,181,170,174,2,16,21,22 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
cd1a8cdf-6996-46d7-b391-6ccf50c86743 | 11,126,127,181,170,174,2,16,21,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
a0950a23-8b51-460f-b9a4-c630a9b07fae | 11,126,127,181,170,174,2,16,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
90f11d78-cf7a-4c08-895f-efb10116f00b | 11,126,127,181,170,174,2,17,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9190e944-6d4b-4a1c-845c-b5858e1b3bf7 | 11,126,127,181,170,174,2,17,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
4103676d-c4f7-473e-a270-921fc08e5aba | 11,126,127,181,170,174,2,17,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0b7d4ec9-3c4c-44c4-b0d1-2e79801efe73 | 11,126,127,181,170,174,2,18,19,20 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
b3328532-a62e-4a7f-ad1a-79c26b0e447c | 11,126,127,181,170,174,2,18,19,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
c325d9ad-efe5-4d3e-b42f-501345bc4b56 | 11,126,127,181,170,174,2,18,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
518fd78e-b1c2-4592-a503-8195c37e2fa4 | 11,126,127,181,170,174,2,35,25 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
cb41a450-e4a1-4959-9126-104e5621b9ad | 11,126,127,181,170,174,2,35,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
9df0443c-b817-4fb2-9a95-e4da9e2f5411 | 11,126,127,181,170,174,2,36,26 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
925a0819-33e2-4cd7-969e-6aa5b302db13 | 11,126,127,181,170,174,2,36,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
4d61b527-2e7f-4a21-83c9-9a6c294f0473 | 11,126,127,181,170,174,2,65 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
d391d38d-e74e-449a-ac6f-683820b349de | 11,126,127,181,170,174,2,73 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
b7677e86-97ed-4935-a3c3-1e36d570a7ed | 11,126,127,181,170,174,2,101 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
9111d78f-1503-44f0-a6c1-41b04bbbf267 | 11,126,127,181,170,174,2,188 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
986e235f-3bab-4e6e-998c-a5263cf795b2 | 11,126,127,181,170,174,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
5725b9d8-aba6-4fcb-95cf-f9dfb20c36a6 | 11,126,127,181,170,174,186,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
be8dd9dd-e940-4ce6-b000-9db52e28dc69 | 11,126,127,181,170,174,186,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
5a7a7ece-c508-4dac-961d-546b33bc08d7 | 11,126,127,181,170,174,186,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
7dd62b3e-51f3-4c65-8e73-43392fc77f37 | 11,126,127,181,170,175,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
9f827dd1-f5f7-4923-a1d7-02008427fd78 | 11,126,127,181,170,175,183,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
d3a31ae6-5c4c-4528-8ee1-2db2de14fe3c | 11,126,127,181,170,175,183,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
1a93a9d0-8001-4dbf-8400-e29c9549c6da | 11,126,127,181,170,186,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
0e517350-e1dd-4d83-80d1-12e1fcf006a3 | 11,126,127,181,170,186,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
3095192d-d2aa-4768-94c5-df97c6b8b500 | 11,126,127,181,170,186,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
dd315128-c097-4d82-837c-dd005e524b58 | 11,126,127,181,172,173,176,179,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
ab9b7598-7122-406c-a265-d047b954294e | 11,126,127,181,172,173,176,179,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
4cf1f5da-2dde-4cdc-a70c-ef6703678d00 | 11,126,127,181,172,173,176,179,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
c86d3fef-32e5-4648-a174-5bae35734073 | 11,126,127,181,172,173,184,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
e1bab8d8-17dd-49bd-b41e-9680e05269ac | 11,126,127,181,172,179,177 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 10 | FALSE
8b7973c2-daa5-45b9-b842-417226a1821a | 11,126,127,181,172,179,180,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
0d99c892-847f-464e-8226-00e2ee9f957e | 11,126,127,181,172,179,180,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
ef3b1ab7-283a-4621-90b3-0c7b720ce838 | 11,126,127,181,172,184,185,178 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 10 | FALSE
929253ed-5fcc-42ed-b1d0-c6b66dc666a1 | 11,126,127,181,187 | ASSY - FRONT FLUID MANAGEMENT (4) -> ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 10 | FALSE
7d65990a-fb2d-4daf-945b-de354f1401e2 | 12,2,16,21,22 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
cf25ec5b-cd98-48c2-a2ee-40d7b19965d8 | 12,2,16,21,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
cbd54579-a3e8-48df-91ac-303747eab693 | 12,2,16,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
5e08d0a5-5d00-484b-a73d-7be0ad2532e8 | 12,2,17,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8f835a12-0e34-40c3-a8ff-c20e2c1b49e3 | 12,2,17,19,20 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
c7e54a34-9459-4db3-8510-f3775c38246b | 12,2,17,19,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e585668a-aff7-4739-9ec0-34ad22b5259e | 12,2,18,19,20 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
fc8c45ec-88c3-44d5-8ed6-5ec4f545d653 | 12,2,18,19,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8004c538-20d3-4ff6-8552-d987eac22ffc | 12,2,18,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
30c52c3b-6d82-43c7-86e6-a8e2ea209969 | 12,2,35,25 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
bc662a11-49dd-4d69-8f4f-f5c513604d6e | 12,2,35,101 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f52acd4d-9bcc-45db-82a3-f88e80679bc6 | 12,2,36,26 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
75fd2367-d39c-4ea7-a143-25baff69bbc1 | 12,2,36,101 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
dd1cefbc-24f8-4b54-8219-c6c33133bd8a | 12,2,65 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
642cf5ff-7810-4d3d-99c8-b8eca39c9726 | 12,2,73 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
9da68e33-7e13-4ed4-83b5-322cd53b7e77 | 12,2,101 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
c3d0b713-1b66-4c2a-8a73-84d9858ccf10 | 12,2,188 | ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
c703a733-53c4-4564-a2a3-4a9cbb812037 | 19,20 | ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 9 | FALSE
b13e0e5c-35ef-4f99-a8d8-05578de2e1b8 | 19,188 | ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
70cb2da5-4a5a-41ef-ad4d-9672698db939 | 23 | ASSY - OUTER DOOR HANDLE - RH (2) | 2 | FALSE
8f7b7fee-da39-4d6b-a42f-e9a453b5aca0 | 24 | ASSY - OUTER DOOR HANDLE - LH (2) | 2 | FALSE
f0bafa4b-7e03-4664-a2c1-4692fbbe9994 | 25 | ASSY - INNER DOOR HANDLE - RH (2) | 2 | FALSE
a6da6f22-cfd2-430f-aea5-aa9662f6f824 | 26 | ASSY - INNER DOOR HANDLE - LH (2) | 2 | FALSE
b8ba4e5f-af67-48ee-8b3b-7c2b962d6e5c | 29,2,16,21,22 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
718e863b-48ec-412d-baea-342b4b560fea | 29,2,16,21,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ca3f7935-fba5-4cf0-9058-96b29e1611ef | 29,2,16,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
43b09bd6-f7dc-4536-837d-9cd8cffd87a2 | 29,2,17,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
0020aef4-b2f7-48f1-a195-a40986723036 | 29,2,17,19,20 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
7f567e64-c759-45eb-90fa-0cae43a11a4e | 29,2,17,19,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
be08cf43-c96f-4656-95d9-ea8daa245be6 | 29,2,18,19,20 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
bc02cfc9-6af8-43a6-90e0-a0a3a9263dea | 29,2,18,19,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
606ec99c-ef32-4c30-a59b-3da7ffeb73f7 | 29,2,18,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
7018a6a7-4bce-4843-af09-1f2559e6496a | 29,2,35,25 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
52808b5c-f377-4c8f-8c30-f7b093c8900e | 29,2,35,101 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
2336ab93-4ca5-4774-ad92-b3279cdf7f18 | 29,2,36,26 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
3fcbb2d0-485d-47c3-8428-1b58256fc55d | 29,2,36,101 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
d9b9d487-484c-442e-bd49-1f1c40783f9a | 29,2,65 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
b0c54cd9-6bcf-4426-ae18-5ee1049ccd21 | 29,2,73 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
eecb6cf8-afe8-4865-927c-5b1ee13cefb5 | 29,2,101 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
435abfe4-e745-4dad-9690-5575d36e8748 | 29,2,188 | ASSY - DOOR LATCH - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
301eb2ad-d952-4cb5-ab31-4626e553af1f | 29,23 | ASSY - DOOR LATCH - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 4 | FALSE
84f9ae64-4572-43e6-be26-21e02a6535bc | 30,2,16,21,22 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
f0afe775-7d31-4370-99e1-c58e74d14927 | 30,2,16,21,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a3dcf1e9-e0ce-4315-91b4-b320ee09f018 | 30,2,16,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1f657845-9acb-47dd-9c93-5630d461510b | 30,2,17,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
87d23591-625a-48b1-8d5c-dfadddaad20c | 30,2,17,19,20 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
6a0f5412-1b23-45df-ab13-f00320eb4354 | 30,2,17,19,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
1fd85172-3bbc-4543-9494-291882c95532 | 30,2,18,19,20 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
23bb796c-c60e-4310-9822-dc76322555fe | 30,2,18,19,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
077e9373-463f-46e7-a710-1aa2c4180971 | 30,2,18,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2c39b9b0-08ba-4678-ae16-76e53a91ff2b | 30,2,35,25 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
e93ce2fe-043b-4642-b01c-82fba3213290 | 30,2,35,101 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
d652f5e4-3e8c-46ec-8044-c300c6cca2ea | 30,2,36,26 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
2e336e76-9a5c-46cf-896c-dcd319643a16 | 30,2,36,101 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
e9a6a5a0-c33f-4ea7-8802-ae2d9def0ea9 | 30,2,65 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
85ec34dd-84d3-4c64-97f9-d3c7b10ccb71 | 30,2,73 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
7bde72c3-e9ac-4ad5-a100-3971ee09c642 | 30,2,101 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
705be7f7-e60e-4bdf-8f9e-8b7d4a3258ba | 30,2,188 | ASSY - DOOR LATCH - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
2fca83bc-61c9-4823-98aa-5f49affd9abf | 30,24 | ASSY - DOOR LATCH - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 4 | FALSE
860089bb-315e-451a-b30f-017aede36ccd | 31,27,1,35,25 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
25136d84-506a-428a-afdf-683d8c2eecc7 | 31,27,1,35,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
41a913ed-b7d4-4745-bc45-afd20bf50a1f | 31,27,1,36,26 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
043f6774-ec21-4b3b-b48e-8f09527f5eff | 31,27,1,36,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1c95aa13-fcc9-4e7e-ba3d-19e3bbdb6af1 | 31,27,1,98 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 15 | FALSE
6b3e6b28-b20d-4c9d-aefa-f469a8631518 | 31,27,1,44 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 14 | FALSE
5cb2b92b-8736-46e4-a9bf-c8e1d74dda3e | 31,27,1,47,21,22 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
b9d21bcb-7f6f-49c2-8553-bcb9a8107470 | 31,27,1,47,21,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
dd21ab64-85cf-4888-90c3-531f82d2ab06 | 31,27,16,21,22 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
d2ff169d-3fd4-492d-957f-6bffc267cc09 | 31,27,16,21,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6198be36-3b28-45e1-b2b7-9230d663b09d | 31,27,16,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7679d666-4af9-4a44-b1ba-7062fe126f9b | 31,27,33 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 11 | FALSE
583572aa-fc77-4b4e-b9e1-95558cfb9530 | 31,27,35,25 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 11 | FALSE
9659f51c-734b-4c13-9694-6314ee764a73 | 31,27,35,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
112bda93-f8d0-48f6-a2c7-9b4664b63c4c | 31,27,15,2,16,21,22 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
60f078d4-c27b-4f4d-a8df-d5b60d2baaca | 31,27,15,2,16,21,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0c75164a-9fb5-4a6f-9bf0-6dfa463471b0 | 31,27,15,2,16,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1b745603-2902-4c45-9843-376f33a6c3a1 | 31,27,15,2,17,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2971b10a-b3f2-4235-be49-9db026bb452c | 31,27,15,2,17,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c16b384a-c38f-4658-905c-be016b16728e | 31,27,15,2,17,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
abd38fb2-6a2c-4e77-8aef-6d847c94b4ee | 31,27,15,2,18,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
62e72eba-3a8c-445f-a91e-22989a5f9783 | 31,27,15,2,18,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
95c6cac5-ffa2-4961-ae21-50eb19735dd4 | 31,27,15,2,18,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
91a8ec9c-8c4e-4bfd-87b9-ec037d153407 | 31,27,15,2,35,25 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b865ed20-ef03-45d6-bf26-b5aee1a31f8d | 31,27,15,2,35,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f5e79146-eb1a-4c5e-8d71-ec377ae69076 | 31,27,15,2,36,26 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
527f50fa-b5a5-4498-bd6e-f42e87fd72c5 | 31,27,15,2,36,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
5ee7ac48-faae-459e-b38d-53217ae7de31 | 31,27,15,2,65 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
21d3f414-9d11-4abd-a2b4-55094e968534 | 31,27,15,2,73 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
d14c363a-95ff-46a5-ba53-fdc71b1e2f0f | 31,27,15,2,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
0cbd2c56-672e-4092-a337-c41c04974781 | 31,27,15,2,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
01f2843a-8d3f-4ba9-bb6b-a9d384e096e8 | 31,27,15,13,17,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
a4bc2be6-ee68-42be-90c8-cfce746318ed | 31,27,15,13,17,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
e2ec62b1-7528-4884-b27e-f1facaa98f56 | 31,27,15,13,17,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
fb000c01-6142-4fa0-8df0-3ed63fa4bb93 | 31,27,15,13,18,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
97df656e-8109-47e4-a452-3b003df56424 | 31,27,15,13,18,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
6a70ca93-cbcc-46e5-a3cb-1fb7eed8a0cf | 31,27,15,13,18,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6d6f5464-dc25-4dd0-b0bb-a1992ba4bef1 | 31,27,15,13,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4fb290aa-4f0f-4104-b0bb-f41151f75bb5 | 31,27,15,17,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
dbd32526-cd2b-49b1-af36-55abf89af4c9 | 31,27,15,17,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
ad7a9e9e-f4fe-46ee-9616-8d8fe83c126d | 31,27,15,17,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0704c4e6-e4be-4663-a220-b49bf1b4ad0b | 31,27,15,18,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
c68f2b6b-a4dd-4f2a-a7e3-a8f7741a6ba7 | 31,27,15,18,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7d3e1e7b-23ad-472e-b899-0e57bcee9fe3 | 31,27,15,18,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7a5af22d-4358-4560-9b53-c8ae3420fd56 | 31,27,15,19,20 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
f78ead0e-fe9e-45ee-a366-193c8d37bcc5 | 31,27,15,19,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f30248f3-398e-451a-8049-d367b5e21034 | 31,27,15,188 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
5e59dbbf-c736-49dd-a2bc-b3236680df82 | 31,27,15,23 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 10 | FALSE
de643763-ed06-4937-b37d-1f1d0178790d | 31,35,25 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 8 | FALSE
392bd103-d67c-49cc-85f0-5e0f28c9ff11 | 31,35,101 | ASSY - DOOR HINGE - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 12 | FALSE
94248efe-7e34-4d99-a89c-3604a6969132 | 32,28,1,35,25 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
451edd93-59d0-4515-b568-16128fd6fc11 | 32,28,1,35,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8cff5ce3-bcb5-4d8e-9018-51255dbcb412 | 32,28,1,36,26 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
50d4d37f-9be9-4a0e-a568-8e3a7a1535f0 | 32,28,1,36,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bdde6bcd-fd97-42f7-8593-0e15da695060 | 32,28,1,98 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 15 | FALSE
4fd23a2a-a6c6-4e0c-b3e3-dd059d17a9c8 | 32,28,1,44 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 14 | FALSE
59b0d542-e938-4366-a583-b50da63ac96c | 32,28,1,47,21,22 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
1591fbcd-24a0-47f1-b542-57b132c2a45c | 32,28,1,47,21,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8f0dbb71-0263-4dc9-9781-12699b1650d6 | 32,28,16,21,22 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
33ec2c08-715b-409b-a70d-c8e26224b07f | 32,28,16,21,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
bac85e7b-4355-419b-887b-876eca612276 | 32,28,16,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1f2b6a72-4238-4939-85fc-c73614694915 | 32,28,34 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 11 | FALSE
69c16459-6092-49a2-a021-511fc5e78d1a | 32,28,36,26 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 11 | FALSE
63ecc7c2-53f8-4940-8fc6-ed0f31c58f7c | 32,28,36,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
f5963126-e011-4075-8784-3d1875ba523a | 32,28,14,2,16,21,22 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8b3e8f11-0019-46dd-8f0d-95319044c584 | 32,28,14,2,16,21,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
40cbb9f2-65f5-424e-b65e-bb07fa38752b | 32,28,14,2,16,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
389cfbae-4c59-4db6-b3fb-e4fab69d8883 | 32,28,14,2,17,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6140a19b-f987-412d-999c-b09bd24dd2dc | 32,28,14,2,17,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
688e4f10-c728-4fdd-a4e5-ab1a006f2b90 | 32,28,14,2,17,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
fc39ff06-3762-44db-b2b0-b3897ad86018 | 32,28,14,2,18,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
796ebb1b-2b5e-4f6a-aea4-b8c99c5983f0 | 32,28,14,2,18,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3a4527d4-53fe-4196-a375-ae1d8703bd38 | 32,28,14,2,18,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
36b77678-b041-49bd-b76b-57b970667bdb | 32,28,14,2,35,25 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
7ce6847e-7698-4564-8a77-dddb1358356c | 32,28,14,2,35,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
dfaa2d5d-6f59-4660-a27c-fbb12e12c08a | 32,28,14,2,36,26 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
6e0bce86-8889-481c-b95f-93f687c7346f | 32,28,14,2,36,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2f1db2aa-cfee-45cb-9059-33dafb38009d | 32,28,14,2,65 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f015af16-3706-4381-9a51-66a0e237a28f | 32,28,14,2,73 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
76f4a602-c977-4cd5-8b25-c5a669431e26 | 32,28,14,2,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
8c8bcec9-225f-4e18-a18f-c3dff5835ef3 | 32,28,14,2,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
47980913-ffd0-4c04-b4b9-400564b2bc2c | 32,28,14,13,17,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
8f0167c7-30fe-4baa-827a-02306d155148 | 32,28,14,13,17,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
ec37f4cc-ebb4-4556-bef0-93c714a276d1 | 32,28,14,13,17,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
95cf8736-393b-4cf6-8744-f8bf95bbc078 | 32,28,14,13,18,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
b3543609-38dd-415d-8df3-d14dbb5a9b32 | 32,28,14,13,18,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
6f374f67-97dd-4fc1-87e9-dde45341fe85 | 32,28,14,13,18,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e7f9273b-bb19-4ab2-ab06-920c6607d0a5 | 32,28,14,13,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7bc68e9f-0fa7-4d8e-9df8-54e07e8b401a | 32,28,14,17,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
73ba50d2-cc3c-4d0a-9659-ffe8e7543d05 | 32,28,14,17,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
b3d3c511-cad5-41f5-9ca0-844499f1c020 | 32,28,14,17,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fccfe7eb-8ecc-465b-916a-04e167ea02dd | 32,28,14,18,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
3250cc84-6c48-44e8-847e-1b9203b8109a | 32,28,14,18,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1dd1ea33-fb83-4b19-8bec-9a1a2a72d225 | 32,28,14,18,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f7eb2e83-5d1b-401a-ba01-33fbfb526e8d | 32,28,14,19,20 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
cdbbfc66-8c93-43e5-9168-e20c716d883a | 32,28,14,19,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f1b3167b-8f33-4bf8-a5f1-5c0bc059f336 | 32,28,14,188 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
eeba869f-87a8-4544-aac6-70b3ff6187f1 | 32,28,14,24 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 10 | FALSE
83cbff0d-7089-4540-91e3-2f3b90d6fb94 | 32,33 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 8 | FALSE
9d7efbf3-5431-4079-b311-890158a32548 | 32,34 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 8 | FALSE
b77e13da-e55f-44aa-85eb-c3569928d291 | 32,36,26 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 8 | FALSE
ceba4237-c658-4b62-a12a-b930682042c5 | 32,36,101 | ASSY - DOOR HINGE - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 12 | FALSE
96d17a5d-d8a7-487f-b3eb-418eea407a99 | 39,28,1,35,25 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
25073e73-caa1-4105-8ee4-7595b74cc009 | 39,28,1,35,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
aea598e0-daca-4fd8-8751-9f10ad8c5e87 | 39,28,1,36,26 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
2fe1be41-c013-4073-9766-7680526ca5a4 | 39,28,1,36,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
201ddba5-0074-4d6d-80cd-18965254a156 | 39,28,1,98 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 14 | FALSE
b39cbc8d-7b3d-4a51-b17a-22b860a6e4c1 | 39,28,1,44 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 13 | FALSE
394e6686-27ba-4d52-94ba-3d8efa0fadb9 | 39,28,1,47,21,22 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
0b7c7806-c48d-4001-b8ce-e1a4d0d10f48 | 39,28,1,47,21,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e52defe1-6c02-49cd-85b0-b9335df91a9c | 39,28,16,21,22 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
b88e1ce2-96dd-4c28-9eba-028111eaf4b7 | 39,28,16,21,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2904e5b5-464e-4c03-abbf-83c7c8becb7b | 39,28,16,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
fc9dbfda-fead-4c9c-b780-1173201782dd | 39,28,34 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 10 | FALSE
14d12e82-548a-46be-b887-a3c55195d7bb | 39,28,36,26 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
1ac3251c-1474-40b8-9343-f13b7a09b975 | 39,28,36,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
e9283d90-6b92-4ce5-a108-635b0b71e849 | 39,28,14,2,16,21,22 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
72c7c151-8821-48fe-ba46-7776e5a4836b | 39,28,14,2,16,21,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
1d1d3229-e295-44d6-bdc2-86e3bb3cc3cb | 39,28,14,2,16,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c06fc970-8205-4f95-9c74-caf2b3b1a564 | 39,28,14,2,17,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
c7b90f37-9560-43f7-a6a9-6ae4f54b01bf | 39,28,14,2,17,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
390afc1f-0e6a-485d-a5d7-6291c649018f | 39,28,14,2,17,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5a3b9258-269e-4cbb-b23a-189029b964f4 | 39,28,14,2,18,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
f26ba9b9-038c-4cc0-b438-530ba46dcb17 | 39,28,14,2,18,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
0a5df33c-ccff-4539-8999-49246283412c | 39,28,14,2,18,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d0d387e4-573e-44cb-a62d-52d4e9cab3a2 | 39,28,14,2,35,25 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
d55fb8af-0337-45f3-a966-80cad1997454 | 39,28,14,2,35,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
0dff6678-833e-4297-8815-0ba800842f75 | 39,28,14,2,36,26 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
fbd59df6-74bf-42a6-afef-e43feeaca8ea | 39,28,14,2,36,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
6e612c63-f38b-499b-8ff5-7542952b1c44 | 39,28,14,2,65 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
616cd609-11a7-4b40-9267-a0d42b5a13b7 | 39,28,14,2,73 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
5d990de7-cba2-4d17-b135-292b6f6c0f99 | 39,28,14,2,101 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
6e65d57e-6593-4ecb-a06b-1da9f8983d25 | 39,28,14,2,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
99d9c1f2-ebb0-47a9-bbfa-a3c556efd0f1 | 39,28,14,13,17,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
886a4a88-a129-40d6-a7af-3ecc2f6c5a77 | 39,28,14,13,17,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
9d9cefce-4872-43ca-b16a-c4c5cec72d8a | 39,28,14,13,17,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
fb0b3568-b408-40cd-82eb-40ddedc4f18f | 39,28,14,13,18,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a676f066-fa4b-4744-9f9a-948913bc1f8c | 39,28,14,13,18,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4a5bdbeb-0e7e-4d5a-9f6e-c22ff9747955 | 39,28,14,13,18,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
235b501e-dbed-4536-992e-2fd0781d9719 | 39,28,14,13,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
522361cc-7573-4ac9-abdb-3eb2fa516a87 | 39,28,14,17,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
0564bc0b-c528-48e1-abce-d77b69d53b4e | 39,28,14,17,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
e24932c7-93f2-418e-8789-472747fc918c | 39,28,14,17,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
f3490a7e-19e9-4516-bcaa-d435f9f6dc09 | 39,28,14,18,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
489df911-db72-4357-9e3c-2a8c271ad8c5 | 39,28,14,18,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
aed4731f-93c0-468d-96a0-fc4f292d6637 | 39,28,14,18,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
841d8f6b-e592-43ee-a8ff-74c485a69792 | 39,28,14,19,20 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
b7f0761c-869a-4aa0-9d5e-c0d6f649385d | 39,28,14,19,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e21fcbaf-ee91-400f-9f90-b7a32a8ce8fd | 39,28,14,188 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
1e7d87dd-b581-4305-a9d1-710fe5868681 | 39,28,14,24 | ASSY - ELECTRIC WINDOWS - LH (2) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 9 | FALSE
69d4423c-2993-4bf2-8ed9-9dd824ea4600 | 40,27,1,35,25 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
18b7e192-8bb2-40fd-8479-213aa91f6f4d | 40,27,1,35,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b6d80500-7a9d-4ad0-bdc5-02ea96005c31 | 40,27,1,36,26 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
e78c133c-50ab-42fd-804b-346cff48be33 | 40,27,1,36,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
cfaaacdf-15eb-4364-af55-f6bdacc722a8 | 40,27,1,98 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 14 | FALSE
49a3a27e-6d73-470e-b73a-26560aca464b | 40,27,1,44 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 13 | FALSE
a05086ed-05a2-4da8-b3e4-186c8291dae4 | 40,27,1,47,21,22 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
23d60500-710b-4d1c-ae70-0b4cb9993a50 | 40,27,1,47,21,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
65a54551-295a-4aa7-8c26-40973f26dd49 | 40,27,16,21,22 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
142c49b8-8fce-4767-a94b-1fefd909ea05 | 40,27,16,21,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e6b052b5-6e47-4762-af65-ffa97f3c0e49 | 40,27,16,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
59b1e6fd-a04b-4dae-a57b-057419e8e66d | 40,27,33 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 10 | FALSE
f687cb3f-48b6-4dce-adae-34ed178982f6 | 40,27,35,25 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
4ae00c71-c26d-4535-8f27-f531888ff769 | 40,27,35,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
1fa4c98a-3d97-436a-84a4-070161d00e46 | 40,27,15,2,16,21,22 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
f7daa89a-1165-4844-a6e9-3b272a1b38c2 | 40,27,15,2,16,21,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
553a86ce-def8-4834-a421-b9354551ec72 | 40,27,15,2,16,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
446568b2-18c9-4be4-8210-85fa931cc728 | 40,27,15,2,17,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
201d9fa7-ea0a-454f-bb22-b96c4f6a4a0e | 40,27,15,2,17,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
6e157883-8576-4787-873f-2e847c574682 | 40,27,15,2,17,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3946ac8f-264a-49c5-bfb7-4bb69e5c01f4 | 40,27,15,2,18,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
f02c2f26-89b7-431d-afb6-b4f069aa03ba | 40,27,15,2,18,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b553282b-3cca-40b7-8fcc-1b95bd95d4ef | 40,27,15,2,18,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
220fb7c1-e095-4ecd-9510-ae94bae33338 | 40,27,15,2,35,25 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
2d64113c-c244-4cbf-8297-aadff2cc0add | 40,27,15,2,35,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
ff9cce78-de1e-4b35-bd51-9908deb1d23d | 40,27,15,2,36,26 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
95c81e15-80b0-485f-9744-451b4815b73c | 40,27,15,2,36,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
7a6c32bf-4091-4c91-8734-e9bb609c9aa5 | 40,27,15,2,65 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
85ca1175-4cb8-4617-86cc-7b068c06791a | 40,27,15,2,73 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
91f7bd41-d54a-4465-b42c-3317971723c7 | 40,27,15,2,101 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
613443b0-b2a0-4bcc-8b5c-36eecc374cd3 | 40,27,15,2,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
ec452e88-bbfb-402f-a3a1-869d33d26916 | 40,27,15,13,17,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1ae0f37e-98cd-48e2-bf96-d16a39dccf31 | 40,27,15,13,17,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
7ad711e6-3aef-4c9d-9a6d-4ee449c6b115 | 40,27,15,13,17,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2da304ac-c4af-448f-ab86-656fa88d57ea | 40,27,15,13,18,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2c8d0456-03bc-40d8-8caf-2a74628314ba | 40,27,15,13,18,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
87088330-2be0-42f0-88fb-2e7bf34dce77 | 40,27,15,13,18,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4b62c7f1-4e37-4eab-99cd-e70313bf9b33 | 40,27,15,13,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
9b737998-6d88-417e-9481-e08406c34eb8 | 40,27,15,17,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
ee2f5ab0-1e7c-4e71-91cc-161c7375a783 | 40,27,15,17,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
eb802188-d341-4e05-bd21-fdeb3ae6a400 | 40,27,15,17,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
056082c4-ddb0-48c8-ac2f-f4b1326b8e26 | 40,27,15,18,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
48ec9a01-aad6-4d74-abae-b1a89bc9602d | 40,27,15,18,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2b7a0d3c-067b-4e12-9ecd-217936b539e1 | 40,27,15,18,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d250858c-ea64-426b-9131-c9b59291a008 | 40,27,15,19,20 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
bf87bbcb-0b53-4fcb-97f7-931b57199ae7 | 40,27,15,19,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
80ac448b-e105-447b-8951-8b5157a50aaf | 40,27,15,188 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
deae50c4-f8aa-49cc-8e95-06071611d90e | 40,27,15,23 | ASSY - ELECTRIC WINDOWS - RH (2) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 9 | FALSE
e89eb18b-83a4-4a28-854a-d4ffe9d0e389 | 44 | ASSY - WINDSCREEN (3) | 3 | FALSE
ae403973-e5b7-4353-b265-c5b84387f787 | 45 | ASSY - WINDSCREEN WIPER (3) | 3 | FALSE
1adcf4c1-1320-4625-8a52-6fb0f04be095 | 46 | ASSY - WINDSCREEN WASHER (2) | 2 | FALSE
72331b94-5f7f-47da-8819-0ae1e7d52993 | 50,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
8dd3c051-de93-4df0-a58f-a2c4309526c3 | 50,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
74156156-8c96-4280-a669-8cfe2dea9b06 | 50,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b2d49c33-7df9-4611-a8fd-0f8ed98d9a4e | 50,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
dd4fe851-6584-401a-bb35-bde9dc1d0881 | 50,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
8fd52bca-1bc0-43a5-8adb-611b91e63d31 | 50,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
4a93a746-daa2-4c44-b2ba-496949eb14c0 | 50,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6459327b-4690-4ad0-a37b-4453498d4fe2 | 50,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6ea433f5-36e0-42e4-94f4-a6b6b39aa9b2 | 50,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2f6631bd-f234-4c78-bf12-d6cbfa7b0e82 | 50,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
f148e080-825c-4a8b-96cc-ccee71e21906 | 50,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
cb2446ca-d8f7-484d-9d7b-b83fbc05ec50 | 50,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
40d62055-d267-4d2f-92da-6ca0f1eb91ee | 50,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
f7591225-0cca-474a-8aa1-43b0f16765b8 | 50,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
e0c220f9-c1bb-45c8-8a99-42cc1a1f670b | 50,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
658b52be-f6a3-4ecd-9e7b-17aa9918f183 | 50,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
a8ee64cd-0e08-4228-a891-d14eac94c754 | 50,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
0643ed21-7e14-4d73-9bd5-218d4517f6f8 | 50,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
114f7ed8-35b2-4914-a98b-da472b8b8817 | 50,74,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
87018781-5a1e-4318-9bdb-90ae1ee92846 | 50,74,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
aad98551-7d4a-4c7a-b3f9-f05edf7d2b4c | 50,74,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
32e64cc9-2a96-46f6-aad0-d658f5f22dcf | 50,74,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
a934b988-7a55-48b2-aa06-da6b0f5c8feb | 50,74,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
1b5147f0-5d3b-4d32-b2e3-35796cc3c175 | 50,74,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2ea8a65d-4b7d-44ca-96aa-3cdb5d3e1770 | 50,74,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1998184c-7023-4d24-aa93-3e656b0f95eb | 50,74,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
30764a58-ac36-4fcc-8574-96cded601f16 | 50,74,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
eaf76f6d-c87e-48dc-98fe-5f3e55c1be57 | 50,74,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
bae9e7ba-e693-434c-b85c-1dad06d27da5 | 50,74,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
739b4011-5445-443e-b164-e92237792513 | 50,74,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
35631139-1ad0-4882-a221-fa018c22fffa | 50,74,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
c19c56c1-79e0-4301-bba0-0d047afe9e4e | 50,74,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
87f01c51-e3ad-4020-882d-6f3dde578a41 | 50,74,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
606288e9-e593-4b72-83a6-58fff7328748 | 50,74,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
bcb0ea3c-be19-41c1-bcf3-bc440382e2e7 | 50,74,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
69c82df1-db67-4f7a-bdb5-74988c517646 | 50,76,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3d598f7b-09f1-47b7-9964-364630fe6580 | 50,76,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5bfc795c-d5ea-4e52-b7bb-938c486218b1 | 50,76,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f5725eff-fb01-423b-aead-b72bbba18223 | 50,76,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
573cc0e8-30fe-4b02-b9ba-38b80f287da6 | 50,76,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b933ff40-6cb3-485d-b4bb-2e5c0a3baa69 | 50,76,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c1e300f1-bfde-44a8-a87d-0c6abb9b0056 | 50,76,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
7904cebe-f62c-4647-b4a7-4c09afdfcbd3 | 50,76,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b15a2f8f-5e7d-42d5-9c5e-94e11c0e0e51 | 50,76,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c2ee1d63-e63b-4dc3-b6ea-9ba0f1bbc4e6 | 50,76,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
9a22d1e4-5084-4c03-a436-c466ce4547d1 | 50,76,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
28718bd7-90d7-4aa3-aa01-6d3c691f8dc3 | 50,76,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
4adb028c-141c-422d-81cf-e813d6e76090 | 50,76,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
59ccbfed-04f3-4df5-b75b-323c655b8c08 | 50,76,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
152ca995-37b1-468f-8407-fa4937882392 | 50,76,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
3fedc800-291f-4a5b-a2f7-8e9ab6acb124 | 50,76,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
aa1cc537-9570-470a-9df1-c89ae7debea2 | 50,76,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
ca4aa617-770c-4ccc-a1e6-11a4d6c85e59 | 50,77,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
af25c62d-0108-43b3-bddc-f62188f933a6 | 50,77,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
281fd782-b765-4d30-9b75-7cd5a25239c5 | 50,77,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ffa3d20a-742e-4b8e-8271-244391ef7357 | 50,77,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
5b32d83c-4fd8-4410-9d2b-0a5a8471f595 | 50,77,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
1163a25b-9a7f-479d-9b50-e5affbc9df72 | 50,77,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
1603fb34-3962-437f-8ffe-0c19a3d862ed | 50,77,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e05430e9-abe3-4a39-a9d4-df2b2cb4da2a | 50,77,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7aa4a099-5876-49de-a3f2-b1d8bc7b1299 | 50,77,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7b66668d-6580-48ae-9b8f-ba69ae0d97a6 | 50,77,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
680de27b-c654-4222-b928-eae668ed3615 | 50,77,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
aa629100-0dbd-4f6d-8973-7dafed1b7b68 | 50,77,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
5ccdea61-21bb-4c00-b191-0c3c428eab6a | 50,77,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
79568bae-6a06-4c94-b37d-6171868edfc6 | 50,77,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
6b6fe084-3d66-4ec0-a41e-a185c8861e15 | 50,77,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
606375f8-1404-4fd9-998a-66ff8d7672bd | 50,77,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ab7987ab-d24b-4a5c-90ec-515f768fa15e | 50,77,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
a3a4b736-d892-48ce-b6e1-972fcdadb3e7 | 50,80,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
68badc86-9ae3-4c5f-ba8e-cf7853bf7860 | 50,80,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a224b6e3-1129-4bcd-9728-12682a5ffd0e | 50,80,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ada0d1ff-701b-4dab-a9f5-46228c965b23 | 50,80,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
f28b96e4-40ee-4c23-ae44-0ec4cbd6fde6 | 50,80,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
d2670044-ee87-4a7f-bc6c-c7abbddc7c06 | 50,80,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
01a65012-ba74-4689-94ed-2998aad1278e | 50,80,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9b517b78-e9ee-420e-860a-7455fcc78af9 | 50,80,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d1a11b97-8b48-47fd-afe5-fe5d48d2cdfa | 50,80,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1e0e2eeb-c85f-4f81-ab6a-80a3f8acfbfd | 50,80,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
542cc869-9120-468f-9668-1ec2c81c08c1 | 50,80,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
705fa862-28ef-40c3-9096-b3b6c347a9dd | 50,80,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
7ff8b60d-26eb-4257-8269-5dc46719c8bf | 50,80,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4b43ef15-23cc-438e-a6a4-c03dfb813e9b | 50,80,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
c4142fc0-0a53-41fd-9874-7f246377fbf7 | 50,80,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
cfd30bbd-183a-4f5b-a8bd-71aa5958710f | 50,80,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
5645109d-b4c0-4050-bcc4-76a4ac925cc1 | 50,80,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
141d73f4-b32a-4654-873f-abba9fce7314 | 50,81,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
133d3a4a-e3a3-4fd1-8b90-fde76df121ef | 50,81,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
00bc05d7-cf68-46bb-a0be-6964ab851945 | 50,81,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
39ca9148-9168-4d0a-aec4-60fea848c47a | 50,81,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
b3318490-903a-419c-a787-4b374f5caaec | 50,81,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e7ee307e-d6d6-417a-b2c8-b781ce87db7b | 50,81,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
1904e1fc-c0cf-44fc-8972-43133525e843 | 50,81,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f9044beb-2bb4-4923-9904-4ac3a03d94b0 | 50,81,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3d02dea4-91eb-4d8a-9ca8-66738e815a96 | 50,81,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
cbf018d7-d135-4405-9efd-1595111ed7bc | 50,81,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
c5db438a-c071-435b-9d91-a7871ef67b86 | 50,81,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
17e5ae93-5b2d-4cdf-88d7-0f2d58a126bb | 50,81,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
b6aeef56-1dc7-42f7-bea8-9c7942a36960 | 50,81,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
6ec93947-0f27-4c0a-abcc-7ed7e11d6d22 | 50,81,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
308e4261-dfb9-4afa-8359-d719f8f765c9 | 50,81,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
3f96c19c-e4a6-4a50-b4d5-78ccc38c72c9 | 50,81,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
54b17104-ffcc-4bf6-b507-72047da4dc0a | 50,81,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
6bc69da7-22c3-4166-b3c7-36df3728c6dc | 50,83,2,16,21,22 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
18fd8da3-773c-4f50-b772-1f28efb2ee83 | 50,83,2,16,21,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
54c4f5a0-65ce-4075-b43e-2279fa37965c | 50,83,2,16,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3e547fc9-545e-409e-8150-6a996f650cc3 | 50,83,2,17,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
14e73d59-010c-453a-95ba-66127bb397d7 | 50,83,2,17,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
fbdcb34f-7d73-44e1-b358-ad29d49c1e4c | 50,83,2,17,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7d422294-8791-4b41-8c07-d52603a52579 | 50,83,2,18,19,20 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6fec3ce8-576b-4d47-b77f-e7190b8f0ede | 50,83,2,18,19,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
565b750f-83da-4743-a121-0fd1562bb3b5 | 50,83,2,18,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9cd40098-a9fc-46fe-973d-95ba49291fd7 | 50,83,2,35,25 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
300a6796-6d98-46b8-a4e9-2f9372f1ceb2 | 50,83,2,35,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8bd175de-c680-4f3d-bc1e-b817332cd17d | 50,83,2,36,26 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
16a4e62f-2932-4dbf-8c4d-caa065b21521 | 50,83,2,36,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bbd0f1b6-c564-4821-9e96-b17b69686d77 | 50,83,2,65 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
c81653fa-6f3e-469b-9aeb-af1b4823cc63 | 50,83,2,73 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
bebe25e2-fa0a-4119-9df1-c35fc5fe25ac | 50,83,2,101 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
0eaad4fe-89a6-4653-b3a6-a187c60ae59c | 50,83,2,188 | ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
fdddbd5b-d757-4e32-9fa7-e58ded84a67a | 51,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
0a9761b9-2bdd-47fa-b6cc-aaa9eb26011a | 51,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a2b937e1-f77b-4ceb-a121-9199bd3d5078 | 51,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
53dba718-26cb-4c14-ab0d-f22a0b68d1b3 | 51,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
21c2781a-f290-42bc-aea9-6c5d0b843cd3 | 51,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
26a8167a-6386-495c-a3c0-35f438b113b8 | 51,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
389eea74-fde6-4393-aaab-73ccce6983b4 | 51,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
44c5b287-1b43-44a1-91d4-b39490756f13 | 51,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
b251dedb-e10a-4d07-9bed-2b0bdc24d99e | 51,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e067e8fb-a832-49cd-a186-e6aabe63aaca | 51,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
1f9ec8ce-a05b-46db-b69c-f66e68bcbb35 | 51,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
f99a64f4-3a38-4923-986e-3282629227b0 | 51,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
a9cbcefb-5bee-41af-b77b-701d790aeb9d | 51,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
287ffdb0-03c7-4758-82d6-c5b7580e4eb3 | 51,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
f8244560-b3ff-4d0d-996c-465696de7687 | 51,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
72777c01-a880-493b-bea5-0cef60fa9da8 | 51,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
4b2a6d7b-5d02-4055-bcfd-bda25dccf758 | 51,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
1af8d10d-5940-457e-a0bf-7f439f26223e | 51,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
72dc0e22-7a69-48cf-bc71-5c198c7d33eb | 51,74,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
a3bc6d73-16a4-4e3b-a57f-b9b285dcdbc6 | 51,74,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
26a86753-0917-4243-b566-1cc614c41fa6 | 51,74,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
19cd61dd-c01c-47c4-a8e3-2d24d4b77d34 | 51,74,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
c79da93d-ab1b-405a-9388-e2b9cfeae103 | 51,74,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
112ed674-b614-4bd1-8a2c-b3b52e2b91b5 | 51,74,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
0b412dea-356d-4e8a-a648-f359b07f1faf | 51,74,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6ebc808f-0aca-4323-8d26-83925d5f40b3 | 51,74,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9d35d1b7-5b02-41fa-b665-a888291261f3 | 51,74,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3901e456-020e-42a2-884e-666b37033e51 | 51,74,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
f6976da6-2731-4c69-a586-598800a9b6da | 51,74,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bc3e6a2c-fa82-433f-aafb-5d9591195b32 | 51,74,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
b922ed79-ffaa-4057-b26f-5af40336bbd4 | 51,74,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7c41cd5a-3967-465a-90f2-034750ab819c | 51,74,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
311c8858-10f8-405a-9862-ce19e56069b0 | 51,74,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
1862bcf0-7b03-4cdc-8777-a85d9cc835e3 | 51,74,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d32870bd-f609-46a2-99e1-99c0e71a09b1 | 51,74,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
51120e79-d667-43cb-ad5e-37bab046d16f | 51,76,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
ca610a8b-65b3-478d-94bb-8cf56855e709 | 51,76,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
c9003aa0-2638-475b-be88-97d00d14830a | 51,76,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
201c0299-ef72-4c26-9a3f-31e25f52844e | 51,76,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
092b9648-ec4b-47c0-9fc7-cca55b84f0e2 | 51,76,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
ec13d006-bb01-4617-bbbe-fca781753181 | 51,76,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
8f179a18-8686-4a01-8d2f-e2c0094d2c05 | 51,76,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1c017380-efbe-4b2b-91af-b80f27159a28 | 51,76,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2eb2c864-75e6-4c3d-800a-58eef9e8f906 | 51,76,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3a6ffccb-2d1b-48ff-9f56-2e794c7467fe | 51,76,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
1dd5420e-263e-4168-be8b-9729d92420b1 | 51,76,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
f9c13442-6760-4048-8998-8766d42674bb | 51,76,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
e7c36dd1-c4ba-45bb-a22d-ad567318c56a | 51,76,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b617c9c4-33d4-4ca4-a95f-702ef22a5232 | 51,76,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
bd2f9bec-af15-4a98-9c62-7287a2a8c607 | 51,76,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
d96901b8-7a70-4fdf-9cac-1e6318837d17 | 51,76,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
f9535385-820f-4906-922c-6e2a04a3ffa3 | 51,76,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
1e366327-8caa-4678-9eb8-07c73f8462f7 | 51,77,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
67c2d938-c26a-4055-9f4a-181bc9e3ed52 | 51,77,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
777e37c2-a3f5-483f-9d12-0b4b8467044b | 51,77,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f33a1220-674c-411e-b001-948f0ad48cc6 | 51,77,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
19736c04-ddd9-4fc9-b284-9ce2e76c5553 | 51,77,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b6f5c642-b2c4-4f9f-90a9-7fe52fa686ea | 51,77,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c12ac848-9370-4bce-91d3-2493a5910a8b | 51,77,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
bc1b3c12-a28f-416d-a1f7-f7886a43710e | 51,77,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
dc53b7ec-3455-4a7a-a73c-f3912e7c9abb | 51,77,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6ceca753-bb80-4987-93e1-87916128ecbe | 51,77,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
4b28632d-b6dc-44c3-ba37-04f5d3137857 | 51,77,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4415aff3-b2db-442c-aadf-3c822cde8083 | 51,77,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
7daa1fb0-0c16-479d-a4e8-55cd26ce6e14 | 51,77,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bb31fc25-0c84-48f4-b167-71bfe604ce7e | 51,77,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
980f0ef4-cd8c-449f-96c3-22c312418774 | 51,77,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
7012571b-c25f-4fb1-9794-03061daccb8a | 51,77,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
9f725615-47e7-4732-b2ab-8322c5d43a2d | 51,77,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
f83703a6-890a-4f29-878c-978059fed2e6 | 51,80,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
f5360139-302e-47bc-8abb-a746367f5325 | 51,80,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
967344e7-b8cc-428a-80fd-2fda6a652480 | 51,80,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3d7f0af0-ca91-4125-a5de-f41a32a21168 | 51,80,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
db91323e-ac59-49e1-a3f2-8770323ace89 | 51,80,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
aa48fd12-c5ab-4520-98bd-593204e7b48c | 51,80,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
998fd07e-bb4e-4e99-b1de-e578c293edd0 | 51,80,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a17bad7d-e376-4ce6-ae7c-c1462badc905 | 51,80,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
376f6e1e-33bb-454f-a0f7-dd7fba00ceae | 51,80,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
60fbfbf2-4ed2-4d0e-aa70-773a908abca8 | 51,80,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
daa46b46-a73d-4d8e-8e1f-a226a1364b18 | 51,80,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3409f58c-0c75-478f-8332-e516fe2d32a5 | 51,80,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
405a0ff9-d359-45c4-9b66-dde6c50800de | 51,80,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
03ced901-ab13-473d-baf2-3de15e1c827c | 51,80,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
675cecaa-97d7-4ac2-b4ee-bed6cd6e1ed1 | 51,80,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9ca617fc-50ef-4c76-b334-e83324b651c4 | 51,80,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
7219502b-8070-41ef-85c5-570d1f456f7d | 51,80,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
32d437d5-0061-4cd7-8323-b2d73706ebda | 51,81,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
f8d09cd1-5b7e-4155-a099-09fa08813960 | 51,81,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
decab89c-3f2d-4f2d-8805-2e25eca7fe4d | 51,81,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3a354119-d186-479a-b844-1abde9841772 | 51,81,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
76577573-1dbc-4972-9eba-86c2b7eee85b | 51,81,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a3437c3d-54a3-4570-a88f-b553fa83a4bf | 51,81,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
18427f80-94fe-4098-b704-5c667f37c8da | 51,81,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
46f8d424-8f21-4d42-bb2c-591b3dc3fd06 | 51,81,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2f8feb9e-57bb-4db6-a7fa-30bacd447394 | 51,81,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9324350f-ec52-407a-b201-facb05316808 | 51,81,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
896c430b-6cec-47c6-874e-7c0a554ef805 | 51,81,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bf2f3697-ba96-4f1e-8572-d1c9d02fa229 | 51,81,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
4dfa096c-06cd-49d1-a86b-1cc280afe06c | 51,81,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a447dcae-4ec6-4db8-8520-a5b8dc444685 | 51,81,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
bc8bc990-587b-41f5-aaab-dd47c9e763ae | 51,81,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
4701a58f-d545-484e-9872-766df18ffe81 | 51,81,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
64f2dfe7-feac-43b1-bfe5-90e043a2c14a | 51,81,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5f707494-051c-443e-95c5-8ab8d8a267ad | 51,83,2,16,21,22 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5f8834dd-9772-4be6-9a0d-0bb9345c38ad | 51,83,2,16,21,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0e802316-d8a6-41b1-a983-9805931251c6 | 51,83,2,16,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fbbbbe18-3d74-4d88-865c-b0992f7bf700 | 51,83,2,17,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
88517f35-3490-45fe-93c4-95ed9197dc12 | 51,83,2,17,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a7cefb1b-d499-46eb-ae72-ad9100f33154 | 51,83,2,17,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d7621a71-2d78-468b-a98e-849e96aa8c72 | 51,83,2,18,19,20 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
579945bc-0827-4b90-a699-b281bdde1bef | 51,83,2,18,19,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1b0a7311-373c-4e2d-8d35-cd38be162bb8 | 51,83,2,18,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
8696e243-5740-43c3-88eb-83b2ebd7eb92 | 51,83,2,35,25 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
f1df7308-98b8-43ef-a9e6-acaf98e1344c | 51,83,2,35,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4f17261f-b1d2-428b-a9f7-75f9daeb9438 | 51,83,2,36,26 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
2ce8cb9f-3ff1-49f6-83dc-1d710bddc691 | 51,83,2,36,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7564c20f-868e-43c4-9ed4-a32ab356a6cb | 51,83,2,65 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
a545186f-640f-4794-8bc2-dfced174322d | 51,83,2,73 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
19c05c9f-02a0-4c69-9c80-3ef7a1199367 | 51,83,2,101 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
069f3051-c3c5-4580-b7f4-a4761d47f12f | 51,83,2,188 | ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
98d0fd7d-2142-4805-a2f1-d22f2d729c8c | 52,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
e9ad8e6f-b89d-4136-9a4b-36f35300b74a | 52,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
27552c90-f8f7-4d10-ab24-d18ea6c28b20 | 52,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
82156839-707b-42c5-9404-527a81aeaf5b | 52,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
1f3b01e7-9d4c-4cc5-9aad-bf45118e98fa | 52,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
76593a22-8379-4628-b180-9026d74a4986 | 52,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3e29bddd-41d4-41d4-81b1-d166617304e2 | 52,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
8f812877-d260-4cd9-841a-872c9cf17a25 | 52,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e752bfbd-c0e7-46a6-ba57-733c637e61b2 | 52,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
930ffa47-74ee-465f-834f-4f81da713ec6 | 52,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
e6a73593-02ff-46ee-a4f5-74244b3a55c8 | 52,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
f2912fa0-6c67-4566-84e4-faca0ee40d04 | 52,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
8e265dc3-b552-43ec-b97b-e1fe0bf885ad | 52,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
784ed180-fd2a-424a-b5df-250bf851fbc1 | 52,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
735a9a6a-35c4-4406-a106-859bb188b469 | 52,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
adb09962-da78-497b-ae64-78a8ba04aaae | 52,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
4796b0e9-21f8-4c6b-b064-fafb63c331f8 | 52,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
2d2d9d60-1950-4ef5-b606-7fd32cf38b87 | 52,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
3bef1b81-5e04-4759-9e23-7c0a00842eed | 52,74,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5d2bdd78-8824-4010-a7ab-c990458b5ebb | 52,74,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
51d25c35-6264-4981-ab19-619f618545da | 52,74,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0d0650a6-d567-4e7f-8ac6-2b991f8e71ab | 52,74,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
7754fff2-6d9d-43ec-ade1-df9181263343 | 52,74,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
bd4ae771-762a-4ba0-af77-a67f025a79ea | 52,74,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
14de3f62-95ae-4044-8abf-dce00fbc5043 | 52,74,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
60cc2b46-b58e-4b35-83a8-74051875952a | 52,74,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
bf6530d3-51ed-4bd1-989a-b30b8a2337cb | 52,74,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
84dbbd3b-becc-4545-9d8e-2bc663a34c34 | 52,74,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
694d2e37-a36d-4f4f-9d6a-722da6bf6c31 | 52,74,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9daf6df9-d37a-41d5-bcf8-696b5540c31d | 52,74,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
d8a0d963-b969-4222-9662-fefd27e249d3 | 52,74,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
54d04bcb-8126-4c52-9227-4ec2398c2895 | 52,74,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
566893b2-9869-44f0-95cf-282e618ee42a | 52,74,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9f92c590-3b57-41c7-896f-39ab0a3542fc | 52,74,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
8da43e15-f883-40a4-a379-b320d2e71534 | 52,74,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
6727caa9-0a4d-4a55-a49b-8615cc3732de | 52,76,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
c38768e6-5299-461c-a35f-af449a5b09a9 | 52,76,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b80b577f-afa1-4572-9764-8416c3926fc3 | 52,76,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
284acc7e-ef8e-4dab-90bd-e6d7cf7e95c7 | 52,76,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
26e0d936-2065-4a30-b746-294fe1a7dfc7 | 52,76,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
fdceedeb-667c-4190-8b46-838d2d63a409 | 52,76,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e098f065-2e65-4636-835c-38461c204859 | 52,76,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d2fadd83-ba41-4d94-bbb5-d4892dc8e532 | 52,76,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
529f02d9-d046-499d-bd2d-76df4d0e0f84 | 52,76,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
15541234-0413-49c4-bd4b-e637e8e9dd2f | 52,76,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
536a7524-c07e-486f-834f-f60735e24497 | 52,76,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
038a413e-61de-4af4-9e97-0318c0ec4c21 | 52,76,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
69fc03fd-6e50-435a-8a42-c038d7958610 | 52,76,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
18512341-f10d-46b3-8b6a-49e52a35bc3e | 52,76,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
7d5dc69a-a4db-4357-a4cb-b87fcf0d6b4e | 52,76,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9e6a26e1-013c-4de7-a400-db85527ee226 | 52,76,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
eb8ae791-ce83-4836-9c98-5073b2146abe | 52,76,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
42340719-e069-4087-8858-15e598969d62 | 52,77,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3d49ee3a-c2de-44f4-9514-9d65253dde25 | 52,77,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
16e1b288-0b08-456c-9c30-943ee38e3efa | 52,77,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4ebe6191-a287-4b92-8394-d96de1f9ce68 | 52,77,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e442c3b5-5969-4e9b-b890-4232710380ba | 52,77,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6db572cc-a1fb-4839-9fa7-78d690c0ab3c | 52,77,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
52c9f5d6-cbc0-41c7-a5b5-8fb0d8dc2baf | 52,77,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f2b74404-2675-4552-9018-383a7a1c92a4 | 52,77,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
572bcca2-3ed6-467e-9f52-8a01c8e84e4b | 52,77,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e3930647-e401-4475-9317-81ee5c536287 | 52,77,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
3c4ba4bd-e8b5-4d5a-8696-beab1b193670 | 52,77,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
1675fee1-c0db-46b0-a900-e9731ed8e843 | 52,77,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
2a2abb7a-8c8f-4ac8-b994-a8c432fda08a | 52,77,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
48f239e4-9523-4cab-9f3a-db7bdf21683a | 52,77,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
1a04dae1-264a-452f-8591-0e0089b3aac8 | 52,77,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
8b3f2a32-f4dd-4a04-a9aa-2fe881cd58fd | 52,77,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
23438ee3-5e53-4c6b-b908-b6ca66cb12f2 | 52,77,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
60b87ae2-aab5-44af-b0ec-5acad4efbcb5 | 52,80,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
0cdf7135-309c-4f42-8d2d-ad51cfd424f3 | 52,80,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6865aed0-498c-421e-8269-62eee58eab73 | 52,80,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d65dbe81-c66e-4d64-844c-922453f46b34 | 52,80,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
dc4e11cc-2393-49ad-8dc6-4baaec3fb46a | 52,80,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
7880afac-c3dc-4fc5-9fc4-5d04a6ec9d21 | 52,80,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
a7fbf5e0-7ed1-4f95-9e6b-d09ad00e41ea | 52,80,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
55bc801c-f88e-4bcb-8933-3684646d4741 | 52,80,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4c6bb422-e506-480b-8c39-e777f96d56da | 52,80,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
45275ca4-7500-4a3c-9fc4-6f40b500a93c | 52,80,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
599c0622-0643-4759-a507-f605591fda6a | 52,80,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
287eae8a-4e7e-47ec-b55d-b955073caaaf | 52,80,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
dc3d656a-0d4a-40d8-a3a7-0941d3b1baa7 | 52,80,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
117045f3-9f53-4153-8b20-37675a89f6dd | 52,80,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
cfdccd2d-5f62-4ee1-a3bf-7e55f3c811a8 | 52,80,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
be6ccb7b-0151-43b1-8297-ce9c73135987 | 52,80,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
90bec594-297f-4490-996e-72e6fa02cf5c | 52,80,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
d2b2ce20-aadf-46fd-9748-4054b25efde6 | 52,81,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
50230467-18b7-4b03-af50-f88eb2219616 | 52,81,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
63dd0426-8288-4dcb-b597-68aac559dc84 | 52,81,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a829a4fe-3c7a-4c21-8cd7-e873a2654cf0 | 52,81,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
97b670b0-475b-4a7a-9eaf-6206a2709b57 | 52,81,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a6db6e06-2929-4d0d-b0d5-20d883fa8949 | 52,81,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d9b1dd84-3650-401b-9dc7-48950a922fd1 | 52,81,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ba6b49d8-2b5f-487f-aaba-5c9992baa40a | 52,81,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
84e77f59-00fc-4bd7-b40e-60a863ef9bff | 52,81,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
60ea8a65-b626-4423-9082-ec27dbc088c1 | 52,81,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
893b3a10-d7b6-4dec-bdb8-c34347b5addc | 52,81,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4f2a8a5f-6930-487b-bd32-ad54bd9c75d1 | 52,81,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
719382e2-d5b3-499b-b66e-0aab8a987edd | 52,81,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9fb1ad8d-325e-4cb8-997e-e44310a567b9 | 52,81,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
e371f7b0-c054-47a3-844d-eb5af90286d4 | 52,81,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
c306debc-1c01-4496-b80c-22e5a09d0951 | 52,81,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
1428856a-f52f-430e-bd26-608c3b0cddd8 | 52,81,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
74ba5d13-ff65-4098-85b6-ffa02c97265e | 52,83,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
67e19d54-550e-4f4a-ab22-59035b458258 | 52,83,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6d63eb1e-9b2b-4e63-845c-3467ab8f0148 | 52,83,2,16,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2118540a-0f5d-481a-b5e3-91039ea84b98 | 52,83,2,17,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
7b721248-e2db-4664-a424-2c8ce33304aa | 52,83,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
75286d97-0668-4613-b1a6-522d329aa248 | 52,83,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
74625f10-2979-48b7-9910-a2629124f9d2 | 52,83,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f7e2bee0-6c79-411c-a12a-084732405f82 | 52,83,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a73f083d-267d-4f46-96d3-fc16d9afe9db | 52,83,2,18,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e21cd4e8-55e3-4ada-8f13-af809d652504 | 52,83,2,35,25 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
5ee61887-a98d-4615-87fc-141edb1fac9d | 52,83,2,35,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
89d3d873-4b96-4745-afe6-21a9e05fc4e7 | 52,83,2,36,26 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
d3354ace-2c0a-44c4-ae3f-f638aec3770e | 52,83,2,36,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
ef8a794f-26c6-4491-aab1-48b086efced8 | 52,83,2,65 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
986c662d-2e39-47af-aa02-02db614671ea | 52,83,2,73 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9967b749-2d11-44b1-996e-ce0d755e99e7 | 52,83,2,101 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c9d69d5c-850c-403d-bec8-8c24a7f863d3 | 52,83,2,188 | ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
8a550e6d-bece-4850-b49b-8b59ed4e17d1 | 53,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
0f86f9eb-ff42-4030-9fe8-b32f429545ee | 53,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
16ee40fe-9e37-4e32-bec6-07c44a2ed61b | 53,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
869a3d5f-371b-48c5-8fc3-b6a939d2c656 | 53,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
43060f21-291b-452c-a2dd-3738d45e79bb | 53,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
a69cf06a-fe15-4352-9c05-4e7bfdeffdd1 | 53,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
31ff87ad-23b0-4908-a30a-b89f25cf3c4e | 53,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
7af0b4c0-3cb9-4dca-8eec-bfdb6f084895 | 53,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d7ab2c14-8880-4fde-b74a-fb9c1d609428 | 53,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
35f58d02-91f1-4279-9e85-cca43b392524 | 53,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
3b320185-060d-4a0b-b9b3-2b8875a1ee7e | 53,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
6b162dbd-6153-4941-89ba-62fdf4d6486c | 53,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
b3d453f0-c0e7-4628-84d7-f76ebb96957a | 53,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
943b7e66-f173-467f-88d1-4028681f140f | 53,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
f1b3cea0-e6e6-42cd-be14-4b070bdd5f20 | 53,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
e5e6b49c-aaf4-4bc9-9902-2f3c78b3cd8a | 53,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
5cfadb32-8d78-4283-aa17-017ca502c82b | 53,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
d1b1dfea-11fe-4432-b0b4-296462f1cbd9 | 53,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
0a376593-8558-4024-889d-cf93d84c786f | 53,74,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
d81afcfc-8b7f-418e-9de4-d6b0d759535b | 53,74,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
01609dd5-e45b-4730-9984-67691b244e0f | 53,74,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0cdc09ff-684b-4d08-b589-4370ca7d93dd | 53,74,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
94d4ad2f-e666-4116-8e61-29b6c7cfe5ca | 53,74,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
4fd61d61-2c97-4ca0-a007-0d0492864834 | 53,74,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e70f7b36-f0c7-4b11-8818-8c759c6b59d8 | 53,74,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6ff2c745-b87d-4995-86c9-63c01297cbbe | 53,74,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b7ae3e0e-0db9-4e32-b84d-d6827434aa6c | 53,74,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
98d960a3-1909-4a89-a600-62417b2b915a | 53,74,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
f40b6b76-cdf6-4867-b1fb-aae3d5dd5373 | 53,74,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b01fbb52-f5ed-449d-b5dd-4fdb75f1c676 | 53,74,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
ad1c8ea6-fa17-4655-b473-29387f43abae | 53,74,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
cf827bdd-ed5a-4f70-8f31-8db248acde90 | 53,74,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
9c64c2c8-ffb6-42ab-a664-024a9e366c78 | 53,74,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9b5796b8-22d5-4f2f-b1d1-a085134b47c6 | 53,74,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c197d269-c749-44de-bb3e-86e6b0ef8992 | 53,74,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c32d7c83-2871-4e64-a5f9-6eac9c9c2e8b | 53,76,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
d3f0b264-d61f-4503-8493-ce1ae167c1f9 | 53,76,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ccd9f1c1-4c10-42b9-913f-a1b8c8df5f33 | 53,76,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5b11f203-a3d9-4bab-886f-89f759618ae6 | 53,76,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e6aad827-9cae-4fb3-a1eb-c5b85ae22550 | 53,76,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
5926d327-0f6b-4a9e-abb0-a350f21aa597 | 53,76,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e0bc845e-b5c4-4a64-b625-28ad73e33555 | 53,76,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
56d640b6-bd9b-4ff5-8792-8d95c87db6a9 | 53,76,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
fe7cd176-18bc-411b-aee1-404fc15a6d6d | 53,76,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
8ef9006f-ca86-4afd-b3a8-7868d463457e | 53,76,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
f17f46db-d92c-41cf-90af-2758376e6c95 | 53,76,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
ccfd719e-d54a-4962-89b0-e94d77d4f3cf | 53,76,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
fe7ffa96-5ac7-4a39-b80d-1c061a3c29a6 | 53,76,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
2130f88c-2f88-4512-b9fc-0a65d6585d9a | 53,76,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
b405547d-226d-464f-8ab6-4bc220239336 | 53,76,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
d4149bf5-ccb9-488b-bbf8-948f1595cfb8 | 53,76,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
f8a908e1-c756-420c-a460-80fedb6f489c | 53,76,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
ed882c00-179f-4ce4-8626-c48ec16c0338 | 53,77,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
e4b9f0f2-df67-4b32-9339-b602c0a3d3b4 | 53,77,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
19aecaa8-7e89-42a1-a8fa-2f4f68193457 | 53,77,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
203ee456-5c64-4b81-9bc6-d7dc6a3cd74e | 53,77,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
923a4f89-6af0-4b0a-83e0-28f34a1d9b77 | 53,77,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
c0314e67-fcce-4969-92d8-666966675d9b | 53,77,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7dd9ecb6-4140-4261-bee2-667425c8cf5f | 53,77,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
fca66384-3c8f-4245-9090-fa6bf89f7ded | 53,77,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6ff2fd46-2274-4d08-b1e6-54447a5351c7 | 53,77,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b15c4e0e-42dc-4312-92d9-d33cb9f45a8b | 53,77,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
30ff8aec-383e-4bef-bc6a-fcec3af63919 | 53,77,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9f91b1b2-ccb9-4ae5-a11f-c7cc181ec4a7 | 53,77,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
9c72db62-ce58-4e0a-8243-5e5bd4942bd2 | 53,77,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9e00007f-0853-4539-bfb9-006b50367222 | 53,77,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
c78cf8a7-3e10-47be-9b27-acbe183bc175 | 53,77,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
ab21f0cb-3bcf-45f9-b287-869906f0aa06 | 53,77,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
23b8f29d-3d25-49bb-a77b-eb3384a7b406 | 53,77,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
72ae2f40-e0d0-48d8-ae26-75a94c795b9e | 53,80,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3f583bd3-3bde-42ac-a38a-87bc6e8d7761 | 53,80,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
43dad979-7cd5-4ff0-ae1c-0ab91b39f0e8 | 53,80,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
77afa9fa-911b-4f20-9b38-7ab9ac9e1ac4 | 53,80,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
cc295a08-4b0a-4532-943d-a825c587edca | 53,80,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
276d33f7-1d79-430e-b661-8ccc04e71d35 | 53,80,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
9c90743b-cc4d-4530-9cda-f3ccf28bf770 | 53,80,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
fee89ae8-98e1-48a6-aa6d-0468cde0d21e | 53,80,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
55b01102-6324-449a-acab-7ce263020709 | 53,80,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7513ed9e-e1d5-4c08-83e6-41e96eff8ec8 | 53,80,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
0d596063-68b3-4caa-827e-6d66c93843d9 | 53,80,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
2fdfea0a-a16d-491b-a837-130192ed658d | 53,80,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
f887ef05-41a1-41a4-b082-fab0a60fa0cd | 53,80,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4e35a7c3-e7aa-4aa3-901d-10722da267e7 | 53,80,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
81157c00-b640-4327-baa7-ed8a06bfcfd3 | 53,80,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
3c12c224-95c6-40e6-bce4-530bec6a6081 | 53,80,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
10cbb7f4-88c4-4b2d-8b37-b8c0bf819271 | 53,80,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
91c3c39a-9d88-4f8c-90a4-82a6e81ad04a | 53,81,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
9beb6caf-a141-46e1-b5ae-e2ff92e5f7b9 | 53,81,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
61ebc22a-816d-4f58-9810-98fb90cf76cd | 53,81,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
01a5bbf6-4555-4ce1-a463-00e001590f47 | 53,81,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e7eaa24c-9c42-4723-a4a0-af3a18ba39a1 | 53,81,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
2ec4c519-e260-4b76-8b1d-247243d4cc2f | 53,81,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2fb36404-c0df-43e6-ab9b-8251d15583c9 | 53,81,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9e2401ef-cfc3-4773-a233-bc546ecf9ebe | 53,81,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c9e09b70-d1fb-4a63-9fa6-c95a71840fd7 | 53,81,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
718b64c4-ada5-4917-aa47-9365d71440b0 | 53,81,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
5d253370-b258-460f-b3e1-4e18a3338572 | 53,81,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4e7a41ec-dc0d-4143-a52e-029273d39d9d | 53,81,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
bcd84e8a-ec12-40c8-a0cc-726f09f7c3f1 | 53,81,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
324f928b-c84f-4d34-a752-2297cfa835a7 | 53,81,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
71b16c16-72d0-42cc-863a-51f9d5719c86 | 53,81,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
72e63aaa-b28c-477c-a4df-1007192db0b8 | 53,81,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
6d18eca9-bf1a-4e20-bf0f-9656046e563a | 53,81,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
81beffa2-91f3-4fbb-a0cc-8a4b212b6289 | 53,83,2,16,21,22 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4b5dc230-96f8-4ef1-a079-b68dbeac960c | 53,83,2,16,21,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
bbfe7899-b863-4b6a-824a-0e33e769a0e6 | 53,83,2,16,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7f726210-5636-45d9-8114-83cee959e7ed | 53,83,2,17,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
1098bc47-eeed-4a9d-b581-850b8b5ca5c1 | 53,83,2,17,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
24355c26-2329-47b6-8c98-cb65fddb39ac | 53,83,2,17,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
3d1548e8-ac34-4e29-9945-9b6258bcd416 | 53,83,2,18,19,20 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
65da5861-c694-4d82-b77e-27bac43bf496 | 53,83,2,18,19,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c2e4b49d-1621-44f8-90cc-18d251182b60 | 53,83,2,18,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d9fca106-a685-44c1-9763-1610e79b3fe7 | 53,83,2,35,25 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
62fbfecd-d065-4858-89f6-32827f594d5e | 53,83,2,35,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
5200a763-3399-4490-8a8f-7582b6e64139 | 53,83,2,36,26 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
0f659398-b7c6-4138-884d-2307ac12c8ca | 53,83,2,36,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
d87abd22-76fe-4233-ad9d-facb1a2150cc | 53,83,2,65 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
97164484-f276-48e2-b7ae-f555c1297d33 | 53,83,2,73 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
a22c7903-bed8-48d5-9153-5ecde3a3475f | 53,83,2,101 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
a6d80ee3-86fa-4b6a-8ee0-56650173f290 | 53,83,2,188 | ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
e1ad2455-5ee1-435a-8f71-e2b046df2ca2 | 54,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
a289487a-acfb-46b7-81bc-fca265e86917 | 54,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
cd95274a-644e-462a-b972-d58f04be8342 | 54,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b23c19d2-e3a2-4ef2-bb29-3d191913264b | 54,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
bf3bc0aa-57b1-4b9c-82c0-9397ac253212 | 54,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
e7d757fd-a5c9-446b-a684-038d5ee5786e | 54,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
86814d67-176d-4b27-9af9-2fca1cde5fff | 54,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
d4d8e8c2-dde8-4554-a30a-a17b8ab5a450 | 54,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e80994da-eb22-4f78-8679-6f3cc56bba57 | 54,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
83c59c45-4468-4bac-a29b-97592c4198d8 | 54,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
06bbae05-b6f6-4014-b579-89ad431ffd16 | 54,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
8cb769f3-629d-4e46-b58f-5734e425841f | 54,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
123524cb-9539-42c2-8a9f-92192db180cd | 54,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
09e0c675-0695-49a2-b1a1-17ef38c52139 | 54,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
164b88e8-1008-48c8-9348-88bd3ad8303c | 54,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
6db8ca35-73f3-486d-8dc7-d1c0e1618dfe | 54,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
2058b8cd-d3ec-4386-a502-617accd89fc5 | 54,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
b94c0e6a-752c-4b35-b2c5-bd0aeaf6fff1 | 54,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
37d0b329-36d6-479c-8659-e59059e680dd | 54,74,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4b77febd-dd69-4b82-af6e-9be2c8052e3b | 54,74,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
89a49a0b-7b11-484c-9570-bda66f2d7de8 | 54,74,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
de1e3c62-3445-4d37-afe2-d1648c09ad9b | 54,74,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2ef1cdfc-0b1c-4f70-9683-316aa759a97a | 54,74,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
95dce8d8-09dd-4973-87a1-54d86db3c5f6 | 54,74,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
03ffaeea-db8c-40fe-a142-8a9717a9a8f8 | 54,74,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f6ce0c2c-32da-4b6b-969f-1081df025888 | 54,74,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b99d8213-5f64-4053-b3e6-a6183eb4ce98 | 54,74,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b1948d89-1bb6-49eb-9885-ac74aa1aeadc | 54,74,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
c0324977-540c-40af-8b89-8d3f2c9b6607 | 54,74,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7428cdc6-6ad9-4c75-b0c5-65aa25bd51ef | 54,74,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
429c1fbd-bde1-4b4b-9e23-b03e0008945b | 54,74,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8a84504a-d674-4312-a4a7-1d8312a9a299 | 54,74,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
53a1d416-bbf0-4cb9-8ada-d2b4db20ffb7 | 54,74,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
71df9c1c-cf27-480c-a80f-cbff4a11aed0 | 54,74,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
8987659c-8bf0-42bc-b54c-05037e49b93c | 54,74,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5db50329-a78a-40f8-be26-d6e4a6def077 | 54,76,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
f855fde0-d880-4991-bfd4-b62aad71b0ab | 54,76,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
d0706745-fb15-4cf3-a920-df208ce71244 | 54,76,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c646b9d8-9b75-4298-940f-6573972a3753 | 54,76,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
8c20834a-aea2-4853-8973-66c6e57519fb | 54,76,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
80d9ba53-910a-41ea-b229-046828cd188c | 54,76,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
29944439-235d-455e-887e-3fb5381a3eab | 54,76,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1c8c0af1-c6aa-4594-849a-ba5ac9d3aecd | 54,76,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1487131c-1a0b-4318-815b-2f1b3a6e249f | 54,76,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
dbf3a796-1210-4a21-9196-0f1558dc4c82 | 54,76,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
e5cb776e-d2f6-47a2-980b-2028c747d8dc | 54,76,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
0333b84b-0abb-4634-a422-9ed15b951f32 | 54,76,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
c2d44b74-c179-483e-9700-afb1d3de7e19 | 54,76,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b732af2c-bc05-413d-ad2b-967cc16c292d | 54,76,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
773abb8c-38ac-47f6-a6dc-d1e4eb0caa06 | 54,76,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
6ab1d071-f683-42c4-9f6e-eb842578795f | 54,76,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ba1b3ed6-71aa-4a00-ae39-8898aca35d1c | 54,76,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
0ed7f492-a111-49cb-9160-9e723c78aba8 | 54,77,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
dc8d945b-0725-46ab-a6f6-1efdcb4c4149 | 54,77,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a99b9f97-b386-476b-ac34-fb84f1c16940 | 54,77,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f8cd4acd-1c04-4a04-9d64-b7f874fafeec | 54,77,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e821b3c2-cafe-476b-8e37-8841d388c000 | 54,77,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
7b9d0072-0ef7-42bd-950b-2def94d2658e | 54,77,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
60af0aea-f2ea-4876-96e5-eacd598a2b81 | 54,77,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
928e6b0f-5cde-42a6-a024-0c15bc4dd555 | 54,77,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
aca8b073-b549-4ad7-8b9c-13d801c8c226 | 54,77,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9bde7f61-73b5-4197-aa7d-a0fb06c1a97a | 54,77,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
ea87ac7a-3e88-435c-92a3-b6ec240ea377 | 54,77,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4dab797e-1214-4cd4-911f-f1da7bb7f3e2 | 54,77,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
fe3061f3-5d07-47cc-b071-93c8c2eb8c84 | 54,77,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
c249a2b1-6f5c-4d3c-948f-1ab130f7d1f6 | 54,77,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
eab067fc-5be1-4213-901c-53db036b08cc | 54,77,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
03ed6392-5f19-4b2f-a04c-7af861e79c40 | 54,77,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
f2a95269-50e8-426a-91d7-302fc059df4f | 54,77,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
7759a9c5-8194-40e7-bfc5-0a6d1e5fd9e5 | 54,80,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3ad153ef-0133-4279-89bd-6d15796233ce | 54,80,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
fa46bdb7-b869-4960-9f40-fec9ba31d753 | 54,80,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6c73ec65-d9cc-4397-9b40-7d4dc0794b77 | 54,80,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
fc40c2b9-d8a4-4687-80be-91cb6516ccd9 | 54,80,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
60ea45f4-fc6d-495a-a472-dd1ebbcacc3b | 54,80,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
f1692196-5ac1-46ab-9386-805586cb926e | 54,80,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1ba12869-6452-4cd2-a24c-302e9b8912d6 | 54,80,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4397ad6f-5fee-4c9f-a67c-a6ec9b8506f8 | 54,80,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
bee785fa-ee89-4867-867d-dbb7edabe7d1 | 54,80,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
0b6bd931-0934-4b56-b801-a6eb594972ca | 54,80,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
973c6bfd-809b-4119-8a4f-af80fafa61ca | 54,80,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
fd2478e7-f83f-46c7-9d85-b411ca845661 | 54,80,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
834b2b46-c8ef-4b2d-9a84-77ad31d6fb97 | 54,80,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
3100d59c-e47c-4740-adbd-a4a3e105d175 | 54,80,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
60e29ab0-1e8c-47a8-a6ef-ada472cdfeba | 54,80,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
cb09d0d0-e206-4697-9a14-e0f52149215a | 54,80,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
959be15d-2688-4f00-8904-c9160ab64054 | 54,81,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4258f974-d052-48a0-82da-89432e301716 | 54,81,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
66d3cc0d-5243-435f-bfd0-c18b31f56175 | 54,81,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
96d399fd-0c1e-420b-8c94-3becaab07771 | 54,81,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
98824efd-6fba-416b-9157-a14f4ec71abb | 54,81,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
df6f1f18-ce31-423d-a4ff-fc42c51683d3 | 54,81,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
aeb15fc8-a8bf-404f-a00a-286b991d3d47 | 54,81,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a8ca549a-1558-4d09-a46c-3d585e92ecc7 | 54,81,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ec901e75-fc34-4e83-9106-44b36e6df5e0 | 54,81,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d29a15ef-d5f4-4dbd-af68-7d8b3431d942 | 54,81,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
e0015cfd-d925-4c01-ba88-ae8a0ff61512 | 54,81,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e27395d2-14ec-42b4-bb7a-59de3612b55f | 54,81,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
5d8fa1f3-fa08-479f-9a36-b0d9acf39d30 | 54,81,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4af06dc7-ff01-4a8b-b4cb-1ca62e3405d4 | 54,81,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
e78750e6-6814-4f29-b0b3-cbb286070a43 | 54,81,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
b263c8a8-fdd7-4f46-a15b-4406278b819f | 54,81,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
afab1301-b3e1-4036-9033-50e476a3e077 | 54,81,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
9105a176-e4e0-4313-8bdd-e8f22336facf | 54,83,2,16,21,22 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3bcda094-8eec-4eb2-9490-878b9b750d01 | 54,83,2,16,21,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2a11e36f-2d9a-46cb-a571-22f505cd21e2 | 54,83,2,16,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9c1245c4-2cfe-4bb5-b748-9c027a30abac | 54,83,2,17,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d4f12e23-534e-497f-912b-2ec66c436664 | 54,83,2,17,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
c129c778-019b-447a-b51b-320d00b9776a | 54,83,2,17,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7d20b445-6960-46c1-ae8f-e772c895d199 | 54,83,2,18,19,20 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c80af6f9-7fa0-4ddc-9424-b7d5df846ac6 | 54,83,2,18,19,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
73f8c4e3-a36a-47a0-88db-f8c9cf0942b4 | 54,83,2,18,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
46e767d0-1c8d-4b93-af6a-c3b6c838b919 | 54,83,2,35,25 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
5949a536-b221-4cf3-bb54-8f25721d244c | 54,83,2,35,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
55ca855b-d77b-4a93-b94c-1d8ce6c427e5 | 54,83,2,36,26 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
d9621b36-7ca2-4d99-aaf8-15ce42447a7c | 54,83,2,36,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
978ee97b-de98-4363-8cae-4404a6f77d4d | 54,83,2,65 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
16fed688-f551-463d-aee7-553e9ce5917a | 54,83,2,73 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
050a3867-290d-4ff5-916f-3676c4c30fb9 | 54,83,2,101 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
16b201d7-3324-4b61-8cc8-69e30d55f82d | 54,83,2,188 | ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
51835a9d-0864-4773-a94a-9039fa2bf3bb | 55,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
ce14620d-c639-4160-94d9-5564d432593f | 55,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3d46392a-9ffd-4bf3-bc3a-57ce69040e39 | 55,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9d14faa9-601f-4533-b726-7fe9f63929e8 | 55,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
e9ecec21-4b82-4416-bccd-d90e63f20d02 | 55,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
1c2b54a9-36ab-4248-8e2e-19558ae634f0 | 55,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
bff6b7d4-8e0b-4429-84ec-9b71d58d1228 | 55,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
4888bd1d-a0f3-483d-a990-d0d907648626 | 55,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
8a3cbcb1-c9ed-485f-a944-7bd57320e4fc | 55,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
f4c28119-ee50-4ffe-8e28-857f421f55c9 | 55,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
cf10235c-f8ec-4793-8c81-d7b400b078be | 55,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
3b98d6f6-1c91-4e5d-b0b0-e32c3f2259c5 | 55,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
4fc1a56d-9dbc-41ec-b3f0-c10dc70267c6 | 55,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
22e5e0fb-d8f6-4b5e-a8c1-67772773a196 | 55,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
9ca8cc21-012a-4af8-a21c-82b1fc49be66 | 55,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
df73283a-02c9-458e-96c2-e5f6c23070dc | 55,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
9d070847-8aee-4184-99a3-17646aec8249 | 55,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
3a990964-1dbd-427a-88a2-e16a8e2f1726 | 55,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
5822eb1e-4f6a-45a3-85c5-725375c706b1 | 55,74,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3b6b0441-9a50-4741-bd9e-c2b053b0458f | 55,74,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
20790b04-69b4-446c-b3ec-4d2819eba1af | 55,74,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
92783b6c-c619-42c3-81e3-cb7e19a81270 | 55,74,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
73aacabd-d061-4352-8264-7fff846192cb | 55,74,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
0da03d04-539e-46fa-a8c3-67f56abe26fd | 55,74,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
26776fb8-d482-4aaa-91a9-427bf469c9ce | 55,74,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9e76533f-8da0-4a7b-929c-7f77a31734d6 | 55,74,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
147cef1d-b874-4625-a019-ba651bb3ec24 | 55,74,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
85955c7c-fdc2-416a-8be8-9114e307566e | 55,74,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
680265fb-2884-4046-835a-ba1ff03bf3d5 | 55,74,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
2cc3c9cf-8f35-47aa-85cf-87362ac190a2 | 55,74,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
02135735-1f65-45e4-b73a-b2200de3ea90 | 55,74,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
490f2481-a18e-4520-a912-53b035e246f6 | 55,74,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
587f095c-3bd6-4f11-8b98-c53309534f0f | 55,74,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
111aa136-ed32-43da-b098-57c26b2f681a | 55,74,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
e36d4537-df43-4196-b073-b2c9f78392b9 | 55,74,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c77300f2-b62e-4b8c-a9c7-932cc19ac09f | 55,76,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
1a4c1b10-b2ef-4d97-ac66-84a6969b36bc | 55,76,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b8132004-d9f1-4137-95d2-57eb9380d701 | 55,76,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fe2f9b25-15fa-4559-b49c-25bfb0a7c775 | 55,76,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
60a7231c-0abc-4862-83f7-491e19b92db9 | 55,76,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
39b37606-ffa1-4fc7-85e2-64a44b729de2 | 55,76,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
19f26354-8d79-4722-b0b6-2d81c507a12e | 55,76,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
293698db-164c-4db6-a6a4-48aa20f3859a | 55,76,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1c1acc88-5e94-4bef-880a-35e8b976aafb | 55,76,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c3a168bb-6977-4c4d-ab5d-b63c694ae54b | 55,76,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
3c4530e1-b3a8-4cc3-984c-2ef408996bd9 | 55,76,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3b589985-85f4-47b2-b2df-7acc43df4311 | 55,76,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
e84be7c4-f175-4cad-88c8-bc94b9a08ee7 | 55,76,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
f867244c-b006-43df-bf12-e6522fcea698 | 55,76,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
07f491b6-0356-456d-bfc7-2b8cdb15a1ff | 55,76,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
4eaa9afb-dc2d-4b87-8b7b-11cb01e0b5da | 55,76,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
3091a212-6e82-4979-add7-1efddfe37ee3 | 55,76,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
549c2547-49c7-4504-92df-0d790118235f | 55,77,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
eaed5372-5e8a-4ba8-9f4f-51e903e0da8d | 55,77,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ed4bc4e2-059b-40b5-921f-1cace5703478 | 55,77,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
093371d9-ca4e-4d2b-8603-0dbe3081eefa | 55,77,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
35c3adcf-5ee9-4bf3-b214-99f9f7d34e45 | 55,77,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
9a0feeab-7c46-4bda-be07-c49f569a14f6 | 55,77,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
39d1bf5d-8b00-4ea2-afc0-393d1d4974b5 | 55,77,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
41cb4d3c-85b4-4e14-94a2-0159931dfbff | 55,77,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
93bdb354-f8dc-4732-97ce-38a3682bb91a | 55,77,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5daa27db-79ac-47bd-9ddd-7c060ce9f9fc | 55,77,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
964f7280-6771-4bca-84ec-3a4e0ad81ccb | 55,77,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4804eb65-a447-4e5e-951c-72d3e30dba53 | 55,77,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
a69b6368-aff7-456d-9ee7-88822f195c54 | 55,77,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e5884d4f-0db4-4b94-a518-23923015e5c9 | 55,77,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
31574f60-4578-4a18-9601-92238731b7f3 | 55,77,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
def89d04-5634-446c-b9d6-0e95702fc796 | 55,77,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d196940d-3bd1-4d19-bf3c-53533a30a8b1 | 55,77,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
42a9fb2c-2c81-41da-a355-809ef1989ef8 | 55,80,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
d050f2d9-a41f-48ea-8660-88e3eb722bec | 55,80,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3330ebb8-eb60-4c77-8e46-a6e21c065282 | 55,80,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f5f6ce2f-7ddc-44ee-bec7-4bcc265d1b00 | 55,80,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
be676da3-1f2b-4b99-8459-259c352267f3 | 55,80,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
433fcf90-634a-413d-b2a2-a3853363a637 | 55,80,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
bbf6e2e3-66c8-42f3-976d-3e315287c45b | 55,80,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e97cf2b8-7420-441e-a099-116bca80cba4 | 55,80,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
458c56f0-8d0b-42ed-9d0e-618dcc1c5f9a | 55,80,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a2fdd4ef-ebb2-4f87-b19e-a741aca1fab6 | 55,80,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
2d77554a-2d6f-4e01-9f70-f7874e8ce536 | 55,80,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
2729c163-1436-4e42-9711-fb168da3dfba | 55,80,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
6a286448-2d91-4b96-bace-bb848b97a9d2 | 55,80,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
81b88b0d-95e8-422b-ab57-b9d3795bf67b | 55,80,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
2199170a-1bf7-4d78-9b34-a9df629da529 | 55,80,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
0d41101a-b653-417c-a640-a1a2967e52f7 | 55,80,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
1c6cc6a4-afba-4f0d-9f81-3bee284c0c3c | 55,80,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
d0cab431-3125-4b10-8e1f-f9dc74fcaeeb | 55,81,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
9e9efbab-6834-45e6-b2d6-6977239cddd0 | 55,81,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
94557c26-a04f-4563-b2a4-d4fbafac0379 | 55,81,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
08f725d9-b4dd-43f1-8ba9-e41a30a3e9ea | 55,81,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
80394105-77a9-4d8c-b314-d0073f12652c | 55,81,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b33b1f8a-f960-430e-8ef8-388ad93ce5c0 | 55,81,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c4bc288f-fdf0-4abf-9b69-490c7ebd5aac | 55,81,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ae92b17a-3db6-4423-886f-caaf6249ff9c | 55,81,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
0e3a5f15-f61d-475d-a4d5-f2d7ce9daa7f | 55,81,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5121941e-9cfa-49b1-92b9-b04bb9d1406d | 55,81,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
d76404b4-d2a3-489c-a110-f531f2d577da | 55,81,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
480565b0-6f08-46de-95a2-0904877b35e2 | 55,81,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
d00df268-567e-4d3d-8235-db8af91dfc02 | 55,81,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e944840f-d28b-4db1-bcdb-0b1434716d15 | 55,81,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
3df030b6-ae16-4b0a-ad9c-563c97539003 | 55,81,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
d0eef6a5-96c3-46d7-ad34-d8d20edb89fa | 55,81,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b128354e-f305-4b82-a133-a04f0ef97a87 | 55,81,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5bff7575-f0e1-443e-91b1-988a63e5e356 | 55,83,2,16,21,22 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
2867a2db-6d00-49dd-9c9c-5a51ac4f9b46 | 55,83,2,16,21,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9978aaf9-9091-4fa1-8a01-3e1ef231c2c9 | 55,83,2,16,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
afe1c88d-9129-486e-9c05-095d606b0865 | 55,83,2,17,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
9994638e-d4b4-4e8c-925c-bed11cd7435d | 55,83,2,17,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
9a996f5a-f8ba-41a7-adb3-0be55f315fcd | 55,83,2,17,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
eb28fde8-58f4-4cd3-afd6-5575d3001e8d | 55,83,2,18,19,20 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
64a1a436-0162-4d22-97d1-ecc2b0ff15cb | 55,83,2,18,19,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ea90e5c9-ff52-4ad2-abe3-6894c8bc7b9f | 55,83,2,18,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1021a505-6c3c-459b-bcf4-b45ec08538bf | 55,83,2,35,25 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
faf8f768-7b44-46e5-942b-b11cfd01ef01 | 55,83,2,35,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
d43383bc-798f-4f2e-9c3c-c2313e2acd84 | 55,83,2,36,26 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
ac353405-ebea-436a-b406-8365ad16e5b3 | 55,83,2,36,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
137c1baf-3cf9-41bc-8789-5aecfaa95af2 | 55,83,2,65 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
0c867bf0-d33d-4c82-8be2-728d44360237 | 55,83,2,73 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
965216a3-7064-4d4f-bab5-721d1ce37edc | 55,83,2,101 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
642a1514-e827-437b-82f5-7859a6ccbefd | 55,83,2,188 | ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5b6110b9-ee15-43fe-b37b-79e231998c32 | 56,54,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
50764484-74d0-4550-8b65-e84d7a0e0f93 | 56,54,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
35f712ea-c083-401c-b17c-5aa3cf406e18 | 56,54,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4123e69f-9067-4aa7-9e57-75056e642b5a | 56,54,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
8da62588-0512-4593-9b28-85f996a70516 | 56,54,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
280ab5df-ee30-423b-9abf-b79aa2e675d0 | 56,54,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
0be76f43-6ba9-46d1-9f5c-bec129ffbf1e | 56,54,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a4081639-9344-4b9a-8ca4-0c1bde99a3ae | 56,54,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
df7775fb-3d72-4e0a-91b3-050bce88ef01 | 56,54,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6d2148fa-443d-4b9b-b8e1-ec30962550c2 | 56,54,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
36208be5-91ae-4348-a109-65b7de2d5549 | 56,54,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
0c9ee2e9-2aa8-45c7-a1fa-906310c49e63 | 56,54,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
f5cba9a2-2b44-41af-9091-d962d1faa90c | 56,54,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3700cbc7-7cb4-4465-96ba-6c8f11ade27a | 56,54,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
d6717062-89fd-4fc2-9908-bc4d73d25dd5 | 56,54,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
68ea5ffc-548c-42e7-a2c0-220e9a10a936 | 56,54,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ac1d5882-5e4d-427a-972b-7b57d6c46f3c | 56,54,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
7a383200-e975-4072-8900-4dfbee248e4d | 56,54,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
fb965685-a574-4ba2-a33b-2b6378fc36ca | 56,54,74,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
a228270a-c49c-45b6-bc73-b86ff619be5e | 56,54,74,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
f1d55b1e-e374-49fa-92cf-2e121c3873eb | 56,54,74,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
bebedb5c-52b4-4cd7-a29e-f92f69e7621d | 56,54,74,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a2f810f9-3f8f-4d83-b9b3-8cff7a57ae08 | 56,54,74,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9924d2af-2830-41ef-acb1-13df28e23994 | 56,54,74,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3be75126-608e-4f28-bb3e-51fd8f0be619 | 56,54,74,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
2c021502-9ed8-4a62-b4d7-7697b6a8cef9 | 56,54,74,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e8cddb79-6f0a-47a1-ba75-4cdfccc9300e | 56,54,74,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
42b26385-76c4-4a44-b58b-9979a73774a6 | 56,54,74,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ffc6689c-cf53-4911-82ce-2d143a7e8d48 | 56,54,74,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3e5b3e90-1814-4aa0-8e69-10b75eefdb18 | 56,54,74,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
235b6dcd-e25d-4aa1-8cad-288a3e015528 | 56,54,74,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3e39ab70-3918-45ab-a1a1-6a2c2b0bd067 | 56,54,74,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f6da34ba-1ed8-4e3c-a218-3acbbe09f9c0 | 56,54,74,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
03b8d4e9-c4e0-4e2f-adfe-c6534dfb670d | 56,54,74,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
0d7b9f55-2043-4fe5-bc77-fc3901eb1bb4 | 56,54,74,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
abca777a-dc67-4d30-889a-9a472188f6b1 | 56,54,76,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
3e51b8c5-94d0-469a-a1ec-16fb386aff02 | 56,54,76,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6fb7cc93-9fdf-44fa-9517-07ab8c9710cd | 56,54,76,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
46b84f44-47a5-468a-99c7-16c3cf1d4d1d | 56,54,76,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c9fc9601-bf9a-45b5-bdaf-8c43126db9e2 | 56,54,76,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
cf2a9337-e2fa-4504-9d31-77cd2af2738b | 56,54,76,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
14453f85-059a-4082-8897-06f59e9f7a62 | 56,54,76,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
570c336c-51b4-41c0-ad68-61e41b11e85c | 56,54,76,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0f166ce9-35df-42ff-82a6-5f306d60dab9 | 56,54,76,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
33e15bff-b9a4-4dcf-911f-ff28b9d29e95 | 56,54,76,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
12e64e98-3af5-41da-99db-c73311edc8ee | 56,54,76,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c841f524-9bbe-44bf-8282-cde96c0bc77b | 56,54,76,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9a6dd89a-be20-40cc-abc1-9326db78ebca | 56,54,76,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a2fe0bf9-1fd4-48af-821f-fbc315a873c4 | 56,54,76,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
612f647f-302c-4aeb-bcfa-f30dfbadc43f | 56,54,76,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
143a40bc-c8c1-4297-9715-3afd9f444eaf | 56,54,76,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
d0286191-f5c0-4a90-a706-07ea5c040af8 | 56,54,76,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ea62c389-ba34-4fcf-b18a-9573c4ae2e4c | 56,54,77,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
c99f3a73-0aab-435e-a147-bbd5ea3bc83c | 56,54,77,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
9457ea40-d04c-4b12-8fdc-fcc48347ab62 | 56,54,77,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
af43b461-3edf-4478-802f-17990a3dea1d | 56,54,77,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4bf10db4-fd18-48bc-ac0f-c21d38a405aa | 56,54,77,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e3258715-7d48-492a-ae09-dbc4df765d7b | 56,54,77,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3ce62668-5fe6-4e97-ab1f-edc2712c20d3 | 56,54,77,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d0bf961f-e229-4e87-b314-30a5c8c87956 | 56,54,77,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ae4392f3-58bd-40e7-ad0c-7d65c3637dec | 56,54,77,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f41e70dc-0896-4e91-8cfe-ba5c838c7609 | 56,54,77,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
4c109973-cca0-4bdb-a7ae-90e8fdfe36fd | 56,54,77,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
93e4d8d1-12b7-46d7-82cb-f71be16be5dc | 56,54,77,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6cf5df3c-6e5b-4c82-a577-f6e085177042 | 56,54,77,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
cb7a8590-cff9-4861-be2f-f936338028c1 | 56,54,77,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
111ebd2a-cf1e-4cd0-bf0d-d536082a9511 | 56,54,77,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e9fa0689-294a-4527-b502-e86c6896cc59 | 56,54,77,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
40da1351-92e5-4a09-ad1f-1adfa95316ec | 56,54,77,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6e5e66f6-4880-444d-9b45-95ff9e5220ea | 56,54,80,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
49f3142c-aec9-4b98-b21f-b6203fbef46b | 56,54,80,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8527f79f-bbe7-4728-ad52-9c628b7484bf | 56,54,80,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
99daf6f9-dd6c-4cc2-a495-08d02b9f9024 | 56,54,80,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1950fc1e-1707-41a2-92ec-ecaa958c2a12 | 56,54,80,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ac6e3702-5142-4017-8457-511300eda4a5 | 56,54,80,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
da55caff-c668-46fb-84de-21580a5ec214 | 56,54,80,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ebd45cac-10c4-4c8e-840d-90c2528064bc | 56,54,80,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ec2d71f1-30ca-4d42-8730-72ee819386f6 | 56,54,80,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ab3c1213-29a4-4103-a1e3-6b181c711deb | 56,54,80,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a42513f0-962c-47e1-9eac-62ef5cb64bc4 | 56,54,80,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
be8f508d-8a5a-4856-b617-877d658c4f43 | 56,54,80,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
1476eecd-a5dc-4419-8661-2792de4487ef | 56,54,80,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1b650141-faa0-4bb9-9d46-7f45055ad573 | 56,54,80,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
ad240aa8-c8a3-40e8-8d88-4dffcc06a564 | 56,54,80,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
dadcb238-c752-4648-8c74-32fce86b0467 | 56,54,80,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
75b1c7bd-d4a8-4fe7-8950-44338e762696 | 56,54,80,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
5e50c050-ebf0-41e3-8da6-7e2cbcd8db34 | 56,54,81,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b7d0f027-cd74-4c10-8660-f3822a66e4b6 | 56,54,81,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
29026c81-6169-4cdc-b217-073c86dc5b19 | 56,54,81,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
41f36da3-3a16-414d-8645-bbc5983ec7d3 | 56,54,81,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e52a7d08-d10e-4a88-abde-a0e7f42ff6ad | 56,54,81,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
00992c5a-6f99-47f0-bbe1-022e53e3551a | 56,54,81,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d4faf12c-e00d-47c3-9aa3-19650be20f82 | 56,54,81,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d343c997-2e4d-4972-8f94-7a15dd5ea453 | 56,54,81,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e3bb8718-21cd-476e-9501-7c03685f7ed3 | 56,54,81,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c4a919d5-5649-4dd3-8c25-4b6ce71bea1e | 56,54,81,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
fb7e5b1e-a599-4e97-a57a-ef95ca010849 | 56,54,81,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bcbb057e-df36-4ef0-a418-44c84a24beda | 56,54,81,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9b021dcd-f536-4c96-b0a0-aa0c08beb530 | 56,54,81,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1bfb0043-d811-4a0a-b1dd-bbd33e3e01e8 | 56,54,81,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
cb91924c-a470-4f27-a0e2-57b134599af1 | 56,54,81,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
ef9dd469-92c7-4e31-a958-1f78405e2f81 | 56,54,81,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e605b37e-ba4a-4d2a-917d-128cd775c9ce | 56,54,81,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
84864dfc-7c92-4c0b-b7bc-c029a207a746 | 56,54,83,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
7bed79d8-b1ac-4cc1-b087-7389b1652883 | 56,54,83,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e4200a32-4ad5-43e3-8fed-e62a6d41271d | 56,54,83,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9d987160-6014-4b48-8712-c7e7f083536e | 56,54,83,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f264f4aa-a3a1-40ca-b5d7-c7fa125c19e5 | 56,54,83,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
02209547-a7eb-4554-8613-7384a963f8ad | 56,54,83,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f2b47140-58ee-467e-9e1c-c66cdca338e6 | 56,54,83,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1e119bf8-4978-4cbd-a1b8-fb406d338597 | 56,54,83,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
99357385-851b-4a65-8654-5713787abb2e | 56,54,83,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a90049cd-6ffb-4d97-b247-b75ec2d52e91 | 56,54,83,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
3a800e95-d729-44e0-9e0b-e81d0df01e49 | 56,54,83,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
58b25745-d085-4a32-9b26-a391f9a0bb29 | 56,54,83,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
fa03a094-828f-4d2e-b30e-fe36cc894a62 | 56,54,83,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d7903707-cf72-4c31-8509-1ce0f5ca38c5 | 56,54,83,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
b54251f7-d261-4636-bf7a-166b4f314835 | 56,54,83,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
075dc7d7-9869-4b35-8069-78a9b139ee70 | 56,54,83,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
88ff472a-d056-474a-b79b-f1ccba590b80 | 56,54,83,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ffc0232e-8827-47f7-8dc6-90db031cef24 | 56,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
505392df-1572-4f51-b919-7ac1e4679872 | 56,74,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
cc9c066c-7906-4479-8d79-44474a0a210f | 56,74,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1814f0b7-095d-40a7-a720-d0be2bb6ff8a | 56,74,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ad519f13-83fb-4446-b5d7-807641a9363c | 56,74,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
59ee9dc2-dad6-4b7c-8c0a-f8e4afd417f2 | 56,74,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
2cbfd7f4-9668-438d-b777-adbb32636149 | 56,74,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
80471ce0-1196-4917-ae24-44097464cb81 | 56,74,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
fe372543-2b8b-42a5-b0b6-4fa0f142f699 | 56,74,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a1bd1ef9-0537-4121-b692-dff0503ed85d | 56,74,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
64aba524-4da8-4bde-8ad4-6803b0615cca | 56,74,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
cacf1b26-2dbe-420e-aeac-dcc6de3fd9d5 | 56,74,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e2da9a24-73ca-493f-a2ae-d7fe860be423 | 56,74,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
f2c6062f-e1e4-49c3-b035-bdc90c6e2291 | 56,74,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
27b77f37-8e39-47b7-95b8-01e7368387a4 | 56,74,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
dcd12da2-b0f7-4aac-968e-295da1f8f45a | 56,74,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9d321247-2467-45c0-ac41-7897e812301f | 56,74,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
7aee3978-184c-4ee6-92f0-f4329d436a6e | 56,74,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
b8c17a5b-e437-4113-904b-4941e96956f1 | 56,76,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
efca8c04-baed-439e-9117-dcfa3505e8de | 56,76,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f1c7a500-6cc7-46e8-8c64-7838ef728f6a | 56,76,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1bc5e555-b5d6-4df0-9ef5-dd9878023e84 | 56,76,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
372f0881-338e-40c4-bb6b-9a6a7c28d86a | 56,76,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6e334c31-349e-4f62-ac2a-40b6d41030a3 | 56,76,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
051f45d5-6243-482c-a35c-1eb63ca408f5 | 56,76,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f50b8314-5c4f-4532-8590-7e92c77c8810 | 56,76,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
27bba82d-f1bf-40fa-9103-4295870d3d40 | 56,76,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
68991749-4d0d-41bd-9a09-56cfe9403f63 | 56,76,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
ce8fbba7-56b8-4434-9e29-ca10279b0fab | 56,76,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
deb3ae7d-5cf4-444b-83b7-464a2839bd0a | 56,76,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
aeb2f756-c598-4e23-9525-c0f5114b36fb | 56,76,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
388f71c6-84cf-4e1d-a3f5-c0994192b4b2 | 56,76,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
8203a57a-b85b-4408-b34d-ddf0d0bac9e1 | 56,76,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
10f893cc-2720-4444-80e3-74ba7d6154c3 | 56,76,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
62d4edc1-c6b4-4adb-87a9-e1f0a5013354 | 56,76,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
e9d2c53d-e92c-4578-9ed2-9f638cda1cf5 | 56,77,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
028379ec-6d2d-4af6-a7ae-eb224054ad6e | 56,77,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
caf9fd15-3e8f-4a9c-92c3-963fabdadb05 | 56,77,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
559bd54f-18bf-4aaf-a630-91662c90925f | 56,77,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
180ade1b-955a-43a9-b697-3ba0e533545f | 56,77,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a3a5747e-7353-4334-8c25-b9c2f12fa2c2 | 56,77,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
29c4000f-f3bb-40a5-a28d-712f9318b09a | 56,77,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c58deead-451c-4844-bc70-0d8c2f0909e2 | 56,77,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9d141eb1-ee52-43aa-bcac-42fc8e3d56ac | 56,77,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f6de4421-3bc2-41fd-8982-f626abcd8319 | 56,77,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
26fdce30-3dff-4039-92ed-935a25e2aabb | 56,77,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
05c5215e-3668-414f-9d28-264cf0a81ee3 | 56,77,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
c6cef4ce-0af9-40f8-a1e5-e590ced47b53 | 56,77,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
19a4a2eb-a022-4e01-b1a3-27f511a779bb | 56,77,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
fd376122-dee0-4dc0-a5fd-de30469b547a | 56,77,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
d1fc810e-3b19-444d-9d7a-597950c1aea8 | 56,77,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
4c6fdd8a-9f12-40d0-aaaf-0c63a359ab1d | 56,77,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
4c6ae620-489c-439d-b421-9881ed56cb51 | 56,80,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
988a492e-8ecb-4fda-96b0-63a092964ab9 | 56,80,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e8782817-7551-4887-985a-82f812d69a9c | 56,80,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
cb910a31-f8d2-4a8d-96ef-31e03a652121 | 56,80,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2d231591-19ab-4692-a848-5711a2de9ded | 56,80,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6d33bed7-085b-4f70-8faa-00abdee2a1c9 | 56,80,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
ba5aad58-37a9-4767-8c90-97576f70b12e | 56,80,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2afa3390-625f-4d90-9382-d9f616fc4a18 | 56,80,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
085bdb95-df81-4de5-b319-a7e25e86e9a3 | 56,80,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
20dc5bd5-a39a-441e-b0ed-1ad375e897b0 | 56,80,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
2c9f7f2e-b7a9-4a36-8ee5-8803f990a2d8 | 56,80,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
74adda2b-57dc-42e0-96e7-7adf97c4dba8 | 56,80,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
3d4990dc-490d-409e-82b6-b2f668b211c3 | 56,80,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bb94508d-3ff1-4f13-9f04-e441fa90aadc | 56,80,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
76d2cfc0-b1cd-4e26-9296-df3c176d42aa | 56,80,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
0f70584c-bd26-4707-9056-b8544015f03e | 56,80,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
fa9bb603-4f56-4034-b7da-897c8bff5b93 | 56,80,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
8732e64b-9ea8-4b5d-b905-703ba69293a7 | 56,81,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3eaf4e79-fac6-40ba-8095-84a8c8c13dce | 56,81,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
45299ea9-88c5-49a8-ade8-f869128591c0 | 56,81,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
35bce196-74bc-44df-87c8-6cd87aae50d6 | 56,81,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
11047ddf-262c-40ea-9c91-2706682cbd95 | 56,81,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
170de357-391f-4a1b-897d-3072fc45a10e | 56,81,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
426d34f1-f487-4c3f-a7b0-b94fa997de0d | 56,81,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e453ef47-521b-44cf-943e-b7db1848c4ab | 56,81,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f2e2c2f8-0d69-4940-9ffb-abe14151152f | 56,81,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
aae5fc4a-9e6f-44e4-929a-9a1968facc77 | 56,81,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
e59b785a-b247-4dc0-94b5-b421e29325a6 | 56,81,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7ac43393-e97b-41a5-b7d7-64a71354f61b | 56,81,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
87abe15f-8a20-421c-88ae-7c723b238130 | 56,81,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7b7e9abb-c80b-4157-99ed-931dbd6eb6d4 | 56,81,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
2d70b5b7-d4ad-44a3-b681-c286cbddef6e | 56,81,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
b9e83291-c23e-430b-8301-6f3114cfac50 | 56,81,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b5679756-8519-49f4-a468-307e0ec3e6d1 | 56,81,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c69898dc-74fd-4687-93f8-d1fa0abd0382 | 56,83,2,16,21,22 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5c4ded14-b3e4-423f-ab54-10292263e76b | 56,83,2,16,21,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
bf862737-c817-4320-b0aa-d471fec90af5 | 56,83,2,16,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f82e97f9-d8b3-4c59-b67f-da17a67ca55d | 56,83,2,17,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d4085eae-3b19-4b2b-bd5b-409589935fd5 | 56,83,2,17,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
4d144c54-2011-4a3f-86cc-f85a8869fd06 | 56,83,2,17,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
ab180d44-261f-4641-b2d3-3408f1151231 | 56,83,2,18,19,20 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
18e0760a-6d3c-4f22-9bea-92471493c831 | 56,83,2,18,19,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7a9e9f0a-417f-4ef3-b421-67d1dcad7a68 | 56,83,2,18,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
546cc9fb-56f6-48ba-9581-c793a5e174db | 56,83,2,35,25 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
9505d147-fd4e-4111-a1fd-96a70ad1fa0e | 56,83,2,35,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
54d087aa-2424-4a69-8384-2ff41dbec20e | 56,83,2,36,26 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
54a8c98e-0ec5-481d-8def-4ea977c365bc | 56,83,2,36,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
c8f66f6b-c074-4449-ace0-636f912e11fd | 56,83,2,65 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
94e99e77-7307-4f5f-ae8b-e0423d775ef0 | 56,83,2,73 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
06b66e8a-7219-406c-a1a6-8fac61fd5924 | 56,83,2,101 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b0dfe6a7-1bd6-40b9-ad0a-0b26d02a6178 | 56,83,2,188 | ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
7f07e6b3-7263-49c3-acab-21b1c43d0bd6 | 57,55,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
3eb52072-343c-4563-a343-bf3704c1e48a | 57,55,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f35bd054-53d5-461a-be9d-d1f9bb8aef00 | 57,55,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
937c0b59-bac3-4312-8d60-0c0b605bd6b7 | 57,55,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
cafb979c-3234-49a4-946a-992720f2a1a3 | 57,55,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
1c78a24b-3fb9-4e0b-b145-ea892d75fe9a | 57,55,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
93eb3570-c896-46e9-923b-46696dbd753e | 57,55,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d2b27da4-9509-464f-b7b2-6d7fe2df38ab | 57,55,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b7e5887c-6865-40a3-8b52-af8cf949f081 | 57,55,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
66bcc28d-4a6e-43fa-850b-ad4f4f463e50 | 57,55,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
a7d80640-24c8-4f3f-9c11-4782f3a61378 | 57,55,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
c440de07-4bd0-4a49-967d-4abe92ee7e67 | 57,55,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
3caeb192-0610-4c6d-8561-bceba10132c6 | 57,55,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
25aaad63-0ca0-4824-9fd2-1e2576436273 | 57,55,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
5703b5d2-f858-424b-afad-90bae08061da | 57,55,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
90329500-eaca-4d18-9c44-263a498958c7 | 57,55,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
e729ae52-06de-40b2-b3e1-5cc7e76c297e | 57,55,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c459ee31-76de-4fb2-8b5b-1838ae75d9ad | 57,55,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
9b120807-2e96-4dfe-b4ff-325cf06ea7e4 | 57,55,74,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
82f10eec-5dae-4b3a-8a76-4157a2f8fe66 | 57,55,74,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
33f13fbc-06e2-46e0-b26f-8c579ffae622 | 57,55,74,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
92b8ead8-3772-489c-8b85-3ed01ace3087 | 57,55,74,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
75d75d4e-6995-4b51-8e2e-f184e080f080 | 57,55,74,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6518730e-3277-477d-a126-4457fae2584e | 57,55,74,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9c2d1cf9-a6d9-4fc4-bd8d-1a4b8512e1c0 | 57,55,74,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
33001476-76b0-48c1-b1b8-0e119cb607f0 | 57,55,74,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
534bb019-923c-4336-8f2b-88b520c614d2 | 57,55,74,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9134da29-8ca4-44ba-a5d0-6f3f934137f9 | 57,55,74,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
c3894437-1df6-48c6-8a45-8d933a5f8e8e | 57,55,74,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
dcea2aa1-ccd8-48b3-9588-ac089e164df9 | 57,55,74,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
796cf39b-8446-41b5-8e91-f4422a8e34b4 | 57,55,74,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
dcdb7241-620d-46c0-8d82-7dda246f1f22 | 57,55,74,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1f24a935-0f74-4fe1-ab13-54430fb70a01 | 57,55,74,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
52ce399c-4c1f-47d3-8bc4-270bde43835f | 57,55,74,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
d7c5df65-564b-433b-b48e-6caddcec5d41 | 57,55,74,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
215e7ad1-46c5-4ce5-8852-68b4488a3c66 | 57,55,76,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
26b4df7d-c087-40f5-8678-b8dc72f14cdc | 57,55,76,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
52059d42-00b7-410b-a7bc-b53519d26a83 | 57,55,76,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c62f9447-9d43-4648-a8a3-28e497660bdc | 57,55,76,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7b85b1e8-41ef-4d99-9cf6-849a68cb7a92 | 57,55,76,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
45ac976b-666a-4c6c-90fb-eed1a433bc4e | 57,55,76,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
febb92ba-96be-48eb-9de4-ac93b7e47ff0 | 57,55,76,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c8ce6aba-9c29-4b43-842c-69c566fda770 | 57,55,76,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
cee7a79c-67a7-484d-be02-94299d4025b7 | 57,55,76,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d7dc73aa-989b-4b8a-9ec5-7b981ea81416 | 57,55,76,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
eda69a57-5562-453a-97ff-103e92328bee | 57,55,76,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ee21d21e-8298-4257-bb18-0db4d7d29e15 | 57,55,76,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
532bc52e-45f9-47e1-84b3-35d05b2981f2 | 57,55,76,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
45b2ab49-3976-481b-ab14-5a1ab1931fb3 | 57,55,76,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
dd4a1cac-4e63-4d6b-9919-88117112ed45 | 57,55,76,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
c3923a9b-262e-40a0-851f-0b2ba178669b | 57,55,76,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
c35ce24c-e33d-41c4-a1ec-7cef4d94603a | 57,55,76,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
764dd031-3cab-4617-96c0-0d013ca9dbc6 | 57,55,77,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
a65f6200-f52e-4d6b-9dd5-164fc034c5f1 | 57,55,77,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
0bcb21a9-f3d8-4a2b-bff4-fb846cd14273 | 57,55,77,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6d8666c8-210e-4c8c-acad-fb00dd3fd0bd | 57,55,77,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
81ba3721-404f-4e5f-b9ae-48abc47ce7ad | 57,55,77,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f451727b-6cc9-4b1c-9fd1-9ed379e4465f | 57,55,77,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
16c02e5a-112d-4a06-9197-75b9e0e15b4a | 57,55,77,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
04aff5a1-af40-45ab-b196-5255a1152e48 | 57,55,77,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
243e69d6-4bc0-499f-86d0-52bb73357188 | 57,55,77,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7d685ece-afad-4b1d-a880-0e6ed005b8f8 | 57,55,77,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
52b8e3da-58be-414b-80e1-793d65dc54f3 | 57,55,77,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4b1413f0-d18c-4cac-8f61-e63691cdf938 | 57,55,77,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
f62d765f-c76b-4e6e-8d26-fb20b665c90d | 57,55,77,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
7b95950d-2977-4be4-8f91-0ef4b20da880 | 57,55,77,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
3a34e0cb-42c9-4102-99b7-338ac3cf727e | 57,55,77,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
82c4b926-4379-4e0e-aa1c-76e5e81a7d9b | 57,55,77,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
aee385df-febd-4bfc-908b-8498a11c8517 | 57,55,77,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6f770647-a8f5-457d-9ade-b0bff39c92fd | 57,55,80,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
d5c52adf-6ab3-4c2d-81cf-8e3b35a1938b | 57,55,80,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5c14f1d8-8a08-479c-b05b-647e4bde3023 | 57,55,80,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
39b207d3-b191-49c9-a102-78b95fccfc0f | 57,55,80,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b96e4957-0bc5-414c-b7cc-5ea6cb68bd3d | 57,55,80,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6abb6ddf-e7a8-485d-8278-b6c9e0dd7577 | 57,55,80,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
131a67a9-258f-4e1b-a5a4-8dd88170f38d | 57,55,80,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e6a095c1-481f-43b7-8977-7bc47deff98c | 57,55,80,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
61c007ef-f88d-4414-a5d3-223a08c75e50 | 57,55,80,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
11c1edbd-6845-44f0-82b4-36bc435a0888 | 57,55,80,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
53c617a7-dd9d-4cf6-9128-55bdb72c37d0 | 57,55,80,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a4539825-8c7f-4c12-9a44-73b91c452487 | 57,55,80,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
56fc5492-139a-4dcd-b823-1f7846851bfe | 57,55,80,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
78b989f9-3421-4106-8469-caa2a092e224 | 57,55,80,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
3c528e65-8a7c-4049-98cb-74a839b194ab | 57,55,80,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
6105dfd2-fad5-4f6a-95b0-d539611a5cc1 | 57,55,80,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
0418492d-e7ab-4680-9ab4-6a9ff2c5126c | 57,55,80,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
b24cefb1-9815-4a0c-b6c3-0064308da5c4 | 57,55,81,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
8dc1811a-432f-4525-ba58-c09d2e4ebc44 | 57,55,81,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
82130327-75d3-4fcb-b9c0-030bb58fbc07 | 57,55,81,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
35b4019a-de0e-4253-9d22-e9cb6126cdc6 | 57,55,81,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
2b175f47-1e71-4344-a5d0-251f61f3cff6 | 57,55,81,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6de385a7-bee3-44f8-ae73-52b3ca288ca8 | 57,55,81,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b4a93e00-6f3c-4853-bb83-59f790ec2f68 | 57,55,81,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
36df1612-2269-439d-b71e-125ab29140dc | 57,55,81,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
146842eb-37e7-49c1-ac44-02a4b40f3aec | 57,55,81,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
128f11f6-476b-4a15-8f56-41e314ad488b | 57,55,81,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
d0b95398-a1f1-4ad9-a5e3-6782f59d839b | 57,55,81,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4bb1248c-9a75-41fe-a2b6-631bc8f0986f | 57,55,81,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c5224fcc-f515-4e05-bd38-13d88c755a49 | 57,55,81,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6e11773b-fc25-4889-9f13-439df7279818 | 57,55,81,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
75189a85-a69f-414d-b11e-da8797c1f79c | 57,55,81,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
f0f236e0-b188-41cc-830b-0405e28d5b19 | 57,55,81,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
4f6180c9-3b76-4be8-b2cd-9185ff651033 | 57,55,81,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
75bffc91-3e12-4c88-8733-d6c84c5af172 | 57,55,83,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
16357934-a710-4ca4-a21d-cd0fac2ea2f4 | 57,55,83,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2805b1a7-dd96-444a-bbe7-3a048448f4dd | 57,55,83,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
577ea3b0-08e9-421b-8c5c-e411a1777444 | 57,55,83,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
202171df-5df9-4872-b984-ad346288c939 | 57,55,83,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
eb1553be-d291-4458-afa5-089a9c4e268d | 57,55,83,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
137ac291-4771-41f9-81bf-e17c883147e7 | 57,55,83,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
3762006f-9be6-4dd3-819e-6dae5b305eaa | 57,55,83,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
460b2e7d-5feb-49d6-8d34-e020716b057e | 57,55,83,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b364c75e-58d5-4b53-97e7-6e1910286457 | 57,55,83,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
35f3edee-1c44-4955-a66b-ad3b485295f6 | 57,55,83,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
831392e5-6322-4096-95af-022b31681759 | 57,55,83,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
a780d8c7-b697-4d0c-b189-835ee91f42a3 | 57,55,83,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
71a212d2-7469-4802-9b74-e98f6bfcdbb7 | 57,55,83,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
d0b1ca68-86d5-45f1-8166-64ce74ca6ea6 | 57,55,83,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
a82d6326-c254-4e06-b729-c009e47b35bb | 57,55,83,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8db25c5d-c9b2-417f-b19c-20ef6f015567 | 57,55,83,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
1a92532f-2acd-4d47-94a4-279247f77cc9 | 57,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
190eb0d0-61ef-4ee3-b425-cb1adf9a6937 | 57,74,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
9c809727-ae52-41c0-a66e-fad16cb779aa | 57,74,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3ecb92d7-0ee2-43b2-a739-b9cb88e06960 | 57,74,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ec47c62f-784e-4741-b650-5a9239ff2684 | 57,74,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
70f384db-284f-4e2f-b6db-7b6a9b0777ee | 57,74,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
858b995f-e6e3-472d-839f-65b15296741f | 57,74,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
668221e8-0fb7-4669-b7d0-0a4ffc54d14a | 57,74,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
44ceb6b1-1e24-4f35-ab7a-52a43742b4ea | 57,74,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
bcef2051-c3d1-43aa-82d6-d774f05d1de5 | 57,74,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5746761a-f1f3-4ff1-b4ca-fceb061d66e1 | 57,74,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
96345f7a-7df4-47d7-8efe-923ec709a4d3 | 57,74,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
83a65762-21a0-4350-941d-ff13a4cbe336 | 57,74,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
ee094019-7471-4a75-8ee6-5c185d661b43 | 57,74,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b7a70b5c-7117-4238-93ec-fa56049baa71 | 57,74,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
80516f07-0adc-439c-9b52-9c3c3eb2c0aa | 57,74,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
d2b266b1-5117-4678-8232-9ac20f5389a1 | 57,74,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ac06d466-ebac-4263-b52d-79917f709b83 | 57,74,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
db69cfdb-e6b9-4553-bea2-194812386cab | 57,76,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
67386d64-08cd-4c47-b0e3-d43ebe3d35df | 57,76,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e29979b3-34d2-42a7-9efc-4f63b1f09d69 | 57,76,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a7b8f55e-e1dc-4649-b477-0804f5ff40c6 | 57,76,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e6339c65-13a4-405d-bed8-5b7cc1a78461 | 57,76,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a9b25e1d-5af4-405f-bca3-c366722778f6 | 57,76,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
9c50dae5-8f83-4ba2-ba18-bcf573601ddb | 57,76,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4dfc6642-7a9d-445a-85a0-e63342e7754b | 57,76,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9918ada6-8299-4fd6-8b85-eba6767f6594 | 57,76,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
54ced2ed-da9e-43b5-b954-1c6b73420b57 | 57,76,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
6f5d97f4-98a4-4054-8009-ad9734e341c4 | 57,76,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
abcb7f4a-7505-4de5-ab9d-56a677bb3589 | 57,76,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
2320912e-98c2-42d9-87c4-891ad800d5fc | 57,76,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
51000270-58b8-40df-a8d4-5f31e2a04a4a | 57,76,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
4d95edab-7ca2-4e44-9e6e-5e344533e8f6 | 57,76,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
7cdaa75f-bb7b-4f84-8387-e59deee3a7c0 | 57,76,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c7c9a40c-5694-4ecf-9990-79953cf0b02b | 57,76,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
7ec626b7-a829-4e7d-b699-4353cf2b4625 | 57,77,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
043e706c-979b-4008-bb81-117d188ed701 | 57,77,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0367e6fb-0cb0-45b5-af83-8efcf502ef99 | 57,77,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bb5d0df9-8eff-4466-a94d-f97f651ba43b | 57,77,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d5530c06-06c0-426e-885b-d2dbb40dee0b | 57,77,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
2af2426e-d2f2-4c42-aa4e-de6a90857089 | 57,77,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e24a54ce-c55f-4bb8-9b7b-1bf6364171db | 57,77,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
097b3065-4237-415a-ae63-8629ae271b56 | 57,77,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
39eef624-9114-4926-a222-b8aeae443529 | 57,77,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d8355d10-92af-45ca-9086-50c9e9d69ee6 | 57,77,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
cac014d4-a776-4887-9471-9726c3758586 | 57,77,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
580a7741-278b-4875-ad0b-ad2aba0fab05 | 57,77,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
c8898fb7-f396-43ae-ad23-1f67ed43d196 | 57,77,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bbf5f712-fa9e-48e4-8038-8a352ac9adbd | 57,77,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
2e6a2b13-d25b-439a-b2c6-7460fc1f4ee2 | 57,77,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
c14664e0-52b0-4c47-b73e-fbb1b8c70742 | 57,77,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
dbdf8d0c-b2e1-40fe-a4e1-fe9420044f2e | 57,77,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
558b7b98-172a-439a-9f1e-286078148a5f | 57,80,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
7fb52bdd-58ae-439c-b723-95806afa3f34 | 57,80,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5e4d2f41-dcea-4d26-983f-2584556df563 | 57,80,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
46e744bb-a658-4b94-9272-e784686bc4c2 | 57,80,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
58c681bf-0552-404d-b826-1bc87bf1b47a | 57,80,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e0c789be-e5ac-445b-9051-0c7bf681e7dc | 57,80,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
158e7e94-bb0a-4897-9751-bd2c6f53fece | 57,80,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c15d7d42-f760-4f4b-8a0c-bdb908b92978 | 57,80,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4350fad6-259f-4559-b042-5f312deabb10 | 57,80,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a256d5a5-66d2-4fcf-aec6-474e2c58ee94 | 57,80,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
846d2f21-6763-43ee-afe3-61f321715cae | 57,80,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
dcd0214a-d214-4a85-b63f-c04a3edb73bc | 57,80,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
96695e09-fc43-4adc-93a8-ea289262c704 | 57,80,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
69893ac2-5a2f-486a-9663-4a6bb1e7e2c0 | 57,80,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
ea0330cc-8a9c-403e-88e8-92ca8f4a85dd | 57,80,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
30cb739f-100c-4787-8806-03a33a8a0b07 | 57,80,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
cf22016a-dda4-4502-b2c7-434281e3bc06 | 57,80,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
66940400-59ea-473b-8760-2f692f009634 | 57,81,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
22d57a08-a87c-461b-97fa-e0dfa02f7d5b | 57,81,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2357a1ac-8e8e-4da6-8814-f3d62a0141a0 | 57,81,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ec78a633-4fa1-461f-b834-1e2ba01416ca | 57,81,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
dfc2117d-f455-4330-9441-b765626775f1 | 57,81,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
91d717cd-dafd-4ee2-ad0b-a6137eda81ae | 57,81,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
ad17b302-e2aa-4227-8f80-c5f2ece7910e | 57,81,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
3889d849-4ee0-4bd6-b6cf-1fe022801dad | 57,81,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3bc24b8a-6bc2-4a80-b22c-21db4a3c7e09 | 57,81,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
44f0bfdb-6437-4546-aa54-01aaf674d50b | 57,81,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
21bc34c7-d25b-4100-bad3-b4f98218e1c0 | 57,81,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
0b9c7e7d-1e42-4256-830b-50044e9932f2 | 57,81,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
8b4b42ba-e01e-46d6-8ac6-6d2df20f7392 | 57,81,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
46754ef3-08c8-4591-b1ba-54b053e032cf | 57,81,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
0e044f0d-7607-4132-843d-886fc4f0e397 | 57,81,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
0c04a87d-4b96-4ae1-8876-b1d88a1b8303 | 57,81,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b9f15f09-ae44-4b5b-b3fe-d3ec58033341 | 57,81,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
11e4ff9f-0cb8-427a-bb57-ffce4e02f9c3 | 57,83,2,16,21,22 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
57f81e0d-016c-4c31-8ab5-55d53cee40d7 | 57,83,2,16,21,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
939ec9e2-3f2f-437f-88cd-27a8c198be76 | 57,83,2,16,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1248e8ba-cd3f-4558-87c2-032d3fe4e989 | 57,83,2,17,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
898f1b24-1ffc-4cb1-94d6-89f19336604f | 57,83,2,17,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
61229f50-b126-46cb-993e-ce27de8b86ee | 57,83,2,17,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d8ef931b-3341-4667-8ee7-63129d160933 | 57,83,2,18,19,20 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
99952b24-daad-4fae-84e0-6e9649839f90 | 57,83,2,18,19,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
69bacbf6-eec1-486b-8e41-3964900b6ac2 | 57,83,2,18,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
27c315d0-87fe-4632-a2b6-684cce36d42f | 57,83,2,35,25 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
ba4cd094-b60d-42cb-8355-560147cae85d | 57,83,2,35,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
5db7fc25-f8de-42e5-8da5-d3bd1c58a84a | 57,83,2,36,26 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
867d3c6d-cb16-474c-996a-a70e8d5970f4 | 57,83,2,36,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
2dac20aa-dcb4-42a8-9c6d-59efc5c1478d | 57,83,2,65 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
767a86bd-1b68-4155-9c41-bb89a6d7d9bf | 57,83,2,73 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
b12d9b34-7937-4584-9843-0d39176dfaf4 | 57,83,2,101 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
bc23a8ef-8927-4b20-b989-d1fe268fea27 | 57,83,2,188 | ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
685a1131-3adb-4106-a4bf-3c1ae9752d18 | 66,68 | ASSY - REAR UPRIGHT - LH (2) -> ASSY - REAR DAMPER - LH (2) | 4 | FALSE
8274e004-3ee3-4104-8148-0d61003534d9 | 67,69 | ASSY - REAR UPRIGHT - RH (2) -> ASSY - REAR DAMPER - RH (2) | 4 | FALSE
d7800b2e-39a1-4476-a015-e4cfe0f0627b | 70,61,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - REAR TOELINK (2) | 6 | FALSE
d9fa58f4-8fad-4abe-a0df-1c84467a7d75 | 70,61,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
687038a3-8782-450c-94c9-f78e6c09e70a | 70,61,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
30b8906a-1903-42a3-a1e0-6a5ef082846a | 70,61,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6733c737-88fc-4486-9011-e8d17195daa0 | 70,61,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
69c79996-e381-4af0-b44e-d0ae2261d18a | 70,61,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
372193fc-f1a8-4f62-8f5f-1074ea18fd4e | 70,61,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6992bd61-b269-4c79-8e58-cb002f911591 | 70,61,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a3ce63ea-f350-43e6-a7d1-43f01d489cd2 | 70,61,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ab014fda-d896-4502-a308-591a38aaadf3 | 70,61,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e2b64776-ea1c-49f4-b2e5-c98530474448 | 70,61,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
2cfdbcbf-9b81-40db-bf39-e7068fcd6565 | 70,61,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
274501b1-2cd0-4744-8da5-e527fc5d8f44 | 70,61,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
3b56819c-11fb-4a30-a83d-02a8a8b9db81 | 70,61,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
33f6335b-3a51-40e7-b745-959b42eb7a46 | 70,61,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
daa83588-9aa8-43a6-bb07-542760249471 | 70,61,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
a8357d75-13da-4ba4-ab86-986281a39290 | 70,61,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
4163ebff-41a3-40b6-87be-6f73eb7a2a03 | 70,61,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
e7a86488-0891-4ca8-af7f-1f9d7808af68 | 70,62,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - REAR TOELINK (2) | 6 | FALSE
b9330207-e8c5-4030-838a-48603da2313b | 70,62,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5102a520-85a8-4901-9a61-7f6f1932037a | 70,62,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
51d922c8-5d7c-4e65-ad40-e682c2b4bf4b | 70,62,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
045e101d-132d-4868-b226-303911d72e46 | 70,62,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
418b19fc-b8a8-4638-866e-4c68039a191f | 70,62,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
22645803-6fe3-4b70-a08a-aa91dbddf422 | 70,62,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
41dd0134-accb-49cf-adc5-417e17d1678a | 70,62,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9dadc3c7-0e57-4d4a-aa06-35898506de70 | 70,62,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1ade900f-9ac8-48e7-acb1-ad7efc8f5338 | 70,62,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1762f463-9877-4197-8189-324dbabf2d68 | 70,62,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
71998ddd-97ee-4754-ad5c-220e8932eda7 | 70,62,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8b950734-70e0-4cd4-8168-589da3dfecab | 70,62,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
9364f655-4e2b-432e-b3d4-e56dcf1802bb | 70,62,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8ba68f36-8723-4834-a83c-f9a926079ada | 70,62,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
33423dbd-71c3-405f-a541-a8751d1902a9 | 70,62,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
f42e4162-4144-4ec9-8f83-e9521b2a269d | 70,62,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
5376852d-d9b6-4e02-a7aa-5b321bb1b534 | 70,62,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
1dd53030-e37e-4a78-a0c3-56c91ffadb0c | 70,63,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - REAR TOELINK (2) | 6 | FALSE
28e1c6bc-bfb1-41ba-b16f-8853b60775aa | 70,63,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
85a7c502-4872-4548-9dc9-bb975d2e1485 | 70,63,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a8b55b44-b3ad-48f0-a4d9-f32ee84ba968 | 70,63,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5d605f6c-7126-47a7-b80e-604c1ad13b50 | 70,63,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
b11c2745-fa8e-4557-8847-80cbac894f7a | 70,63,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e1e3f043-999b-4cd0-a3d7-4fb9ce9f9221 | 70,63,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
f95a2a74-1046-4f85-a082-a5a5e502e015 | 70,63,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1943d99d-ef00-454f-80f2-b05ae9387cc3 | 70,63,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
76528f10-b59f-4239-83be-af2a5ce8f75e | 70,63,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b694c7e4-07b4-4118-8030-44b700c56657 | 70,63,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
36276302-b0dc-42e8-8fa9-f5d3815c2c4b | 70,63,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
1d223c7a-e7e6-40af-a644-c9fd342a602a | 70,63,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
cf744f5c-f9db-4786-a259-915fa3bea4f9 | 70,63,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a3beadba-b335-4e5b-9be3-b5e01d3a3726 | 70,63,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
21153519-a364-4d5b-8186-9d51adeafadd | 70,63,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
79d85c45-94ae-481a-83ff-cd99fdd99c0b | 70,63,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
8fadd10b-aa0c-44dd-8417-1560bcf48074 | 70,63,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
be00d40f-50e1-48f0-8bd5-75ca62e5a392 | 70,64,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - REAR TOELINK (2) | 6 | FALSE
f7e48d01-cb16-4e28-8a05-601b92d9c3cb | 70,64,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
9e2fffc2-6a6d-4884-b2fd-e00ffcb2e734 | 70,64,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
88027bf3-55bf-4f87-adb0-ee74b0f0d546 | 70,64,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3ea89dcb-d9ed-460b-9ab9-0b37695d8d54 | 70,64,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
9f624476-e4d4-48ac-83ab-f679721a20fc | 70,64,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b24fbc60-a717-4384-930d-e182158da0df | 70,64,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7a3ee862-bd1b-4b87-9425-8fef30d0042b | 70,64,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6ff3f5fb-256d-4181-b65d-e9e4da10526f | 70,64,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
71a012a7-f6ac-4eb4-8b06-36448dcae1bb | 70,64,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6160aa76-e932-43c5-96ca-5cf7bfe8d801 | 70,64,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
f54a9f6b-baf3-4a95-ac58-dd96191f960b | 70,64,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
84946c59-cc90-48a4-afe0-6f5f5337abd5 | 70,64,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
47befe77-9be7-4f21-8413-91d998eb1e07 | 70,64,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
778f2401-d79b-4c14-9fcd-4ba6462eeefa | 70,64,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
d43e8a93-2621-4c8a-b4ba-344d32402624 | 70,64,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
6b74b0bc-669c-496d-a84b-94a022ead2a3 | 70,64,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c7b2750b-780c-4258-8fb7-1b3fc028b78a | 70,64,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
4d0ad7f7-f0cf-462c-84f1-3f5037846a84 | 70,66,68 | ASSY - REAR WHEEL (2) -> ASSY - REAR UPRIGHT - LH (2) -> ASSY - REAR DAMPER - LH (2) | 6 | FALSE
49fc42d0-a549-4f8d-b30c-eddc8e6af31a | 70,67,69 | ASSY - REAR WHEEL (2) -> ASSY - REAR UPRIGHT - RH (2) -> ASSY - REAR DAMPER - RH (2) | 6 | FALSE
b624741f-b589-4aac-8bd2-ccccd913e4f4 | 70,68 | ASSY - REAR WHEEL (2) -> ASSY - REAR DAMPER - LH (2) | 4 | FALSE
fe82c428-44c5-4781-a734-2f1bb7f7ca2f | 70,69 | ASSY - REAR WHEEL (2) -> ASSY - REAR DAMPER - RH (2) | 4 | FALSE
3776452a-9d4b-4d51-a4a1-640ad30475b6 | 70,78,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b7cfe1c0-ac93-4e18-807c-c676ee526a5e | 70,78,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b0858fdc-5fca-455e-b7b7-e7ac60c08cbc | 70,78,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c175cd22-a96b-42d2-8917-8aacf67b6027 | 70,78,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c32ea2cd-c4fb-4209-8843-4b1d94d74c01 | 70,78,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e6021c39-1654-460d-b8b5-20fb26518669 | 70,78,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
daf3605c-5c7e-479e-a4fe-52ffc0694835 | 70,78,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e8a5043a-dd3e-415a-8654-83495dcd6b1f | 70,78,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a6d7fc58-5f5f-40ea-9453-5465cc452af5 | 70,78,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b66cd852-1423-46b7-90cf-baa76c94fab8 | 70,78,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
cd1ffdbe-d9f2-4131-b2df-654c80736820 | 70,78,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
16c3fd05-7f90-4b3f-bde0-4d61f8e193b0 | 70,78,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
e94d5fe0-6823-4871-ad23-a8f90ca913d0 | 70,78,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
41556f6c-0644-4728-bc8a-55fa4dbb5447 | 70,78,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
225c8299-1205-4367-b0aa-e5ddf545e3e7 | 70,78,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
2c26ff26-efb1-4764-84c1-d5e5dcc3e14a | 70,78,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
88323cc1-9c97-46a3-bf1a-66cc7b6253f5 | 70,78,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0beb2665-819d-4a3d-a8e6-9f9e0548e4b6 | 70,79,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
3ddd83f7-c12d-459a-9a5b-69dc2ede2a1c | 70,79,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2df6773a-d476-4ac1-b492-f107769a56cd | 70,79,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6adc2618-fb40-48e2-a5ee-ea8fd0a899db | 70,79,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a89da7fb-ba56-45cc-b5e2-28e3b4a3ddb2 | 70,79,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2c072488-38eb-4bd8-831c-c58342e6e3b3 | 70,79,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
af02c942-35e3-4f46-bbca-e8e3d6ca12a4 | 70,79,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
270af16f-f3a3-41a5-a402-5387f232f66a | 70,79,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
bfaba894-0f0d-4244-8585-947b68148d78 | 70,79,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b1f4a35c-d409-42f8-97de-0c335bfafc4e | 70,79,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
6001dd0e-0336-449f-9a6c-c3c0f6c5dfa7 | 70,79,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
74bfa870-2e89-418c-b601-643aad8e8d60 | 70,79,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c16b3012-9b7c-4744-beb6-7682bf3a10f5 | 70,79,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e232e667-5327-489b-a069-21b41ba82976 | 70,79,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e7dc4707-0f71-4dea-b0bd-8397082daa1d | 70,79,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
ed2cb5ce-ce49-4a06-b9f4-9b0c81bf7987 | 70,79,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
a52673e6-3f8b-438e-9160-2e68052100fb | 70,79,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
f8b7ae1e-e696-41fa-9599-8ead350efb8f | 70,82,78,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4d3c3a0c-c54c-4372-9d30-919d6ccb632e | 70,82,78,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
9b882600-126d-4dc7-89e9-e1f2f1cb0b4c | 70,82,78,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
881b35f3-960b-453a-940b-0ad7792ef2c4 | 70,82,78,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
45ffec5b-3b90-4324-ad35-dbfe79fa5a53 | 70,82,78,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
52c22c48-3335-4200-9a22-5607487b06ea | 70,82,78,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ca4d0117-9f72-4c14-9e8f-0b1eb9394c8a | 70,82,78,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9d92e849-6b81-4445-9a9d-5fc39f511fa0 | 70,82,78,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
aeab6942-5ef1-41a5-b626-aa90e75ef39a | 70,82,78,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6c2e0723-62cb-48e3-a88f-e412f0b95607 | 70,82,78,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
d637cffa-3a9a-4e9b-95b1-fd3215d04b5f | 70,82,78,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
fcb61cb1-7da0-4886-8ca9-6034802b8bfc | 70,82,78,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
82703347-2f1b-4319-8710-0a0427b00bbd | 70,82,78,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
3ae4a200-75ef-476e-9ff0-748ff5c77d6a | 70,82,78,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
6656538e-094a-41ab-9c8b-6510af0400bf | 70,82,78,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
4c750e49-17aa-4685-b3b7-2d6e054c60a9 | 70,82,78,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
68a5d962-1360-4452-bdfe-e86b27a8afd6 | 70,82,78,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
4bf21b0a-3fc4-4933-991c-c5a67e195e0a | 70,82,79,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
d5705793-aea3-42de-a7ad-f4d2e7bd7d0d | 70,82,79,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0c9cae52-cdeb-46bf-bae3-67ad2e1cd363 | 70,82,79,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
256bad1f-5272-41bc-8305-f3b51042d51f | 70,82,79,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2d36402e-e345-48b7-aa76-ecdac4c0abd1 | 70,82,79,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0eb0fe6b-f6fc-47be-a5f2-31786873b562 | 70,82,79,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2baa6d28-4f4e-4609-801c-174d9d561c3a | 70,82,79,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
cf405e45-9547-455a-a56a-adb715cc02d5 | 70,82,79,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
84bea20a-db2a-4a14-b03c-fa785e49ed9a | 70,82,79,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d12f8910-4107-4be4-b9b8-6d8c539500ae | 70,82,79,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
f7b78621-e3e2-4a91-9445-5af926042b43 | 70,82,79,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
149b416c-4ddc-409f-a629-6c530e8e2f7a | 70,82,79,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
87262c92-3f00-403d-97cd-01e2605ba091 | 70,82,79,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e1123516-2eed-4920-b01a-e0cd3c048f82 | 70,82,79,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
80b67eb5-b4a1-4aed-a58a-e4bb047dcf7a | 70,82,79,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
51094a2f-7153-48a8-97aa-3a4795301802 | 70,82,79,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
74ca2df2-3abb-49a1-af67-651bf78ad6b0 | 70,82,79,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE CALIPER - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1d690d12-d615-4a86-9f70-f2d187affdd9 | 70,82,84,77,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
35406657-f9ef-42ab-8249-93883a318c0a | 70,82,84,77,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4ff00bb9-1cd1-46d6-82c7-87280e02ce87 | 70,82,84,77,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e0406a29-7ae6-41b6-be58-48ed0d4d7f7c | 70,82,84,77,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fa0c0126-d9d9-49ae-a796-0ecd8fb1c796 | 70,82,84,77,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d912c959-eef5-4d85-bcef-7296dcebe954 | 70,82,84,77,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
acba95f0-8c82-43d5-a22b-0674581d1880 | 70,82,84,77,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ff34668e-c38d-4c6b-84b3-2f3b887dbc19 | 70,82,84,77,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6e78f1a2-0182-4191-8a13-ac0449772a29 | 70,82,84,77,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c62192f6-e27e-4953-8ac1-3c725ade91f9 | 70,82,84,77,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
032e4ad6-41d9-4039-b525-c85f4993d636 | 70,82,84,77,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f9da2972-7a10-4a08-be13-b44b594317a7 | 70,82,84,77,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ba0a655a-0b11-43ab-acd7-9447b39a99de | 70,82,84,77,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d2b71409-f226-4747-b41b-4a865b6d9dc9 | 70,82,84,77,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
c7c56b0e-9136-4ba4-b8e8-287188c77e10 | 70,82,84,77,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
1d82e6f4-d8ef-407a-b48d-4c668dfda6cc | 70,82,84,77,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
98f5cf44-75ba-4732-992b-54dc9befe535 | 70,82,84,77,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5d0173c9-6bd7-4512-b47a-3bef7e82d744 | 70,82,84,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - HAND BRAKE (2) -> ASSY - DASHBOARD STRUCTURE (6) | 12 | FALSE
f368691a-4d4f-410a-8c77-c33d522ecbdf | 70,82,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f928ab68-8c42-46ac-8168-852080d6f091 | 70,82,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2cca6ffd-9afb-4456-947a-738a5a6e8ed6 | 70,82,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fa0c9a83-d00a-4b67-8fa7-20536c0eeb5f | 70,82,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f8956700-e08d-4401-b71c-a2e34f956f1a | 70,82,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
da084e1c-7c9f-4af4-9cab-79c731f2d593 | 70,82,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
77a380e2-4aba-4e08-bd02-9c01d2094021 | 70,82,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
321f38a3-0e3a-4c5c-aa04-29db4ee4cfcd | 70,82,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
acc0bd12-02fd-405e-9b97-0edddccd8aef | 70,82,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f4290dd6-f20d-416e-8302-d415192f6932 | 70,82,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a71ee5f6-9359-4ea1-98c6-784862980f26 | 70,82,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d1ca9712-fcad-44a6-aa01-4e93434ae089 | 70,82,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
da17d85f-6a73-4fe2-b863-9068cf5a5bbe | 70,82,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
2d71f5b1-59e2-43b6-8447-e3e5e0fe5c01 | 70,82,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
8c4ca7e6-159f-4974-9184-b588685775d5 | 70,82,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
66ac1bd0-f993-4896-a438-6ba1eb334443 | 70,82,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ab210bf8-0fee-4478-ac26-225877b8fea7 | 70,82,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE DISC (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
4cecc8d3-4d5b-46be-9577-a9e8394b48a1 | 70,84,77,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
79886956-585a-4f32-81f2-947bc8d21ea6 | 70,84,77,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b97db8f3-056f-477d-a4e3-2c56db3d002f | 70,84,77,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
38e5ba23-16dc-4f1c-9397-bc9aa15474a4 | 70,84,77,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6c25ed8e-2922-4350-b48b-31a679b58423 | 70,84,77,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
38c7640a-3ce5-455b-8022-3e5972a9f250 | 70,84,77,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
65523f79-28f7-4ac1-b2c8-c535fb7b5698 | 70,84,77,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
4f53359c-c1ce-44c8-85eb-ec53c98d868c | 70,84,77,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c9abbfd0-3be7-447e-ae33-a6fd4a76a87b | 70,84,77,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fa1aa1e5-d235-4ed1-bb5e-19d318e3065a | 70,84,77,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
463dbeb9-ceaa-499f-b3a9-d3951e35a5d1 | 70,84,77,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
caedcf61-2396-4514-97ff-d9290c7d2cd8 | 70,84,77,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6671bd6e-7e3e-4a22-baec-7febfa7dc059 | 70,84,77,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
f6989f3e-7869-490a-a4a0-9ee370f88295 | 70,84,77,2,65 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
7f7dc8dc-c3e2-4c27-8af2-e915479389fd | 70,84,77,2,73 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
07182a15-6e97-46a3-ad70-3ee0fb4c701e | 70,84,77,2,101 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
854cb610-1400-4444-b480-4c755880c4d5 | 70,84,77,2,188 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
274ac335-be3e-4923-a26a-6b583e82108c | 70,84,101 | ASSY - REAR WHEEL (2) -> ASSY - HAND BRAKE (2) -> ASSY - DASHBOARD STRUCTURE (6) | 10 | FALSE
9131e314-aff9-463c-b9bd-0fbc9116a2b8 | 70,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
1e1e63b4-5ae5-4954-a72f-5f2eb4e14de8 | 70,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
56e36134-7595-4b1a-ba17-6fe39b878eb2 | 70,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
94d8df21-ec07-4387-b708-c8283d18aaf2 | 70,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
2d77a5bb-cab3-44f7-8e15-df3426579386 | 70,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
1aa1d7fc-2283-479e-aaf3-2f744ae78fd3 | 70,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
835e84df-34fe-448d-a162-4805e896e25c | 70,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
3c18009b-9048-4d60-abfc-db5d52821dd9 | 70,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e08a765a-04af-4f8d-bd8b-822b2f0ce501 | 70,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
fb1b274c-b04c-403f-b8fd-8483a238e64d | 70,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
e9b8ca5d-a140-4b2a-812d-3ecb8cb07ad0 | 70,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
4d03d78e-da32-4cde-865f-c3ce5447f064 | 70,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
e4545bd2-644b-42e0-942e-ab05858a211c | 70,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
4d412943-dfda-4c50-8e31-1c5cd0d83cff | 70,2,65 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
e9e46794-1cb5-4c20-ae40-f2cbc523de07 | 70,2,73 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
e2623efa-e120-4b17-86cd-f2893a52629b | 70,2,101 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
cb6a4120-2a87-4def-b9ae-2941daf530b5 | 70,2,188 | ASSY - REAR WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
d9401503-07f3-4c48-b3b1-94c0ea533f63 | 70,14,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4186140d-7b01-469b-aee2-a122874a6b2d | 70,14,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
156e0dd3-b937-47f4-85bd-c7603daed5b6 | 70,14,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fded8404-bb75-4bb0-a1ab-33e279d96bd3 | 70,14,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e7802494-53d9-4524-a3ea-a1e60d072371 | 70,14,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
4e883566-f7b7-4db4-836f-7332194219ad | 70,14,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6ad234fa-f4a6-4c6d-af69-1974bb96f830 | 70,14,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
64b27c5d-d5e6-4022-a766-18317324bfb8 | 70,14,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
21e75d7d-98e6-4d62-ae27-2c90b2caadf4 | 70,14,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
eb38e616-05af-4ad2-ae5d-4c3594ef58b8 | 70,14,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
460a8427-88e0-4a69-86de-e2a2cdaba0b8 | 70,14,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9ca1e38f-436c-4d37-af07-aad5bf4cacd0 | 70,14,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
2d60488c-e3c1-4eb8-b198-048dc48caed3 | 70,14,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3cafb355-9522-499d-a132-3324bb407ff0 | 70,14,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
657c7c71-176a-4721-90a4-bd4c03201b6c | 70,14,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
b11b595b-849e-445a-a909-f23b92df1f29 | 70,14,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b8e7550e-b3fc-4959-833b-879fb44c0e0a | 70,14,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
66dd3b7d-6fc7-4e46-9be2-eec88089c497 | 70,14,13,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3ae49ccf-177d-4a69-b3e2-a5e0eb54bf22 | 70,14,13,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
3316810a-563b-426f-8738-6f0f530aaebd | 70,14,13,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a05cc589-d1cf-4559-8d21-fd7237636357 | 70,14,13,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
9fa1753e-24f5-4767-a2b6-4dfaf3ef4387 | 70,14,13,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e5ed3a69-c56d-4e6c-9c0e-f462940d52d8 | 70,14,13,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3495e6a3-50d4-44bc-bae2-1ee53422721c | 70,14,13,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
90783142-5eba-4c59-8bba-2bf1c73db5b1 | 70,14,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
423a9b7a-0818-4432-8a75-a179ebb20365 | 70,14,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
3f21cd76-45b2-413c-8412-b184256b2812 | 70,14,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
bf8ef522-7989-460b-ad2d-19b3ed65d82c | 70,14,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 18 | FALSE
9d734906-1bb6-402f-8d25-daa4dfe3bc16 | 70,14,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7b344530-0b36-4ad4-b858-174e9373365c | 70,14,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c857dec4-6dba-46b0-9073-b0ba63efaa5c | 70,14,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 13 | FALSE
6daf473d-6ef2-461d-bf0b-ca6431302bca | 70,14,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
48dcc57f-746a-483b-b8bf-1c1c16a21957 | 70,14,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 6 | FALSE
7aa8da27-f427-4a6e-b323-1f1ffc9819b5 | 70,14,24 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 6 | FALSE
c7d6200e-547b-4d27-bf87-716e8acb1c17 | 70,15,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
b13e6640-bc9f-48c4-be9e-530aed3411bb | 70,15,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
afe35e6d-64fc-46b8-8a4c-9d15fcf045c3 | 70,15,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fbafb1f7-ab2c-41fb-b7ee-351c864d67e5 | 70,15,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
9f57fad8-1bbc-4902-8e09-e8572f6ca4d4 | 70,15,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
caa34c9d-2480-4228-881f-aa53cc916104 | 70,15,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7607fdba-82b7-4e2a-ba18-c65880d4812a | 70,15,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
994f0d1c-be5f-4775-bacd-c671d05e9845 | 70,15,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
46548ac8-906a-4066-9a9f-771a61f52847 | 70,15,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5e505423-27b3-49f9-a32e-8303a9906f95 | 70,15,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
547c1fd5-3e89-4c72-bc92-2b5ae64b4209 | 70,15,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
47fa9931-dec6-4185-9c92-a4c35695f91a | 70,15,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
cdbd6f58-d92b-48c9-9cb6-15adc74835ba | 70,15,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7b9a20ae-aec9-4971-95ac-aaacf0e72159 | 70,15,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
ad62f3d5-8671-48c7-a29d-a1c5af10a0a0 | 70,15,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
9aada09f-38b5-46cf-b016-e795b5b1587e | 70,15,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d5ea8347-d2de-40d6-9475-276cb664e35e | 70,15,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
661f9b05-b9ae-4b1e-a624-ddc68a3e82a7 | 70,15,13,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
55f402ae-7782-4a6e-b9ee-d9394b500734 | 70,15,13,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
927eda01-5434-4a50-b2d8-6805979e90d4 | 70,15,13,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3e8942f9-2fe7-43bc-9ffa-76da8c2b4f8d | 70,15,13,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
1dc4566b-dd68-4309-a3d1-5c9ab1a30b25 | 70,15,13,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a532499b-68a7-4957-89f3-e4ab138111ff | 70,15,13,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
d3cebc3b-5f3a-4807-b732-43803d73799c | 70,15,13,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
b35fe397-d660-4684-9b9d-1fcf53ed0108 | 70,15,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
f955e182-8e94-4e22-9c53-e4f19b427366 | 70,15,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
a72a7bc0-445c-478b-813c-6e1968ca185e | 70,15,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
3c14cf75-abb9-4897-b903-2634116f598e | 70,15,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 18 | FALSE
ac9cf5ea-0e77-4563-91e6-5940fc23a27d | 70,15,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d2cd3820-d2d0-4729-837c-f6add841fa0b | 70,15,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
d623202b-e53c-4533-b136-bcde1b65e77a | 70,15,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 13 | FALSE
9a741357-0f2d-46de-a249-62fb9b853598 | 70,15,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c8c391c7-e713-4c94-9119-def0c82fa645 | 70,15,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 6 | FALSE
2e63ed70-8212-44dd-8ae8-94a5dc8d11e4 | 70,15,23 | ASSY - REAR WHEEL (2) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 6 | FALSE
03c90396-878c-4359-baea-4f7d5820c90b | 70,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
ba92578b-9c00-4746-8796-faf037e539f3 | 70,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
0ba82fab-9b82-4a2f-8860-13693ee6b65f | 70,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
3911734e-bb51-44ad-b78c-dc25195918f1 | 70,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR TOELINK (2) | 4 | FALSE
2520c24b-80b8-4203-91f7-ddd189b4d908 | 70,80,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4351b42b-45b6-47a5-ac8c-0d33f54da96c | 70,80,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
7a1da448-3ff5-4841-94cf-a3b95a840272 | 70,80,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ef0af1fa-5c2f-485d-a1e1-5dc665b98d35 | 70,80,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
46b87be0-8680-4099-afa5-b2d7a4dececf | 70,80,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
bee88679-a53d-4fb2-94cf-6d912d2f2a98 | 70,80,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
0fc12d3e-2a55-4746-8924-43f7d7ab963e | 70,80,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
161b046f-f96b-4103-bb1a-82b9d771e129 | 70,80,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8f6805a0-a2fe-4e41-993f-d7d9176c2d45 | 70,80,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a208ad80-be99-4ed5-8f41-acd64decebca | 70,80,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
40a72f47-ea1d-4835-8c8b-62254618734c | 70,80,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
dfd87fac-fe2f-4a45-aa0f-64f4b3a49e1f | 70,80,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
9da47957-3620-4352-853a-a45dd2ab06e4 | 70,80,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
250c83b8-2801-4ab4-ad6e-89607c9bcc50 | 70,80,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
f8c3d703-a227-4984-9f4c-b0ff1a6af3bf | 70,80,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
6dd1f841-080f-4c7c-8ef9-6ca201eb1318 | 70,80,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
59c9a7b2-5279-4f2b-b45f-e6ffadc1d1fb | 70,80,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
3902a350-2cdb-4586-9507-69fce85183ad | 70,81,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
05c11d1b-fb2c-4422-816d-ecbc045cb224 | 70,81,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
cf708007-27b5-4926-aace-da4cd2d2a76b | 70,81,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d5e99deb-8744-4b62-8f08-260d1b28160f | 70,81,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2d57836a-cead-4199-8c8a-c4bb639d4a33 | 70,81,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
9ef41a01-1488-4b1c-9028-58532f02101d | 70,81,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
8919fdd3-28c3-43de-a218-917ef8064038 | 70,81,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
b1a21072-5ec3-4efc-a750-6a1cef5276b7 | 70,81,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ba7dcd4d-e3a2-479e-ac74-c28bfb697989 | 70,81,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7921a56c-3755-44c0-9c6a-4d48fd0bd8d7 | 70,81,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
5ef9f078-3dfd-466b-9704-76e4da058795 | 70,81,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8582f3b2-130b-472c-9947-3554701a5e25 | 70,81,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
30772bf4-229d-411e-9a82-bca8fa0f03fd | 70,81,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
d7ec54fb-54e4-46f8-aa54-a25c5ba29b4c | 70,81,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
bbb0b799-1635-4acf-88f6-5b1b35c6e527 | 70,81,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
a162772a-d525-47c5-b3f5-019b6de0bc5b | 70,81,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
4b66366b-f417-4514-8088-a48898f84887 | 70,81,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
2f94211a-7f7d-4fc4-8294-8117de21834c | 70,83,2,16,21,22 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
109ee01d-bdc2-46d0-866e-9bc78f2a2e42 | 70,83,2,16,21,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3ff112ae-7dbb-4060-8c31-f3b1c961f98c | 70,83,2,16,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e0e67afc-a2ce-4f98-8d7f-b3fcb2c45c4f | 70,83,2,17,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e1370324-551a-4e3a-a822-c6a3b19d302e | 70,83,2,17,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
dcf0cf0d-4a5a-4c13-9ba5-fc6bdcbf6799 | 70,83,2,17,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
b2c00747-0fd6-4208-873e-54f59a2e76f1 | 70,83,2,18,19,20 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
53c2cca1-4329-4c09-877b-94702f17c448 | 70,83,2,18,19,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2118839e-441b-4ae7-8584-b45782ddefdb | 70,83,2,18,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
8ca20da0-d6d4-450b-bae6-768504f482fb | 70,83,2,35,25 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
42f5622a-fe74-49ef-a20e-34f76985dada | 70,83,2,35,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
38dd7b0b-44e8-4553-9788-45d66964cd0e | 70,83,2,36,26 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
72db8821-7041-4753-94fb-5b6536ad8173 | 70,83,2,36,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3f504f83-d6d9-4143-bcb5-3d42ab02c23a | 70,83,2,65 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
03ceced8-4922-4c67-a742-7f067c4dd38a | 70,83,2,73 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
71d8556c-7e2e-4df8-a65b-b0cbb805a4ca | 70,83,2,101 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
90ec4116-8b07-40d4-9af1-3cb2c1b53b7b | 70,83,2,188 | ASSY - REAR WHEEL (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
8452f1d3-ae30-45e2-bcfa-cbe9c7f77f2f | 85,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
e895b536-a694-4974-b4a8-cea1cd1cd9cd | 85,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1a55467e-2ccc-4f39-a461-4dd92c8a963e | 85,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
20341a1b-550d-4182-860d-d99285d4dfda | 85,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
1604f857-b812-4ebb-9104-da0e3fc9df77 | 85,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
18b79034-1b3c-4fe7-a3b7-d4db0d10f262 | 85,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7c2948d0-75a4-4956-8c61-02d28481f661 | 85,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
76f8d585-5b59-4c6d-ac7f-0a69e8cd3145 | 85,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
9082e93d-f677-4cc7-8ecd-6a526ead7215 | 85,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
51429f67-e4b0-458e-bca9-9766034be2e4 | 85,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
a1263ec9-2ab6-4bc8-9843-5fe50e0c5fac | 85,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
d690d9b2-e1af-4a29-a746-b697c51efea7 | 85,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
4d865ff0-027f-4552-9d15-12e4d64cede8 | 85,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
b9b2c495-c7c8-428b-849f-b1a1cba45236 | 85,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
f59a9b7c-449f-49a3-b5b3-61cc53ba2857 | 85,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
09f02d24-8a18-4b63-9025-7990afe7d171 | 85,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
b9085fe3-2f28-4b5b-9866-b9196f55dd54 | 85,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
c5441c9d-2c85-4cce-a1b4-4fa06ca4c461 | 85,3,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
d7f0dc20-abae-413f-a2ba-817734e8a88f | 85,3,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
67104474-8aef-4869-8e53-d14df182002a | 85,3,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8d3c9b2e-d253-4a23-8278-ff3cf9668d18 | 85,3,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
7b7bee0b-e7d6-4141-870e-2449323cb54a | 85,3,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
72164ef3-35bf-4004-a86d-5cc3512ca635 | 85,3,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
47dc8698-7837-40ce-b0f7-87af30a39294 | 85,3,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f0424bfd-6cd2-4f27-83a7-85347977ec36 | 85,3,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
87149f75-1bdf-490c-a0d3-5f5e04750f2f | 85,3,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
90c53b4d-5e9f-486c-a6c8-91e8621c1505 | 85,3,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
a4c00618-90e9-483a-a2f0-74407f7e94e2 | 85,3,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e032527d-01ae-47d8-95ed-fa27ac96c932 | 85,3,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
e787fbc0-15c4-4f35-ba55-fbbf5cf801ab | 85,3,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9a5d47f0-91a7-4db8-8539-093c21dba147 | 85,3,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
1b259a66-c0c8-48b2-a577-8f7b752f69c2 | 85,3,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
c6066f49-fcd2-4e36-b88b-6c3f97648b70 | 85,3,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
bc86159f-bb0e-44ee-be6e-4392f6c83759 | 85,3,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
9a70435d-897d-438a-9038-784dde447b24 | 85,3,188 | ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 6 | FALSE
dcdeaeca-319b-44fb-b3ac-74aa3b2c5be8 | 85,4,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
dab60900-e883-41c9-8f62-a2d0d2e4e2e9 | 85,4,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a03f09ea-4ca8-40f2-8186-4134f15be017 | 85,4,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6f45e1cb-66da-4902-b5ed-cd4ef27332cd | 85,4,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6c2d1194-da8a-4568-bb9d-85b6ea422c31 | 85,4,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
78a5774a-d5d2-4d9f-a47a-e56072e49c0f | 85,4,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
00b8e588-6ada-4080-a44f-8c02d0c8b052 | 85,4,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d0d041fc-d1e7-47b1-98a8-427b95a1358b | 85,4,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
eb21a497-0dd1-4724-beec-3029ac9fd255 | 85,4,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e534ee9c-2839-4107-a139-a8619d0add4d | 85,4,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
18501093-a5e1-42bb-9836-b5ac827c6191 | 85,4,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c408e956-0728-4ca5-9251-a0812dac2cbc | 85,4,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
648fa2fc-a731-4ea8-8b27-520815dbdcd6 | 85,4,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0106d511-6581-4e30-9f75-53b5b97b2c06 | 85,4,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
b6e3e4a0-0280-4b29-b1f2-43bd33f460b3 | 85,4,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
f98dcc73-7665-4bc6-b33a-54ddf5c3fd7d | 85,4,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
d309ebbe-f67d-4fc8-b0dd-8b018c7a645e | 85,4,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
28148cfc-98d5-42aa-a22e-ee58bcd8ac3d | 85,4,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
b6523427-bb68-4113-995c-64207bfbce05 | 85,4,74,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4fcdf623-c1b4-4f97-8e70-cf924e806cf6 | 85,4,74,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
89d96f97-9d21-4b58-b6da-5428b2cda08a | 85,4,74,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
7dd8bbbf-30e2-4f53-8c82-f592ef6699b9 | 85,4,74,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
820904c8-b5e3-4545-89e7-f26bdf88eb85 | 85,4,74,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f490f7a7-1424-46e3-b175-15b0c2a81a0b | 85,4,74,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
252d3840-3de0-4b28-bf87-7ffd92b2b2cf | 85,4,74,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a79b44f4-043b-466f-a5d1-fa3d9f25763c | 85,4,74,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
7c4d7338-86e1-4e2a-9dac-c310562c6b0c | 85,4,74,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d8b9f66f-576e-4daa-b2a7-38465a793a83 | 85,4,74,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
967c375e-22da-49d1-8379-0e848d0e612e | 85,4,74,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
84c2f1e9-f49c-4cad-b6c9-972643b53229 | 85,4,74,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
0460c14f-13a2-4234-a1c3-a75ea562e2c6 | 85,4,74,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
fecf12a4-e944-4457-a805-c8ead59b9c78 | 85,4,74,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b16542a7-9ca9-4aed-b89b-456e33bdb6d0 | 85,4,74,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
bdb9ee9c-c03d-44b3-9ccc-7deeba74e2f3 | 85,4,74,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
7cbba4be-b6fe-4de8-a837-ddd9d87d37de | 85,4,74,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8bbbf8c3-14f9-4331-838d-c6d840eea4c7 | 85,4,76,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
344d036d-ab5e-4ca0-a233-19252d145055 | 85,4,76,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
87f8fb31-ec40-4eaa-a521-3f5018d58693 | 85,4,76,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f542ce1e-2694-49f3-ae15-7f1ef4fe6393 | 85,4,76,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b8b9c62a-4083-4c77-83a9-b1b7c06053bf | 85,4,76,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
94201558-5da6-478a-89ea-d4fe52e26a3e | 85,4,76,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7784665e-75a2-43a9-8b54-cbbcede81be3 | 85,4,76,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5bcf36f9-e56a-4dcc-bbd5-7eba7299d506 | 85,4,76,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2eb12d84-8d37-4cec-a857-b42a9044418a | 85,4,76,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
424f6cc3-f730-4f37-bf5a-00cd10e990fe | 85,4,76,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
c0df045a-e094-4d2b-a5c3-2d53a9bba164 | 85,4,76,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
694b7812-debe-46b2-ba2d-4340e18652d3 | 85,4,76,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b9a07e0d-073a-4537-98da-00a0bc25ea87 | 85,4,76,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
8735d722-2eef-44ab-b25e-e77be1f5d852 | 85,4,76,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
758c32fc-e36e-49f4-93bc-6360ce0f45cf | 85,4,76,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8b0b03cd-2103-4992-b7c4-263691363367 | 85,4,76,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
4fc44ae7-94c6-4e55-b81c-8748a18b9029 | 85,4,76,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7ecbe941-f8ba-4408-bee3-3909b65663ed | 85,4,77,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
9d105bbe-e8f2-49bb-9b6f-ccc4941ce7d8 | 85,4,77,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
11f59fd5-1cd2-474d-9122-d862dc41e90d | 85,4,77,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
96a00421-2fa1-4962-8591-5493f57ff231 | 85,4,77,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0a547a4a-cc27-4d56-9cf8-11ea90be7dc5 | 85,4,77,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
fa0b13c7-6ef0-48b8-b96b-b4c3cb6f47d9 | 85,4,77,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7776d8ad-746f-4e7d-8cae-5f037e7d7f60 | 85,4,77,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
f66230f9-6f23-4197-b3cc-09ba63cd9cab | 85,4,77,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3bb7a9d5-a319-47d3-84b6-3e1100196026 | 85,4,77,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
74adcc78-50b5-47a4-b7fd-33e71564a242 | 85,4,77,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
c2d40859-631f-4404-b86c-47a47e0388b4 | 85,4,77,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f98ccd59-f62d-4538-9f70-7204e1740d87 | 85,4,77,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
5a4bc29b-28ef-4f49-ab07-d48c9ecc489d | 85,4,77,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
5a57d219-5c07-4bc1-8041-e285f9d87f7d | 85,4,77,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
a27b2911-aaed-4e05-99b1-2925af723edf | 85,4,77,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
48a3466f-dd99-4173-a50f-b020e41b616b | 85,4,77,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
39871222-6eaf-48d1-9a54-a4f061156ddb | 85,4,77,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f96c1e08-cd50-4504-b37e-4a2a6bc95d76 | 85,4,80,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
f7e7027a-96f3-461a-ac4d-12ada31dbc4d | 85,4,80,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
6d70c88e-e501-4347-8d7f-4c96b4464268 | 85,4,80,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ab38d38a-8f1a-42ba-aa48-827312bf19cb | 85,4,80,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a7f1efa9-3d43-4a0d-8221-6ea5f27132fb | 85,4,80,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
88210e0f-6088-4aa3-a8d9-7f97b86ae3cb | 85,4,80,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
31e3d7ff-b75f-4fab-b698-ef8918e96962 | 85,4,80,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
3c1cf028-92a1-4c4a-ac67-7f2334309528 | 85,4,80,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
116df956-2d77-48f5-a4c0-86c5763048a1 | 85,4,80,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6d9493a0-2710-47d3-96a6-8a937fb7479d | 85,4,80,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
96a94a72-b425-4d6c-88e0-57a47a1328ce | 85,4,80,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ae867ca9-3586-47cd-a853-aa2251595f33 | 85,4,80,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
39b60f67-b4c3-407d-926a-3335761d980d | 85,4,80,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
0c8f55dd-7e9a-49b2-878c-f2a758d8f49d | 85,4,80,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
d9c6701b-5bd0-4fb9-98d9-ae2ae9a0e0cb | 85,4,80,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
06a01101-6088-4814-b7eb-9c8cc142d193 | 85,4,80,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
793d2f1f-9380-461d-83a5-aee65e991cd2 | 85,4,80,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
c9134b54-9097-482a-97ff-8b2cbd1bf68c | 85,4,81,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
e386b8ee-7beb-4771-adec-d66928d87b03 | 85,4,81,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
c25367c6-0444-40b6-8a9a-8a86d846185c | 85,4,81,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e62a4e1f-8dff-4f81-855f-b37c83a239f7 | 85,4,81,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
152af1cb-40d4-4f9d-a339-0d513b7651d7 | 85,4,81,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
46bd0ec9-4b1c-4677-ab40-3b0e6e85691d | 85,4,81,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ccf47552-c110-46e7-a8b1-515fd299815f | 85,4,81,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2982c744-ad48-4099-bc62-eb13b9672ed6 | 85,4,81,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c1c403fa-c1ef-437b-aac6-faac9947b0ba | 85,4,81,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7e82f6c8-d31d-495e-a071-cd533114071a | 85,4,81,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3ffab5e1-889a-4c34-b61c-9ef8266fa441 | 85,4,81,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
10f7a874-c0c3-4163-a0d7-8e650e1eb6f8 | 85,4,81,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
246996fa-d3e3-41c4-90ba-4fa4db8f8c4d | 85,4,81,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c2d54b35-2e20-4acb-be21-649200dbafd5 | 85,4,81,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
857796ea-6650-433f-88bd-df36092ae2f9 | 85,4,81,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2a3c908e-7afa-4ba6-a6a2-f0b9bc4afcbf | 85,4,81,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6a12dd24-eff4-427e-9cbf-b0d676011f45 | 85,4,81,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
18ca44ff-6c5d-4406-9dbc-24a55956f20c | 85,4,83,2,16,21,22 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
fe96d980-cea3-4d69-aba3-a7011c4c9402 | 85,4,83,2,16,21,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
48131316-769e-41fa-83f2-22da015c58f4 | 85,4,83,2,16,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
df90ba4e-83b2-4120-9a73-18c800b1831b | 85,4,83,2,17,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6347b1ec-4f1d-42cb-a42b-e05eb0ebaf45 | 85,4,83,2,17,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
81311d27-7416-4a27-9319-041ddecdbd16 | 85,4,83,2,17,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
74950831-de46-49ba-a0eb-760894c7bc25 | 85,4,83,2,18,19,20 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e9c77934-cf92-4c80-8975-e7fff41aac13 | 85,4,83,2,18,19,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9033f7a8-bfd8-4ca9-81c7-714365a4da2d | 85,4,83,2,18,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ff82e613-9948-45cd-a1ea-ce0a828c64f4 | 85,4,83,2,35,25 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
9bcd58b5-2937-41ec-ba6e-572f993d2b21 | 85,4,83,2,35,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9ad271ea-4add-41c3-a55e-34ec76e47f37 | 85,4,83,2,36,26 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e166f3ac-d259-47b6-be8d-359e9690b05d | 85,4,83,2,36,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
02a42830-0455-43b1-9610-9ac6d2114bec | 85,4,83,2,65 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
8015a3b4-9230-4170-a839-79606ca422a8 | 85,4,83,2,73 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
753c0067-67ed-46fd-97a8-f2cc5ecd98ea | 85,4,83,2,101 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
40853556-95df-4351-a774-b9e98d3a5dab | 85,4,83,2,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8c91c85d-3600-44ff-8aa7-525bfd181428 | 85,4,188 | ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 8 | FALSE
19810d1f-186e-4089-a005-4c9b61098236 | 86,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
0e30d87e-e3ca-4207-af7a-26c1f49053a8 | 86,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
74183492-2382-460b-b2fe-a4e95eb0c9b1 | 86,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
16bbe8ad-105b-4624-8f98-5ebdbade470b | 86,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
70541a24-9272-48bf-a187-cdc3deb3d467 | 86,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
d7d9b719-296d-4c74-81d3-310eb428c1fb | 86,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7cd79399-a9d9-4179-a3bd-1977f529d68e | 86,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e1d47e50-1802-4406-b028-f29a3d39ef38 | 86,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
5784338a-603d-4df6-ae72-18850ba79639 | 86,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
597cf887-9c83-4108-9572-90ceff499ce0 | 86,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
6fa4db2b-ed86-43ec-b22d-cebafa6ed1cf | 86,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
5bded319-64e8-4dbb-b889-bdb98343ec3e | 86,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
aa93bbad-4a01-4df0-b0d1-ecdfb6f288bf | 86,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
e57787f0-f78b-4a7b-897a-3cea6c85f48f | 86,2,65 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
af894c08-a919-432f-a1e2-111e52cfcd3e | 86,2,73 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
5fd5fac5-6617-4c6c-8cd0-e8b110100794 | 86,2,101 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
274d0f6e-8576-489d-9747-2006b7df3b4f | 86,2,188 | ASSY - STEERING RACK (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
d4d5b82f-5764-4cfa-94f9-9e781c12d07c | 86,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
b0f2daa7-845c-43ab-a511-290949ccccd7 | 86,74,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
a22478ea-e814-4641-a400-c84f43a7b069 | 86,74,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
895a6c66-d2d5-45e3-9fdf-0d3c917310cf | 86,74,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
684143b8-9892-4ed0-ad2a-74ee298ff70b | 86,74,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
0c428da7-0824-4f1a-afe5-d80195f971c3 | 86,74,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a748f842-f49b-4bec-8b8f-ade646a30288 | 86,74,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c2f73346-e925-4800-99ef-12201ee4ada5 | 86,74,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
48deff1d-f912-4bf4-849a-e98f94225ee7 | 86,74,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d9a63a7c-c502-45e0-9952-b40f2eac047e | 86,74,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e15b4cfc-02bf-4b0d-8dbd-a24e2ae0e876 | 86,74,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
0fedc834-70ea-4381-ad6b-54771397fd43 | 86,74,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
d8685bc7-918d-415d-80db-4f937d3ae341 | 86,74,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
e7868cce-0213-4a4c-bf5c-a6befa80dce9 | 86,74,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4c52f9c2-7539-4d5c-9bc3-9af5d89d9cb4 | 86,74,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
301e24aa-c7c2-42be-a8a4-9d90dd4f5d88 | 86,74,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
b0a88293-9b14-4247-9b0a-1965ee701cdc | 86,74,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
3ce20549-9624-45cd-8736-4e886e8c53db | 86,74,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
bc124732-1c60-4cb5-ab33-1287e209d7e8 | 86,76,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
86395286-0130-49f3-bef8-668a0652e0c7 | 86,76,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
cbb1908f-2f01-4e80-beb7-a6b4e383e721 | 86,76,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6da0968e-9a0e-4713-9cd4-66941767c8da | 86,76,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
61f54233-d749-420b-89fa-3ce0d5c6f234 | 86,76,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
defbcee6-6e15-4db6-ae39-21df7130fd2b | 86,76,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
3b7c1bab-145a-484a-aa5e-b232605e456a | 86,76,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
07dc5656-0ec5-4517-b3f4-628a6ef454e4 | 86,76,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4297d6e0-5d5f-45d7-9b60-77351f66f1b5 | 86,76,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
811b3e92-ec57-4cee-b35c-b8931877e6f9 | 86,76,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
de71f78d-4123-4b1c-895e-87ff10b4d876 | 86,76,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a00d1e82-3691-46ae-845f-30039e9f07ab | 86,76,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
ea0e2580-dea1-4e36-b37a-d86588344ae4 | 86,76,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9ba1c8f9-96e3-4c0f-8fa4-8890fcfa0884 | 86,76,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
d2cb5858-2c1c-44e2-a62e-0a123132db30 | 86,76,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
aaad8300-35fc-41a5-b5d8-d6d61c59e625 | 86,76,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
38517c6e-46cc-457c-820d-5b18ec42c7f5 | 86,76,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
d7ebb114-09e7-4ec4-9146-3984ac470359 | 86,77,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
6d31ca8e-895a-4bc9-9d11-ff63a8522862 | 86,77,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ea860437-f4fc-4b7d-b0d8-4f2363aeb8aa | 86,77,2,16,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c3c6db25-47df-4ecc-815b-46edd3277b70 | 86,77,2,17,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
87c54a36-b729-4759-8ad8-017def76fb9f | 86,77,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
423ed67b-0314-4f48-ba24-3ba541406c9a | 86,77,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
86984aaa-3552-44e0-b438-f84b4f8a5c12 | 86,77,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
cfc474fd-4466-40b5-9b02-37fb876d81d1 | 86,77,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f6ae188d-782d-4a9b-85be-67bb9d1360a7 | 86,77,2,18,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
343ed029-9785-488a-9c6f-071102d7fc03 | 86,77,2,35,25 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
a0900640-11df-4a8c-a0a8-6f1322afa21e | 86,77,2,35,101 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a3b57f8a-018b-46ba-9baf-f334b4fdc232 | 86,77,2,36,26 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
dec62dc8-d3c4-4d0e-9a9b-23f3473114e1 | 86,77,2,36,101 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9cba0c71-7352-4f9c-b4e4-81515ed1fe4a | 86,77,2,65 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
1b221007-7cc4-479c-9317-7635a8f96c12 | 86,77,2,73 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
68c0e286-c03b-43b1-9802-614623c98220 | 86,77,2,101 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ec4f2b36-f7e6-40e3-b6d3-aa0efd5732e2 | 86,77,2,188 | ASSY - STEERING RACK (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
016a4bcc-d35e-4c17-b2cc-014d10614bba | 86,80,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4f8a1df5-9e11-4616-bafe-a0a59fe610ca | 86,80,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3e4d769c-7e94-4c53-9b01-be4f6ecba8ea | 86,80,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0c5389bb-4f61-4d06-81c0-ec3a4cfbd079 | 86,80,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
f618f3e6-1b3d-4324-8051-5a7f104169a7 | 86,80,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
374a62ed-9ff2-4ba3-881b-c95cbe428a64 | 86,80,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
df48c164-690d-47a7-975a-2f7a16c1f86b | 86,80,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9c7a5e5e-469f-4abd-a46a-a0f3370a3ac8 | 86,80,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
effcff80-68d7-49f8-9489-76baec3a37d6 | 86,80,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
df6450fe-afe1-4e5b-be9d-92762812c419 | 86,80,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
69f9161c-d93d-4560-9f97-ec20cb319e3b | 86,80,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3343e618-9dd1-4cfe-8774-fee47c4ac572 | 86,80,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
2245b5a1-c1d6-45fe-a918-b679c010c946 | 86,80,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
bafa793b-db8f-459f-977f-d4c053a73c5f | 86,80,2,65 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
c6cf7c1e-8d9e-48cf-986a-11f0b98ae46d | 86,80,2,73 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
de21c0aa-41cb-4f86-9f16-8546d3d4fd66 | 86,80,2,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c68e3c5a-91a9-4dc9-b20c-6a904b2deb0e | 86,80,2,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
8f97d2da-3179-4f6d-b360-61f6145a5843 | 86,81,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
1c1685a3-1231-4880-8a59-ede579ecfb17 | 86,81,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
360a9ba3-d805-4417-9567-2924367cf368 | 86,81,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5cdb0ccf-1d4e-4c89-bb3a-7fa67e25c593 | 86,81,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
2b3cc4f0-a087-40b1-bc33-d32b1c57d870 | 86,81,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
29683024-4fd7-4959-8349-23a538ee2d11 | 86,81,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
52aa3a8c-d352-408e-b098-40cad853ddb5 | 86,81,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
7307f5c1-290c-408e-b41c-c93b9daf3c83 | 86,81,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c432ffd5-85e6-4520-8c24-a9c8c85ec699 | 86,81,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b7310a73-449c-46e4-8504-a29522e3291a | 86,81,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
eeb4a8d0-6e05-4557-84c5-0ab2ca231d64 | 86,81,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4723a2cc-00ae-44e2-a3a3-cd86969c48f7 | 86,81,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
73fe2cd9-3506-4270-b12c-e7d89b4f5e12 | 86,81,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
ad3dba14-afd6-458d-a01d-bf08070ab096 | 86,81,2,65 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
3ce3efba-3958-485d-b1cc-0239cda8081b | 86,81,2,73 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
dfae0f60-99aa-4629-b6bd-aa352da0d4a9 | 86,81,2,101 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d0714278-321e-43a2-8b2e-4e1ecc6cc85d | 86,81,2,188 | ASSY - STEERING RACK (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
e6ef73a0-4a37-48ac-bee2-9ceae1a9f7b7 | 86,83,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
217e9151-0194-4c26-87eb-7976aed0718f | 86,83,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a0e50e9f-a44b-465e-9c31-d6f07a58909f | 86,83,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ba0f9274-7efc-4ccc-8932-9f32302e93f4 | 86,83,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
62f0d228-8089-4d55-8699-19cf5fa04f65 | 86,83,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
70dfe970-64c7-4d2e-ac1c-01008047e509 | 86,83,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
399df677-a4b6-4486-8865-81e8bce14891 | 86,83,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
3adbed7b-eeed-4868-8860-7c350f1d04f1 | 86,83,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9aaeb639-0551-401c-a12c-7c60ffb052fa | 86,83,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
94126830-11c1-480b-b0fc-4e4745ba4024 | 86,83,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
94678402-ff59-420f-b2b8-4a8a03e87628 | 86,83,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e5e80d41-8227-4705-9eb4-3edf62d202af | 86,83,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
40326bba-a014-49c1-8259-b8b0b0d990be | 86,83,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3ba4be34-7794-49bf-9d2b-367c2401f660 | 86,83,2,65 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
22fbe7f1-ddcd-48c1-b1ce-e6c83f96dc61 | 86,83,2,73 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
bad1a417-cc77-4603-9057-e7859020c276 | 86,83,2,101 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
4996439e-2f79-4b95-a3f7-695ca27fc939 | 86,83,2,188 | ASSY - STEERING RACK (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
151ae63f-ea39-45c5-befa-a2dc8cf4d74e | 86,85,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
218fa732-a991-4d80-878d-33996b610901 | 86,85,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b0e11740-db6c-4c72-b875-62e073ccbfab | 86,85,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
38aa3db2-8e6b-4094-abcb-9eb8720439d4 | 86,85,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
cbfa7602-1faa-4105-8b8f-216ab990aa35 | 86,85,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e810de44-6f55-41fd-937e-57a5a1ab9e51 | 86,85,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
10182405-e350-42e8-9911-6e5a451379d4 | 86,85,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
44cad928-6a44-40d5-aa39-d676f3edd40b | 86,85,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
648d413c-7d89-4ee7-b420-205ff1a0040b | 86,85,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ec9cdec5-281b-434c-aba9-64aaf2847129 | 86,85,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
e3908568-173c-451b-8f3d-1c959140154c | 86,85,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
5d908082-3f3b-4061-bf72-8c184e10a0c4 | 86,85,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
ad0c2071-7e7f-4366-85dd-750ff6d0cf01 | 86,85,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7f7a9fc5-06b4-43e7-8902-6de3a011a82b | 86,85,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
04edc23b-1964-4b7b-835c-ee8905f3f5b3 | 86,85,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
00fa7635-ef4f-4b39-9ddd-810fe4c15216 | 86,85,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
4ceab20a-6cae-4df0-a28f-b1ec9b4a0bd8 | 86,85,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
7aa9e961-dd24-4aba-b5fb-d21c0396d500 | 86,85,3,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
c4d8855b-2191-4cd4-b0da-4f1a1ddfa2ca | 86,85,3,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
91bb67ef-db4f-41c7-99c7-f71f92c4ec3f | 86,85,3,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
76c6b3f5-7960-4f35-ab43-c6e79c03ed42 | 86,85,3,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
21538cc8-e47d-4df7-ad6e-f66c6105f62f | 86,85,3,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
5019cfaa-c9d7-469e-803c-34284f7b37e7 | 86,85,3,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
dc20f966-118e-4526-8dcd-2b9305fa4196 | 86,85,3,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f7963177-a566-41ec-905b-47cba7927df5 | 86,85,3,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b28c85a9-0569-45fc-939b-73810dde92fa | 86,85,3,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6369f6c7-1888-484b-b0ec-5a6cb28ab0a3 | 86,85,3,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
c589da03-40d8-496a-aafa-ebaf69331dee | 86,85,3,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
583478f6-6662-48df-ad04-1a5606eb02a0 | 86,85,3,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
46521e55-0da7-4628-9d2a-b6cf3e1deff6 | 86,85,3,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e9a91252-fbbe-4c0f-b05d-a313c21d2477 | 86,85,3,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
a397fb38-19f6-4c07-8cf5-33133bbe4b66 | 86,85,3,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
83052793-3edc-423e-9a67-759dbd70c22b | 86,85,3,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
4ab29e06-a1b0-4904-bea8-5a870e11fc60 | 86,85,3,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
88cbb271-0685-4fab-ab2f-7ba4ab5ac2d4 | 86,85,3,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 8 | FALSE
a74c6ebf-2278-4d18-811e-0fbd81862ab0 | 86,85,4,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
753cf129-1b9a-4701-b0ca-cb791182c08c | 86,85,4,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
329c30d5-cf70-4544-aae2-c9b470ed9daf | 86,85,4,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f9dca52f-fabf-4397-860e-91f0cdec5938 | 86,85,4,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
eaea44c1-a8cb-4f99-a1cd-a0310d58604a | 86,85,4,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e2652eb4-b55d-46f8-bea2-fb056449f1b0 | 86,85,4,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e98c7dda-e555-4431-91d0-bd623ab89ace | 86,85,4,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
7c4804b6-fe13-4db4-a940-b4baf3617d3f | 86,85,4,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8c9a4264-9647-42a7-a635-d223b17aaee3 | 86,85,4,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2c921dc3-6b7b-4535-9c29-fb880c807cd9 | 86,85,4,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
d8d8af2a-54cf-4a15-9afc-cc1aee889073 | 86,85,4,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
0ea3aadb-11d5-4cdd-b68e-334e67759d92 | 86,85,4,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
40e4e59e-371c-4c50-829a-fb99ca9c5cb9 | 86,85,4,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7d704a2e-7cb2-462b-8dac-6093ff087cf6 | 86,85,4,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
24bc80e7-dd07-45f0-9187-3686a58873d3 | 86,85,4,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
538e9072-9867-4d87-8e5f-d2de951e734e | 86,85,4,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a4ed427a-3161-4af9-9f4c-25cd8cebc515 | 86,85,4,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
03e9dfd2-cfdf-4f79-9bb9-9a51bd9745df | 86,85,4,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
72080326-c07b-4d4f-a630-ee59b1f73eb9 | 86,85,4,74,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
e75f98ed-eb32-439c-8a10-0bd37832d59b | 86,85,4,74,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
f615f33d-6a7c-4af7-904b-18f5f8d71e6a | 86,85,4,74,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
52afe409-79ff-4cfb-b343-c40629c6e684 | 86,85,4,74,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3fad237a-9141-444c-8ac6-ff63a9551596 | 86,85,4,74,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
027df73c-7f17-4ea0-9bb1-dff3ad1dcacb | 86,85,4,74,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4fc4ff14-ace7-4926-b95e-dffa0a9deb54 | 86,85,4,74,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
dc74c43f-fbbc-4f41-878e-e5587dd7654a | 86,85,4,74,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
528fec16-c829-4a00-8fe9-657bff20dd3b | 86,85,4,74,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5d5a1744-ab08-4684-b992-fa7b5b403279 | 86,85,4,74,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
ead4c2ab-ef87-4f16-a122-ea3d153ebcec | 86,85,4,74,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
693aabe3-728d-4b8e-955c-6ea3ff266f9d | 86,85,4,74,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
e506e2aa-4c8b-4e17-8c8b-aa3318128e34 | 86,85,4,74,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
04012eb2-d5e7-4c26-a35e-446d028f69d5 | 86,85,4,74,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
f20f7a92-8c16-4d33-993f-edcf3977bbbd | 86,85,4,74,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
9fb8cc9b-6bcf-48d7-bf9c-ae4ed15dd7a0 | 86,85,4,74,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
847ba49a-b564-4771-9676-f09c745c21cb | 86,85,4,74,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7eb95c4a-36ce-4864-a7a3-fe895ffa3d50 | 86,85,4,76,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
836584c9-5bb3-4fe5-8844-fcc2f030f8ca | 86,85,4,76,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
b338e958-c795-42da-854c-2039e419e10e | 86,85,4,76,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2bdcae5a-29fe-4ab2-80ed-97bfd54e30cc | 86,85,4,76,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
423b9731-f526-45dd-b151-f152f12d28d0 | 86,85,4,76,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5a202060-0dd3-436f-9639-d9e20e45b567 | 86,85,4,76,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
86a99e7f-94c0-4c1a-b219-e38c2a7624a0 | 86,85,4,76,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
4e160a30-d478-4f12-8c37-2dcf10316993 | 86,85,4,76,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
94e270f5-c624-471b-b1e1-f71650196e86 | 86,85,4,76,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9288cf47-c7f9-44e2-85b9-c7578e6f9c76 | 86,85,4,76,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
c0d4de0f-05c5-42d1-95c6-7e708ac61d66 | 86,85,4,76,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
69f8e7f2-2118-4232-bd81-bf269e8a58b0 | 86,85,4,76,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
36fa8ff6-7fd2-41a5-b919-337199a1c2c0 | 86,85,4,76,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
2da0383d-d75b-44d3-8b06-7c2a01ee107d | 86,85,4,76,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
e4b14514-6b2b-4936-bad3-087c62b35066 | 86,85,4,76,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
2632bdbe-b078-4e32-a9f5-75da117ba132 | 86,85,4,76,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
85d181e4-d262-46e5-a4f3-dfe5f1801a13 | 86,85,4,76,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
0553be19-a44e-4757-b3c4-72236f5ae4c5 | 86,85,4,77,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
f333f3e7-6bc6-4b8e-ba98-ca5c6b77637f | 86,85,4,77,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
d4aedcac-a0fe-4470-a778-9d121fc282a2 | 86,85,4,77,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
05c410e6-3137-4f68-95c7-ee4e9f3b3cfe | 86,85,4,77,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
28e7f66d-11b5-480e-984c-ce61d46be4fc | 86,85,4,77,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
3fc1bad6-9034-4bcb-ba01-12ca0564185a | 86,85,4,77,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a888d317-8605-4e6b-a3bc-04bfe754df63 | 86,85,4,77,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
c4a0315b-7452-46e7-aa9c-b6a392769120 | 86,85,4,77,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
66d8612a-246b-4ad6-bba6-51acfaa0bf27 | 86,85,4,77,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
35b11fae-e461-4cff-af5f-b6aad2bee134 | 86,85,4,77,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
035ab04b-af7f-4cc0-9efe-9bf25205ba6b | 86,85,4,77,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
3e150f31-8610-4fdf-bf08-9bed0af56da3 | 86,85,4,77,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
0004c394-13dc-4c02-85cf-d0555053e5d3 | 86,85,4,77,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
390506d2-af05-4757-980b-3018ddf128c6 | 86,85,4,77,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
3845870e-9270-47a2-9af9-c88fae9c7a02 | 86,85,4,77,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
c60107b6-d728-4830-8006-9bf01f33b39c | 86,85,4,77,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
836419c1-0099-4789-a704-8810e001b306 | 86,85,4,77,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
b221177e-3185-474b-ae1b-38b36de2efa2 | 86,85,4,80,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
e36a1152-6069-4df3-811e-ca2b378e8fc9 | 86,85,4,80,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
29638007-14b3-4317-a8c0-7235e4650b66 | 86,85,4,80,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
962651c1-397c-4bae-87ec-61209e16c4b8 | 86,85,4,80,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
11e57885-de71-48cb-b999-d58c7d099032 | 86,85,4,80,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
0fcf5cae-7ccf-40a3-a391-f4c06af53103 | 86,85,4,80,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
55583140-fa58-4711-9c4d-4306aadea1f5 | 86,85,4,80,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
b68cc343-e237-4eef-8b76-10fc4585986a | 86,85,4,80,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
9ddad723-3308-4900-94f4-748b89201561 | 86,85,4,80,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8bccf3b3-33d9-4eaa-a6dc-df7f1e4c0d52 | 86,85,4,80,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
922b5abc-571c-4f9c-ae3a-cf8440589859 | 86,85,4,80,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
ca7f40b2-3cd5-4743-b7a5-a9c042ec3f7b | 86,85,4,80,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
1a445bb2-a569-4230-a84c-4d8cfe2f8525 | 86,85,4,80,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
662fead8-f09e-490f-8c95-3ca1ddf3703d | 86,85,4,80,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
b05ba1c4-3548-4b1f-a355-08605158101f | 86,85,4,80,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
b7157927-925a-41bb-8d9a-8327b3475b80 | 86,85,4,80,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
d18a4a27-0aef-438e-b5bf-8d8187a40ea5 | 86,85,4,80,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
32738b12-e29b-47af-bc66-235979ff8a0c | 86,85,4,81,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
1ae019b5-9208-4388-9fca-b1b4540f4e76 | 86,85,4,81,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
37cb1954-c630-400a-9a37-960c3ebc13db | 86,85,4,81,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4e32bdf3-a0f6-426e-a1a6-0ba106be4657 | 86,85,4,81,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ff7e02d9-b2ba-4eb5-81be-fe44aaa75b19 | 86,85,4,81,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
22ecc1eb-2736-4500-9811-59e6223252c1 | 86,85,4,81,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8e26b933-3b3f-4dc5-9d67-15422b9a7f7f | 86,85,4,81,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
20859d97-2147-408d-ae91-e938a57e145d | 86,85,4,81,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
6659bc12-b112-4ddf-bece-c0159fdc9741 | 86,85,4,81,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0241ac6d-8ffa-4068-b7e2-577ace5a06e9 | 86,85,4,81,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
043dc8f3-3ef7-4670-b940-038c61145e2a | 86,85,4,81,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
4b176b07-90d9-4cad-b572-ce071b5ba86d | 86,85,4,81,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
7e4f8489-2375-4277-84c6-27eecdc9472f | 86,85,4,81,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
7161b60a-d925-41e9-806c-303104594535 | 86,85,4,81,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
dcf5f265-65a6-422c-97c1-ed01379d0ac7 | 86,85,4,81,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
3a3b40a9-1bfc-4800-b17d-368853075cc2 | 86,85,4,81,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
37445ce1-f363-4b01-8ea0-6689fee5d34d | 86,85,4,81,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
981c87e4-de63-4960-9212-406dacdf4dea | 86,85,4,83,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
8eb9c73b-b56d-4788-acb7-382337a72784 | 86,85,4,83,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
739fce38-3442-48e3-9c3b-e2f70e14f01b | 86,85,4,83,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
08b96881-9909-4c9e-85a8-cc37d6d60b77 | 86,85,4,83,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2684f239-265c-4baf-b1cf-c26f7f36c5d4 | 86,85,4,83,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
aef177a5-9430-4537-a43a-dcf88f4ae030 | 86,85,4,83,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
000b9946-05e6-4186-8d00-78cc89832779 | 86,85,4,83,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
cb46576e-21bf-4cfe-b49c-5481d14e8091 | 86,85,4,83,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
dcf32944-adf7-4882-9422-957d4fdc6b8c | 86,85,4,83,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
35abc9ee-1f96-4129-a925-d8e089ad765a | 86,85,4,83,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
d3a2e1e7-0390-40fc-b5dd-289a754761e8 | 86,85,4,83,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
cb3ecebb-a991-4fe6-aea3-fd609681eb3a | 86,85,4,83,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
de52744d-d34f-49c2-bb65-f18d3725a60e | 86,85,4,83,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
0ed45cb4-be10-4f68-a7ad-29bfaf02429d | 86,85,4,83,2,65 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
b816933e-d3de-4c3d-9e38-9103a42d4238 | 86,85,4,83,2,73 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
c3653696-4876-40a8-95ac-d5d58d3b6cb9 | 86,85,4,83,2,101 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
17715fb4-ff72-42ca-9b0b-a7552fe9ef60 | 86,85,4,83,2,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
a57db385-0d35-4911-a462-b7ac13461445 | 86,85,4,188 | ASSY - STEERING RACK (2) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
ac1b42d4-98ec-4b9c-b7c8-8314bfe39db2 | 86,54,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
93255401-352e-4030-a07a-4b18be217dd1 | 86,54,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
d3294ce2-6d04-41e0-9df5-e7f57dde0d67 | 86,54,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4d77edb6-472e-417f-b097-ec9ded0598a2 | 86,54,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
57f57748-b20f-4362-9794-8747102e0eb3 | 86,54,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
2b54d79b-93f4-478a-81a9-ff6da46ac673 | 86,54,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d3c61430-9571-479f-948c-7063a9dd2ecd | 86,54,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4db05d29-8650-4538-958b-910b672caca4 | 86,54,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9d2b4a73-b4b0-4118-9de1-93c8f375195b | 86,54,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
74b989ae-b303-4ef0-8f68-d60923b807e7 | 86,54,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
c2d187e4-0507-4872-a294-ff99919fdaab | 86,54,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
f6b8feaf-088b-4f77-b3ca-743545ee9b02 | 86,54,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
bf5a5c94-9041-4bf5-8547-f92318918aa6 | 86,54,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
4818d35f-2179-4d14-a1a9-886df1ccdf16 | 86,54,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
9ef7587d-f3a8-4790-b55d-6083f71de493 | 86,54,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
84955948-7ddb-4fcc-b8c1-3ffffcc60b86 | 86,54,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
61523995-b71b-4993-b356-6b5409012dbe | 86,54,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
bc5a17cc-320f-409d-bb9f-dc984055cf8c | 86,54,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
e3f4493f-4038-4929-ad4e-deedfe39c74f | 86,54,74,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b54247a9-b6ea-4f7e-9193-bfdfa11a9375 | 86,54,74,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
47f7295e-90f2-480c-b296-db298d5a824f | 86,54,74,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
44c65262-a9d2-4597-a5fb-208a03b19f63 | 86,54,74,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3b9e8192-ea9b-443d-ace4-478d03750f7e | 86,54,74,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
84dbb069-315f-46c5-a164-c397cafed5f3 | 86,54,74,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a35ae8c1-24f9-4bf0-81bb-b5b8a8787f54 | 86,54,74,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
11f9f720-bf04-498e-974c-e2087099baa7 | 86,54,74,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
697cd176-e433-47bf-9a48-f75910d6dd08 | 86,54,74,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9fa05e7d-76ab-45df-802f-f5b06159f9ff | 86,54,74,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5e2018cc-7b62-4d86-851e-af44f8bbd677 | 86,54,74,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
518c584c-4ca6-4a0e-9e5f-edd7e2993bb6 | 86,54,74,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
7f873d68-a95e-4682-9ea3-518fecde4819 | 86,54,74,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
5fc7724d-50c0-4893-a01e-a2d666e2ea07 | 86,54,74,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
dca84ae8-29ef-4580-847a-1fab05cff5c1 | 86,54,74,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
1d47a18f-4d2b-4ed9-be2a-29d70e4e9e43 | 86,54,74,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
05a2daf6-85c1-454f-8b7b-b3c774f90933 | 86,54,74,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
167a1685-ff5c-4d25-a6ac-bbdef2d51e76 | 86,54,76,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
470cc75c-b73f-4879-a27d-b0f27986895e | 86,54,76,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
82e8dee2-7c1b-4de0-8c14-2e0937b1abb3 | 86,54,76,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f0944eb1-9115-41fb-a5fa-5abea3318ec2 | 86,54,76,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
37e80012-c083-49f6-a88a-0c95879074aa | 86,54,76,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0a8fce95-66ea-4d87-b17a-7c9f74efe5de | 86,54,76,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
71e5b9d2-bef8-47f6-b224-0714952d4623 | 86,54,76,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6096b560-d402-4ea1-a3dc-a93888985488 | 86,54,76,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f5bfc745-f641-4dec-b8a8-15b0616f5652 | 86,54,76,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
084c5546-6d20-4f95-b138-e926f20e4823 | 86,54,76,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5395c432-7e81-42fa-b84b-e79a4de606b5 | 86,54,76,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4ba647cb-3c91-4cce-88ac-c6c280c816a0 | 86,54,76,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b5faebd5-d590-4d17-ae51-97e786568caa | 86,54,76,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
28cefd3b-c903-4945-8107-01c34b341e5a | 86,54,76,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
6ae8c391-c4b2-4e06-a1d5-752ca50e1195 | 86,54,76,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
acb9a7f0-80c5-4123-a7b6-75f135df1db7 | 86,54,76,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
547d2534-6d46-4158-8148-7ff6c71c56b3 | 86,54,76,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
9b5fb5db-b858-4476-83f0-51d83f6ce378 | 86,54,77,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
9d923037-c67e-490e-b996-d45ad7f617e7 | 86,54,77,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
72ba00e1-a95d-4270-a0a6-85af153b2396 | 86,54,77,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
eefd135e-5605-4158-ba29-ee225ea7451f | 86,54,77,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
94879cd1-4691-4789-85a4-19c029d4e885 | 86,54,77,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c6efd0be-c78c-4475-aa2b-301479f32def | 86,54,77,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
89bb6004-c3e3-481e-af2b-439968aced92 | 86,54,77,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
5d94c305-974c-4af5-9de7-285a7193d0d8 | 86,54,77,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
18b531ab-7564-4dc1-9d07-f7470937e4da | 86,54,77,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2cc8c4a2-2e37-4dbb-a0df-ab536a66a569 | 86,54,77,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
bddca3a0-7611-4d63-9771-995305deb666 | 86,54,77,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
854df134-118a-450b-bf3a-244e9eebc9d4 | 86,54,77,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
637e9644-f350-4e02-82a8-0877f5ff5650 | 86,54,77,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b339ab0e-f45b-4d1d-90fd-f574f4d69fae | 86,54,77,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
b28ddaef-1621-4a8b-a91f-8d7f464a5452 | 86,54,77,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
257cc1c5-a8fd-41af-ba10-9d95e9f5e1e0 | 86,54,77,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
61806914-cd01-4cb0-83ba-5df8094e7502 | 86,54,77,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0ee0ff90-ca1c-4373-8e5e-302bfc3cc7b3 | 86,54,80,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
89720935-88c9-4013-828a-545819bce41e | 86,54,80,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
9cf2c4b3-9d65-4291-a7de-8d03e18e9a9b | 86,54,80,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
002d5ff8-e871-4ca4-ab7f-7f5c29e7bca4 | 86,54,80,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
23e153c9-1329-4bcb-95e4-c7b33cbea470 | 86,54,80,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0d45e1cf-80ff-497c-a46f-35b62e7de6ac | 86,54,80,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
821cce2b-37d3-450b-b569-30e26c618341 | 86,54,80,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
301f278d-d2f0-4fc5-a787-d652cebb64aa | 86,54,80,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
719d9b0c-0c79-4e86-be08-65577b7b70e3 | 86,54,80,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0e67327e-6afc-4561-a02f-ab4315188ad9 | 86,54,80,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
1ac9f1b9-527f-418a-a023-9c693ca6c6b6 | 86,54,80,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
df75d490-ab53-4206-8c2f-3eb7d8c1775b | 86,54,80,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b2a2ffdf-6459-49da-887f-8083bd9c2e54 | 86,54,80,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b8f69e5a-9784-41a7-a373-ab84b3ca4da0 | 86,54,80,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e9132e0a-1c88-45c7-aaad-0fbfd19c4272 | 86,54,80,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
885c7cb0-bb81-457b-9050-621f4c771b38 | 86,54,80,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
2a1d6b61-429e-475b-9736-a2a1f9537b4d | 86,54,80,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
199f7323-0f7b-4dbd-bec4-b788ab5ffed4 | 86,54,81,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
92819808-bf22-4097-94e9-cc7f6ec8447b | 86,54,81,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
257a6d67-4ad9-4706-a7e6-5163789a22ab | 86,54,81,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a0d8a132-6d76-4f8f-9b0f-6ee414241495 | 86,54,81,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
160f9c91-117d-42c9-913b-b2cb0317f0da | 86,54,81,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d5719a01-76ed-4ddb-b3c7-59994b7d5e45 | 86,54,81,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
364da9a3-1ee7-4b8d-9474-f61c515d5972 | 86,54,81,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a4f40ea7-7300-49b9-9094-1c95cdea80b4 | 86,54,81,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b9c949db-65f8-4033-972e-41f0ace1a063 | 86,54,81,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a20806cb-3842-412a-8982-bbc784b3369f | 86,54,81,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
d60a6331-0e11-4381-89b4-bfb5fcdccb5b | 86,54,81,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
f379367d-9bf4-49af-a46a-249268fe6b22 | 86,54,81,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
ab95731e-cd8e-4adc-9ee6-e4b49a44b817 | 86,54,81,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
cb309fc8-ce21-4d2e-a403-16a7b0c4c116 | 86,54,81,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2b65d54a-25b7-4ac9-b084-ee2ca47b9141 | 86,54,81,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
9252651e-efa3-44c2-a05c-b65eb881789d | 86,54,81,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e03c373d-138f-4c43-b373-f8645b08643d | 86,54,81,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ed1cfe41-f38c-43d0-b65e-b92864fc87d9 | 86,54,83,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
664f75cd-991f-44a3-803a-19732e0e5c55 | 86,54,83,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c4c3f33e-d5d3-4dbf-a648-65cb893d2535 | 86,54,83,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
eb5a9f58-1010-4003-add3-62c597f9b234 | 86,54,83,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ff35c836-8ab9-4e9d-8f3f-1b4e5aed388d | 86,54,83,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2b88425e-f4c9-43cf-94bf-ca48220c286a | 86,54,83,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7e01fd03-f932-49bc-aa24-36f47cee1da5 | 86,54,83,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
fe1ae6e9-66c2-49b1-8718-9abfc62547c9 | 86,54,83,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a41804c5-35f0-4226-b444-a488d8932fec | 86,54,83,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b1beb8bc-a19e-40a6-b601-fbd881d57f2b | 86,54,83,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
7595b8bd-6ea0-470e-b5a1-811f6365e2b8 | 86,54,83,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
73d39775-ae0c-44e5-88a0-8a751c008e54 | 86,54,83,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3ab0d5c4-dc07-405c-b9c3-fc92c65cddb1 | 86,54,83,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
74c2e29f-69a2-47d9-9b9a-aa0772782fc1 | 86,54,83,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
eaee04fa-35b9-426b-adcf-62a0000d6c0c | 86,54,83,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
edc6a221-eac0-4436-9d39-197eeeeebb1c | 86,54,83,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
246c44d4-0d4f-4bec-8011-f89d30cf5d76 | 86,54,83,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d9e78597-f094-438f-9aaf-6a46cc397a9e | 86,55,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
66c4dacc-57f1-4086-a549-041371342a37 | 86,55,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
132dc952-cd1e-4b64-bc0d-24d944d7db5f | 86,55,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6c370e16-96f0-434f-9a15-1fd2ab0f49fa | 86,55,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
643a845a-137d-4721-8e7e-6fbc14ef9043 | 86,55,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
cfcd279c-775f-48b6-80f2-1a12cd02b67f | 86,55,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
0836c5b1-b282-41fa-876c-c62b9c3a577e | 86,55,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
03887777-5aa0-4269-a9a8-4a316c1baaa7 | 86,55,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
88c855f2-5527-4411-94c9-c97e25389c89 | 86,55,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b69c9ff6-3760-40a4-9bc2-aede2ddb0f1d | 86,55,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
5d71fa55-50a7-4fe1-943a-5dc2a9a1ff38 | 86,55,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
93cd477d-0dee-4840-9eca-ba4f9bd7e9a8 | 86,55,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
be3894e3-ce39-464e-8641-f963c7bb2e33 | 86,55,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b8fd7da1-356f-41d2-97d7-cd59db9e0c80 | 86,55,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
a2225bcf-8b88-4569-a372-e0c8d3b19d1a | 86,55,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
c76e4963-a545-424f-bd06-e02723fc5203 | 86,55,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
786cbf30-6b5e-468a-a861-40873ab734a3 | 86,55,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
6fb2a4dd-ea3f-4867-9bf4-993e1ec194d2 | 86,55,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
2d30d57d-fa5c-4eaf-96f2-fc7854ea6f57 | 86,55,74,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
968450ec-982b-4aca-8356-a91ff5dc4246 | 86,55,74,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5c968c84-6b07-478c-9733-3ef16ad60a2f | 86,55,74,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
27663010-793e-46fb-9e4c-518e2858f9df | 86,55,74,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
14bc7c65-1452-49c5-98fd-69168cf9195e | 86,55,74,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a0f38119-826c-4b52-a1d1-d632a4d537b4 | 86,55,74,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d6aa81e0-7df6-4efd-b5cf-8671dd91fabb | 86,55,74,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
23002b4d-4b51-485e-8f48-e4c9e0fcc499 | 86,55,74,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6a24fc35-8e82-428a-a78f-b2220e4ba3cf | 86,55,74,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1939f162-4cd1-4f96-b85e-294ec5e23e1b | 86,55,74,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a0e6645c-c167-4225-bb68-0e03273a3d84 | 86,55,74,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
16770282-bd21-48a6-bdec-cc792ceba0c9 | 86,55,74,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3bcf383b-8dfc-40f1-a968-0bf04875a4a7 | 86,55,74,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
33dc4868-0383-4c9f-af08-74d143856c7d | 86,55,74,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c8b65e61-6b95-482e-8d15-d774366bab86 | 86,55,74,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
4437505e-79f5-4ccd-83cf-e8e7c47afc6f | 86,55,74,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ddd1d330-b071-4cab-a988-b7e7b010d29b | 86,55,74,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
26445990-777e-4e0b-9c45-86be469cfb43 | 86,55,76,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
713f6b0c-f2c8-4fc6-beee-ab92dc6f5912 | 86,55,76,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b68ff504-3de7-4275-8f41-b486a764fe25 | 86,55,76,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
742a8f8e-c718-4a25-8c50-f47a471a7503 | 86,55,76,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
034c10ed-4d23-4852-b746-4b9f4179f8b8 | 86,55,76,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
cbe3dd90-76a1-427a-91db-9415f2f720fc | 86,55,76,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
73736324-0534-4156-b370-5a54be3fddb3 | 86,55,76,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
984c4b4d-3651-41ec-921e-b385b25f453c | 86,55,76,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8e966c00-be2e-4e79-a496-c4fdb54e6e23 | 86,55,76,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fe903107-ec36-4683-beba-ddadf39998bc | 86,55,76,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
b5570f37-ac52-45be-8b8e-8f8f2e66cf2f | 86,55,76,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
7230df52-d02c-4936-a128-f35420dbfa7f | 86,55,76,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
10d0d67e-d913-4726-9323-b7e8efc312bb | 86,55,76,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
12a1fb3d-4a1b-4c08-9939-e1500b2d2702 | 86,55,76,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
24784ea9-19fc-409d-a530-58cf46a47f65 | 86,55,76,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8b0e3de9-ff2d-4406-ad1f-d4e904427d26 | 86,55,76,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
75b63579-bf14-459a-97c4-18ee5840c8cc | 86,55,76,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
c3bde548-bbda-49b6-97d3-e856e5454c67 | 86,55,77,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
9a612235-6acd-46b2-9543-076ba3ef00c9 | 86,55,77,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
bf2cb0da-7755-4461-858c-addc8c3be818 | 86,55,77,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3ff16695-5d8a-451b-a560-02f487a16f72 | 86,55,77,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c76e285c-176c-4620-85c0-002f868c0aef | 86,55,77,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8b6f7d7c-668e-4b73-9218-6d9c12eaaba3 | 86,55,77,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8b323903-2ce6-4c57-93ad-dcd43e522b83 | 86,55,77,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
371fd129-badd-4940-ae2a-d14c375ab3f2 | 86,55,77,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
933c8892-5e12-42d8-8f81-90c606472bf7 | 86,55,77,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
842fccb9-c7e3-49d0-a1b6-072f153c6ea0 | 86,55,77,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
b93b2e28-96f0-49ea-8cfd-76ecbd2d82aa | 86,55,77,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
35815cfc-3a66-4730-8eaf-4220c6f99af0 | 86,55,77,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3f894a98-bd63-4374-b2cb-2eb7bea8c8d6 | 86,55,77,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a47a4c22-3b31-4e22-b9a2-ff7d0d0aab46 | 86,55,77,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2df13dc3-cc82-44bc-bb27-e3925e1d6dbd | 86,55,77,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
676bdeda-2d2d-4a1e-aa98-7d939e240132 | 86,55,77,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
fc764cfd-5e68-4737-a10e-565bc7930b90 | 86,55,77,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
80835180-af21-41e4-ba9e-0dffdff1261a | 86,55,80,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
66d70c89-125e-4ea6-8e4c-eb579bb4dbe8 | 86,55,80,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
83377a7f-15e4-4016-85f3-1b9b2a995107 | 86,55,80,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8f872323-affa-492e-9be2-6bfeaf86091a | 86,55,80,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7405132d-f938-494e-8e96-4cdf11802d9b | 86,55,80,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2538ac58-c19b-4b15-be85-6658a4d482fa | 86,55,80,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9908fcb6-f354-418c-81f0-498d900ad087 | 86,55,80,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
67ac32b9-d235-4512-909f-4cbddd3f878a | 86,55,80,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7f2f845f-a4eb-417b-b804-f0e0eac24a79 | 86,55,80,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ffa5b697-ac77-4ea6-811a-876dc75bf58c | 86,55,80,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
56acd07b-36b4-4aed-8bd0-77df3bed2c04 | 86,55,80,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
47c6e2ed-8e5c-47da-a01a-1168ea82c1df | 86,55,80,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
831a3846-b29b-44dd-aa9b-7bd30cfeec75 | 86,55,80,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3aecae01-65ff-4557-b8af-64f562e918eb | 86,55,80,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
87747d3d-a298-43f1-b03a-e12ac4071219 | 86,55,80,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
56fd64fa-2b88-4ed6-96f8-4cf3675fbb07 | 86,55,80,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
242c7c71-b208-4f9c-adce-ed589c3b55c6 | 86,55,80,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
b92b8cf9-8dbd-4252-b2fa-3d9d1cd5cefb | 86,55,81,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
c168693f-d529-4b74-9843-95575744f7e3 | 86,55,81,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5a3d8f6f-80e4-4020-a872-ab9a96cecaf0 | 86,55,81,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
08e4ef0e-8d8b-4c21-a83e-766e57207eb2 | 86,55,81,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4758216b-a1ce-403e-9517-57e7f1c3b76f | 86,55,81,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8325ebc0-cd12-45c4-b590-e6b1adcac168 | 86,55,81,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
638c3123-12aa-4c5a-8358-0e1250266025 | 86,55,81,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
67bd6e55-4c0a-4be8-b7f1-a0368b4bb721 | 86,55,81,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
778034a9-a2d0-49b0-8629-8c320a457294 | 86,55,81,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d1adb64d-f4a2-4fb6-8196-990078b978ab | 86,55,81,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
84fd24db-e6eb-42dd-89ab-c6da46c23249 | 86,55,81,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
31e172e2-c84e-4a40-a736-8bc512f99ff4 | 86,55,81,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
a0e4edfe-d5b1-477d-9d2b-cb6af93be9d4 | 86,55,81,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
eeffa99e-ee8b-421c-bef4-5e72c1311eda | 86,55,81,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
786ba759-f717-40c4-b15b-7af2aab2633d | 86,55,81,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
4fc8a692-63a8-4dc3-8cc2-ce9c9d07b600 | 86,55,81,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
bc3b7d53-7a20-4255-b1b5-0d7f5877a5ca | 86,55,81,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
66e51c3a-fce5-49cf-bd17-d20dcf4d18f2 | 86,55,83,2,16,21,22 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
7a704046-6c17-4c99-aea7-9bf88b5b863a | 86,55,83,2,16,21,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a197cf80-4d0e-4029-9ede-18d949b02728 | 86,55,83,2,16,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
effeaa75-a525-4a0e-b103-813bf57c15b4 | 86,55,83,2,17,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9b2826df-9597-4478-ab89-6894549867d5 | 86,55,83,2,17,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
418a3edf-6880-4907-8db6-faac84f8fa55 | 86,55,83,2,17,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a8baf279-eea7-493b-b636-8a34617e27f4 | 86,55,83,2,18,19,20 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0650025e-ccfb-4712-87c3-9c2da691d7c1 | 86,55,83,2,18,19,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c31a1292-0dd6-44c9-b5bf-f88a273ac933 | 86,55,83,2,18,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bd1f6153-0cca-4aee-b5b7-c30fef0674da | 86,55,83,2,35,25 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
af176b9b-b6d6-4629-866a-c9efd4de9c40 | 86,55,83,2,35,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a58f38b6-ceb5-4d18-b016-300bf5f052e8 | 86,55,83,2,36,26 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b7de2127-1fa3-4a91-8d6d-af65cadc62eb | 86,55,83,2,36,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6839d3de-0ba6-4ff8-9672-9addcb1d8178 | 86,55,83,2,65 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
475bfb9b-1ac4-4a5f-89fa-ef3e052c310b | 86,55,83,2,73 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
1f89f4a4-5de5-4c67-a881-38df316a95c8 | 86,55,83,2,101 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
5bc58474-ecd0-43b7-8d80-38de7d5ec306 | 86,55,83,2,188 | ASSY - STEERING RACK (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0963c22e-f396-43e3-ad4b-6da1c9ddb1c1 | 91,16,21,22 | ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
05b560ee-0c94-4932-a013-cf9b13b19703 | 91,16,21,188 | ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
81473bcf-da11-4dce-bd62-d8d48b3d970d | 91,16,188 | ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
0293469a-3f2e-4dc0-9ac3-78789a878c47 | 91,147,19,20 | ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 18 | FALSE
06eb7138-0921-4b8e-aff0-f4b6cf25e4f9 | 91,147,19,188 | ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
0affac09-820e-40d1-915b-fff9977de113 | 91,147,149,19,20 | ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
d521f53a-cdf8-4a1e-b264-8a0dfc339ed8 | 91,147,149,19,188 | ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5b5634c7-4229-4841-9744-a819419bb243 | 91,147,149,188 | ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
979f08ab-926f-45a0-abc3-48bb9fcb932c | 92,16,21,22 | ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
f15c440d-d89e-4e11-8454-b5643de9e714 | 92,16,21,188 | ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
56c6303a-18b1-41a0-96ae-c16b07a41f9b | 92,16,188 | ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3989cb13-a632-4e91-9801-535df0d1008c | 92,148,19,20 | ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 18 | FALSE
8402d166-6826-4ed5-aff8-8439974a4bd9 | 92,148,19,188 | ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
12bc5e46-649a-49c4-9c17-dbe8be6ad7c0 | 92,148,150,19,20 | ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
7325f0c6-c1ff-4c55-9956-ee6aeaa68f56 | 92,148,150,19,188 | ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
c7fe2032-b1ef-4417-b9f1-0ac80fc657a5 | 92,148,150,188 | ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
d1ba25d3-ed3a-44f6-b6c3-06f071f936ec | 107,2,16,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4dcf6e00-ae6d-4647-adbd-757fa8b5d24d | 107,2,16,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
82871151-1623-42e0-87f6-b60bc987abe5 | 107,2,16,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
176277b9-c273-41cc-9be4-e907316035a8 | 107,2,17,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
03bcf482-d2df-4e01-b1e1-b82a6d6f424f | 107,2,17,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
860ace57-175d-4d3a-a51e-88930e16ec63 | 107,2,17,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
51486da7-48ea-4e29-80c9-e6410bd3951b | 107,2,18,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
251dcb38-b56b-4d81-bd8a-223b1829ade5 | 107,2,18,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4910d977-c8e1-426a-bdd1-04153ee33e22 | 107,2,18,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
17a6c14e-042a-4aed-af86-55edb72e3356 | 107,2,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
a9165daf-42aa-44b2-8ce7-f05f7ca0d3cf | 107,2,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
701310c0-b03a-40da-8562-0d39bb14201a | 107,2,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
9a5137ea-eed8-451f-aa09-4f3e7fbb2ec7 | 107,2,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
aaed0f6f-3cc8-4902-b174-67089aac6751 | 107,2,65 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
a909b51e-a56f-43c5-898f-eefd6c29066f | 107,2,73 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
ac9a10f0-6b2c-4b81-84bb-818a6b5c0e32 | 107,2,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d8e830d0-4467-4135-a7e4-a0787165b93a | 107,2,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
47b39599-3d45-48b5-87b3-aedf9baae89b | 107,106,2,16,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
e09ea2f8-44ce-4f2a-9d12-d6355ca76c72 | 107,106,2,16,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
07e9414d-f0e6-4a85-9343-13cfd3efdcb3 | 107,106,2,16,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
c0634398-05c1-497f-a0cc-076ad0dfddd7 | 107,106,2,17,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
79bf8437-7ad9-4a9d-8426-7ca368c6ccbb | 107,106,2,17,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
2515587b-5355-4719-9b12-ccb1218e5a73 | 107,106,2,17,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
02410172-82af-4e43-9ef0-0a4d994bfc26 | 107,106,2,18,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
7a7153f0-90ad-4984-a953-6e9aea7bc817 | 107,106,2,18,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2cfa9b6e-d44c-4be0-a781-fd18b523ce49 | 107,106,2,18,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
226be75d-c2aa-4bd1-bc93-ce337d5c0a95 | 107,106,2,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
fe4c6cbd-18b6-410d-b9a8-c7735595dfa8 | 107,106,2,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
11268d58-bbbd-4c57-a98d-ddd90b89272c | 107,106,2,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
d2ad650b-b79b-46b3-9d3a-fd82e2098de3 | 107,106,2,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1ef7d600-d3ba-47e7-9c33-f34292f3bc70 | 107,106,2,65 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
e23a39c3-fcc3-43f2-a839-324fb3562533 | 107,106,2,73 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
1b73d306-5b24-483e-98cf-b993e775b929 | 107,106,2,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
acd62776-f78b-474a-ac79-35b2a95b3eb3 | 107,106,2,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
27aeac0e-b55f-41cf-9a32-41eaeb896baf | 107,106,105 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT RAIL DRIVER (4) | 12 | FALSE
755b4c6e-3619-4199-a10e-8215f9883b02 | 107,106,110,2,16,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
8c8413a7-41d5-456b-8b48-c745321f3e9f | 107,106,110,2,16,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
7cae7411-bca1-44c2-8d08-b3d434a15aae | 107,106,110,2,16,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8175dbd6-a67c-49fa-afd3-76cd9bf4f1fe | 107,106,110,2,17,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e6c22b9f-7c26-4201-bc30-7f9223ea2466 | 107,106,110,2,17,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
8b7638bd-c620-49dd-a2cc-318abc133879 | 107,106,110,2,17,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d26ecb63-13da-4ad7-b122-4bd800d1554c | 107,106,110,2,18,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
8d2fa240-c445-441a-b8e0-8d64f7bd5552 | 107,106,110,2,18,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a8436cf4-af4a-4e2a-a707-180aca804c51 | 107,106,110,2,18,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
21a2b89c-dd5b-4b65-8905-098a1513c165 | 107,106,110,2,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
559eee86-ffc6-427a-b394-a3378ba89c7f | 107,106,110,2,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
12f01c74-ca7b-4b69-9471-473034ce9fe7 | 107,106,110,2,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
857aa5fd-702c-4ce9-b8f4-8da544b154c1 | 107,106,110,2,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
635b7ea7-94d6-4c81-a35c-b34d9bd2386c | 107,106,110,2,65 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
10c16225-263a-4c25-a4bd-ec5cd3a7ea86 | 107,106,110,2,73 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
726aa0ab-ac7a-45b3-958c-934c7a2d97e0 | 107,106,110,2,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c1f562c8-1fef-4dff-80c0-2cd76f5d0a4e | 107,106,110,2,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c6b17999-33e0-42c8-a7e5-09e33f62086f | 107,106,110,1,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
9ebdab92-1df2-428c-a0c2-4d5afbf8645b | 107,106,110,1,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
4a2b0c61-5fe8-47bc-a5ea-1bc0d5fc243a | 107,106,110,1,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
fccbe795-80ea-43b1-9b6b-876430100515 | 107,106,110,1,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
f7fbaf2e-9286-4c7e-9a79-4d1a6ad2c6d7 | 107,106,110,1,98 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 18 | FALSE
8556aa0d-1fd5-4d51-a0de-4b644ed87264 | 107,106,110,1,44 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 17 | FALSE
54b5f491-f49e-48de-a2be-c7a13a1ecb56 | 107,106,110,1,47,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
3d2c0522-ada5-448c-9c78-f1312a777e82 | 107,106,110,1,47,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e36005ed-72ac-49b5-8f38-d5b36d3ca923 | 107,110,2,16,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
18bee2f8-3f20-4fef-9441-9270133fe49a | 107,110,2,16,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
90bdb0f6-877f-43fd-bd42-81aca6abbfe5 | 107,110,2,16,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
59325367-4741-442f-bf32-3ce20bf75c32 | 107,110,2,17,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3ed41c1b-00e4-484d-998e-232f08f29a9c | 107,110,2,17,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
69d31be2-0a42-4fe4-944e-828274b661aa | 107,110,2,17,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
080dde0b-64a9-49c2-82c8-af23a715bd77 | 107,110,2,18,19,20 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
b0f3a9df-e7ef-44f1-b482-1f70f2c72ade | 107,110,2,18,19,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
13cc14fa-2618-4884-bf7b-1aa99ffbede7 | 107,110,2,18,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
ee8fb581-28f7-4143-a5f3-3fee3be8c3e1 | 107,110,2,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
e48aadd8-0dac-4e09-bc33-e41604d49216 | 107,110,2,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
cf588893-55e3-44f6-a5b8-a494da56fde5 | 107,110,2,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
cc3db1a1-5789-4e56-990b-7dbcb8f61037 | 107,110,2,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
7e959355-0af4-425f-9478-2cf44c0736c3 | 107,110,2,65 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
c60dcd63-8f08-4331-9532-b5fffa040a9b | 107,110,2,73 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
93487b26-6ea0-490f-8b94-8c8e044a8ffa | 107,110,2,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
e646aad5-9372-49d4-9ee4-d1e4cae23b99 | 107,110,2,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
5965647b-8bcc-4900-8ef5-3834db3b30a9 | 107,110,1,35,25 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
b739d743-3d8f-4f8e-a41c-8eabdfbc3e07 | 107,110,1,35,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d4e90e80-976c-40b9-a38f-87518b1896e4 | 107,110,1,36,26 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
15fbb3e3-7d5e-404f-9392-17c1e28e89a4 | 107,110,1,36,101 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
e99c31d1-f2a1-47d2-8114-e58e462a23f3 | 107,110,1,98 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 14 | FALSE
5957363e-6d0c-4c14-9a60-6a46ae2f3277 | 107,110,1,44 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 13 | FALSE
691054f8-14f2-4ca4-b3fe-3250a5bef02a | 107,110,1,47,21,22 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
988af317-7288-40c4-8840-d93d3a922cc1 | 107,110,1,47,21,188 | ASSY - FRONT SEAT MOUNT DRIVER (4) -> ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
dc7af8e7-fec8-4fbd-89e0-357a6b16c01b | 109,2,16,21,22 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5fff52fd-6b6a-4d18-9617-cd5c0ed2a048 | 109,2,16,21,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f293fd76-20fd-4649-b3b3-58cee837deb6 | 109,2,16,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
539babc9-5a8b-45f0-95e3-ea30fa95a0d2 | 109,2,17,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
3ebed27c-4aad-4328-86df-447aeb6fd4f6 | 109,2,17,19,20 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
e9bfb72e-4547-40fe-a6be-a9507450a367 | 109,2,17,19,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
12513524-a34d-4193-a2be-28c7e2ba6331 | 109,2,18,19,20 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8f4582b1-b78a-4145-909c-c406e80b83bb | 109,2,18,19,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8d33be1d-3b3c-4079-8dcc-aa8b4409219d | 109,2,18,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
bcbc5f9f-da51-460c-a7d7-c06c0531f075 | 109,2,35,25 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
96cfa57d-e550-45c7-8b0a-95c80ff13cbb | 109,2,35,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
eb159d51-ad61-44f9-aa09-762a9c18891b | 109,2,36,26 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
75c1cd51-fe6e-41b2-9c61-581bd0e2de4a | 109,2,36,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
9f0bc78c-bd83-4efb-a363-49e5464bf94b | 109,2,65 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
c71d3272-1053-40be-a4b8-2db009acb53c | 109,2,73 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
e6cdcf8e-3fe4-4c71-911f-abfffd6c85b6 | 109,2,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
2d4f41a5-6b8e-4e01-9d91-c63b7c13e548 | 109,2,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
e7d5d664-6540-4125-aa23-fd8c4b318e5e | 109,111,2,16,21,22 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
d841ec2b-cad1-4791-a0dc-eed0a5f3f281 | 109,111,2,16,21,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
23443757-0eae-4d8f-8228-ec894bf5b9f5 | 109,111,2,16,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
bba17969-a71f-4052-9158-9085461aaec4 | 109,111,2,17,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
59499f3e-ba93-4c1e-912e-9b6a8af67ca0 | 109,111,2,17,19,20 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
d6423546-f087-4409-88f9-9fea2e7332f4 | 109,111,2,17,19,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e58cd8ae-cbf8-4afa-baa3-313f5704111d | 109,111,2,18,19,20 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
84d7c37f-00c2-4d18-b798-09e06d878b50 | 109,111,2,18,19,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
207d2263-fe68-424a-a674-665fd69a52db | 109,111,2,18,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
1b47188e-23fa-4c23-b7ea-04c2e78209a7 | 109,111,2,35,25 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
d2c3caca-0b8a-42fb-9e2b-e40cbf3a46d6 | 109,111,2,35,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
0293f0da-4f0b-4720-bf2e-ebd056b3217a | 109,111,2,36,26 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
83e491cd-ea20-461d-bcd1-a3de45489043 | 109,111,2,36,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
8d9b0b6b-490f-47fe-9026-599fdb90678c | 109,111,2,65 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
658cd6a3-39e9-4c5d-b3b4-a0902ad71b68 | 109,111,2,73 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
478ac19f-4e6f-448c-8c41-a72231ed0cb8 | 109,111,2,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
f3bcbe10-3b81-4669-bb48-5cc26b46a898 | 109,111,2,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
2ed0f1d9-47d5-4952-a0e9-3e18c463e112 | 109,111,1,35,25 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
9ef5db4b-f5f8-4b84-918d-a1ab4198fbfc | 109,111,1,35,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
01e23b57-696b-4738-a5fe-89e17efe3b8f | 109,111,1,36,26 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
689fdf9d-3bf2-4f46-a822-edee478cfe9e | 109,111,1,36,101 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
cb75bf67-51d9-4f7b-b1d5-c37fc851c63e | 109,111,1,98 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 14 | FALSE
388db674-db85-41ef-ba65-614c98d6d21c | 109,111,1,44 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 13 | FALSE
3ed4d911-07e9-4f5f-bdab-cb13f3b43bae | 109,111,1,47,21,22 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
abcd1d9e-aa8e-4c8d-b8bb-82fee7b47267 | 109,111,1,47,21,188 | ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2457ba70-18ea-429c-832d-e9e8e9012537 | 110,2,16,21,22 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
b3bbbb7b-8f4e-4d16-a5e7-58526cf09ba2 | 110,2,16,21,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
1ae62dd8-761c-4fee-afe6-4826a789af40 | 110,2,16,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
076506e5-e5ba-4ef4-ab05-c24e4e62d902 | 110,2,17,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
d4b98bbc-30f9-4bf8-b507-5cc5f115b8d1 | 110,2,17,19,20 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 18 | FALSE
0bf8f30d-38b4-4c16-b872-50b2503f02c8 | 110,2,17,19,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
eae98ded-2f2d-4fbb-a073-3f8f797d1575 | 110,2,18,19,20 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
b07c6ba3-fb8a-4764-bc2f-50e9b2bbc976 | 110,2,18,19,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
17d909d9-8ffe-4d7c-a6a2-69b6fbe1fb27 | 110,2,18,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
81d9eec3-3a6c-42d3-88d1-f3f3dcbe299a | 110,2,35,25 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 11 | FALSE
16c88446-6d58-49eb-a545-6a4542143735 | 110,2,35,101 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
e87c89fd-041f-433b-83f7-6cf22efd5c27 | 110,2,36,26 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 11 | FALSE
6061759e-3799-446b-9adc-a32d2a975dca | 110,2,36,101 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c39ad48a-3af0-444e-bc69-3ae734d28230 | 110,2,65 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 8 | FALSE
ce1debf9-4b3f-4043-b755-914888985284 | 110,2,73 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
e22c6e37-4657-4492-beeb-03f01da85939 | 110,2,101 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 12 | FALSE
9d8bd36c-1135-4d40-8064-b40af83590eb | 110,2,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 8 | FALSE
a2d4ebd3-b9ba-4206-b274-f260f2fdee50 | 110,1,35,25 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 11 | FALSE
a3a885d4-e2ca-4832-a194-6b83e207a754 | 110,1,35,101 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
c191f607-691a-4674-b589-072424dc3f4b | 110,1,36,26 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 11 | FALSE
0fd77ed0-bdc4-4726-89d4-b2f356acab23 | 110,1,36,101 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d665fab8-9bbe-4fb8-9563-f3b208be3a52 | 110,1,98 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 10 | FALSE
0b2a13ed-a178-46c0-9955-f16ca71b6a7a | 110,1,44 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 9 | FALSE
3ae7e283-e635-415f-a334-f7a8e3037ea1 | 110,1,47,21,22 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 17 | FALSE
2f0156ed-5bec-420a-8c7f-a393e13df945 | 110,1,47,21,188 | ASSY - FRONT SEAT BELT DRIVER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
40b9b563-169d-4a83-800e-cbcfbde5e0fc | 120 | ASSY - PWT HV WIRING - LH (2) | 2 | FALSE
7ff3d09a-37a8-4162-b9a0-dbd92108c5c7 | 121 | ASSY - PWT HV WIRING - RH (2) | 2 | FALSE
271815ce-856e-48eb-beba-5731d06745ce | 122,7,2,16,21,22 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
02c10878-2ed4-4349-bad9-74362bd9aef5 | 122,7,2,16,21,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ebe812f2-aa82-4219-8068-46a5b58f3af1 | 122,7,2,16,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1b06fea6-3e07-4a6e-9bad-85064b2b68fc | 122,7,2,17,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
faac2891-90a5-4527-99fe-40cc3072e4ee | 122,7,2,17,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
febbec08-8263-42be-b098-be1e4135b36e | 122,7,2,17,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
68e3237d-c92c-4a43-b59c-8613703f4104 | 122,7,2,18,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
aa5a4e6a-45d1-47f2-b872-60570d55fbb2 | 122,7,2,18,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
3e087682-750a-4364-bc6a-a2863dc0c234 | 122,7,2,18,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d7113a37-1b7d-43ad-907a-db0db108c4df | 122,7,2,35,25 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
d4740c18-948b-446c-8d41-66ee3f66f2d4 | 122,7,2,35,101 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
e55d404c-3e91-4389-8912-e2a794c85761 | 122,7,2,36,26 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
fa2ca2af-7151-4a47-bac3-b355aa698144 | 122,7,2,36,101 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
038dc34f-8a1f-4b72-b4ff-43b7818ceaad | 122,7,2,65 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
a282f988-a6c5-4833-ba70-c69dba11f5c8 | 122,7,2,73 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
2a67c264-a43b-4426-9ada-e6da9b45dc91 | 122,7,2,101 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e3d56ee9-10ed-4d52-bd99-bbf117219280 | 122,7,2,188 | ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e611cfff-a7aa-474f-b656-ca692f3d4f85 | 122,114,7,2,16,21,22 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
251e2481-21e0-45f5-ae20-3553795d36ec | 122,114,7,2,16,21,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
3acafdc9-036b-4ee5-85bf-3f0ace446e84 | 122,114,7,2,16,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
675f9e06-b203-4e92-ac8b-15ee2e43b894 | 122,114,7,2,17,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7276110e-2cce-4900-a5b0-1d321937eeea | 122,114,7,2,17,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
60e4e775-d081-4d5e-823c-b1050d4c0cc5 | 122,114,7,2,17,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
7a55b068-1562-49bd-b6ec-e99364d5cbfb | 122,114,7,2,18,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
94282c44-7dc2-4f27-b9e2-f9c6fe298aa1 | 122,114,7,2,18,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
91f6d814-7510-48be-94e9-b3d858da7121 | 122,114,7,2,18,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2e1ca407-4a87-464d-8fe5-7939f21a0bba | 122,114,7,2,35,25 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
cde6022d-e500-4ba8-92ba-b44ff5b38870 | 122,114,7,2,35,101 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
f1aa2f88-a2c4-4a88-aaf0-e5daa5ba4926 | 122,114,7,2,36,26 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
e608a074-bb5d-4487-9a9f-49b5b34e2c26 | 122,114,7,2,36,101 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
936e516d-9df5-467e-bfa1-3b90e2dde7de | 122,114,7,2,65 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
107c6765-ed4d-4c6c-a375-90ad31176f20 | 122,114,7,2,73 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
20101c5a-de87-4b1b-971a-3c56aa58f763 | 122,114,7,2,101 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
c4ff0ea3-db94-4042-9d81-39ba3a9c9737 | 122,114,7,2,188 | ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
346c1d1f-9490-4dc2-a4dc-9fc628d11db5 | 122,124,2,16,21,22 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
98c5d022-2947-4b04-ad6c-810fafe51da9 | 122,124,2,16,21,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
3637ab09-bfee-4684-b31b-0e5e9f188ff6 | 122,124,2,16,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
4c5f299f-656e-493e-b841-db98fd7432f6 | 122,124,2,17,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7559b7f5-0f44-4851-b34f-4359a157c1ea | 122,124,2,17,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
4055c42c-d059-43bd-8615-a376febaf9cb | 122,124,2,17,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e6bb9435-c5fe-40ef-aaf9-c5b442253062 | 122,124,2,18,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
640f9054-3631-4908-9573-aeaf69b3d44d | 122,124,2,18,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
7fb05e09-43a9-49e7-9d26-ca8325f1cb1e | 122,124,2,18,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
84ead2ab-a0b6-4847-ab32-e24f87ced536 | 122,124,2,35,25 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
57c0f85e-da81-4812-986b-46a412060ea7 | 122,124,2,35,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
1560aa94-a1d3-46cb-9e01-6bfce396ab4b | 122,124,2,36,26 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
09773cd0-5f0b-4210-bfac-cfc5fc7a4d7f | 122,124,2,36,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
810a7e65-802f-479a-810c-1a1d20b50e65 | 122,124,2,65 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
368748e5-b0ce-4c02-a391-65e9cff87aff | 122,124,2,73 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
24934dd6-de93-4908-85d3-57fa07f56174 | 122,124,2,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b2853f48-009d-45ce-b464-10b36d481467 | 122,124,2,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3a0238c1-d86a-4d07-8a1f-e098cf339033 | 122,124,7,2,16,21,22 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
86529bba-9ff9-4002-9f02-624505b7e71a | 122,124,7,2,16,21,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
98b5f338-2070-41b8-882f-ca0897b66ed2 | 122,124,7,2,16,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
c6d77ac5-b386-4adf-a166-c71ed9c0be76 | 122,124,7,2,17,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
838da354-8b9f-4ccb-97dc-9930c64c1ec0 | 122,124,7,2,17,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
0d9b9a98-c82a-46d5-8b9e-89efad555ead | 122,124,7,2,17,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
0dd47f88-02d8-478a-86a6-bb0f65dca521 | 122,124,7,2,18,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
b5c542f4-6edb-42ba-be2a-503281a48fb1 | 122,124,7,2,18,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
dec6d319-0665-4d45-bcfe-ab2775761590 | 122,124,7,2,18,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c5683dd9-9903-4536-afa1-d790aeb2d3f0 | 122,124,7,2,35,25 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
94f02e58-ba41-489e-97ee-0b199044399d | 122,124,7,2,35,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
d5c355a2-5da7-4c1f-a89d-207900f0a7bb | 122,124,7,2,36,26 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
049b5a5c-8505-4596-8866-3736931cf4a7 | 122,124,7,2,36,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
7893fe51-1cbc-459b-abd6-3ba42c626d09 | 122,124,7,2,65 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
81e03c75-6197-49ab-8412-03d74e2b198b | 122,124,7,2,73 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
a5b0659e-3697-4df5-8a17-696ac8389296 | 122,124,7,2,101 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
51802260-5971-4383-935c-745f0d096f6f | 122,124,7,2,188 | ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
cfa61867-386c-45d7-90b4-631d88d52cd6 | 122,2,16,21,22 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
8c9903ba-9ec0-4beb-9ae9-1416fd3d7410 | 122,2,16,21,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e08bc34d-bbc3-4f38-a0bd-66615ded03e7 | 122,2,16,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7bb84d29-30fc-46ab-9163-415fd4d23b3e | 122,2,17,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
df085f89-bebd-4969-9907-6848f5c8b2cf | 122,2,17,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
1aece6eb-0b6f-480a-a983-f8298f2090c8 | 122,2,17,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f6c0e5fa-67e7-4ff6-ab7d-57c11d67298f | 122,2,18,19,20 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
ccd7e8e0-26d7-4864-98f6-301f4abcf616 | 122,2,18,19,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
159228e3-151e-41ee-b15b-2da8a690bd07 | 122,2,18,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d3ecf5df-2cf5-4eca-8a7b-9398031c0744 | 122,2,35,25 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
5a4fee43-d493-4715-9512-ba856d0a20c9 | 122,2,35,101 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e943dd7f-9adb-4ed3-822e-f2cfd8ad8c7a | 122,2,36,26 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
bd4838fe-b9d7-4e84-aaef-cb53e1b58b68 | 122,2,36,101 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
1505cfba-7c59-4dca-ae2f-e3e1022d6a97 | 122,2,65 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
59e37faf-8ac2-4e74-acf2-68bfe35e2731 | 122,2,73 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
9b97676e-085c-4c1a-adf5-036ea64087e5 | 122,2,101 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
910ab167-0fd7-466f-9571-4aae701704eb | 122,2,188 | ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
2c955943-409c-4520-87d4-587c90f0e2a2 | 123,7,2,16,21,22 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
6703fecb-4302-41f1-9fd5-45431386d9ab | 123,7,2,16,21,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
78d0e4a9-8557-4033-9fa4-d7911ea4ada8 | 123,7,2,16,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b124c02c-b6cc-45cd-9edf-52646bbab88b | 123,7,2,17,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
758f6578-4844-4896-b762-79a01a8110e6 | 123,7,2,17,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
21c66e12-607e-4e78-b81b-6cfebbc35a19 | 123,7,2,17,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8899e251-1d34-4b54-957b-2340dacfd52a | 123,7,2,18,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
9d0ba9ad-4665-482b-93f6-0a3b240acf14 | 123,7,2,18,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8c9955ce-b4f7-47b0-9a96-64b64f5e2e18 | 123,7,2,18,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
b6bbdab4-0e33-4f68-861c-91d0594775c1 | 123,7,2,35,25 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
09685807-eb02-487f-97a2-318c0b3043e1 | 123,7,2,35,101 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
1b9046b1-5e45-4954-9097-6f9687b64366 | 123,7,2,36,26 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
96f7a017-c72d-444a-b8f9-7c0deb920c88 | 123,7,2,36,101 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
8603b4bf-349c-458d-8c07-19ca7621a648 | 123,7,2,65 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
b65c38d9-8c0c-44ae-ab4f-047641f2df89 | 123,7,2,73 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
d8bd6413-18d1-42c0-80ac-49419e66c01a | 123,7,2,101 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
6b5009a4-575a-4931-b4a8-1ce77e769fd3 | 123,7,2,188 | ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
dcee0937-04a3-42fc-98ee-548af4bb2696 | 123,115,7,2,16,21,22 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
38edab28-d2d2-48e9-9d4e-ff1a4ed9d997 | 123,115,7,2,16,21,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
f86e1165-672a-4640-b4b9-0039dc3246db | 123,115,7,2,16,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
d48a6c45-2e1f-4def-9ad6-1aa1465745fc | 123,115,7,2,17,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
4d773cf1-e907-423e-bebd-20308521bc55 | 123,115,7,2,17,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
f4299499-c68c-44d9-8d7f-2983868cca26 | 123,115,7,2,17,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
1ade113c-1814-48e6-84c1-1e9c56cc5fcd | 123,115,7,2,18,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
7318a004-6a69-45bc-8e73-26326d772ec4 | 123,115,7,2,18,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
12dfb89b-00dc-42a7-87cf-8f3c5babc2ba | 123,115,7,2,18,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e0d41bcf-ca03-4bdc-bb11-5fde4477af66 | 123,115,7,2,35,25 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
a212b119-b4f0-4269-9ec9-c945ff46c9ca | 123,115,7,2,35,101 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
10d96d95-97fe-49df-ba1b-24b3a4c16b7a | 123,115,7,2,36,26 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
28140a08-6d37-413e-8d52-e9d330adb9f9 | 123,115,7,2,36,101 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
ee2f437b-2eb1-4132-aeb3-8e14c66f11fb | 123,115,7,2,65 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
8bc0ee66-a747-4c34-a47a-4098f8982200 | 123,115,7,2,73 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
6b11dace-9f6f-48be-bce8-7fb0647221b4 | 123,115,7,2,101 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
b9946127-732b-4383-b4be-57b51aeb238f | 123,115,7,2,188 | ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9c3401cd-769b-4042-99de-24df66976704 | 123,125,2,16,21,22 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
f24126b7-daec-4ab8-9fab-1042e3d37f8b | 123,125,2,16,21,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
732c06e8-6047-4616-a8af-8cde2be03ea9 | 123,125,2,16,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
911330c0-753c-4f98-b16e-5a5a9f348773 | 123,125,2,17,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
93724497-58ea-4411-810d-cc7e9e2afc03 | 123,125,2,17,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
26a4c331-d60b-4a45-879e-ddf4baf7eead | 123,125,2,17,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
ab1bbb43-0840-45c8-acfd-a4e06a79ec0a | 123,125,2,18,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
4ed3f919-f9a2-4025-8832-59f45bda0c62 | 123,125,2,18,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
fb483cf9-b536-4aa2-8514-77775eae521c | 123,125,2,18,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b5d765b5-0ccf-42df-af07-1b1586a5d3cd | 123,125,2,35,25 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
1bc438f9-b4ca-40f8-b9f2-005b60e9d80f | 123,125,2,35,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
3ae57c20-e23a-4690-82e8-10e94211d794 | 123,125,2,36,26 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
cc9f7109-7ccd-49e6-89fd-e4dad35792a3 | 123,125,2,36,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
fe754c71-dc46-432d-b0e2-2c50285a8f9a | 123,125,2,65 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
156e1ad4-88d9-4317-9de1-bc5217cfdb24 | 123,125,2,73 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
17d40186-39c6-44c2-943c-2b2e26fc6c94 | 123,125,2,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c8c84d9f-c138-442e-a96f-53755fc685a9 | 123,125,2,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a7c5181f-4b2e-44dc-bbda-6098ceba1975 | 123,125,7,2,16,21,22 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
9e499bb0-097e-4630-8ff7-dff164ba606d | 123,125,7,2,16,21,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
4a8a5143-1e8b-4deb-9a17-43b3d9b9e8ee | 123,125,7,2,16,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
698b4279-91c7-4e33-a631-b1773d739edb | 123,125,7,2,17,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
eedc2993-9d6a-4f5c-aa59-01ab2f9c84f1 | 123,125,7,2,17,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
9116b3f4-b7c0-4073-b36e-24d78b0ac1b5 | 123,125,7,2,17,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
b99a4b36-7d80-4765-8a7b-31b20283f89e | 123,125,7,2,18,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
4039d117-eb7a-4cda-b88c-9fa142deee22 | 123,125,7,2,18,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
3139a9e0-1217-41c2-a44b-f9f321a894ea | 123,125,7,2,18,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6aeb4ce1-08dc-4b4b-abc0-333f577cf488 | 123,125,7,2,35,25 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
9987c67f-96f6-4fa5-9834-92252aa4e9fb | 123,125,7,2,35,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
881e313a-bf62-446b-824a-0ed189d5cda9 | 123,125,7,2,36,26 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
2f431f29-baee-4a54-935b-fd4ef2a4725e | 123,125,7,2,36,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
de3e7e67-a271-4f7a-b903-215318271fad | 123,125,7,2,65 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
a53f39f3-e483-4c98-ac62-eea70a02944b | 123,125,7,2,73 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
db22df7a-48fa-4cb4-ab6d-f2e79c64a3c1 | 123,125,7,2,101 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
303fec75-289d-4fb8-bd35-ddd300959261 | 123,125,7,2,188 | ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1e916393-7d25-45ec-9797-8b257dc557c1 | 123,2,16,21,22 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
5b16a0b5-4476-414b-896b-069db4f78fcd | 123,2,16,21,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6147a756-f2a1-4933-900a-82324dce1433 | 123,2,16,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3c89610b-7459-495c-984c-e5df561a158e | 123,2,17,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
664bf8f8-74dc-426f-8b58-712da9af9ff1 | 123,2,17,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
3a510257-2002-4643-8888-236cd2e42b5f | 123,2,17,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
136151fd-fb73-4292-9cee-761b8696cb52 | 123,2,18,19,20 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
3756299c-4fc4-449c-bdf2-f511234d31ec | 123,2,18,19,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e12aa9a2-13e8-434d-a363-b320fb2ac2d3 | 123,2,18,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
eb097850-b0a1-4d27-bc82-5bd4236d4ae3 | 123,2,35,25 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
18917bde-0c5f-4bb8-962f-0ae9aeba573d | 123,2,35,101 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
73473ada-bd3a-42e0-8c29-20f552a4bb01 | 123,2,36,26 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
5ddc7a38-8631-4958-bd43-2a5494ad07ba | 123,2,36,101 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
93c8a28d-b63d-41af-920b-7d6d6cef2ecf | 123,2,65 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
cf6c2855-62a6-46c6-87d0-f799250c5a37 | 123,2,73 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
1e88cf8c-20bc-4957-a067-177c16f78ab5 | 123,2,101 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
54257dbb-c186-43fc-9c46-651f916a2437 | 123,2,188 | ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
f23f8663-053d-48a8-a004-ee93717e7f12 | 124,2,16,21,22 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b5456b73-f338-414d-8bdc-f0ec1bb6c3ff | 124,2,16,21,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e804deed-4438-4094-99dc-36692d34f4d2 | 124,2,16,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
20f8b5cc-8338-4646-94e5-08c4e6da7237 | 124,2,17,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1ee1e296-c772-49c8-a6e8-56d834209462 | 124,2,17,19,20 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4e79f259-5537-45cd-9ade-efeb71e098c4 | 124,2,17,19,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3d028b3a-50cd-4849-9509-52e8f1348fc7 | 124,2,18,19,20 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
75d66fe3-f17f-41d3-a619-1ace00584936 | 124,2,18,19,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c92d6514-506b-4acd-924c-7584ae94458e | 124,2,18,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
76cc2d4b-2410-4dd3-b317-2db58dc5b726 | 124,2,35,25 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
b11d6e2c-1ee0-4778-9cec-a14bad658ce6 | 124,2,35,101 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
87438244-0873-4b56-8236-0dbea6432b16 | 124,2,36,26 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6e4b747e-7731-4ed3-a893-6e1d2003083c | 124,2,36,101 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bd6ef6aa-0658-43c3-8f4d-a4eb757c55ab | 124,2,65 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
0a8b728a-2754-4382-b4d8-741831c311c4 | 124,2,73 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
9a18688b-1eb4-46ee-9587-b0a64176e3b0 | 124,2,101 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
69d644d3-697d-4c5c-85ca-79f04c5056b1 | 124,2,188 | ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
8ba75fd2-498b-47b3-b12d-a2f7e5145466 | 124,7,2,16,21,22 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
70e8f1b0-aff8-44b0-a396-3a059ad19258 | 124,7,2,16,21,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
c199d693-31f4-4805-917a-19330eabdf88 | 124,7,2,16,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
12df07cc-6a82-4586-9570-afd585af4b1b | 124,7,2,17,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
478061f5-52d3-4870-988c-f2701a8c51e3 | 124,7,2,17,19,20 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
04e214ee-af3e-4cbe-a3c2-893b93453890 | 124,7,2,17,19,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ecf19b51-2f7f-42c5-803f-f5b2c3512254 | 124,7,2,18,19,20 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
08b88207-6454-41bb-abe1-3be6000af12e | 124,7,2,18,19,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
1ce16f03-8d82-427c-b0d3-1de516ee9be0 | 124,7,2,18,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
999bca99-4e85-450c-a61c-191635435a99 | 124,7,2,35,25 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
0219eb2e-24a4-48d6-9a14-74012e4d9fab | 124,7,2,35,101 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
bc2b1454-a5e6-4ac6-beea-65d484e0b233 | 124,7,2,36,26 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
87787c6c-f0e7-4f0e-8a49-a1c46e4a27ff | 124,7,2,36,101 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
f6108895-925b-4d3d-9b79-df5cb951dba7 | 124,7,2,65 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
4d942115-516e-4767-bc91-21f61d0eb0ed | 124,7,2,73 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
8df79262-e888-414a-9cef-7965535a6894 | 124,7,2,101 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
2ad92126-0a92-40e2-a452-1b023f710f0c | 124,7,2,188 | ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
931090cc-1437-4122-8415-89ec55681486 | 125,2,16,21,22 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
bff1e2af-1595-430a-bc04-3a1c69e1e0ab | 125,2,16,21,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b248ce4c-69f8-4b2a-bc6a-4a52830477e5 | 125,2,16,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
aca88e67-cf1a-4055-a39d-356cecbdf94e | 125,2,17,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c1efbb54-f222-4ba6-9395-6eb94b630f81 | 125,2,17,19,20 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
493aadd7-ce8e-48fa-b878-da5c38d4805c | 125,2,17,19,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e06f6acb-34c1-49b8-b762-586da306770d | 125,2,18,19,20 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d8870c64-af49-4775-991b-fd38d72e18bb | 125,2,18,19,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
38556621-0d06-43e5-9e15-b8faf8e3c994 | 125,2,18,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
424434e0-139e-46ce-a329-979e74f8014c | 125,2,35,25 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
57ff282b-e44e-4351-a5de-a2178d4191a3 | 125,2,35,101 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
f09d68ba-c5a7-45c3-96e0-d42132e4358f | 125,2,36,26 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
26d12a41-773a-4c42-9c5d-4080c0a8206a | 125,2,36,101 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bcf59979-cdd7-458d-9861-50e02fea9417 | 125,2,65 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f9bb6af1-e8e3-4586-aafb-505973567177 | 125,2,73 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
52a9dbbe-c786-4094-9baf-489e1bd2dc30 | 125,2,101 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
c3d299f3-48cc-4060-bf3a-bdddf2b74347 | 125,2,188 | ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
81fcc0b6-5d60-4183-8d58-d8c64fa9cfc9 | 125,7,2,16,21,22 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
32703961-2985-4c01-b914-f857c1f8d330 | 125,7,2,16,21,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
1bbda0ea-958e-4c66-a8d4-17d1f633c56d | 125,7,2,16,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a583f690-2f27-4b72-a622-4e3232918791 | 125,7,2,17,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
411191e2-64da-4525-b82c-1e88d0f7b431 | 125,7,2,17,19,20 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
505980c4-d2f9-4ba1-b13f-e5df2a94b138 | 125,7,2,17,19,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0488bda9-1362-4af9-b10f-4585556bc2d0 | 125,7,2,18,19,20 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
fd8ff601-85fa-4f1c-aae5-9c2b219ac509 | 125,7,2,18,19,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
bb368f25-b4c3-4a34-b8f8-88a763e4b438 | 125,7,2,18,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0c9c09bd-0f7d-4337-8387-579ea877b871 | 125,7,2,35,25 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
54b9d24b-54db-4697-b51c-0e5513c417f5 | 125,7,2,35,101 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
afb0584b-3c6a-4dc0-9ef1-6650419bc100 | 125,7,2,36,26 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
e4cf9f10-31da-4993-a4b4-4f060a33509e | 125,7,2,36,101 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
f5f1108b-27ad-4edf-a1d8-1f1cddb83501 | 125,7,2,65 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
a19a7389-30aa-4a3f-bc71-92fd57830fc6 | 125,7,2,73 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
fe519d43-b9a4-4f61-8a9e-539d82222a2c | 125,7,2,101 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
d869c6ae-9c81-4b69-8351-2dbab565dad3 | 125,7,2,188 | ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
32321d89-2c71-43de-be06-5efe4e0ef969 | 126,2,16,21,22 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
6a553b5f-4544-4b6b-bce8-c0b0fee6de5b | 126,2,16,21,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9416369e-dd4f-4f50-a57e-1be665869cb2 | 126,2,16,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ae6b76c4-e84c-4c51-b6e3-c4e47dfd2c0d | 126,2,17,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
302eb0db-9e0f-418b-89c5-e6ca442157e3 | 126,2,17,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
a923f931-d425-4640-9959-6438bb73c5b2 | 126,2,17,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
9a2e7182-b7c8-4575-93e6-06aa9b937fab | 126,2,18,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
eb6a6b96-d99c-4d60-a8fa-eb49af740b94 | 126,2,18,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ccfdc0be-b667-4cba-8e62-5e7631133f42 | 126,2,18,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
18c26b30-754d-4165-97cb-2da416e9083d | 126,2,35,25 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
46f9bdcf-ce7f-4fdf-8dc6-1c565913e305 | 126,2,35,101 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
5b5ae360-d1b9-4ab7-aa7a-73238ca88642 | 126,2,36,26 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
0bb23fe4-fa90-4912-88cd-607d9cfa3324 | 126,2,36,101 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
71ffd1b5-6326-4331-b76e-1fb18684c660 | 126,2,65 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
5fde0e12-9af2-4251-bb3c-45bc5b067b53 | 126,2,73 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
283880aa-5bc7-43c8-a0fc-88a69fb99abc | 126,2,101 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
73141581-1f92-4c93-a251-4b087883a014 | 126,2,188 | ASSY - BATTERY MODULES (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
636e70c8-7002-4cb0-8778-418d81059f92 | 126,127,128,136 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 12 | FALSE
88b34406-e9fb-4833-8756-10bdb474f418 | 126,127,129 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 8 | FALSE
e6925ef8-20a8-4ac8-a41a-04ae230a3430 | 126,127,130 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 8 | FALSE
d4739a88-7735-471a-964f-7cf96de08b7b | 126,127,134,136 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 11 | FALSE
7a99b5eb-1264-4e4e-b589-c66bc8e972d6 | 126,127,135,136 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 11 | FALSE
ee411ecf-3c76-42ed-b428-9a1acd397834 | 126,127,181,173,176,179,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
0d119911-3029-4e6e-b240-fb796002da1f | 126,127,181,173,176,179,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
2a22e1a3-0f0d-4ff6-8e09-613c6a774dd7 | 126,127,181,173,176,179,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
efbaeaf5-b8c8-44b3-9ef0-4c016f4d8582 | 126,127,181,173,184,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
c5ca8eee-d6ae-4682-8088-ae22b9c107eb | 126,127,181,176,179,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
7d44b59c-de15-4f6f-b54f-f9289d3b0299 | 126,127,181,176,179,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
31142810-c4ab-47e4-802e-bca8ad4019da | 126,127,181,176,179,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
a8d8bfd3-8721-49f7-a629-7b74100726f6 | 126,127,181,179,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
484e3c77-7905-4cf2-9464-ec5ad7b21bbf | 126,127,181,179,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
f78b94b3-5c3c-417d-af55-01f493b7505f | 126,127,181,179,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
ca7d2ba9-c66b-49b4-bb85-5c8477a5b727 | 126,127,181,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
698aecec-4a6e-4731-99d5-b858fd7b4517 | 126,127,181,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
e959d486-8fe8-449c-83eb-5495f604cdf7 | 126,127,181,182,12,2,16,21,22 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 31 | FALSE
8c8fad9b-1567-4166-8539-4c69a221d2d4 | 126,127,181,182,12,2,16,21,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
bde42925-5d84-4054-bbad-eaa70539b8a8 | 126,127,181,182,12,2,16,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
bfefaeeb-3ffb-4a1e-841b-2823972fa17d | 126,127,181,182,12,2,17,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
65572703-4b07-496c-9b71-f5d41819c0e2 | 126,127,181,182,12,2,17,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
a2d506b1-1aad-43ac-9833-aaa0128a0859 | 126,127,181,182,12,2,17,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8012b55f-9d92-44ea-886d-7d5367ca4d31 | 126,127,181,182,12,2,18,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
413a3bb5-d9f3-4d6f-ab10-96213930d208 | 126,127,181,182,12,2,18,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
0953dcc7-659b-4648-8562-543c9236e125 | 126,127,181,182,12,2,18,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
70e401f5-1d70-4069-bafd-baa2b3a6ffc8 | 126,127,181,182,12,2,35,25 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
f055c476-f293-495d-84f9-3528bc426494 | 126,127,181,182,12,2,35,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
31719488-d6ba-4f37-80b7-0d24a416b0a3 | 126,127,181,182,12,2,36,26 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
c536bd51-bbbd-4e0b-a2f1-7d65a0412905 | 126,127,181,182,12,2,36,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
1e2adc5e-4619-4dcf-8d18-8fce613fb649 | 126,127,181,182,12,2,65 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 18 | FALSE
0710b3f2-23f5-492e-9581-0acbb15e4f0a | 126,127,181,182,12,2,73 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
14abee39-5ddf-4104-90c9-10e1fce574c3 | 126,127,181,182,12,2,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
961767c6-86f9-476c-aa7b-55f2538eeafd | 126,127,181,182,12,2,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fb71af85-5bb5-4c7b-89a6-b64002934ad6 | 126,127,181,182,183,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
648da179-2074-4307-b3f7-3b69aa860f43 | 126,127,181,182,183,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
a7c7affe-bf97-457d-9cec-1989e0a49d13 | 126,127,181,182,184,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
43cdb06f-ead0-4877-9216-996246a6f610 | 126,127,181,183,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
c2630988-ac90-4682-bacf-c1ed35eae7a7 | 126,127,181,183,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
05ae3469-f700-447a-ba17-186fa9b49ba8 | 126,127,181,184,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
c053af70-5de5-46fd-98ab-d59dfb86f370 | 126,127,181,170,174,2,16,21,22 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
09a3fc7f-3188-4ca0-8d07-0dbf911897fd | 126,127,181,170,174,2,16,21,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
3dbaf50e-634a-4364-b325-f0f3ac321e31 | 126,127,181,170,174,2,16,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
eef21c1e-25a8-4ca8-9284-a5c8512f993c | 126,127,181,170,174,2,17,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
63db0494-12e0-4369-84ed-f2920e389c43 | 126,127,181,170,174,2,17,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
5be07f8b-92bb-457c-8110-d90c641f4f7f | 126,127,181,170,174,2,17,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
16d701d5-55b2-47d9-b57e-0a6f2092bd8b | 126,127,181,170,174,2,18,19,20 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e6561608-d9c1-494d-b6a4-c7421ff684b4 | 126,127,181,170,174,2,18,19,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
87513083-a159-4535-af83-37c064f238bf | 126,127,181,170,174,2,18,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
99946d7d-d1a5-489f-ad59-654d90067e43 | 126,127,181,170,174,2,35,25 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
d52ce121-d82f-4912-a70f-774341f2f090 | 126,127,181,170,174,2,35,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
2f97445b-62ae-49ce-ac25-3cf73cd7cd8b | 126,127,181,170,174,2,36,26 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6dd4ed9d-0613-4b2a-93b2-ae51c9ada684 | 126,127,181,170,174,2,36,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4bf29403-3137-4a5a-b191-b367766cadca | 126,127,181,170,174,2,65 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
267725eb-711e-4b78-ba2b-2027e0e80795 | 126,127,181,170,174,2,73 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b1910c38-f890-4772-81f7-b94211892cbd | 126,127,181,170,174,2,101 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
3d16e5dc-754e-422d-9f32-d87d6764d40f | 126,127,181,170,174,2,188 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
306bedba-c3c8-41f5-89c8-973d5771a2cf | 126,127,181,170,174,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
a34aa312-b760-488d-a40b-0776ae84f972 | 126,127,181,170,174,186,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
d7726e9c-fe42-43d5-94f0-1bc6bb421458 | 126,127,181,170,174,186,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
ec9a5e23-9dad-4e81-9d45-31f46aeb29ee | 126,127,181,170,174,186,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
22cb2a54-c36d-4d1f-bfb2-8038b34f5ed3 | 126,127,181,170,175,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
8cc4a1de-bcfc-4234-9f2e-a6dceaa3ad73 | 126,127,181,170,175,183,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
623b15b8-9b75-4b4b-a664-7b892ddc15c3 | 126,127,181,170,175,183,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
cf2c3931-7e8b-4e43-a2e9-db8b4ddc11ce | 126,127,181,170,186,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
03fa43f2-0742-4bde-99a4-3efce8082100 | 126,127,181,170,186,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
1ceedee7-228b-472b-86e2-7c383126f4cd | 126,127,181,170,186,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
0818fbd3-9c03-4eb6-a5fc-41e9b145f12a | 126,127,181,172,173,176,179,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
741b956c-1fa2-418a-af27-627993eb23b3 | 126,127,181,172,173,176,179,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
9980364e-ccf4-4548-8cd5-1fb013f96833 | 126,127,181,172,173,176,179,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
84d7e917-b37c-45aa-b78e-06e9856b19b8 | 126,127,181,172,173,184,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
5f616509-e338-4448-9b6e-c050dfe9b247 | 126,127,181,172,179,177 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 6 | FALSE
2548990d-7181-4861-a51f-ff60f0a09b99 | 126,127,181,172,179,180,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
58e92fbf-be46-4d30-ab10-8cb9df1acb9f | 126,127,181,172,179,180,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
f00aca77-82d6-4215-9133-849b3fcf4727 | 126,127,181,172,184,185,178 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 6 | FALSE
ccc020b5-4ec0-4c20-8393-9af20f7c55be | 126,127,181,187 | ASSY - BATTERY MODULES (4) -> ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 6 | FALSE
c55a0f48-14d5-4e68-aa5f-112eb955d0cc | 127,128,136 | ASSY - BATTERY PACK (2) -> ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 8 | FALSE
fc72260b-60a9-43ba-9ea0-1f186d874ef0 | 127,129 | ASSY - BATTERY PACK (2) -> ASSY - BATTERY HV WIRING (2) | 4 | FALSE
92e35597-45ce-4cad-805b-5d76b0e488fd | 127,130 | ASSY - BATTERY PACK (2) -> ASSY - BATTERY LV WIRING (2) | 4 | FALSE
f18b39e4-20c9-41e1-93fb-247bf4280cea | 127,134,136 | ASSY - BATTERY PACK (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 7 | FALSE
ac56fc7b-3ab4-4c27-91dd-0bbadc566d88 | 127,135,136 | ASSY - BATTERY PACK (2) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 7 | FALSE
584b9e57-96b6-45f5-901a-10a26d7f0204 | 127,181,173,176,179,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
445c0661-7b10-4a57-bc6c-fe44a07c6e7f | 127,181,173,176,179,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
f2ce0a7a-0540-43bc-81ff-75aba923fb1e | 127,181,173,176,179,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
23ec8b3f-86cd-4fda-b7c6-583b96e23adf | 127,181,173,184,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
de7475cf-6cd3-4b13-9cd8-bc9059855f01 | 127,181,176,179,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
c8a77973-9a8f-42a6-866c-0efd192ebf07 | 127,181,176,179,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
6ba900ab-5a53-4ce8-a8ce-5566aae361c6 | 127,181,176,179,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
d3f8cd7b-bfbd-4646-8717-bf2a6ce4ce4f | 127,181,179,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
fb34801d-d138-44fa-937e-21e37c93a0a4 | 127,181,179,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
112f92cd-6485-4dbb-bb66-024f81313cab | 127,181,179,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
2cd6a246-5626-4ee1-9ff6-f097caf613c8 | 127,181,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
c4c3dbdf-47d4-4425-bd4f-13bbd8cbf275 | 127,181,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
d2379ca3-6dfe-4343-94ae-c1b2b5e18ff3 | 127,181,182,12,2,16,21,22 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
bc536d8d-7892-47df-9d15-0abba04ee325 | 127,181,182,12,2,16,21,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ee6b39d3-2cf5-4ce9-a7da-1ffd2fdc45e8 | 127,181,182,12,2,16,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
690bdc63-e210-445d-8d54-1c2b0f6e02d9 | 127,181,182,12,2,17,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
9723f42a-3c85-4853-8366-8e792253fc51 | 127,181,182,12,2,17,19,20 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
6f660579-87b4-465b-9f12-c17f064ef9d2 | 127,181,182,12,2,17,19,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1e638d3d-9843-445d-9650-83f449244a8f | 127,181,182,12,2,18,19,20 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
4d0b88d7-5f30-49ca-be88-e5a6688d5fca | 127,181,182,12,2,18,19,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c9462d1d-bcfa-4c1d-9da1-8790360138f2 | 127,181,182,12,2,18,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
56bd8822-313e-4870-ba53-3e36e2a33b4b | 127,181,182,12,2,35,25 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
68cc969d-9bcf-4b3c-be5e-3f5bb8d62438 | 127,181,182,12,2,35,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
66ea252a-035c-404c-9940-46de934f8a13 | 127,181,182,12,2,36,26 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
e336a189-524d-4287-97f6-92e1f65177ba | 127,181,182,12,2,36,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
40a5b51f-029e-4743-9e14-f3a38ac04372 | 127,181,182,12,2,65 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
1261abb7-2eb9-44f2-9dbf-97daf0d0e923 | 127,181,182,12,2,73 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
948f724d-1576-4742-a873-75b61866d7e5 | 127,181,182,12,2,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
57b889ff-71f6-4c64-a910-572d01ee8263 | 127,181,182,12,2,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d6a114ee-a488-47b5-af7c-e2ee3b430e10 | 127,181,182,183,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
45b8f07c-a60e-4660-a43a-dbf8f5132afd | 127,181,182,183,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
6e7141e3-dea3-4b24-a8c2-95843a95ec55 | 127,181,182,184,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
2d45d6e6-97ec-477c-b1cb-e17ff7a93072 | 127,181,183,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
1664befa-3397-4aa5-b499-0aa72c4622c3 | 127,181,183,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
6f197605-e42b-45a4-8899-672661199cc7 | 127,181,184,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
584bff91-4c17-4fa9-ba6f-77529a17c104 | 127,181,170,174,2,16,21,22 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
b2be186f-0a6e-4f49-bdf7-c8e33673bcc9 | 127,181,170,174,2,16,21,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6125c374-e4b5-41c6-9817-80d9e5957b57 | 127,181,170,174,2,16,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a297e89a-83fa-43da-8db8-e204c8901d56 | 127,181,170,174,2,17,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
60cc0059-ac20-4877-be2d-b21b4529a805 | 127,181,170,174,2,17,19,20 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
a0a9fe17-52e7-45f9-8805-310ba2d75ea2 | 127,181,170,174,2,17,19,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
55c1793f-7222-4229-adf6-0fdf53558dc9 | 127,181,170,174,2,18,19,20 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
73d8a968-5127-4c66-bb28-db5227ffbbdb | 127,181,170,174,2,18,19,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
fdea8d30-c089-4b62-9a03-3eda8aa0d9ec | 127,181,170,174,2,18,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
4ce1d62a-ca8c-408c-aa87-803cdfe6116a | 127,181,170,174,2,35,25 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
dbe5b1b1-0e17-4bf6-ad77-cc102ba891ed | 127,181,170,174,2,35,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
7f27a581-3392-4c90-8c86-62c8c87e5a5f | 127,181,170,174,2,36,26 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
6828f2c0-9f28-4583-9dc5-df155c61acc5 | 127,181,170,174,2,36,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
49d8e026-ce67-4faf-99b6-28ffbefcb5f6 | 127,181,170,174,2,65 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
1ceb8877-0ae0-4182-9707-22dd96b93268 | 127,181,170,174,2,73 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
fc9bdea6-6cfa-43f2-99db-4b7dc17f20a7 | 127,181,170,174,2,101 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
6bc77e5d-3b67-4e4e-b19d-53e4d3396fce | 127,181,170,174,2,188 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
75f79c09-7c1f-4bd9-b642-b25b6f11b7a0 | 127,181,170,174,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
a28e1716-7197-4fb5-aa38-3fad6e04232d | 127,181,170,174,186,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
3fb03702-f95e-4470-8b87-4c57e7860757 | 127,181,170,174,186,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
6d20dbf1-7221-4ab7-8dbf-ed7cf15eb7ff | 127,181,170,174,186,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
b9b47a13-d929-4cdb-9c97-d659f5c5ba1b | 127,181,170,175,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
48b4b54b-5c74-466a-964e-0a5e716d84a6 | 127,181,170,175,183,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
f3835675-04cf-4fbf-86dc-e111def5342e | 127,181,170,175,183,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
de38a93c-b5aa-4043-94f2-04162b8b7250 | 127,181,170,186,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
12fe3425-cf76-4b02-ba15-a03cdbac6335 | 127,181,170,186,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
82874e15-16c3-40cf-95c6-080eae610f4e | 127,181,170,186,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
738c4cf2-ebc0-4c6b-906e-f344bce4e43b | 127,181,172,173,176,179,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
c7347af0-ff91-4f2d-8899-436393800022 | 127,181,172,173,176,179,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
a75ed444-3547-418d-bc87-9915531f6056 | 127,181,172,173,176,179,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
41c7f581-543c-4489-b085-2ddd0dd46aab | 127,181,172,173,184,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
9e7421ee-aad7-4b45-8e60-93a5d8a207e4 | 127,181,172,179,177 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 2 | FALSE
1ef0256b-e013-4a29-a060-5559883db42d | 127,181,172,179,180,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
13b3b2b3-8b7d-49b5-b6de-135a38d44305 | 127,181,172,179,180,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
21f45b53-a17d-4445-b9ba-dca048560f1f | 127,181,172,184,185,178 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 2 | FALSE
722862fd-7de1-4784-8393-25fd7e4560d1 | 127,181,187 | ASSY - BATTERY PACK (2) -> ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 2 | FALSE
d1603d54-a922-4e61-83aa-62553049f850 | 128,136 | ASSY - BMS WIRING (3) -> ASSY - CONTROL LOGIC (3) | 6 | FALSE
87a6952b-dcf0-4c47-9a62-fd745d4435d3 | 129 | ASSY - BATTERY HV WIRING (2) | 2 | FALSE
69e5bb43-a632-4962-bbb0-ef42f5e736e8 | 130 | ASSY - BATTERY LV WIRING (2) | 2 | FALSE
28c56971-46eb-4009-935f-215444cffc0a | 131 | ASSY - AUXILLARY POWER WIRING (2) | 2 | FALSE
41967c12-5973-42f3-a410-ccc5c99fddaf | 132 | ASSY - DC-DC CONVERTERS (2) | 2 | FALSE
2014a381-310a-4c8b-89a3-81909c0f0a9c | 133,131 | ASSY - AUX BATTERY (2) -> ASSY - AUXILLARY POWER WIRING (2) | 4 | FALSE
1d46f9ad-f169-4cc1-a978-ca6d7d5671ab | 133,132 | ASSY - AUX BATTERY (2) -> ASSY - DC-DC CONVERTERS (2) | 4 | FALSE
4b0094e0-07bc-4473-a459-f6f6ff8065ab | 134,136 | ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 5 | FALSE
b99abb9e-c939-4823-bc26-c521174619aa | 135,136 | ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 5 | FALSE
fbc31e22-6907-4d3b-8e95-c55bd2a59591 | 136 | ASSY - CONTROL LOGIC (3) | 3 | FALSE
40a090e9-3f7c-4a84-91be-1ad691076278 | 137,187 | ASSY - ECS MODULE (3) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 3 | FALSE
9400a52d-02af-4c9c-b8c1-9bee2d77ace4 | 137,134,136 | ASSY - ECS MODULE (3) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 8 | FALSE
f529c1d9-8545-4b4f-969b-26c8ce0beae2 | 137,135,136 | ASSY - ECS MODULE (3) -> ASSY - ECS LV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 8 | FALSE
c9859324-2178-447f-a0ca-b47fa1e8df96 | 137,136 | ASSY - ECS MODULE (3) -> ASSY - CONTROL LOGIC (3) | 6 | FALSE
36990ffb-44b4-467a-b417-e443b54a8dc1 | 142,1,35,25 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
1fe558d5-9454-4001-8628-4a49cbd564ad | 142,1,35,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
13235c08-6977-48cb-8c66-e376c8f6cf34 | 142,1,36,26 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
fea01af1-460f-4d27-a7b0-5fdc8e6a515b | 142,1,36,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b73c753a-b3b7-4201-9517-decf7b2d44ce | 142,1,98 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 17 | FALSE
8ceaed71-31f4-4e8d-9870-838a6c8d0fce | 142,1,44 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 16 | FALSE
1e2d92bf-bb59-4071-bdc5-8aa3cbb3e430 | 142,1,47,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
33b5b723-1fa8-4c78-a3e6-8ec7d0974701 | 142,1,47,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2e563e67-a378-49b4-957c-fa081da5159c | 142,141,140,134,136 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 19 | FALSE
4059426d-7e38-45cc-8f5f-16ba93f961ba | 142,141,140,136 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 17 | FALSE
acf81035-7c44-4832-a3f7-92e189aaf4dc | 142,141,1,35,25 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
ce35b1cf-28df-4ce4-ad02-1192c1e3486b | 142,141,1,35,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
7120c922-9cb2-4601-a25c-a93030ea1ff2 | 142,141,1,36,26 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
321d190f-1702-4cdf-b616-fa3cd6537602 | 142,141,1,36,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
b04e2ede-c08e-4dfb-b094-0941e05a1623 | 142,141,1,98 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
ed065556-bc05-46af-bdde-549c9baa603a | 142,141,1,44 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
29fba85b-e4d6-4258-944d-3478fa37ce0b | 142,141,1,47,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
fb1cf0d2-743b-40c6-aa69-c20fb17f7a30 | 142,141,1,47,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f186249f-cd4e-469d-8661-af422e4cb7c3 | 142,145,1,35,25 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
f8e7bc72-f72d-479a-9d45-ed26fbbeef92 | 142,145,1,35,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
c4ccb1e3-c21d-4194-b2cc-4470d4db25fb | 142,145,1,36,26 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
c44715da-5e15-49b8-a438-821be7987a94 | 142,145,1,36,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
f0441f0e-d660-436c-8a2b-ce641a2ebf2d | 142,145,1,98 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
12a2d23d-00d5-47d6-ba2c-1d879fb034ba | 142,145,1,44 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
798187e9-1c96-45db-acd7-e8e04908dfdf | 142,145,1,47,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3885e95f-009a-4ddd-af4c-9950e04c4542 | 142,145,1,47,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
67b8076a-62b5-4404-8d9b-95b6fb34bab8 | 142,145,19,20 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
ebbccad6-df2a-45d8-ad40-09b32765f15e | 142,145,19,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
836b9bc1-82e4-407d-9b0f-e10e86840951 | 142,145,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
0431e5eb-55e5-4ded-a35d-012f0af698eb | 142,145,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9fe62ea7-3899-408d-b577-62d7d7101c20 | 142,145,141,140,134,136 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 23 | FALSE
d40b68b6-4db0-41a0-b6cd-f4a2205288a2 | 142,145,141,140,136 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
2e458ac2-f0c3-4b9b-8afe-e8595cc16944 | 142,145,141,1,35,25 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
8f41a348-48cf-4808-b8a5-a2339bd5d226 | 142,145,141,1,35,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
d6b585b1-e397-41de-8179-32eb467cab55 | 142,145,141,1,36,26 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
0344a30d-5d69-4c32-af72-f5770894f991 | 142,145,141,1,36,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
eabcfb5a-7ad0-49b7-b38c-cda67189b9f2 | 142,145,141,1,98 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 25 | FALSE
8720fd5a-0757-4e47-87ea-b9a3f80c8340 | 142,145,141,1,44 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 24 | FALSE
bac96bc7-bac0-48a7-a5cb-ca9c7b86ab4b | 142,145,141,1,47,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
a2437840-fe12-4715-a32d-4beb0801900f | 142,145,141,1,47,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
50a79882-ffca-4d88-8b25-2fd8589c7b0d | 142,2,16,21,22 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
b8887631-a823-4f8c-9c71-9abcb6be2d4b | 142,2,16,21,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5d53f2b2-7651-4fff-bd64-5ae7bdb84428 | 142,2,16,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
d9f57332-c871-461d-941c-bc48db0adf7c | 142,2,17,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
dd54dfeb-5fb7-425d-b33c-475db214eb74 | 142,2,17,19,20 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c3c5717a-f370-4cc2-9b8d-f5c016712271 | 142,2,17,19,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5b79733e-4c35-42c4-8508-94fbe37b2420 | 142,2,18,19,20 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
bc79fb2d-55df-4ba9-a294-b50808ec0d9b | 142,2,18,19,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9b3b5a74-aef5-4a40-b453-ef48c62295fb | 142,2,18,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
de07abe2-65f7-4d5d-8d03-9e7010d7ccde | 142,2,35,25 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
06e11d10-583e-4313-bd84-6d77b8cf73ad | 142,2,35,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2cfea98e-5bf5-4c41-9d4e-ef92c4fa7c30 | 142,2,36,26 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b29fe364-54da-4085-bbe2-0908749503af | 142,2,36,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1e832577-702b-4610-b305-b56437748256 | 142,2,65 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
dcd5c7c0-3aeb-4a0f-b75b-f8a1b67432b3 | 142,2,73 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
17a0e0eb-cabf-4d8b-b85b-cc0d8ced91e3 | 142,2,101 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
52d5644b-4c60-4147-8981-05e8cb2e6b64 | 142,2,188 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
98760435-f069-4f3a-903c-fb862f42a4f5 | 142,98 | ASSY - SOLAR ROOF ARRAY (8) -> ASSY - CEILING (4) | 12 | FALSE
83a13fb7-7db7-4420-a4ca-9670308deda7 | 143,19,20 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
e27d3b59-d660-4dd1-ad41-2f3b7d9df943 | 143,19,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2d05397d-693c-4be2-973b-7b1b15902e6a | 143,141,140,134,136 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 19 | FALSE
55a2d7db-2289-48b1-8d50-9a0d439c0a71 | 143,141,140,136 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 17 | FALSE
b87a46ed-7291-4903-bf19-333334f0d859 | 143,141,1,35,25 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
ebd0107b-1918-4738-a630-3fc147ab8403 | 143,141,1,35,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
654dcc5f-af81-4e52-a854-e5fe04fed32b | 143,141,1,36,26 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
59e7aa30-6882-484e-8f37-bde0baa5ced6 | 143,141,1,36,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
bc987953-a6e0-4f42-9545-fd9bdae67397 | 143,141,1,98 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
ba2c9200-2447-4969-82f4-c89b9d4f6782 | 143,141,1,44 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
c33f17ab-25df-452a-8b0e-9f6667ec97d1 | 143,141,1,47,21,22 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
7496e671-cd87-41d8-b00e-071b0a044d91 | 143,141,1,47,21,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b12d78f7-945e-4022-85a5-a8285b8575c0 | 143,145,1,35,25 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
340e66eb-85c3-4811-8269-88ddaa03240b | 143,145,1,35,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
80a398dd-b3b9-401f-b4b9-4ff72adae4c7 | 143,145,1,36,26 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
e604c4e3-dd65-4708-b21d-a4f5f388bd27 | 143,145,1,36,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
8435f7b1-9180-4198-a537-5024179843ed | 143,145,1,98 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
19b0807e-e3bd-4fed-90d5-1d2ad02d0f10 | 143,145,1,44 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
f84737c3-af63-40d3-be71-6d87010ae51b | 143,145,1,47,21,22 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3ce3b6d7-ab06-4f25-bcdb-7d86d06d6d23 | 143,145,1,47,21,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
38d95faf-d547-4533-ae92-1eb8a1f496b8 | 143,145,19,20 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b06f537e-ec3b-453b-9bc8-dec498b8dd6d | 143,145,19,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
b2fe2b57-24a2-400e-b83f-974a1ad19bff | 143,145,21,22 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
2b2b5c75-8016-418a-98ac-02817cbe06e2 | 143,145,21,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
138f8363-1185-46ac-9f33-f0b287bd66e2 | 143,145,141,140,134,136 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 23 | FALSE
1b700917-5e74-46ea-89f9-9b9bd8e1216f | 143,145,141,140,136 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
48c075ad-30cc-4b98-824f-8472872150b8 | 143,145,141,1,35,25 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
3939f497-3f5b-4903-8aab-e858fdb204f2 | 143,145,141,1,35,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
495d7043-74bf-4380-a6ae-891d4eb372ee | 143,145,141,1,36,26 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
60ec2c35-c3f9-466f-9ef8-ac1ac58bc958 | 143,145,141,1,36,101 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
f7bc0dfd-80bf-41ed-b38f-6bda00e75f2a | 143,145,141,1,98 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 25 | FALSE
f34def7d-a2c5-4c8a-88bf-1680019a6d52 | 143,145,141,1,44 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 24 | FALSE
d530d7cf-cf9e-4654-a967-58265d03e636 | 143,145,141,1,47,21,22 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
c8ca30fe-f722-44a1-8ca1-c801f75727a4 | 143,145,141,1,47,21,188 | ASSY - SOLAR BOOT ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
06238ea8-c8f0-4360-83ae-4797c55682c5 | 144,21,22 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 16 | FALSE
309c3821-e53d-4699-af8b-d4b0e1dd792d | 144,21,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e36a5b3e-fe41-4523-88b2-5d2dfeaa8884 | 144,141,140,134,136 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 19 | FALSE
b81520c0-513e-447f-8543-673ca45f84fb | 144,141,140,136 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 17 | FALSE
c6ac5aa6-f93b-41dc-a4c7-b291067d9f4b | 144,141,1,35,25 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
60a6ed1c-7339-4783-ba71-d6f70a180836 | 144,141,1,35,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
2e4dd56c-d401-434b-ba1a-e0dee661ed14 | 144,141,1,36,26 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
e0dbcc65-6549-46f4-85e7-aa4b5297a86a | 144,141,1,36,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
3beb1056-9eed-430a-a7ad-69dcd23a6461 | 144,141,1,98 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
1fe671b6-7179-4380-af05-63b3f204e9db | 144,141,1,44 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
f19ada20-274f-42e1-880b-19224730ba40 | 144,141,1,47,21,22 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
757e70dc-5cbb-415c-a13d-0ec1fe1523d3 | 144,141,1,47,21,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
eb4f4cac-f63c-4999-97b6-cb334e2877cf | 144,145,1,35,25 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
05d3d6f6-1009-4073-be11-84e7ea200c86 | 144,145,1,35,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
e8d2ad8a-f86b-410b-9326-fe076b5f6b1e | 144,145,1,36,26 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
afbb6568-6edd-4a59-b197-340ba2fff010 | 144,145,1,36,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
ff3d011a-099a-4c0d-9c5b-e727d4c74d80 | 144,145,1,98 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 21 | FALSE
1df24c07-5c6f-4afd-803b-94fa6ded6f43 | 144,145,1,44 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 20 | FALSE
efe8a6b7-1c36-457a-b653-0cbf63570e63 | 144,145,1,47,21,22 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
76a343f8-9cf5-49d4-8c5b-9a47faa9ed26 | 144,145,1,47,21,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
080b3806-775e-4a58-bc7c-90ab58e4e6b8 | 144,145,19,20 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
f641efb5-1967-4c6f-a11d-337db1e79da4 | 144,145,19,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
264f381c-cb53-4a0a-8ac6-3948f7e8793c | 144,145,21,22 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
a91c6b26-ae55-450a-ad3f-0011ec9db63d | 144,145,21,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e3e6a29d-430d-4e89-89e5-e597ed6acc42 | 144,145,141,140,134,136 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 23 | FALSE
5d338f63-ddef-47ec-92b5-3d735f6cdc54 | 144,145,141,140,136 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
ef64b822-6f3d-4989-80af-dd4384ff1ca2 | 144,145,141,1,35,25 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
110adad2-0f06-41f1-a55a-e220c15c2bb0 | 144,145,141,1,35,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
902f8091-8d4e-41d8-a388-0ff982c9232a | 144,145,141,1,36,26 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
b1751ff5-7323-4a41-9bf9-bdd271fb2911 | 144,145,141,1,36,101 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
8ce07def-ada6-44db-b400-e35d82a501fd | 144,145,141,1,98 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 25 | FALSE
c19e5a8e-797a-4bc5-9803-a3aaaf1c4bc0 | 144,145,141,1,44 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 24 | FALSE
1ccb48fe-c474-407b-b0da-91e4cd3e630d | 144,145,141,1,47,21,22 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
c3bbd339-447c-487b-aa36-dd739343ed99 | 144,145,141,1,47,21,188 | ASSY - SOLAR BONNET ARRAY (8) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
ca3db8de-1065-4358-9b8c-d2095fea97bc | 168,2,16,21,22 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
f85ce0ce-8632-4d04-bdb1-0eaf415d7314 | 168,2,16,21,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ea60d1f8-0b55-4f7e-b8f3-e53e13030ae1 | 168,2,16,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
12a755a9-3f23-4a00-ae91-35badf388300 | 168,2,17,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
7e37caf4-71c0-44f8-8910-87119db19483 | 168,2,17,19,20 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
0f82384c-8232-419e-a078-832ed52fc080 | 168,2,17,19,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
15f1af5a-6968-48f1-9b05-eb6056e22cf0 | 168,2,18,19,20 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
b87c08ca-5eba-4356-8fe0-25a04db47b7f | 168,2,18,19,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
50fa166d-c398-44f2-852d-9b8530b308a0 | 168,2,18,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
188899f5-c372-4cfe-b611-43209fdba959 | 168,2,35,25 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
84e6d6b8-6c01-45d1-bd3f-26705228b836 | 168,2,35,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
b1c875fe-f49f-4980-9908-869ef0a0c46d | 168,2,36,26 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
5bbe2f22-2682-4de1-aac0-7edc33ca3fcf | 168,2,36,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
b519f494-3268-4a20-81dd-c18ad84517a2 | 168,2,65 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
7081ad2d-4500-4bfa-93bb-592ce4626600 | 168,2,73 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
439a262f-51d1-478e-8017-b57cc876d16e | 168,2,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
7f9bdd3e-691f-45d1-be01-168d7b0846d5 | 168,2,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
305599ad-2df4-41cf-9b37-06114b13c6fc | 168,170,174,2,16,21,22 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
b519674e-4a88-4ef5-8a86-e06376c21686 | 168,170,174,2,16,21,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c58ba877-2607-4846-a6b5-5f29c38b5a1c | 168,170,174,2,16,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
9f053a8c-ccef-44b6-b830-4fdb6d34c487 | 168,170,174,2,17,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
1b89577f-31dd-478a-bfd5-07ab7ab4ceb3 | 168,170,174,2,17,19,20 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
84b6af56-bdc4-4810-9878-7567d2e55e37 | 168,170,174,2,17,19,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
9da3cf49-0a48-4ae0-82e6-cc68360a7dbf | 168,170,174,2,18,19,20 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
43a0b89d-41fa-43ab-b86c-03e47bd6a6de | 168,170,174,2,18,19,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
123f026a-4cec-4704-b779-3eaea73ffd5f | 168,170,174,2,18,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
f0ee7298-651b-42b7-a614-bfee99922733 | 168,170,174,2,35,25 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
c1103159-66c5-4a20-86df-4225aca92eb5 | 168,170,174,2,35,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
4a3f3d71-b3b4-4822-8e27-a8d412461fe7 | 168,170,174,2,36,26 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
f08d1192-2605-436e-af41-5215aba03266 | 168,170,174,2,36,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
83a5643b-4815-4f84-837a-05fa48e7634e | 168,170,174,2,65 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
7542f211-9156-452b-a8c6-3217bb4c95d1 | 168,170,174,2,73 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
2f6ffe94-1f18-44db-b8ce-d51ae2131278 | 168,170,174,2,101 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
a967dce4-48a5-4050-b97d-7dbd481228d5 | 168,170,174,2,188 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
0df04d60-b319-4556-aa44-f59753c86923 | 168,170,174,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
a447c6ed-9e05-4b90-bd08-ceaf1e50619d | 168,170,174,186,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
e7510e0a-32e9-4ac1-9d3d-7af082c90a86 | 168,170,174,186,180,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
0ca09dde-a428-4037-b22a-274b1f8ff746 | 168,170,174,186,180,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
0875095a-abeb-4319-8556-af06acc03688 | 168,170,175,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
a8354fa0-bd0f-4d0b-940a-284a3912fdce | 168,170,175,183,177 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
982eb0cf-7f56-4803-a8a2-5049bfcb3e1c | 168,170,175,183,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
61315382-299e-437b-8a58-7d5b0a5e6ffb | 168,170,186,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
3a49f106-cda7-4558-8a51-6e6ef9e4173c | 168,170,186,180,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
46264454-413a-4955-ab2e-5a990c8d1d4f | 168,170,186,180,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
a85e3102-c34e-4b61-ae84-66395bbd8bc0 | 168,171,172,173,176,179,177 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
1d1a5ad4-96a8-4f6c-8e06-c7f23e65c84f | 168,171,172,173,176,179,180,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
fea98991-44a5-4561-a724-06c45abc6a7d | 168,171,172,173,176,179,180,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
784be627-6193-4428-bdb8-4257e1ffa7c3 | 168,171,172,173,184,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
f45f2362-5647-4b9d-a5c6-c6e5350ff5e4 | 168,171,172,179,177 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
1fd25161-d6e7-42fa-a60c-5aac15890ee1 | 168,171,172,179,180,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
4fa72159-fb2e-484b-9ecd-18fe4abbe3c8 | 168,171,172,179,180,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
81bb8fd2-db5a-4c90-8054-2b7729868885 | 168,171,172,184,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
d38b6c78-a1a9-43cd-9730-473af2d178e1 | 168,171,179,177 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
8e52aeca-d84c-4182-9ad5-8632bfa696f0 | 168,171,179,180,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
538543ff-eb3c-42fa-95a3-8b29bbde391b | 168,171,179,180,187 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
8bda3643-b78b-4f40-9f13-cb97d2a4c3e0 | 168,171,184,185,178 | ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
cb706673-e90c-4025-9971-a44598a867cc | 171,172,173,176,179,177 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
83912f46-82cc-4f1c-ae2f-0ea1f6ecf51b | 171,172,173,176,179,180,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
21ecf54e-12d5-4ad8-9356-2dd17ad6ed97 | 171,172,173,176,179,180,187 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
a766a924-e270-4304-9064-7fcda6f1f9d0 | 171,172,173,184,185,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
232e6669-d544-4c0f-b77c-14f17728e091 | 171,172,179,177 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
c18484e6-3725-42f9-a7d4-6a4e8beda72c | 171,172,179,180,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
f20be251-ac69-41f1-844d-2c5e06bf6141 | 171,172,179,180,187 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
0821d6e4-5dad-4d96-b220-1bcbd7d68960 | 171,172,184,185,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
3848c9cb-7a74-48cf-b647-4e9d1a9f2468 | 171,179,177 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
5b6cf579-7e16-4c19-9380-62326ed3e577 | 171,179,180,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
3496b671-7fc6-4d35-8e3a-100a7ac50a72 | 171,179,180,187 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
5151437e-0ba3-4367-a359-19792c519020 | 171,184,185,178 | ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
9aed55b2-6c5d-444c-b1cd-28b9d044368a | 172,173,176,179,177 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
e6210b4d-5a19-496d-8315-20d7f50ffb9f | 172,173,176,179,180,178 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
4cc80d59-200e-45d0-8bdd-9e12b05a33a1 | 172,173,176,179,180,187 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
feea19f8-1dda-48db-bb6f-741e1a27d0ab | 172,173,184,185,178 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
c9e9543c-5057-457c-ba21-5a42e64f8643 | 172,179,177 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
9c17f1ee-bddd-40aa-a5b1-44a32cf7df82 | 172,179,180,178 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
0162b530-f5d3-4ce9-911b-58db0c1ec28d | 172,179,180,187 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
55722eb9-4004-46d0-9619-ff716c9260ef | 172,184,185,178 | ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
ae33a582-d016-47cb-8d8a-07d7515ff631 | 173,176,179,177 | ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
d2d56214-8b3a-476e-af51-873465b35174 | 173,176,179,180,178 | ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
df413c1e-57ce-4846-aa65-be6700a3b8e7 | 173,176,179,180,187 | ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
29e5e06d-1790-41a0-ac4d-20a6b4f8f834 | 173,184,185,178 | ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
26c43e97-3edf-4c2f-a4b2-25c5a6561108 | 175,178 | ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
b2beaca0-e878-42c1-9d51-2a59c7ac000d | 175,183,177 | ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
1604f1eb-8433-42ea-a358-2bfa8a7e8ae6 | 175,183,187 | ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
2c624949-6bf6-4a7b-b806-6a3222ead557 | 176,179,177 | ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
fc349eef-7aba-4857-b354-f8d10aa1297b | 176,179,180,178 | ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
dd97adc4-ee67-4e09-be35-4a9420f3fd63 | 176,179,180,187 | ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
662f6a2e-8085-4093-ba30-1a1b998dfa8c | 178 | ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
4e4fedb0-b97f-405d-97df-e946a5b3796d | 179,177 | ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
ffb69dc3-9ad6-4a22-8e90-286d48ffb934 | 179,180,178 | ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
d34e1247-81eb-4d98-9f9d-6004247b3121 | 179,180,187 | ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
bb995ec7-09e9-4e21-8b89-6d87425772f0 | 180,178 | ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
437b0496-5845-4c81-b341-d7812ed980e9 | 180,187 | ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
dda6a863-40dd-4e22-942a-4a650bfc717b | 181,173,176,179,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
b0eac093-097c-4be5-9ca8-d5a2ae7ff939 | 181,173,176,179,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
c8449d75-56c0-44d8-9889-72b82af69c5f | 181,173,176,179,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
26eed5c0-4694-41d0-97d5-7d7b094cb0d0 | 181,173,184,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
e547ba0d-d708-436e-94e4-a9659589217d | 181,176,179,177 | ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
9ded8917-76ee-407a-b51f-6d0636fd8c34 | 181,176,179,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
626efe3e-4fb4-44f3-810a-a42955fbd4f3 | 181,176,179,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
2349b48a-d20b-42f6-97e2-7096855fb529 | 181,179,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
21a22eaa-c96b-4cdb-aeae-e6fc8be2513e | 181,179,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
ca9ae6d6-6eea-478d-b474-8caaee2c2a2e | 181,179,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
0acbf564-a688-4672-9da7-1c48ffd3bd91 | 181,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
d46f7bba-e0e2-4a12-8c4a-1e24c07d8687 | 181,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
ec2288a0-2567-417c-86e4-5a7e07186eb8 | 181,182,12,2,16,21,22 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
59fad522-6371-4ddf-aeb1-7f19b9a4b930 | 181,182,12,2,16,21,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8c2adef1-b88d-47af-86bf-7688705de1b9 | 181,182,12,2,16,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
f98cd85f-d8ee-4998-8e0c-c2d3cd0670c5 | 181,182,12,2,17,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
969f4e8f-f4c3-4f70-9d46-2812b6393eb5 | 181,182,12,2,17,19,20 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
b971bc3d-15b2-4e6b-95f6-aaf8f6494126 | 181,182,12,2,17,19,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a4a654b3-84bc-4555-af0d-28c695e2d423 | 181,182,12,2,18,19,20 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
cb797576-d3f9-40cc-8a5d-f4c963a91cd4 | 181,182,12,2,18,19,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e78aa52a-dc0d-4723-8e28-160bdb8da60a | 181,182,12,2,18,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
4f17cab6-9389-41fb-b1d7-873b10bcfe11 | 181,182,12,2,35,25 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
c0f385d9-4165-4586-9bc1-2caa1fd008d7 | 181,182,12,2,35,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f2625a61-eaa2-424a-83c8-0c33136a252b | 181,182,12,2,36,26 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
cecd34d1-db04-42c0-af02-2ad09ba7d56c | 181,182,12,2,36,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
1e5ae6b2-aab1-4d66-b900-8697eac6a55e | 181,182,12,2,65 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
c40ae394-357f-4e53-b79e-0e83e89594c2 | 181,182,12,2,73 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
23ea5b23-42e8-4378-bd06-fbe6bfcf34f3 | 181,182,12,2,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
9354ce5e-340c-4774-ae41-c06df4e7f2b5 | 181,182,12,2,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
4bd1b14b-6726-4ff4-8013-57dff979e699 | 181,182,183,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
c931f879-55a3-4432-bd58-fd06002fc73a | 181,182,183,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
81c97ad5-ce73-4690-bade-20ded90586b6 | 181,182,184,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
7c85e175-f48f-48dc-9e83-beec8ef4ae1f | 181,183,177 | ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
414f22b9-0403-4315-87d8-a3d9e55a1cad | 181,183,187 | ASSY - FUEL CELL STACK (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
800441e7-60d7-47b3-b5c4-1aab8a99f05f | 181,184,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
32d5c7c9-6fb6-4c65-be0f-3d3e1483ebe6 | 181,170,174,2,16,21,22 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
78612e57-af56-4cd2-a5e4-096dc729200c | 181,170,174,2,16,21,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
764d5275-4696-44ae-a066-be33ba7a95f2 | 181,170,174,2,16,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
5ec3d2db-f699-46fb-bbd8-1cef21604040 | 181,170,174,2,17,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
9d2e6ce0-45d1-47d8-ae25-b37a31a640ef | 181,170,174,2,17,19,20 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
49c5f9af-75f9-431a-9141-0ae6ba366b65 | 181,170,174,2,17,19,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
4c1c5608-15a5-4997-879c-dba05e3ae405 | 181,170,174,2,18,19,20 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
c494f9dc-8f8c-4544-a28c-8ca5d5ec60ef | 181,170,174,2,18,19,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
f7895fb5-509a-45aa-a031-64b762abc140 | 181,170,174,2,18,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
35466f9c-1a52-4574-9ec8-1b8fa64fef74 | 181,170,174,2,35,25 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
fc5d2cdb-0d0c-47fa-889a-a18970f6d164 | 181,170,174,2,35,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
2f3c57b1-0c0c-45b2-9239-35908e4f6976 | 181,170,174,2,36,26 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
dddfbfd8-3662-4c74-84f3-d7d9ef220b17 | 181,170,174,2,36,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
3d7870a4-b6d6-42fd-9823-e96d956aa931 | 181,170,174,2,65 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
b4a5bee7-5efc-4adb-9bd8-9f6231b8df9e | 181,170,174,2,73 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
92373c4b-b286-4543-a58d-0fffc78937d3 | 181,170,174,2,101 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
92c9efbc-9aa4-445b-b74e-f7b87148f4f9 | 181,170,174,2,188 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
d7d96cf2-436a-4020-addd-9e1ec9797233 | 181,170,174,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
9d3a5bb4-6a10-445e-9b19-144715f6bff3 | 181,170,174,186,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
bf8391bf-d862-4980-adf3-be58f6687abb | 181,170,174,186,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
f9601cd9-51fb-4ac9-acae-c59bbd5c3f1c | 181,170,174,186,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
bb585658-7e07-420d-9924-e1b80acb0411 | 181,170,175,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
3a89d4e0-d113-4cee-81d9-b1c348a5593b | 181,170,175,183,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
26474988-41c6-430b-8291-2ed4f84c7745 | 181,170,175,183,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
f129e0a1-5ec4-4e1d-b5e4-48033a66d154 | 181,170,186,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
2a438990-b02a-4f43-8b5a-1b61f0079735 | 181,170,186,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
18c169bc-ba89-482e-ac69-c23a10fbc45b | 181,170,186,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
46426adc-cef2-4669-9d01-42d5b59e5c16 | 181,172,173,176,179,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
9ae3df90-467a-4dca-9d9b-0c584757c48c | 181,172,173,176,179,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
6ecc3bf1-a402-4995-80fd-e2f9c6b6d6f1 | 181,172,173,176,179,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
a2a06979-3dbe-48c5-b14f-3560dadc98e5 | 181,172,173,184,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
fe1e6e0f-2cd0-4f78-853b-e5254d99f569 | 181,172,179,177 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
401ea8a6-00e0-4b0e-9faa-0339ef3092c3 | 181,172,179,180,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
68e1028c-ed6f-4a06-8a3a-535b9a49dc1f | 181,172,179,180,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
a6a13f21-ba45-4fb3-b6b0-1113044154bd | 181,172,184,185,178 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
357ed5b0-5382-4e26-b84e-4622c74a5a59 | 181,187 | ASSY - FUEL CELL STACK (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
ac0033b9-5b2b-420e-a0be-e4a1bd53b5da | 184,185,178 | ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
7b85e406-98f3-4a91-9724-0e50758f436d | 185,178 | ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
78867c6a-0b27-4bfe-832c-6f3f7c4a18a3 | 187 | ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
feb3808e-a948-4797-a2b4-1dda81a1ac45 | 190,188 | ASSY - MAIN COMPUTER (1) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 3 | FALSE
67e25598-9422-4878-acfd-83e5c5d8defc | 5,2,16,21,22 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
c21061e5-c113-4c87-a855-5ad7bb9f016c | 5,2,16,21,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
dc48660d-bdaf-49c4-8128-05f85105eb23 | 5,2,16,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
046a2292-9cf0-4574-b3bb-402dfa4030b4 | 5,2,17,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
db709261-c3b2-4741-b82f-4f3c9723b6d5 | 5,2,17,19,20 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
62a6bf75-fdfc-4aab-922d-f841109d841a | 5,2,17,19,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fbd2514d-a6a7-42c5-b026-404d26eb6038 | 5,2,18,19,20 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
66192022-a495-41b1-bbc3-40d1aaf393a4 | 5,2,18,19,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2a69ff4e-342d-44c6-ae7f-bcd77857b03d | 5,2,18,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
626663c9-8cf0-4adf-a117-f8ed4c1ce9bc | 5,2,35,25 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
140cf40f-8132-4923-b369-612e62555285 | 5,2,35,101 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
db8539ec-776d-4bd6-873d-0aa649d79223 | 5,2,36,26 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
eb1e72bb-446b-4b35-b88a-a76dce78a5e6 | 5,2,36,101 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
86b3c838-0958-4729-bddd-0f3f3d038b57 | 5,2,65 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
381c515e-bf7c-4cc9-8a3d-6ad0f4a04307 | 5,2,73 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
e443e8eb-1e5d-4509-b68d-85a85193321c | 5,2,101 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
6e98d10b-0781-4e64-8810-303e24f6265a | 5,2,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
aca25fbd-5975-47ba-b42b-0170a7df0923 | 5,188 | ASSY - REAR CRASH STRUCTURE (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
bd7b91a0-0c67-4a66-afd0-7e254186a381 | 37,27,1,35,25 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
7dd6362a-8c83-46d0-ada7-a43f5d4d8054 | 37,27,1,35,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
5da8fef7-9559-43d7-9e95-1fa74edf7fee | 37,27,1,36,26 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
5fdfd717-8352-47c3-bad9-f51f2509ba00 | 37,27,1,36,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
4c071f0b-ed9e-4e31-a134-2218e6586c80 | 37,27,1,98 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 20 | FALSE
d3640639-8867-468d-a476-b043bce52616 | 37,27,1,44 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 19 | FALSE
5d9ec0ba-e7be-48ed-98d2-25d9d0ee868b | 37,27,1,47,21,22 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
3d3a319a-7b4d-4e74-af9a-91db498f8239 | 37,27,1,47,21,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
f5280a5b-30db-4b08-9b21-7c84cbbd2aa6 | 37,27,16,21,22 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
6899125e-2942-4575-8521-5faa0a79e309 | 37,27,16,21,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
fd4a46cc-131b-4db1-a33d-d0778c5ba352 | 37,27,16,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2de3b10a-05b2-4cfd-b6e8-ca8a58501013 | 37,27,33 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 16 | FALSE
53700ac1-8d4a-44c0-8b8e-f6c898b50f2f | 37,27,35,25 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
2be5590d-09a7-4e5d-bb01-19c41344cb85 | 37,27,35,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
70da9484-5b8b-4493-b489-612bac6d9571 | 37,27,15,2,16,21,22 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
6edb6b48-bd3f-4858-b39b-67de12fbb246 | 37,27,15,2,16,21,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
115c1451-5965-4f80-9e73-21dd80b73f7d | 37,27,15,2,16,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
c0b3ad2d-2dae-449c-92e2-6b89b02fa1a2 | 37,27,15,2,17,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
31a690ec-1777-4637-a68f-719c54290f13 | 37,27,15,2,17,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
45b76209-c53a-4d76-be2c-267bf09f8ed1 | 37,27,15,2,17,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
6b2ea645-390f-4f9e-9e27-c8d1771cc64a | 37,27,15,2,18,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
b140844e-37c4-41b2-ad34-515d830c3f60 | 37,27,15,2,18,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
7c8caff7-0dd8-4ae0-bee3-5394b42c47cc | 37,27,15,2,18,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e9da7c25-272b-46f5-816e-424a56c29f22 | 37,27,15,2,35,25 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
62ca75cb-c8a9-483d-a18e-84310b8442d1 | 37,27,15,2,35,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
ceeeab6c-5760-4b99-8540-4b8dbb9aa1e1 | 37,27,15,2,36,26 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
5f3fa5a1-ce34-4452-9290-249b0aba32fb | 37,27,15,2,36,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
062146f9-8864-4540-a7b0-69b392c9fd05 | 37,27,15,2,65 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
6d1f494a-7ab0-4380-b632-55a540934065 | 37,27,15,2,73 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
3fcdf0ae-be76-436e-8ce2-f4ee4d0cf0be | 37,27,15,2,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
9ef87000-b7c9-437c-aa5d-5c751a8bf5f4 | 37,27,15,2,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
5ca16475-468d-4c7b-a256-af4df86ae74c | 37,27,15,13,17,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
55c194cc-90d0-44dd-9d2f-521a69945546 | 37,27,15,13,17,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
62d7b396-e149-4af0-903f-3fa435b98fbe | 37,27,15,13,17,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
3a35a18b-438d-4b62-afe7-158bff961c96 | 37,27,15,13,18,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
e077bf11-abb7-4493-a221-e0ab3a837d65 | 37,27,15,13,18,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
9a7c6014-056b-4e7c-8022-192a738141d8 | 37,27,15,13,18,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1dcc0e38-466e-4ea8-8dc2-a6da175159b3 | 37,27,15,13,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8b6bfd75-bea0-4b43-87bc-04aed1e7ecf3 | 37,27,15,17,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a1b3dd18-3ac1-44ce-809f-dada800aea3e | 37,27,15,17,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1a04818d-b84e-485d-9ac9-e1b9de57ebea | 37,27,15,17,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d76b686a-39af-46d8-9c64-a3096ac09805 | 37,27,15,18,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
f0212418-ac02-4774-be39-e092c1014228 | 37,27,15,18,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
13be26f6-344a-4aba-bbd0-ac273d726df8 | 37,27,15,18,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
cc3cf044-8477-43a5-82e7-fcee74fd6fd7 | 37,27,15,19,20 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
940c0a90-9d3c-4e86-96d1-e6bf290eb284 | 37,27,15,19,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2338c132-c305-4197-a3c3-4de3733b6bc5 | 37,27,15,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
32889716-46ee-4967-bf5e-8cd4c360efa2 | 37,27,15,23 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 15 | FALSE
eed53071-5cc5-43d9-a10f-fc152f6c007d | 37,35,25 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
065da9e6-555d-472e-a7c2-7451f13cd7aa | 37,35,101 | ASSY - DOOR AUDIO - RH (8) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
d198b437-8074-4278-8806-f3c4321ca1e3 | 37,167,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - AUDIO CONTROL SYSTEM (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ada754fa-f6cc-4890-a6ce-72c5f61e57d4 | 37,188 | ASSY - DOOR AUDIO - RH (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
d43298ad-aec6-4c7e-a937-c1f0bd7561c6 | 38,28,1,35,25 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
b9c82522-36b1-4486-8637-9ffcf03d1d5a | 38,28,1,35,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
253f0311-7e36-49ec-9d43-7a82d16a3248 | 38,28,1,36,26 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
49e8a82f-ce24-486a-b0fe-6a476dcf0aef | 38,28,1,36,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
b75e5c16-e24f-417b-b268-9cabae4773a4 | 38,28,1,98 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 20 | FALSE
e7a5a458-3b86-47dd-b78b-2bdcb35604a2 | 38,28,1,44 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 19 | FALSE
8bda8bc3-dcd6-4ade-af62-5533282e6475 | 38,28,1,47,21,22 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
7a0659f0-77e6-4fd5-8f64-d788425db470 | 38,28,1,47,21,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ddc3d240-7f94-4f6e-9f04-b2501ec4edcf | 38,28,16,21,22 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b951b99d-7906-4160-9a63-76b59415bdc7 | 38,28,16,21,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
848b2e85-d8b0-4c37-98dd-40653069c13c | 38,28,16,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2ebddd9a-60bb-45ad-8498-505820dd98d0 | 38,28,34 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 16 | FALSE
a1fd2f4a-788c-4f77-89b1-0c3f5731cf36 | 38,28,36,26 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
7f487366-a0a5-45a9-b3cc-b513f949b5fa | 38,28,36,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
445ae817-a1cb-436f-af82-ed2d1fe531c6 | 38,28,14,2,16,21,22 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 33 | FALSE
cbf39c0e-7008-421e-8289-1c365c81f79e | 38,28,14,2,16,21,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
24c24cf8-f3f5-4105-97b3-bf1c9cf9d36a | 38,28,14,2,16,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
9517c278-eeb7-4b70-9fb2-a72be0f58905 | 38,28,14,2,17,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
25b17f1e-9bb2-44c9-9762-c8caa138f61e | 38,28,14,2,17,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
1b4007f1-cd1d-4348-b0ae-0a969cbb37c9 | 38,28,14,2,17,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
2b0bd4c0-be83-4461-8e41-c5ecb9784cf0 | 38,28,14,2,18,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
2e40b289-2223-4387-b903-a5e54ec666e9 | 38,28,14,2,18,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
26986199-ce68-4f27-ae47-faa944096784 | 38,28,14,2,18,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
522f7ba9-5e62-40cc-8143-7e29bed81b89 | 38,28,14,2,35,25 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 23 | FALSE
f8ff4131-baea-4cf6-8f1d-0cd04ab85a79 | 38,28,14,2,35,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
d5e869ba-af43-4409-a803-7c5f4ba4e388 | 38,28,14,2,36,26 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 23 | FALSE
38aee540-17d5-4d53-b7e7-9df59b4a0a63 | 38,28,14,2,36,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
d650569a-54fd-48e1-ad59-77249c83279b | 38,28,14,2,65 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 20 | FALSE
dec51cc4-c900-4ef6-98a8-92116e2e887a | 38,28,14,2,73 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 20 | FALSE
42bb5b64-b016-4432-8e6e-f22d58e15883 | 38,28,14,2,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
363fea6e-1886-43a0-814c-be7441605273 | 38,28,14,2,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9905fd2e-ea71-4aac-8fae-cec897d43941 | 38,28,14,13,17,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d6b4cd41-1255-4114-b146-819e29fe95ca | 38,28,14,13,17,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
235afe03-7e85-4109-93ec-6003d4a38cd3 | 38,28,14,13,17,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
a42a19dd-fe9a-4bde-9eb3-99fd2a146f4c | 38,28,14,13,18,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
90c786ff-7d3a-411d-80c5-ce397f9a6dac | 38,28,14,13,18,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
2be50e69-ed61-4a9f-932d-6034b22c82e8 | 38,28,14,13,18,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
ff99c92b-7e93-47d4-9803-026a69e1042d | 38,28,14,13,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8eee9b10-61d6-4a15-b8d5-76890aed6a41 | 38,28,14,17,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
90e2e8e6-e13f-4026-8bda-623f50238d48 | 38,28,14,17,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b87545d3-6743-4bb3-97c6-a38a9571566f | 38,28,14,17,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
169c1971-87cd-474d-9b73-840941245ca2 | 38,28,14,18,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
c4949990-83df-49f5-8fd3-977eb4458cbb | 38,28,14,18,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
280399ae-3bc3-4694-90bc-2c9e758d4f2e | 38,28,14,18,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
800f2d23-68fe-4340-a4b0-fee6a65938c1 | 38,28,14,19,20 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
9b8f045f-0d62-4d57-984f-fb527d0232ef | 38,28,14,19,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ddf8ed66-e5d6-4f10-aedc-450f54483b6c | 38,28,14,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
b4fe27ff-6bce-4d4a-8661-52c3c890cd01 | 38,28,14,24 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 15 | FALSE
043e29d6-67c6-4457-befe-6e412d91548d | 38,36,26 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
c0a1761d-3e43-4f88-a035-968a730de6a1 | 38,36,101 | ASSY - DOOR AUDIO - LH (8) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
cb9f1919-cae6-467d-bf9a-dd144ba8500a | 38,167,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - AUDIO CONTROL SYSTEM (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
dbbaa0aa-a24d-4c45-8bfd-3f6cbc3f5051 | 38,188 | ASSY - DOOR AUDIO - LH (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
a7e1367c-2f79-4a6f-8ad0-5a8ae9b67bcc | 41,6,16,21,22 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
2edce3e5-b868-401a-ae6c-db806efe7b81 | 41,6,16,21,188 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7985f41e-2289-43a1-8f67-70d4453ce444 | 41,6,16,188 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9a81ba4a-0496-4bcb-8bea-adaffd62e3d8 | 41,6,188 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - CHASSIS VENTILATION (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ebf5410e-7faa-4f52-baa6-dcaadd87a48a | 41,16,21,22 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 18 | FALSE
7214921b-a40b-4d9f-aa60-aa439da84817 | 41,16,21,188 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6e3d67fe-f76d-48b5-b204-957a02ab27f0 | 41,16,188 | ASSY - ACTIVE AERO FRONT RADIATOR FLAPS (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
e6355c32-e425-4008-9764-367050a14cc7 | 42,43,16,21,22 | ASSY - ACTIVE AERO MOTORS (2) -> ASSY - ACTIVE AERO CONTROL PCB (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
954c1582-f7b6-414d-b4af-f44333171eff | 42,43,16,21,188 | ASSY - ACTIVE AERO MOTORS (2) -> ASSY - ACTIVE AERO CONTROL PCB (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c157d542-0f96-4b69-8b09-03983cb491c9 | 42,43,16,188 | ASSY - ACTIVE AERO MOTORS (2) -> ASSY - ACTIVE AERO CONTROL PCB (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
a502698d-52e9-4616-8504-c08a9d7d7268 | 48,2,16,21,22 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
12dee54f-3918-4a00-b06a-e8753c3c9da0 | 48,2,16,21,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c949a7a7-26c2-4e3c-bd70-c17e05f8ddb6 | 48,2,16,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
98caf467-3ec9-4564-8a76-41a46353b1b0 | 48,2,17,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
b5c9038b-2348-4a2c-b593-020046b4bd9f | 48,2,17,19,20 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
65f485fa-8ae1-4b72-b9dc-a704dc1f05cb | 48,2,17,19,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
f7584f32-3440-40a4-9076-602dc1cadb45 | 48,2,18,19,20 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
34f2f4e9-d685-4804-a076-5d636baedf6a | 48,2,18,19,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
ea5fb005-aff7-4056-86bd-4f6ad8848e72 | 48,2,18,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
42d1c2ea-8a1e-4da4-8cc7-81dae21cf658 | 48,2,35,25 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
cdff9adb-cfc4-413f-aa65-75e2e8181f5d | 48,2,35,101 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
dcf8dec4-0908-4f9b-bbaf-095c3a73af7b | 48,2,36,26 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
f80065c3-d35c-4537-bf9e-6b35c5a15bcf | 48,2,36,101 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
be70c4e8-eb62-4242-af91-556a34953692 | 48,2,65 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
dd70cc5d-9429-42b2-9784-40f839d5a0a4 | 48,2,73 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
9b91c836-dbb1-4662-bc2d-213ccaff5983 | 48,2,101 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
8091a251-385b-46ea-8bbc-307befa9c97b | 48,2,188 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
810f5bf1-eb9c-44a0-b315-447c6ffb301e | 48,49 | ASSY - WINDSCREEN WIPER MOTOR (2) -> ASSY - WINDSCREEN WIPER CONTROL PCB (4) | 6 | FALSE
87b358ce-18c2-41a8-b746-6559c781ec38 | 60,50,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
4e885c85-14d7-480d-88dc-7b1a40ddf36c | 60,50,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1c69d9fb-d03f-4765-8619-7d2041ffc60d | 60,50,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5a1595eb-10f6-4149-9871-dfefc8d647b1 | 60,50,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
bf87d2d9-77b7-4245-a6fe-248f02296c9e | 60,50,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
96105e33-7318-4ead-8dc0-364cbdaf13e6 | 60,50,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
d0872282-46f5-4157-b169-25351572eec5 | 60,50,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
686195b1-3b06-495f-96e3-d01c127a8bf8 | 60,50,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
abe3f06f-1fb9-47a2-8401-da268f7f707e | 60,50,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
269e455d-b137-48da-917c-74574e79a538 | 60,50,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
a1a67947-d5f3-45e5-b511-19ae9fa06ced | 60,50,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7c4c477b-ba4f-4abd-86e4-a33fd63c2064 | 60,50,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
4353bd84-6ad8-43b8-8c68-776d8badcf6e | 60,50,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
8272201d-17f8-4367-b7cc-7a9f5903c0b4 | 60,50,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
af71b180-eb39-426a-a7be-a65420cd332f | 60,50,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
3ddabcb3-84f7-4c89-b199-7eedd68f0daa | 60,50,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b6690eb2-ace6-4e98-8592-0f74bf2d5846 | 60,50,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
fc6e9d87-699a-4a44-b0f9-36f2820b3459 | 60,50,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
459636ac-e604-4c62-95e8-e6ba59f8ee28 | 60,50,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
12816484-627b-43f3-8e5b-c07d85eb05c0 | 60,50,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
f3d3d9da-fe9f-4e7f-b697-6e5f66c3526e | 60,50,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9538d091-e0eb-42e5-8ccb-fe3bd7030535 | 60,50,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a05cc161-9643-4312-9f94-8d0d65a4a65e | 60,50,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8bf36e42-ff04-4ff9-a280-9f0adc78bd7e | 60,50,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ab6f0240-a616-414a-961a-66074ff6c9c4 | 60,50,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
066da1a4-c30e-4b4a-a071-5470a479c2d4 | 60,50,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b06151ee-59c0-49b1-afac-ad6117fc8bf7 | 60,50,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
44659801-a206-4d62-afd8-adff638bf71b | 60,50,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
7aeaf4d4-85a4-4351-88d9-feaba3a8dd87 | 60,50,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
55df2182-bc45-4d6a-ae4d-4e38a7c0c7da | 60,50,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
246268f4-71a6-467d-973b-e0fb87724d35 | 60,50,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
70e86faa-4185-42bd-8080-d9f29f5cc8b9 | 60,50,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
281bb959-1737-4e10-a3dc-ee858be5cfa5 | 60,50,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
5ee0efbe-780b-4888-bdc9-325f8ca9fb68 | 60,50,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
2ed61d9a-5565-49f6-8bf7-bb3b0c622dfb | 60,50,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0ba81e91-a6b7-45db-982a-796462cb74a7 | 60,50,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
64622bc2-fee0-4682-b712-352f41691def | 60,50,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
33b39b63-f15a-4888-9b9c-0706643b887a | 60,50,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
37e9f5c7-4c23-4fe3-bb37-787464744cc0 | 60,50,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
213ca5b2-4d6d-47ad-8c40-8c7e1f1b3218 | 60,50,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8a55000b-7a88-43b8-a7f1-2f5d7ad5336e | 60,50,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d154ae3f-70fe-4945-96dd-1f7aefc170a6 | 60,50,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
da16a407-2f5b-4f4d-883a-f52ac3bb2a4d | 60,50,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a34d4d65-79de-40dd-882d-04638acef412 | 60,50,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
db7c46a8-7141-471a-bb4f-041a33991bb6 | 60,50,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ef9473f8-6e9c-441f-aa45-ef53b91206aa | 60,50,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a7926c00-7832-4f72-8686-f53d97ec217e | 60,50,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
89646883-ccd8-45f3-b54f-0c5608ce52ff | 60,50,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
cb84f581-62e0-4a3d-9a44-2a4d48c2a647 | 60,50,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f9a02631-8ecb-419f-89a3-b78366cf7349 | 60,50,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
13e96151-a259-4bf0-adc1-0a9b354503fd | 60,50,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
75bff988-0f3a-41ad-b1c6-e52718857d91 | 60,50,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
1e6f2dfc-b238-4e70-892a-18e6d98a024e | 60,50,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
fed0cd5d-a157-4826-88b5-4f04449f3625 | 60,50,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
bef9d3f1-3417-48b7-9201-f2808c00858f | 60,50,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0328ef35-e189-4c89-8103-c164a90a323b | 60,50,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e6d4c4d6-d5bd-480c-84c2-07982fd208c0 | 60,50,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ece5bd8f-a796-482a-85e9-96f15647abdb | 60,50,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6714bc62-f18a-4226-8c5f-8b5a594db880 | 60,50,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
466a8e9a-7517-49ca-a4fb-04297b0e9349 | 60,50,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9b29b9c6-d637-40c9-ab4d-dfff600a2c57 | 60,50,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
69cfb72b-f31a-4431-8f34-66192ff59142 | 60,50,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
2570f4d5-8076-4674-8c05-af7727d45c78 | 60,50,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
142d1c25-7d77-4b18-b7d4-8077c736dc77 | 60,50,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
14b4f9d2-e71d-4a69-8484-c2a4b7c88ab1 | 60,50,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fadc5614-eecd-4fcc-8541-f53d2005ad66 | 60,50,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
8d8ea512-b604-4c2c-89ed-e3e75a5d4c5e | 60,50,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
336426df-60bf-4e8a-9889-4b4f9c76a4cb | 60,50,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
95204897-6838-4fb0-baf5-8c8bca1e611e | 60,50,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
891a144b-9e79-44aa-9cd6-403216a1ad13 | 60,50,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
071635fa-38d0-47a9-a9af-4dc897309205 | 60,50,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
1b109bd4-8642-44ae-8df8-acda26923e32 | 60,50,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ba24afe6-a2fb-4c5b-90ab-6c201b75d562 | 60,50,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
99a1e611-539e-4b52-90e4-8f5d6d141fd9 | 60,50,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
85330027-367a-4c8e-8ca5-35f0dbc55a3e | 60,50,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c341fa24-582e-47ae-a548-c5ab4adab6fc | 60,50,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
27e802e6-c785-47aa-a83f-8cd6c92cc45e | 60,50,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
015931f3-be85-4e55-9f6d-8deb0678ceeb | 60,50,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ec124a1d-21e5-4421-b3ee-39985256412b | 60,50,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
702483de-980a-4c31-bb35-8726f3908676 | 60,50,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
87de1593-c71f-4bd0-bf77-7bb71a31597f | 60,50,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
18bbef53-24f8-49ec-8acf-37dce559e0cd | 60,50,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
24bc63e6-081c-4f10-add2-1a7edc0d71a6 | 60,50,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e26d5aca-2269-4e04-bf9d-f0e483c53158 | 60,50,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
161fb9ce-083e-421b-96a3-6c7fb0db54d5 | 60,50,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
b93f80f4-ef09-4ea3-a018-473b6b7bda13 | 60,50,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
f5b87e76-2684-47e8-ba51-234487350157 | 60,50,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
41b0dbaf-1f04-4928-8dc2-7796749ac708 | 60,50,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
639b666b-03fc-4ba4-a921-129f6cd0bb1a | 60,50,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7b312bce-023b-43b0-9b48-a67ce6087579 | 60,50,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
80cc4c5e-a733-4c22-ace2-360d314d4cad | 60,50,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
5be040b8-2554-4c84-9043-ce74eff7dfe1 | 60,50,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
60c33cb7-49f6-43df-808f-7b50031d7a15 | 60,50,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
49922148-66c0-4d8c-9773-ccc94ff602b1 | 60,50,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e5466c9f-2c4f-4fc6-aa64-a6e1fefbb029 | 60,50,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a309586f-57c3-4b60-88ac-6c5229dc6982 | 60,50,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
0fdf0004-fff9-4f84-bce8-f3c7e3aaaa44 | 60,50,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
72bd7527-c6f1-4fe8-aa51-95bbecfd1c85 | 60,50,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
ed52ae7d-6dd8-442b-9741-f5c8c5a2808f | 60,50,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d84edc93-f229-4dd0-b734-a89d991622e0 | 60,50,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
3c7e51c8-9fe4-4c7d-875e-b9c8cf95d28a | 60,50,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
d64e6be2-61e5-4ef7-8f6b-990544aa6f0d | 60,50,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8b75822a-413c-4dbb-93bb-d294fa5ad432 | 60,50,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
24ef6c61-7d6e-464c-8ce9-f2eda1d4d0be | 60,50,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b7c23232-5be4-4690-a37d-cc17f35ebd9e | 60,50,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
66d842db-297e-478f-9877-3adfc6ef5404 | 60,50,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
db9132a2-76a0-4d45-8b37-0f095cfec796 | 60,50,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ac07b118-e69e-4fc2-8852-4f6a6d2e6912 | 60,50,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
281754e5-8ea9-4d8f-8ea7-0c12fe2ed136 | 60,50,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4d9715ca-5426-48d5-a1af-bc5aa2c9f810 | 60,50,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
bf45f9cb-5f65-460a-b675-e4343792010e | 60,50,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
19fcd7cc-4dfb-4c49-ae86-e535d8dad441 | 60,50,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
adc2d06f-36ba-4e20-81f2-29e382b1c4e9 | 60,50,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
aa1bb764-41c5-4a2c-a10a-0e2a7a7a91dd | 60,50,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1bf548b4-35c5-4dc6-92e1-ddc3efb13ff0 | 60,50,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
34b19494-0beb-4377-b3a3-6cffab684a1e | 60,50,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
60675134-0d5f-4ea0-b9ff-6bb08e483260 | 60,50,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f97fab06-1452-4a27-8d9d-87c738088d1b | 60,50,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
fdedda38-9d37-4853-99c6-78e0ca84057a | 60,50,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
fe4399d0-4abb-4b86-ad36-d5d5bb303b84 | 60,50,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
3cb64ed5-4f1d-4a7c-852c-3e8ab99d8387 | 60,51,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
45d3d834-0e74-48dd-bad7-a125389f6574 | 60,51,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1c8334d4-49dc-4f06-8e71-939e71c774f1 | 60,51,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1d81c12e-2b97-404e-be64-08dd3400c674 | 60,51,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
957c8531-073a-4912-b18d-d95a74811871 | 60,51,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
69d3aa6d-8f1f-4df8-bc6e-0755108977e0 | 60,51,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6683be03-06a1-4f50-ada3-493e57cefde8 | 60,51,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
bd211208-3e9d-4c98-91fd-0b573a211d55 | 60,51,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ebe6e2fb-c6f5-4c6e-b95a-8a9dc52313ec | 60,51,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
78c28ed9-1cce-4768-974f-8c007f50c248 | 60,51,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
1e8ce9ff-0e1b-4363-b97b-450cba1ca903 | 60,51,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
6c41234e-c7df-412f-ab7a-8d66a309c4ae | 60,51,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
c61bf045-b7bf-4e21-a20e-5833aa9b5cb9 | 60,51,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
c7ec3060-7713-40b0-a76b-073c37cd0d9c | 60,51,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
ac8afb6a-e558-4f8f-b627-6af5a6c7cb6e | 60,51,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
5e621101-4ea6-4606-89f2-bfd3dabba3f2 | 60,51,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
299fb31c-074c-4657-8ddd-30e95dcd1475 | 60,51,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5e26733e-ec85-40f3-ab21-bcbf0a30a5fa | 60,51,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
3670e942-e930-4814-b9b0-29c8b1824dfd | 60,51,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
1958ada6-5618-4b43-a67a-0073b3f84341 | 60,51,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e18fa62c-e89f-44ec-aba4-1e574c2c98d1 | 60,51,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8fbacbae-5e5a-4e02-aac2-c15323e8fbc8 | 60,51,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
31f5990d-fb64-4908-a485-6303fd5c69c1 | 60,51,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e2074923-65a0-4c2f-a04b-0064fb5a0572 | 60,51,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
497d1451-c60d-422c-8cff-d0668b148643 | 60,51,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
78b8225b-a2e9-46b8-9531-28eb7cd69ff5 | 60,51,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
04b951f8-6f24-4fd6-b02d-2ca1c1990d75 | 60,51,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
df947a7c-dccf-417f-a0eb-a7c5afa7d086 | 60,51,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5f0f1022-f6b1-473a-8a3f-d034a6482294 | 60,51,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8e3aa1bb-dfec-41fc-af59-7b50e54cde09 | 60,51,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
0b11ada7-a336-40ad-a145-d8a15e982d5e | 60,51,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4da1446d-83b0-4883-bc99-00e69aac79f0 | 60,51,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
443f15ac-cfd4-44e0-af95-d466ca289e84 | 60,51,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
40ebd1fa-1236-4ba6-aff5-53d17faee188 | 60,51,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
adc31c53-4611-4a29-b5a2-534895f09e3e | 60,51,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
72cf65ef-5c3d-4519-a4b1-5d279baa8735 | 60,51,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
7bf01cc0-8949-4017-bf35-8d27c0477392 | 60,51,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
708acc56-b9db-4c27-8a72-0712a0bdbeeb | 60,51,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f0d3eea7-2ee0-41cf-87c7-95f8e65d2a3c | 60,51,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ff4d1ce2-15ae-47f5-8fdd-5910b4b4c8ea | 60,51,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8ad89d6d-fc03-426d-bdad-637af93065ec | 60,51,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
924bf57c-8584-42f0-a572-92546d67dcd9 | 60,51,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c5f1e868-88b7-4577-9b43-2c7f00651b97 | 60,51,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
adfad829-6236-4a1e-9cf0-33f7e064054a | 60,51,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
40ddd1b0-7a96-4410-b988-511832fa5784 | 60,51,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
fe7fbf87-a8ba-41cb-840f-60458e81af34 | 60,51,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
806ce6f0-2c51-4ddc-8532-8ddc5e8fabd6 | 60,51,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
4c9645a6-430b-4dc4-9c56-283dd5f17f33 | 60,51,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
5c9aab73-c70f-4b62-95db-5b3a520eacf1 | 60,51,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
a0764574-3f06-4c0b-a703-5068f2ef057b | 60,51,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
3bf14d2b-eb29-4b48-8308-2600a6b4ebf5 | 60,51,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
58e68ae2-7902-410d-9b39-d63470359df8 | 60,51,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
7d7e957d-cfbb-4d84-ae65-b886ad374b14 | 60,51,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
2ebfd889-3b03-4c00-9fad-8e3a38712e22 | 60,51,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
956a4fe3-6899-4dd8-a88f-37f8e6488c90 | 60,51,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8f0052c8-7b2e-4315-8293-f3b4a1963ff9 | 60,51,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a1be260d-7563-45fc-9c8d-5f98a94c9405 | 60,51,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2df32d05-2705-4474-b289-1aa0a539593e | 60,51,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
29c39eec-b355-403e-b089-873d5fa6ac48 | 60,51,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
7d157915-4bab-4080-ad02-9e832b9d1cc3 | 60,51,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
4b47cadd-5875-46ac-8242-542629e0d5dc | 60,51,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e7023a96-ee29-4753-a4ef-b884b6572f85 | 60,51,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
8ba2f007-1a30-4a3b-a007-2ef0fdc6df9b | 60,51,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b33d1129-e197-4ad8-9b6a-8a5a2ba93133 | 60,51,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
72276411-f61c-455b-82c1-02cda05059c1 | 60,51,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b6edd13f-9ddc-463b-a71d-53f8d4f28131 | 60,51,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
ae2bc7de-1ea0-4e19-aefe-12043e3f603d | 60,51,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
5bf66ba1-08f8-4841-9449-f4c8cdb6a2b2 | 60,51,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e20a2271-8d9e-4932-939e-d0b1829011ef | 60,51,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
496be8ad-3844-4346-ac5f-887e02e91843 | 60,51,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
ca8a0bc0-b637-4ee5-aeba-58bdc863cdbb | 60,51,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
ffd284ab-46b8-4901-a8db-4d98c3b6a704 | 60,51,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6d23ae50-1b21-4f55-912c-cb8c29949b3a | 60,51,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e2e960d8-1b69-4d03-ae49-bff8458943ff | 60,51,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f6de66ae-761e-46d1-bb09-4bc384947c9e | 60,51,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
11bc0eb3-4dfd-4ba4-91f6-956ae4fdc2be | 60,51,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
5744316e-db87-48a0-a2b8-cea449f98d36 | 60,51,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d7bf41a0-1c87-407e-af97-db3552a98bfc | 60,51,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fabb187b-9a84-405d-ba61-121bded95b29 | 60,51,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
49d49e26-29f3-4966-9075-fca59778d536 | 60,51,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8292bac5-f50d-4ea8-96cc-20eeb86c7368 | 60,51,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b55bfae9-2f71-4bb1-98d0-5385dc647335 | 60,51,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
811886ce-dbd1-43a5-87c3-b8243c9f9489 | 60,51,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
849cef69-aa8e-4cf0-8db7-e593ede3e194 | 60,51,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
4b45e6be-747a-462b-973a-1ad9dcaebafa | 60,51,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
59b73d71-50fe-482d-9337-f0853d8b1cda | 60,51,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
316dfe61-8bd1-4c11-ac2c-5968beb6bee6 | 60,51,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
999efaf8-f52e-4083-ae5c-f6f225c424ec | 60,51,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a0879c3b-6477-4394-b045-46e84b0e0aa1 | 60,51,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
62dc7c0b-bd98-4972-b638-bd0f13e23be6 | 60,51,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
904154aa-4f5a-416b-b369-0b60a29a9558 | 60,51,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
664d9139-7e16-4170-9efd-2fd344fb72a3 | 60,51,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
14c9a4e1-c28d-4913-b6f9-e0c1daa7189d | 60,51,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
107def6c-1313-4d9c-bc4d-b7c0ad7d476f | 60,51,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
eb2aa6e5-eca2-4ae4-990f-9f80286b98c8 | 60,51,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ae2ed93a-3d09-4015-b6d8-60494d1f668e | 60,51,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
7fde821c-db64-402c-bbdd-31c2adae95e5 | 60,51,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
5d7e5d9e-7f2d-4370-94fd-9961f60aa6c5 | 60,51,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
4b965478-57d0-4377-82e4-85f409481b16 | 60,51,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
44fd38b1-1818-4d17-bd3e-1d5ba739aa09 | 60,51,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
99b14e07-2a49-4b10-80b0-968de13a727b | 60,51,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
a45c22f6-bb28-401c-a939-2facafa6d21e | 60,51,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
f632dcf5-82a6-487e-8c60-1f3c84198a57 | 60,51,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
1e1632f3-2e32-46ba-90aa-80ba7a280ca3 | 60,51,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
10f25cf8-d0b3-4e08-94c5-7ca5fbefc1d2 | 60,51,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8a9ad2fe-2894-4b12-9ca0-81f85e25779b | 60,51,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0d72199e-04c2-431e-92da-c062f010f5d2 | 60,51,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b1e07489-e704-4301-9a5d-c25e8a416f19 | 60,51,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
b2e7727e-1ea5-413f-9741-e995628ea43d | 60,51,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
960bd456-491b-4cd4-9208-27faf95228e9 | 60,51,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
310a9220-e758-464f-b26a-cbe2267c4462 | 60,51,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8275732c-f83f-488e-b85f-1f3abc9b690d | 60,51,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a1b892b9-c958-4e21-806a-97d284a83b0e | 60,51,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
bbe36aef-a8e3-4bf6-a7c1-96aefb126ef2 | 60,51,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4987ac9c-a41c-4702-becf-b258487d5cf5 | 60,51,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
749c600b-3ca7-43b1-8ad8-a9a3038f62ba | 60,51,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
78e4d2b9-475c-4fd0-a959-4dda4bc79756 | 60,51,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
24e5b585-dcb3-4834-ac7a-a1ef35599757 | 60,51,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b7325234-3efb-4624-9f15-cc29d28a6e76 | 60,51,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
37aa52c7-9626-4608-b6e8-0d2756c4325b | 60,51,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TOP WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
60ccd209-08c7-401a-a74f-1fd7c99d3a85 | 60,52,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
adcef25f-c45f-4dcd-99dc-a9f7246f8c90 | 60,52,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a280a911-9ef2-4464-bd47-1c83b6a1de00 | 60,52,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
cd5100a8-ec5d-492e-a97a-ca09d38e986a | 60,52,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
bc3c4ff3-6dd1-4e26-a172-d19cb3e25037 | 60,52,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
1005377b-206e-44fa-85b5-588c0a42a9f3 | 60,52,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
01b238fd-9faa-4734-80a8-1ab318e876ab | 60,52,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
71241f8c-ff8e-43a5-a29e-5377dde6b464 | 60,52,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
62d4d232-152a-4886-ad0a-536d30713319 | 60,52,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e44e0bec-ae06-4184-954b-95353ab84b3f | 60,52,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
fbc7ecad-1380-41f6-ab51-d934f740e137 | 60,52,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
470cd8f6-df50-46eb-9c53-325c5c3586b6 | 60,52,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
740890a3-4b29-44ac-b188-c76b581c3a28 | 60,52,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
db4b0d3f-6f25-465c-9821-99def3d9b6f6 | 60,52,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
df52630a-2788-4704-ab3b-8891f10f01a7 | 60,52,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
8c9ae62a-9a89-40ab-a217-93baea6f1247 | 60,52,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
60f0ea95-6893-4dc4-80b8-c99bcac5dc0a | 60,52,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
21c0958c-0f9e-48b5-88b1-a075d24aed37 | 60,52,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
1c155953-e0a3-4fe8-8c6f-71e346c580ea | 60,52,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
5326925f-1cc6-44be-aaf0-356c524f0112 | 60,52,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
0a4b1840-dc29-49c3-9c2d-ca3ba3ac4909 | 60,52,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fcc74d31-7cd8-4d4d-9b69-897fec8e5a61 | 60,52,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
581ae264-b20e-4b3b-85c9-f63ff1e033d8 | 60,52,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
aafe82a7-496b-49bf-8d22-03b6e930db0f | 60,52,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e4752835-ab34-4d3a-996c-98878c1f9862 | 60,52,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1e347a5e-26c1-4ac2-b0c1-43e4c5a3fad9 | 60,52,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2f92367d-0d94-4d23-89e4-944fe0d25a2a | 60,52,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1e797089-f891-4b49-8a0a-07f3d86009d9 | 60,52,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
3fc64f46-8825-4033-806c-df1b2ef409fe | 60,52,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a8be8759-9782-49a1-9e63-1d17a6f6ab91 | 60,52,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5ac5c727-62cb-4435-bf1b-f22fd3074a13 | 60,52,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0f3dcd7e-2af7-4f28-95b9-0f05a84f2847 | 60,52,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1eab3258-5823-4e74-b085-ad1998f0a452 | 60,52,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
64f5900e-b840-4614-80be-d0c2e499a42f | 60,52,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e867f1f4-fb24-432a-a071-072cb28503ab | 60,52,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
2400e992-d17d-4611-a419-ddbbae0d903c | 60,52,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
87aea807-1bd3-4f7a-9fc7-3b5f2943d825 | 60,52,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6a507725-4607-455f-9346-d97667d6f509 | 60,52,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0f590e70-c1f9-4728-8891-1103d81aa77a | 60,52,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
081c592e-909d-425d-80ed-268c0cc7c00f | 60,52,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
baf1b272-a472-4f0f-82dc-1455880e1056 | 60,52,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b188d0ea-f0c2-402a-815a-9db1caa4b983 | 60,52,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ae517213-e7fc-49f6-aab4-096b09a070d6 | 60,52,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
fba27a42-8628-4556-a85d-955627d7f2ff | 60,52,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bb3089c4-a6b1-4df9-81ac-0793a4fe94ef | 60,52,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
62dfee83-db9b-419a-a34b-2259d477d50c | 60,52,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
06f71f2f-7202-4834-8d92-0b02f751e328 | 60,52,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
2b3c4f0b-bb61-46cb-8ffb-d1c6cda3b8d7 | 60,52,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
07af562b-affb-4e68-98dd-81dfd00c2e97 | 60,52,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
0e2d4c74-09b2-4a5a-889c-3a7026df1856 | 60,52,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
7f3a947f-88e1-4d18-a7b8-4d4eb2bbca28 | 60,52,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
d0dda618-828a-4e1e-b10e-e5e24a9045d8 | 60,52,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
36296eb0-5831-45fd-ac84-06f77eac92f1 | 60,52,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
dca2b493-6887-46c3-9221-0528422f5759 | 60,52,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
9391e864-f157-49f6-bad7-e487f097575e | 60,52,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
5bfde013-4e00-424b-8a80-01de034034f9 | 60,52,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
bfefed4a-d23d-420f-a714-9fa41097720a | 60,52,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6191dffb-9e07-4c76-85c9-7ff1d9b904ba | 60,52,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7c21f0bf-ce54-4b5c-ae23-60b86168920e | 60,52,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
80f94463-8c14-4e46-b4b1-570872f9ec0b | 60,52,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
78fa0bdf-37a6-4ddf-ab09-d6e52aa514f0 | 60,52,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
de9f4c42-710b-43a5-a377-759019188fc5 | 60,52,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
e419dc6b-e4bd-4975-98eb-98700b3533ba | 60,52,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e0780491-dce2-4bc4-8d2b-691eb2869709 | 60,52,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
bef39aaa-cc8e-46f8-a9d3-34529dbe5800 | 60,52,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b652ce40-d934-4335-a222-16054baf5826 | 60,52,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
d7cf68f8-dad7-4284-8699-9eed0cd03493 | 60,52,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
7ffc7dfa-b64b-4233-b3e2-67b3953739a3 | 60,52,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
81f61c35-ab9a-4654-8893-740cfbd5bea2 | 60,52,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
62ed62b0-c8e9-4022-93bd-c1d1764b2532 | 60,52,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
bdfa8032-1c7a-4bb2-8bcb-32a5f57b5b49 | 60,52,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
009afd5d-c4e1-46e3-9f90-ae0b1ae839a7 | 60,52,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1d377272-9cc8-4ff2-82cb-6d38c7d3f6f1 | 60,52,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c1d55399-9c2d-4e71-8b17-533463371f70 | 60,52,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
567cd189-7b1a-48f2-86c5-b6d1dab02cdd | 60,52,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
0b48c2cf-49a6-4b63-bdc8-819dbf030415 | 60,52,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f129dc3f-b2d6-4245-88f8-103a065469d2 | 60,52,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6b74bd9f-83af-492a-8b20-307fe9d17120 | 60,52,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0074dd6d-f86c-4170-9b30-3a680df81e0a | 60,52,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5742dc7a-2fc4-4d79-8e4e-c3c40b34cf38 | 60,52,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
9a3ddfea-2539-42bd-b9af-8c1da5ced956 | 60,52,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b6c862ce-21f4-4f5d-befb-a6415250e68c | 60,52,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bad3d993-2919-46ba-b701-bb3640d33e5c | 60,52,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
73d6df8f-2d54-4696-b0a2-68e7af9e0bff | 60,52,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
41f27776-7f1d-4b59-b303-719a7cba66ee | 60,52,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
879babc6-bf49-484f-bbd6-41000a6edf6d | 60,52,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
32a97966-80aa-4ab2-ba5b-61e642375c5c | 60,52,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
0c387dda-871c-49cb-bacc-6e5500244b4d | 60,52,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4e768a06-0c6e-4d50-b6ca-4c092ef2e6af | 60,52,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fc390226-77fe-4669-9ecc-f48fa6e664ec | 60,52,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
48126435-ea63-4988-8aca-1840eb24aadc | 60,52,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f76e3a93-5b36-4460-9639-43868cf7e5b6 | 60,52,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
333574ec-5124-4ffb-b6e5-aedf1cbaccb0 | 60,52,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8eebb440-c99b-48eb-8f72-be640d0551f0 | 60,52,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d43f4370-4315-42f4-90d4-9e02cd27dc21 | 60,52,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
818326f5-f1d3-44c5-ac5c-e00ec0f986c2 | 60,52,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
f0a4b025-4dce-410a-899d-fae3ff09ec93 | 60,52,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0e5326b7-a45f-40f2-9d23-e366ffed7848 | 60,52,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
7ee1b09d-1e29-4102-a190-37013a1167bd | 60,52,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d3cf9689-ef0c-4981-83f1-ed35f6467849 | 60,52,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
04e3d0aa-fbaf-454b-884c-11019b2a5f11 | 60,52,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
700effc3-c627-4b2d-8f6a-a0d78f638ba0 | 60,52,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
17917ccb-a313-4532-b6b2-db01a21b2b75 | 60,52,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
65f9ec9b-26d4-4688-973e-d345f7c73c6f | 60,52,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f5ee4129-1b11-4352-b3d9-0724f48444b6 | 60,52,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
dc52dc3d-a7e0-4d01-9c19-6df471163fa5 | 60,52,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
723d64e8-4eaa-4a71-bdd3-7c4ac35a7be5 | 60,52,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f86d351a-921d-4d78-bd7c-c714633074aa | 60,52,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
209dfff7-cefe-49b0-b71d-3d56d23ea828 | 60,52,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ebb0b45c-0653-408c-afaa-9d160ecc31bb | 60,52,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
38553aac-cfb9-40ff-8277-6fd4010287d9 | 60,52,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9edbac28-1eca-4be2-9487-f4d5da1052d2 | 60,52,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bf2640a3-1470-49ac-980c-967029d9f4c0 | 60,52,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a1597f48-50da-434d-b709-72576b0868be | 60,52,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ebdf8191-1293-4ab8-8074-85e87fd8e1a6 | 60,52,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9e68e11d-8292-4d9a-9b3c-02b7bdeb7061 | 60,52,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
40b6053d-ed58-40b9-9eff-9a19eb5a74c6 | 60,52,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c4c1c7ac-e901-44b6-ba5f-e414ea9b7617 | 60,52,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b29b10b3-6e26-4438-99b7-0327546292f3 | 60,52,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
433d4afd-d338-4aa1-8dcc-3cd86e9b69ad | 60,52,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
4e26055e-f822-46f6-adbd-88061e4c5e68 | 60,53,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
668826e0-54d6-46e9-8dc9-7673509180a5 | 60,53,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
92c2d79c-853f-4ffc-ac36-cf3c105aeea6 | 60,53,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a7a98803-0a52-42c0-a294-2c4637b88a9e | 60,53,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
50bd6c02-be27-4df5-a370-450d2ec5ac00 | 60,53,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
f75b7121-550a-47d1-99e1-573f5aac9eb2 | 60,53,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
86532c83-b75f-4bf5-9612-9b5f1159d3f6 | 60,53,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
97d8fb64-05a7-41c6-b0d0-134f0383540a | 60,53,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f95ff202-8c35-4025-8932-9f9ed13a4cb0 | 60,53,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
2d4fe2f6-7933-499b-bf1a-dcc3861bab07 | 60,53,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
ebce0634-2e23-47c2-a725-fe9813913191 | 60,53,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
00a451df-5ede-4d97-9d6b-c1b9f3f6dfff | 60,53,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
279a8981-ecfb-4ef9-89ed-d3ec8ed6e36b | 60,53,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
ee4ea2ed-7a0d-47b0-a34f-688af2640e1b | 60,53,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
b3c5ca50-b83c-4bca-b779-9c9c56c961f2 | 60,53,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
385c20e4-e705-4b84-930a-2ab8fa836080 | 60,53,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
08baa73e-30fa-41bb-8d61-52a8b3765564 | 60,53,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
fd487068-245b-4dc8-9433-9aea71ed805d | 60,53,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
c2e4c50d-bee2-43f8-a212-5b080e12006a | 60,53,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
938d1162-0ced-4135-9ccb-3c6fe4b7344a | 60,53,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6e146833-c131-4156-a6bf-b496e4625430 | 60,53,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
01534dfb-3b5b-44f9-99a3-6a19da79b41a | 60,53,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ae7bd450-edff-472f-a3bc-38d0d81e58f4 | 60,53,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1643e01f-efb7-4cad-a8f0-47ed4ecd37a5 | 60,53,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
0446f2f8-481f-4b27-89ed-056807786a56 | 60,53,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
9b4a209a-4d5d-4e2c-b565-577f08ea4005 | 60,53,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
64afd502-0bfb-42a2-b344-d7fe88af086f | 60,53,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
85d572e3-13a4-4cf3-9698-9335253cf915 | 60,53,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ffed0e92-cbcb-48de-abad-41e14e2b5f2b | 60,53,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
07ae6798-41ff-49a0-acb1-a3f7a97c56ea | 60,53,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
95f39cb1-7924-40ec-b03b-6214cf2f1a24 | 60,53,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8feb00b6-afc9-44a4-bce6-ff603f097afa | 60,53,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
58838ccd-c0fc-4ecc-8285-e954bdcc5ac0 | 60,53,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
0f9d35fe-773c-43bf-854d-3dcc71bed9d2 | 60,53,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8296bb92-d740-4b24-b497-a7dee983a759 | 60,53,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6b23afcf-2cfd-4ae5-8a55-7b48e8152629 | 60,53,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
a5f6ecb0-56d2-455d-8f76-631daf51109e | 60,53,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4984287e-ee68-4f8d-9f06-3776b198ec31 | 60,53,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4f701a9e-f10a-4676-95a3-3aeb1e587108 | 60,53,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9139c6b2-382e-446c-a180-0840992f74cc | 60,53,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c87d9568-38ee-43af-866e-deb95cce6b13 | 60,53,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
fe16fbe9-7305-4dc2-9091-f4267444f3df | 60,53,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
63b94ea6-c7e3-4cdb-8263-1280d22326b5 | 60,53,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c81c1c59-9afa-434f-8b87-a182a1aadfaf | 60,53,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
510db6dd-950d-4e17-a60c-cc757adf3093 | 60,53,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
f0aa751f-70d8-4a50-a0dc-62c6e4881f3f | 60,53,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d81a793e-566a-4615-aa97-0b70e0f49c3f | 60,53,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5c2afc47-bb75-4fde-b886-af304385e385 | 60,53,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
57897888-c25d-43ef-9519-c2e736835d71 | 60,53,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1824675d-8732-4480-a625-62dc779fbccd | 60,53,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
dac186e1-1ed2-4cab-b900-84d138faf473 | 60,53,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
df58c3d3-8f6b-4c60-b278-a9df34ea8b18 | 60,53,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
03f5353a-c8d1-4cf7-aea0-31d8ccd5df30 | 60,53,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
546d3951-1413-4325-84fb-ff5fe677442f | 60,53,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
3c011942-d93d-4b4d-a069-3f8a12a5e04e | 60,53,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
694943af-d94a-4e51-a9c5-feb8b584fa85 | 60,53,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
aa763569-457f-43fd-8343-6c094a26549e | 60,53,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
fa08806c-70a8-41e5-9f9b-f434a260cb08 | 60,53,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
755a704a-86d7-427e-8fca-f1bc1f8263a3 | 60,53,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ff2b348e-baa9-4e36-a16c-3f78afbb44a3 | 60,53,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
47050675-7f56-4bc5-abb7-6dea553131a8 | 60,53,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c1a42c2e-fad8-4bcc-b066-2b1c8c6ee2a2 | 60,53,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
fad1c491-e64f-453b-a4fe-9379d60978a9 | 60,53,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1569aa64-511f-4504-beda-302b659c8b08 | 60,53,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
738398dc-1a2b-4ba1-9d36-2a619925764f | 60,53,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
30e7b587-ceae-4254-90d5-d0939aacf360 | 60,53,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
d1a515ab-7bb8-439c-bca3-c49bda13b663 | 60,53,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
28b0889c-bb13-49a0-85c5-a6b38c64510b | 60,53,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
1143d687-0cc6-4ec4-b803-dac1867b340e | 60,53,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
bca387b0-60e7-4f6d-b2b2-31bbe216989c | 60,53,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
62b5ac14-a1df-46be-8e27-51170cbabb2e | 60,53,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5a00ecfb-eb8c-478c-aef0-15b537842141 | 60,53,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d88f6a8a-e771-4f10-b17d-21d0d6423121 | 60,53,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9d415659-b25e-47a2-a8bb-4ca087c26053 | 60,53,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
32227ac7-d804-4e7c-ac49-b01d4c1b3882 | 60,53,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a8d177d4-05d1-4de7-97f8-2347a3a8ce7f | 60,53,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
41c6db6d-0492-424a-a6ee-0a6b270b6ca0 | 60,53,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b9584fe2-b2b3-4522-b65a-247662db4956 | 60,53,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0306a273-d082-4f44-a884-c3c525b0a224 | 60,53,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
0376f9d3-7da6-42d7-893e-13a3fa1fafd9 | 60,53,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bb3cdaed-05c1-4db1-9d81-593e07832003 | 60,53,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
e19afc6b-005a-47cf-817d-d7392a88ed3e | 60,53,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
98e15b6c-165a-4812-ae5a-4de4dc348196 | 60,53,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
80327dc4-8736-4100-8807-34aa03ec330d | 60,53,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
2d8ad8c9-7b93-4edf-8e8b-00d1db273c6a | 60,53,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
4de5524b-5806-47ea-ad42-5312eaeb91f1 | 60,53,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d71e6f1b-79e3-4809-a132-803a938fb0da | 60,53,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
2b5dae97-70f1-4f79-a74e-6f80ec320c25 | 60,53,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
25bd7f21-2183-4293-af71-8f6c9456cf1d | 60,53,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2bcb04f2-4877-45d4-8873-d7bec71b8e41 | 60,53,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b6cf96a8-7f1c-4cae-8a96-a38798577977 | 60,53,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4c5252a7-e158-4fbf-8d47-609cc52a608c | 60,53,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
03035fb1-77da-4630-9cad-6bae1378fd5e | 60,53,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
2cae994d-7d74-42bb-8097-e0e89d8c4d10 | 60,53,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5f396ac4-941a-4ba9-b8d6-41246a46cad3 | 60,53,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6904ecbd-f5d3-4675-8e71-8f158800e56d | 60,53,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a76af6de-b844-4ab1-a10e-2993bea4b8e9 | 60,53,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
33076895-8f9b-4208-b903-b9dc0b03cbc2 | 60,53,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
0580db12-eb73-475b-b68a-fa91db0306da | 60,53,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c9198749-024f-4a89-ba12-9adfc983db33 | 60,53,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e0caf13a-cead-4725-a09c-3b6ee4b18edc | 60,53,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
31a30418-d0cd-48ff-bbaa-b2e915dec7fe | 60,53,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9a1ffc88-1f46-42ba-a810-8b961271e94d | 60,53,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ae17d6bc-2718-4bce-a7b8-313605dc4828 | 60,53,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
9f330d33-9520-41cb-8964-60c47e5cd06a | 60,53,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4be98021-783c-447c-990e-1a53666b047d | 60,53,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9191f7d3-34ce-43d2-9e9e-3b9e764b8465 | 60,53,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
73e023a8-de94-4bb6-bbf8-e6540ece5270 | 60,53,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e9a9641e-ec34-4caa-a85e-7e79e7b6131f | 60,53,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
22df330f-a636-437c-a9b1-5136a8f215a7 | 60,53,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ab03ca0d-320c-4893-a840-44270a16442c | 60,53,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
545c9e1e-b2c4-4948-9431-38f20d2b245e | 60,53,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c8b01aaf-e736-4347-a39c-b0a2d68c558e | 60,53,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
57c4a7ef-ed46-437e-85e7-c38a096f24b2 | 60,53,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
74b61308-e4c7-40a6-bbcd-a6f0453cf747 | 60,53,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b2b26d1b-f6cd-406e-931a-dc3dc7487d62 | 60,53,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1cc762c5-8bf6-4076-8c78-dc5bba7b4657 | 60,53,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c654a065-1650-4c1a-93c0-f1a4aa7bd066 | 60,53,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
7b008c7e-daa9-498a-b5c2-4e40132ea486 | 60,53,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
7b2482c2-7054-4ae4-b58a-718a76dd52bb | 60,53,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT LOWER WISHBONE - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
bcb7c956-1b9c-45c0-9574-fe729cccf62a | 60,56,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
0dc7bc61-b30b-4fe5-8cca-b2ab2c06caff | 60,56,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d6d47e99-5b05-4922-95bb-7506c6295260 | 60,56,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
95c54166-e876-4041-9287-5942b060ac31 | 60,56,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d7051a58-096a-4208-8178-686baef639a4 | 60,56,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d7f1fe76-888c-4380-ae39-140f9d5688b9 | 60,56,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9ad52a8c-b1c1-4b63-b206-5283aab6b206 | 60,56,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
269537a6-5018-4982-933a-c308d5836354 | 60,56,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5512a966-16d6-428c-a3f4-3061f685d8c3 | 60,56,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
cf89d03b-c62b-4a65-94ce-53c944203052 | 60,56,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
00292e00-9151-448f-9aea-565f627874f8 | 60,56,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fd0388f5-2736-4cd7-81f0-d14dc6a82a92 | 60,56,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6084eb7a-6774-4de3-91ec-d8da468c1251 | 60,56,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
af550b87-bd9d-446e-a603-844b81c67852 | 60,56,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
fab9675c-e59f-4f5f-b819-5f5bbdd0bae5 | 60,56,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
9f749769-925f-49fe-9745-801cee0cae0b | 60,56,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9cf6bfbf-3197-4ea9-b0f8-6f399d96df47 | 60,56,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
011c7aa7-7575-4f80-82b7-d5d10d8cb18f | 60,56,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
30b949d2-bcb1-4876-b802-e1e552b4a14d | 60,56,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
10ba2d2b-c055-401a-b41e-9deaf40f6118 | 60,56,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4c26fe15-83da-4998-9804-be25cd29e006 | 60,56,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
cff1f6f3-360e-47dc-a5da-8905ec3fa83b | 60,56,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b6e9482f-e191-42ab-b229-3cab5c8fb8e4 | 60,56,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
13b7bed4-3463-43ca-bac8-a0b4e45ef73f | 60,56,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
23451e52-8bff-4785-9791-684c3a7f1281 | 60,56,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
11543bfa-e558-40fd-be41-0cc6bc1fa679 | 60,56,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9b580eaf-3392-4ffa-a12d-cec475e9bb1c | 60,56,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
56832af0-86d9-4c3e-8389-387fe6133aab | 60,56,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
19f2e00e-bddd-4a8f-96b0-58f717a30e70 | 60,56,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4fc8bd42-2dad-4596-a4f6-db5d38d65db1 | 60,56,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
68c07924-bdef-4a42-840c-29908fd0627c | 60,56,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
76a32c65-3619-441b-8740-7010f9a7dbef | 60,56,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
4f6be7cf-ebcb-4046-bde6-37b75df818cc | 60,56,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
b89ed5c1-7292-4fe1-8c34-13af19e2a737 | 60,56,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3ca28743-a659-4047-a911-afeb1ffed563 | 60,56,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e3dff998-b461-4481-a8fa-491ab6e0ab81 | 60,56,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
890b4b58-bd92-4236-861a-02f3da95b21f | 60,56,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d1054e22-cde5-41c1-8069-ca0112f5d1e5 | 60,56,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a85f67cd-0ec5-4aa6-abb4-7b80fda53fe9 | 60,56,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
dc909c5c-b95f-4586-b982-5c69083faf90 | 60,56,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
29fd4636-8c9a-4a09-8a15-9b25816ed5ec | 60,56,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6e0e4c04-9357-4061-9b6e-ee4a88bbe2b3 | 60,56,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5fa36260-975c-45ef-940f-25a9cd8b9226 | 60,56,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c5914424-a4cf-4dfe-a83b-9ca444561e93 | 60,56,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b2a66319-8b29-47ce-af22-8f103c63bb51 | 60,56,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
d91c5684-4904-4345-8e37-c7cabe04b546 | 60,56,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b102f75f-9bf7-4066-a251-d2dc3185ad62 | 60,56,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ce85d0fa-271a-4e91-beab-5339e105d06f | 60,56,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
5f20b44a-a46f-4d9c-b018-2db3b02185f2 | 60,56,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9596a9cb-6d7a-42e4-85a1-6af809873ddd | 60,56,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
5638d9f4-0197-4998-a5b8-412f4343c585 | 60,56,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3da6deb6-7350-426b-bc32-1aede2e14de1 | 60,56,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
96ac9f0f-f482-46d1-8cc2-8d832dd1598e | 60,56,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
09a4cfce-87a9-4e18-91ce-f196fdc9dd2f | 60,56,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d626564b-a55e-46a7-91c5-7fbe26da893d | 60,56,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
95125064-2122-4846-9a3b-5041fcb70ece | 60,56,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f4b467d3-f2e5-460e-9020-065628cd889e | 60,56,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
69858daa-7d6f-4cf1-8fb0-150c6b88f89a | 60,56,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6b700c6c-997f-4329-aa47-50328248e7fd | 60,56,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
8d3da78a-95db-4aae-aa09-cc2a02c32a95 | 60,56,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
637c02d2-f10a-41bf-8eb1-2799d06069b2 | 60,56,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7fab2db3-0943-48a9-871b-bfb6a6f08069 | 60,56,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
1605af71-2c77-4344-b01a-4dd3220224cc | 60,56,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
42bbfd40-87f0-4f57-937f-a91ed4a0f739 | 60,56,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
56815980-d5fd-4739-8347-4be9dd09fc71 | 60,56,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9fcaea4d-2fdf-47b8-a067-09a3aae6890a | 60,56,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
18e59c61-7021-492e-bc0d-a2545734d9fb | 60,56,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
44097f4f-0d31-490b-aed9-f10d9b2d7de4 | 60,56,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f15a089c-53e2-4b63-9214-cddb12c527d1 | 60,56,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8a51672e-9558-4b62-a78b-7c8dcc3c8425 | 60,56,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4c9ab913-780d-4b67-85a1-508d7ef5e8bc | 60,56,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
53a77621-20f0-4562-80ac-e1db39683c1b | 60,56,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
61ff5a68-528e-459d-a639-bda580060b83 | 60,56,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
14a9c59c-0beb-42c1-b864-191d25c15743 | 60,56,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
12a046fc-a89e-463b-b8ee-35340bbc80d2 | 60,56,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
766deb3a-b15a-4c5d-8dbd-659843a9cf6e | 60,56,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e003318b-1af3-4e45-8216-6a41f626d929 | 60,56,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
7dedab56-f347-4115-91b2-3c12ac80a554 | 60,56,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b6c34611-4248-45de-b00d-9b8e73b8384d | 60,56,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
8399fb57-e50c-4cfc-b45f-c49da79634aa | 60,56,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1f84a216-a69e-4100-b44c-e294bbe16da9 | 60,56,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
68d0bac5-0a6f-491e-8b9c-a4f83fe4c2d9 | 60,56,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
272ca9bd-da86-4395-81d0-faa149939caa | 60,56,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
6b1584bd-e030-45f0-9976-b0dd52ef5319 | 60,56,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
4880f627-fa99-4986-a533-8a0a6580ec1e | 60,56,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
0d12b4ba-58ea-4c2a-b5c9-0bb6c596165b | 60,56,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7b9c1cbe-3798-4a0e-b742-f08ba82e465b | 60,56,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
da351ea8-e6d5-4d56-8248-03e4f8d82198 | 60,56,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5f37b2cc-0699-4ca4-9ae7-7cee360b44f5 | 60,56,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
43d11956-fd0f-49b1-b64b-cf9eabea599b | 60,56,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4a49357a-4dda-46b1-b678-b6e85ba6a572 | 60,56,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ccdcae0c-06c1-414a-959f-68ab0b5efaed | 60,56,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0c2c95eb-fdbb-49c2-9604-410d833e47c8 | 60,56,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5c079f1e-52b6-42c5-ad50-e0e6aacde289 | 60,56,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
21a8ca10-0112-4742-a072-a4431e3b6085 | 60,56,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
52e64a90-2834-4bd6-86df-152c233c4c48 | 60,56,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b6afd1eb-f1d7-497e-a865-4931130f08c4 | 60,56,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ac16d3b5-4768-45ad-b0d4-05929fb9ba51 | 60,56,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b50722d7-171f-4bc7-a234-8a5642c64207 | 60,56,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
852dd433-2a11-4fc3-8353-70e18394fc9f | 60,56,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
734bf28e-271d-4545-acc7-89a84ec01d1b | 60,56,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8e43fe69-d2ef-4926-a8fc-2c202a81abd5 | 60,56,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
345da833-2792-41ba-b082-50f05c376e69 | 60,56,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
16ebd794-961b-48d1-8255-917c59666213 | 60,56,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4e3bba7a-3665-4b1f-b100-c486ef8cef0b | 60,56,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
7ee25350-5ad1-4262-86db-c863d2c9cc01 | 60,56,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
67c731f3-c830-4b36-8727-bc833d89b952 | 60,56,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
99571c9f-1146-48be-88d2-6a1a1def0187 | 60,56,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
cc95d739-ddab-4f78-9239-53fcd8d8ea74 | 60,56,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b145a7f9-df2f-42d6-b55a-f63bb7a6ac9d | 60,56,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
13a9f3bc-bc49-466a-8cdb-816a4e968acc | 60,56,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ffcd381f-de1a-428b-8b2c-27e553f4bc80 | 60,56,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
79dd0a51-23a9-421e-9c84-4331a639b522 | 60,56,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
fe4f8547-dc2d-492e-b2a6-07e6f4c833c1 | 60,56,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
38e7386e-e659-4c4a-81ff-c3ca19686f91 | 60,56,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b5a2c77c-426f-4e78-a443-9629698c161e | 60,56,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
78f8e59e-9511-48e4-af79-ae26c6b15d06 | 60,56,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
dd26ce31-e820-4960-84b6-967a11428c6e | 60,56,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
51be9933-431b-4c7e-8f35-f19aa9342f18 | 60,56,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
81d171fe-e3f3-429c-bc6c-eb6f9753233c | 60,56,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2a29bd04-b61a-4f71-9beb-304197c64fbf | 60,56,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
a11958c8-9364-4863-9b0d-8ceeceb5408e | 60,56,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
10c8a9e5-6e24-4516-86fb-76930abef97c | 60,56,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
0fd2bdf7-07aa-40ea-89b4-d73fe0cfd2ce | 60,56,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
16882b19-f35c-4964-be95-6fa19e031ff6 | 60,56,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3698d1da-42f3-4ca6-9264-63566de54d1a | 60,56,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
877e911b-ee8f-4594-93db-bc72a1d59d82 | 60,56,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
5459c424-0279-4d61-be7e-7d7f2de568be | 60,56,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
008e61bb-4ae9-47db-914c-cba32d1a5862 | 60,56,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8f08c910-8984-4e27-b428-955618cecad4 | 60,56,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8dd5ba66-2cbf-4a4e-9820-5ec17b603990 | 60,56,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
af518bc2-84e1-4cee-914f-62f2ac0ec4d5 | 60,56,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a98d5736-94cd-4040-a0fa-f1c232b7e252 | 60,56,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
65dde376-d93c-4ceb-876f-4be78f81e1b6 | 60,56,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
9ae69c58-b8a4-434d-b88b-7c437bf3a12d | 60,56,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
cc0be821-7dbf-4ebc-9804-1958405f8038 | 60,56,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
75da045c-affe-4b62-8042-fb105c22a542 | 60,56,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
66a76776-acdd-4308-9290-000599593f80 | 60,56,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
c5201553-2ed6-4929-8cdc-c0d0dfac4e39 | 60,56,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f654135f-4796-411b-8c28-51ed6c925f04 | 60,56,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
9a386c91-5b67-40e3-8bce-6d9b90a529b4 | 60,56,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
843e40c0-44c4-43fa-850d-2bed366f28f6 | 60,56,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
30850bc8-8106-4c01-9c71-568351d04f86 | 60,56,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
aadf0261-fc31-44e6-8839-2abb15431b32 | 60,56,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6a997228-a37d-4c73-9b51-c0d6acb65e28 | 60,56,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c8108c91-a152-4978-9cef-0386a19830cd | 60,56,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6553ddef-477e-428d-bbc2-52ee1e70d64f | 60,56,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
84ee5a8a-ff1f-4e20-be29-589a9959ada0 | 60,56,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
f9977781-acc1-4c78-83b5-b62097d48dc2 | 60,56,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
116e5f9b-4856-4da1-b473-cf6cd287fe0b | 60,56,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
f0dd1dd5-61a9-451c-b918-36be5dc9aa32 | 60,56,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a987fbc6-47a6-4545-b68d-855de1aa5946 | 60,56,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1582463c-1e23-4bb7-b78c-023a4aab86e1 | 60,56,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
93089595-3d40-48c4-b538-38180230c92f | 60,56,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
160f13bf-b2bd-4d64-a954-947f23334eed | 60,56,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0c051c04-fe6d-4d8e-91ca-15c97a5af1ce | 60,56,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
3db8a868-4835-442d-83ae-1f028069b77a | 60,56,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d97949f4-23b4-4708-865e-6384c10f0a0a | 60,56,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
65dc393d-de89-4b31-9619-d612086aedd3 | 60,56,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f492c623-6287-44db-95fc-727bf2198827 | 60,56,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c9b74983-670e-46da-8d56-6c5d8063bb79 | 60,56,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
951c4186-9dad-4f49-bc2d-ad45e7e41177 | 60,56,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
3501917c-c0f5-4074-9042-ad9ab3fe8e56 | 60,56,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b7b63267-3152-41ee-88f5-e7075fb30542 | 60,56,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1978fcc2-b655-44bc-ae13-55e5f6988840 | 60,56,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
e077848c-f25f-4bc6-8291-9ab492a95ac3 | 60,56,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a511641c-8bf7-4623-8a94-3fad0c0ed4ad | 60,56,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
efd1b754-6a75-4b09-b1fc-dce1d2107e26 | 60,56,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c80a4a0e-fecf-4c80-a0c0-5afbc8805af9 | 60,56,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c5c68021-54ed-4b1a-a8b9-c2ab288bd83f | 60,56,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
39f263eb-e292-4dac-ab60-78fa97d5c31f | 60,56,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
78898e4c-2409-4c11-a62c-8e821d6c5cb8 | 60,56,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
733a44a0-b300-4f9c-a194-03036ba8b363 | 60,56,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b730834b-f417-4bc0-a472-f67ce8360af9 | 60,56,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b157e34f-459d-4dcb-bc4c-68d0d7ea1467 | 60,56,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
17bdb806-ec0a-4feb-b1ce-10e9e441d062 | 60,56,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4805edf5-1a7e-4e0b-894d-6c1119b7d5a8 | 60,56,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
af9c9b12-2e66-4cd0-ad99-08097346a921 | 60,56,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
66e7fe59-ea1d-4dc6-aae2-bedbafb175f8 | 60,56,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e52663db-97de-4f3d-93b9-45b3c7ca805e | 60,56,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a7d87221-2cb3-4fc6-a8f4-bc57f4ed4fd7 | 60,56,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6ac26655-73b2-408b-b262-559dcc9dc316 | 60,56,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
2969203a-fbb1-4693-b63c-af65c5af00bd | 60,56,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
06564522-b88f-47c0-8f21-1a8950872282 | 60,56,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5c3d00a1-ede3-454c-b360-735061864778 | 60,56,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6b59aae8-71de-4427-80b8-7b541fc8dd27 | 60,56,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
13c9402f-3c85-44b9-9d54-d35df2f0d8f3 | 60,56,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
ebf5bbac-79aa-4901-a513-d1d350d8fb8c | 60,56,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
7d0ce9f8-0e2f-4bd5-8e9d-021fb2569ff6 | 60,56,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d9c98839-f37a-45e7-9d83-b43ef071b0dc | 60,56,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b22b5d32-23e1-42d3-ab52-90e91098179c | 60,56,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c1c6db25-f18a-4daa-a489-0480dba9d9dc | 60,56,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
21cd46cd-ef57-414f-a78d-8bb48aac7fa8 | 60,56,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
47258b05-5807-4b2e-afbf-47273d7be16c | 60,56,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e27f3e24-aa39-4946-bab0-6749e7a8897d | 60,56,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
57d5fb23-c284-4446-b224-984f0368e39c | 60,56,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c5adeb13-d6d5-405e-84de-d482c9216523 | 60,56,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6e20aeb8-4c43-41f0-bd13-a70dae1a2ff3 | 60,56,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
abd79fa8-c5d4-498d-8a14-ba416e9b2a1c | 60,56,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5754fd08-89ce-498f-9cef-b7871ab63782 | 60,56,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b967e16b-4c30-46f9-b3cb-cfdedde5badb | 60,56,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3d867c89-7b62-42fe-a461-5ca0c71c6c38 | 60,56,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e0a98c78-459e-4929-87a6-bf94553a0798 | 60,56,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
15e43766-10c2-4631-8ba8-edbca9e66eb7 | 60,56,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
31a59fe0-f85d-4719-a725-4672275c0096 | 60,56,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8374f09c-b110-4043-a01e-bce4d1ae255e | 60,56,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
9c4b2081-f1d5-4b6b-b2a3-5ef7177a09c1 | 60,56,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
d8c15dde-08f2-4cba-8257-79acc254f9aa | 60,56,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d5725783-19fe-4087-8952-c2b36775ac72 | 60,56,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
805ad146-4f2b-4a33-b97e-ccf646266370 | 60,56,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
a4e77d73-e31d-4824-b797-a6a590b9ae04 | 60,56,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a096de5a-3102-4e28-bfc4-a7977a129dfb | 60,56,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b3fd2251-25ca-42f6-9337-1946b0b6e549 | 60,56,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c720fd38-2e58-4044-b27f-e664bb81d461 | 60,56,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
db998efe-992e-4476-a0c8-11f5928469c5 | 60,56,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
cd30df22-abf6-4e8f-b5f8-07b97e8c4df1 | 60,56,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
83acf011-182b-497d-8a95-07efbd36e4fb | 60,56,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8948a05b-348c-42c7-9e27-f04bf504d369 | 60,56,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
e90eca81-ba8e-452b-8f6a-a8b56c6849d8 | 60,56,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e32a0788-8d65-4c89-82f1-ee98698d9c20 | 60,56,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
4ce6f324-15fb-4474-a8ec-834ce1ace6e2 | 60,56,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
067a986f-aa26-44d8-a035-e383d05c3a12 | 60,56,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
a8b99b2d-799c-4c9e-8e58-b3e3dfeeffb2 | 60,56,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6e699bdf-386a-4075-82e8-0274ac27abc4 | 60,57,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
409ffec9-6bdd-4066-ba91-79473cd61cd1 | 60,57,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
d97374b8-b764-403e-922c-c9b6d8d6270a | 60,57,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3b7df9cd-782a-4830-99ea-a010491b7d29 | 60,57,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b2de0ff1-4c46-4b84-a1b6-760bcc11bdc8 | 60,57,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0a0ffd20-6ab1-4ff0-86f1-2a9d782dfcaa | 60,57,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7df2724a-a102-49a6-969c-2f885cb06c9d | 60,57,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8dea4613-efb9-4337-96b6-0586649aa991 | 60,57,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5711ccdb-ddb2-4d95-8ed0-0a68d5837191 | 60,57,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
42323d7e-f17f-498c-a994-09953525e21c | 60,57,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
04cbe6b4-d22c-4cf0-bdb9-6a4ddfeaccd6 | 60,57,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
837b0efb-03ca-4775-98a3-0901dd2193d5 | 60,57,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
e31bdcbb-67e8-4206-885c-7fa3b0e8325a | 60,57,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d0101767-0a1f-4de8-b41c-27ac5dab5fa1 | 60,57,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
ec9ebbb4-07c0-40e9-89d2-4d5fca4abd82 | 60,57,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
03ebaa03-81a6-4a81-b6d2-1f2d7aa296f1 | 60,57,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
b7d28f72-113a-4af8-ba7a-dd7fe6431ebc | 60,57,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
e5394e67-4c14-46ee-b95d-af80a4114402 | 60,57,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
0846643e-2096-490a-8544-519eb03989e7 | 60,57,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
0c1be0cf-d67e-458d-abfa-d251cd96a474 | 60,57,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
97526853-0528-4024-b873-5d2fc41125c4 | 60,57,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f9514e8b-9fae-40d9-be29-a58f2e950b98 | 60,57,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
64e995ab-6d00-45ed-bf80-ce117a822649 | 60,57,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
28e834bb-81f8-49f4-8793-c9bc0fec74ee | 60,57,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a3f26351-8d9b-450c-992f-3cce088d2144 | 60,57,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
fac5e510-84f7-4a26-a259-924559239a27 | 60,57,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
04221f9f-29f8-4536-8c21-e4a727e38d77 | 60,57,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
78de95f1-11e6-4f25-87fa-5a32dd3492f4 | 60,57,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
ff6dea79-04df-4387-a79d-0c9760e9f7e0 | 60,57,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
dfdc50dd-0049-4a62-8aa4-399e9cbe2911 | 60,57,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
4fdff375-e1ff-466a-950a-a1d46f2c811e | 60,57,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
04306e11-3402-4386-8b5c-4b4c2cb5a8d1 | 60,57,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
fb2a768b-5417-43f4-a7b2-35746475419b | 60,57,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
87dec5f7-ddd2-421f-9c13-0f51310cdd7a | 60,57,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
99cb62e3-c06e-4af1-839b-6cbd2c15578a | 60,57,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7c60b383-8277-438c-95c7-a05841a6b3a1 | 60,57,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3cd5ddc1-0563-4fb7-bbff-b6a60a5ce70d | 60,57,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a18334d1-ea53-4064-9e2b-245ef70e4ec9 | 60,57,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b9800183-20c8-4154-9e99-07ae7c016238 | 60,57,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
991ed436-5c71-450e-bbff-0bcb845a85e1 | 60,57,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1414b515-6a74-48e2-8e55-22f141e276cc | 60,57,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f4bb88ad-ad97-4a88-aaff-10fdb5f6a735 | 60,57,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
95bb5c56-9645-4e10-b4cb-12046ad2f48c | 60,57,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2d179c91-e3bc-4257-ba1e-25d2da8ebc72 | 60,57,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b59d73a7-26fd-4f5c-aded-52b6f0331c0d | 60,57,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
858a7d69-cd82-463b-b4fe-475998bde023 | 60,57,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e78a9fc1-a282-4444-a878-2a94677fe4ec | 60,57,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
378edb35-9101-454c-8356-927dc08bfa30 | 60,57,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1bb855c4-1374-424b-9728-54e4c336ba77 | 60,57,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
843d762a-e30f-4ea5-b1fc-42aff1d3df64 | 60,57,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2ad035c8-801f-4f58-895a-489283c26055 | 60,57,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
de2de7cb-8fd5-4ef7-a7e0-9b91985eebd0 | 60,57,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
0b3ad4f2-ff1d-49cd-95bc-abf3b44e1629 | 60,57,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
d383d0f2-e865-47f7-8c39-142fe37b2894 | 60,57,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d627eb6e-8686-47d1-8b3e-338365a85666 | 60,57,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
772b8425-e231-4cca-9ebc-f684d5504155 | 60,57,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7ce5dc5c-5e94-48ad-9e07-b504c97737ea | 60,57,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
55e639a0-0d52-441e-8474-100cf92a7cf1 | 60,57,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a39f2b04-76fe-4ab8-95d7-6fafe7e44b74 | 60,57,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e4138eec-4d9e-4cfc-9921-bd9710e7ee00 | 60,57,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ea6a7ea5-53be-4ee3-9703-91d1ece4bfaf | 60,57,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
16e60b84-6afc-4c12-ad43-186ae3cea0bc | 60,57,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
65ea0bec-5258-4394-8b51-2ae0124da726 | 60,57,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
89ce4c03-589b-4aaa-950b-ee5273e295f0 | 60,57,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
fc9b0c64-1bb0-46d7-992b-19de4d743719 | 60,57,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
818d8c0f-b423-4544-82cb-daedaeb140c2 | 60,57,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
ef948a5f-17f4-44bd-9adf-84db477283aa | 60,57,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
7ee01294-e775-46c6-b8bd-60f9b6a128fa | 60,57,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
503d3f97-0fd2-4963-bcd7-9674ea792b48 | 60,57,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
cb44b5db-f9e4-415d-9273-9f8e4dd0e7f6 | 60,57,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
17070cd5-7dc9-41aa-b5bb-2c5db2b14050 | 60,57,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8b6881ce-e9c9-43f6-80ab-221585551321 | 60,57,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8a3fa134-3a1a-4738-9f45-4f77c72f1dcf | 60,57,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
66170270-4d19-4251-8948-054c59f0250e | 60,57,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
dadaa27b-1528-4533-8742-be36c138d2dc | 60,57,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
14b44449-d226-4b49-9056-af5eab6dc3b3 | 60,57,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
b703cff3-a813-4862-9ec3-a2e69225a6b3 | 60,57,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4dfa6c00-8714-4179-8ed1-63baea52fd58 | 60,57,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a4250e71-fd47-46a5-b1e2-45858f56e0ed | 60,57,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
5ac1c870-6ec9-4c00-afac-4a9024de2c14 | 60,57,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
59e2c8c5-7201-414a-8e64-ba2c13b6cbbd | 60,57,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
aa742cf0-d628-4143-94f6-8b7dc1bdfbc5 | 60,57,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
6bcf5a1a-e2c8-45f9-8754-0c2ace60396e | 60,57,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f33bcb02-38d2-49c0-a9fe-961d2c527ba0 | 60,57,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
00e42219-dead-4fa8-a5a0-04b301537485 | 60,57,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b4d2d5dc-ed0c-49a5-ba58-17880bd7fa51 | 60,57,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
fb7d1b97-9eef-4c81-877a-7218667d1f3f | 60,57,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
bd4515fb-1843-47c4-a2db-6147e5297306 | 60,57,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
e41bb173-bfea-42e7-9d9a-b036397134d3 | 60,57,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
35757c39-a277-419a-9ccd-65b996cfc04f | 60,57,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
400d41a1-3034-4eed-a6ab-966649cc2fc9 | 60,57,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
9aefac7a-642c-457b-bd80-4cf2d6a0c46b | 60,57,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2ef2ed4e-a1c4-43ae-a40f-75d8000bbecb | 60,57,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
409feead-d113-4f8e-b9a7-0caf939fcfeb | 60,57,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a37bd807-7962-4907-8b88-17bf177f2583 | 60,57,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
40ee9ff0-cfe9-49b2-8bf2-81b1d89f72ac | 60,57,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
79ff28a3-6334-4bef-b0c9-71f861b9ac1c | 60,57,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d698fb04-9503-497d-a3ff-b6ed0b792df7 | 60,57,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
04a55683-2ef7-4b55-91ac-9d33173c0cac | 60,57,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b92d1348-953a-4bff-a002-a2b2c4666e41 | 60,57,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
13013df9-1d0b-411b-8c50-f9af9ea89544 | 60,57,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
bfafaf24-b658-42a6-af89-d716d2f76be2 | 60,57,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3f5d610e-c7d9-4c59-8c3f-72e618ca0333 | 60,57,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
6fc58c5a-49b4-49a6-ba4a-1d490132016e | 60,57,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
635d400a-d120-4334-895f-132cd9e0b0ca | 60,57,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8bc955d8-b093-437b-9cd3-9f3ce444f8d4 | 60,57,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e7bac1ad-1c4c-4186-91fc-69e8b00d1ca2 | 60,57,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c43654d7-1f1e-497e-b5e2-5023ac13b446 | 60,57,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6822c0cb-37c2-4583-b855-2068f3bce264 | 60,57,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f9b7d326-621f-44fc-ab16-ee6d7ed7e779 | 60,57,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
20e547ce-387e-4881-be49-72346d6d85a0 | 60,57,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
572009c9-7830-4c35-9119-2e5de8a51fde | 60,57,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
482e78d5-8e35-40a9-89b0-5862ae05279e | 60,57,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
0142ddf2-0204-409d-9831-a4ef1304e5a7 | 60,57,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c1f9b9a3-d5f4-492e-b9d2-da1c08ca1872 | 60,57,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b43e4b36-4730-43c1-a36c-efdbeafe288f | 60,57,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
37ab1cf0-583a-4d19-8860-4705f3670c5d | 60,57,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
16cb3763-ad63-4b14-8b56-38b286147476 | 60,57,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
546fc99a-3a4a-477d-8b50-432b5e673419 | 60,57,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
79450453-3335-415d-8353-4364a587686e | 60,57,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8f922f46-b7a9-47c2-9dff-ec898c767f68 | 60,57,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
c5074bf2-fb5f-471d-8beb-2ad11f9b1ae1 | 60,57,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
0aa3d929-05dd-4a8d-81ad-d68fe1274503 | 60,57,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a598772d-e8a1-4ecc-b688-f69c57da61c8 | 60,57,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6832714b-025e-445d-83ee-2392998351ef | 60,57,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c3753909-06a6-4d03-addc-144a39a133f0 | 60,57,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1ee38743-cecc-4fa1-9d27-cb050cb957f9 | 60,57,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e7bdb47e-8f1a-4932-ae50-116a32511f7f | 60,57,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6b37589f-c096-4401-a62e-7eaeb20b3629 | 60,57,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2f3d8fa0-cc9a-4a2e-a392-399ab57326f7 | 60,57,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e089ad38-1afe-44bc-879f-900a2051a729 | 60,57,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
dcac804d-c450-4df6-8200-cb877ef8b909 | 60,57,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
2d924343-ce93-4ec2-b910-0b96df5fd018 | 60,57,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
02eb931e-1c8e-402b-bcae-6af0ee4b594d | 60,57,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
8cc7b066-d1c9-4d56-9ba6-0d76509cf482 | 60,57,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
502a2cc7-ca4e-4f2b-83f3-9dd27322c746 | 60,57,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
1be8758b-6253-410c-ba06-14209c5c7a84 | 60,57,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
697ec6e9-7fc9-465a-bcd8-af29e382f471 | 60,57,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
91045d74-c3d1-4b1f-80b3-f432616b3630 | 60,57,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
3615fb8d-3c7b-443e-91a3-b866b164bb6d | 60,57,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
59ac610f-de8c-4f54-b9b6-bec98e0f16d6 | 60,57,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4bdc3b1c-faa9-4208-925a-57552796113e | 60,57,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
99828779-94f5-48da-8f00-d41e5e2bf9f4 | 60,57,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ace6d7e2-20c0-4073-91cd-f97aa4fc1cab | 60,57,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
27eeb14b-fc6f-4357-9ff2-7ee7d3e01bf3 | 60,57,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
18716055-482a-4079-894b-b7a0b9e2b09f | 60,57,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5a1ad153-fdca-4329-b62e-20848d98d9af | 60,57,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
40202142-24f8-4ca7-83c5-4956356d5997 | 60,57,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ef1f4a43-547b-4c03-afb2-760cabc5bb02 | 60,57,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e4076c3f-a0b6-453a-bfee-3a32a485be5e | 60,57,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5a01b878-9f36-4854-b05f-64699d360f85 | 60,57,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
837ba3ea-08f4-4375-b9d3-9e35e2a5b937 | 60,57,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
bd5ff2e5-6acc-423c-9737-1fecec6375c8 | 60,57,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b604d2c4-62b6-406b-8f0e-8224b3a3f4a4 | 60,57,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
6cc33d2a-a77e-4b12-bd02-81b1bd0b5f68 | 60,57,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
3e2a26a2-3e6d-472f-8e54-c394e749a3a5 | 60,57,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
2b87a30e-f546-4526-9484-0762899f8703 | 60,57,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
dd96d44d-a0bc-4b73-b954-213a40621618 | 60,57,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
959fa807-e5b0-4f90-a5d7-96ab7eb384f5 | 60,57,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
2765fdd5-05af-4f23-b7b6-105703c69d07 | 60,57,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e34304e3-211b-4f56-ac3a-7e9f9e782656 | 60,57,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
5617db10-5af2-4712-b416-2c596a4b2be1 | 60,57,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
79b16d94-daff-4d4f-ba8a-f3a573312fa7 | 60,57,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
399ac6a9-28ad-4165-be91-20d0e811d160 | 60,57,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
26e1ddce-5ec8-4a40-b743-de6c760082f2 | 60,57,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
4fc7c6be-3164-4818-9fa6-e2bf9a465c09 | 60,57,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fdaa8553-ff44-483a-9a36-9eb3dd23ebc2 | 60,57,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
a90dec25-0b70-4f1b-a225-1f5315754c14 | 60,57,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
7f990147-13f2-4679-b1fc-bc9ae2991e23 | 60,57,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e194dd9f-7e55-4709-a39b-524750b9de88 | 60,57,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
cf15d9f6-4abf-4535-ae50-257267a67a09 | 60,57,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
7ca7dbbe-34d5-49ca-87a5-f6a83dd140fd | 60,57,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0cc7aac5-bb88-4902-b31f-1592183fd417 | 60,57,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
0b7b415f-9eae-40ce-ada9-2e802e7dfa47 | 60,57,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6889bb27-def5-44f6-9ac8-741ed7ef0d24 | 60,57,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
329a4b17-5905-40a2-894f-26d545dc85e9 | 60,57,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4211be53-db30-41a9-af26-ce7254d2d657 | 60,57,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
dfc39926-9fa5-4b49-92a0-b48fe7edbf3d | 60,57,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
40253d78-0df4-47b9-85d2-d2073d0d3ff6 | 60,57,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1eaf5d35-4f6d-475f-9477-efad5805402b | 60,57,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2aebd280-c84d-4853-be1a-1a499c8ce708 | 60,57,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
297cb747-4e17-4147-a72a-843483790af3 | 60,57,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
d862db29-b628-4880-af82-b555cbb2821b | 60,57,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
94397f06-4022-48cb-af12-f013877a6b08 | 60,57,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5c7e8f21-28e2-442b-b70b-604f6c28f416 | 60,57,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e2c44efe-4490-4c4d-855f-e9395df2418a | 60,57,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2384e181-cd1e-4ffc-900d-d8cad59bc9b3 | 60,57,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
9afaad02-68f9-4905-8f38-47d53c2d035b | 60,57,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
93ae20f2-b2b6-4387-bade-22b09e88d351 | 60,57,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6aed6bf9-2d58-43a8-98ef-266ab0088b10 | 60,57,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
8edc99ca-021b-44e8-991e-86fac2af0b88 | 60,57,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
47d46dc0-d330-4d4c-985c-579845c4c140 | 60,57,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fd208c1a-402e-4e13-9991-a3344e007160 | 60,57,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
be388ddd-b1ea-46c0-8254-12d554b13581 | 60,57,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
035b835f-57be-4cd6-8f9f-75b8e1bd8906 | 60,57,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
146c2439-267c-46d7-becf-defb1a042f52 | 60,57,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
eeffa608-3cff-417f-ae83-401a27fabf31 | 60,57,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8b144f94-e706-4df3-a14d-fec925a3467a | 60,57,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
14a57856-1529-4b4a-bc1a-5bb98dac4028 | 60,57,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
13fc9fd9-f58b-470a-8d0e-8592ddb75f2f | 60,57,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6c4ff762-1366-4363-a557-3044c5c1042a | 60,57,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
73bbacc9-4eeb-43f0-a39a-757dbd1b9f38 | 60,57,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1b1f18cc-73ac-420e-acbe-d3e66c2990e1 | 60,57,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2c2bf3e4-8039-433a-bd4c-6e7122679c2d | 60,57,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e535733e-7e1c-4d05-b4e4-0657e5da3b2c | 60,57,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
f49b00d3-3e8e-4649-abf0-80b473eace46 | 60,57,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0beebae1-3733-4b88-93cf-0cc6332b7e3a | 60,57,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
0c0090cc-9a7a-4f47-a11d-d3744efa6e29 | 60,57,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
ce4eee8d-f7b6-400d-85c7-77701433044f | 60,57,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
274d07dc-6bc7-418c-a4d9-510ac452d967 | 60,57,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e3e2750a-bea8-4d06-8344-21511a23ec17 | 60,57,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2400b11e-6991-413f-a8a4-b93aa6ac8ce0 | 60,57,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
bf628a38-590a-44c7-8c73-d9031b1a754c | 60,57,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d7c4346a-3590-443f-9e86-7967220a7d7b | 60,57,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
59b08a53-147c-4133-926a-cde1cd3687db | 60,57,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e4dc78d1-117e-4162-8638-69d22b41b93f | 60,57,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
e325a9d6-f4df-463d-b7d0-75e19bcb7819 | 60,57,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
dde8ba28-b9d4-4196-8090-df90f5cf4115 | 60,57,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
a60d6bfd-db9c-4aa7-afb0-7016f0c4f0eb | 60,57,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
12b84969-8f1b-4266-bab6-f80dd51bb6bb | 60,57,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
9812c50e-03d7-4d5d-a2d5-bf51b35bbc2f | 60,57,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
a309e281-fac9-4b48-ad71-597c81386c4c | 60,57,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e20d0f1a-e2b6-4b95-ba6d-cb396feb1ef5 | 60,57,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
97c0109a-bed3-424f-a73d-59e606ae44f3 | 60,58,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
67ff2ecf-8e0a-48af-8e8c-8056b0cf114e | 60,58,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
208981dc-815e-4681-a3d0-07fc18621e5f | 60,58,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
93b13235-87e7-4be4-a42d-395d9beb16a9 | 60,58,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
1e88c914-3a9a-485d-a663-ea05d02715e1 | 60,58,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
5ae21701-7c56-40da-8097-1b9b13761915 | 60,58,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
14a6d54c-eb39-4841-b376-014870fc432f | 60,58,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
27c3aa35-3bfc-45ab-99e3-418e53b48549 | 60,58,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
42a75381-e1a5-41e1-ba28-2501f02777bd | 60,58,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
98c91b8f-5d6f-4619-b77c-3f2a1c2c8f89 | 60,58,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
46df7247-5393-4068-9748-5f38bd4f976c | 60,58,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
3a05f856-017e-427d-8a84-8922f51f727d | 60,58,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
e25f521f-cd23-419b-9e3f-db49e408a2a9 | 60,58,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
0cd099a7-c538-41f5-a482-c0f7acf872ed | 60,58,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
1630b7e9-8cba-4182-856b-693595e1f17f | 60,58,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
764874fd-298f-4f9d-9824-5c87608979e4 | 60,58,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
644b154f-b2f0-4e30-a610-813693122925 | 60,58,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
5a5e2c5b-120c-40e5-bec1-172e1da7ced0 | 60,58,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
d5abc537-077d-470c-852f-56d278363a49 | 60,58,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
85da841c-532c-42c7-81ed-341f1ca3c19a | 60,58,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2352afd8-0c99-42c9-8283-447a6ea93d78 | 60,58,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b97053c8-a7d1-4060-921c-0171d9f2bc85 | 60,58,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
2f21f5b9-a502-4455-8c74-b09935fe5908 | 60,58,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3a63ee3c-a90a-44bb-97c1-00f92a49719c | 60,58,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a3a381ea-4aec-4030-98e0-d435c8268168 | 60,58,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
dd55d530-0ba9-40a4-b1ae-a3bdb623a705 | 60,58,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8704d973-7501-4c10-899f-2b9115c7dd42 | 60,58,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
2304e9aa-614b-40d3-8bad-497ca598d2d9 | 60,58,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
968f2cb8-2ba7-435f-a747-5f5577103d03 | 60,58,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
cf38b08f-727e-46df-873f-8c05f03337bb | 60,58,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b7336d43-56a5-4ba6-b2a5-65f3d0f04001 | 60,58,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2d6073f8-ae35-4e3f-a268-4bac7d738442 | 60,58,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b85f2678-ee24-453f-9a62-c1c9b37e6ce5 | 60,58,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
acd3ab43-04c6-4b3e-bed2-529ea8a771c0 | 60,58,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6f8c60d2-a9d6-49ab-9d0e-50719a2294fe | 60,58,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
3c6e9a90-6df1-4f8c-b9a3-898ee09109fe | 60,58,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
99b81622-925a-4fd7-adbb-651ea41f9787 | 60,58,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
195b3639-ffd2-4db1-97a5-24a2d52086cd | 60,58,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1748b924-8afe-43f9-9bfe-075ecc793684 | 60,58,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ca1670e9-9de8-4eb8-82be-268d61177016 | 60,58,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
91150acd-913a-4a4a-a238-f291ed3413dc | 60,58,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
405248f9-6aad-4562-8e88-2e33c6f54325 | 60,58,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
b87b0946-cb35-4d40-a649-94358015d963 | 60,58,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0794e235-7ac8-47fc-b5d9-ce33b507cd38 | 60,58,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2eb271ff-262b-42ce-b233-cef837e0edbc | 60,58,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
029bd0c3-0654-43f1-a029-5c8d90c5ea5e | 60,58,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b48c93e6-fc87-4ed8-a9f5-0a33fde19bab | 60,58,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
754da5aa-5388-40cc-aeda-cfeed4a57e3f | 60,58,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e2702273-2adf-4c2a-b57b-c387a6f41154 | 60,58,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
4a36ad56-a291-42a0-bb8a-ac38c5a38f6e | 60,58,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2ceda6c3-7c81-4563-951f-49d8d64e03bb | 60,58,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2114cc27-b915-4c6d-a0cd-afec7cdea6d0 | 60,58,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f5487e64-f00c-47dc-986e-79e8c7bf42cf | 60,58,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
502d696b-4f0a-45b5-aded-3603d1e3fea6 | 60,58,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b29fac53-e206-4c01-bc6c-1b1ac24e2ad0 | 60,58,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ef07e60d-fc52-4ec1-b3c5-0b931bdcc17a | 60,58,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b5fe2db6-9d36-4428-b98a-96e6a533f669 | 60,58,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8ad1cccf-2fe6-4a4a-b3e7-5be1c2627c3c | 60,58,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8f61ce1c-1e19-41f2-83cf-4d53cdb2c700 | 60,58,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ca4483c6-ac4d-4827-aafd-458a778181d3 | 60,58,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
07777bb5-83c4-4479-9233-261d86e1a889 | 60,58,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7b512751-4ca5-4ec8-aec9-31187c396995 | 60,58,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
f6eafa53-60e6-4588-8511-2d61fccc783c | 60,58,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b6c70b30-b015-4f8b-9a7a-a3e9d06756e2 | 60,58,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
85f90c72-d75e-48c1-8f62-f1ddf7fc0abe | 60,58,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7eda7d38-a266-4757-b0b5-ceed8eef842a | 60,58,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
54b4f9db-6991-497f-9c28-129040c41af5 | 60,58,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
7d05ac4a-d12b-4cb8-b4bd-daec1278115b | 60,58,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
bcc6c402-9e53-44a9-a420-b804cadb5e6c | 60,58,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
650d94b5-db20-43db-b9f5-1dd046ffcbb7 | 60,58,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
44d86f47-525f-4595-a3a4-87de5b0f0b29 | 60,58,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f182727f-b569-46d1-ac38-67b763625077 | 60,58,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
45c414a6-075c-44bd-82f4-8345ef37bf74 | 60,58,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
04df5704-b7b0-4938-a2c8-0bafa0dc0aa7 | 60,58,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d14f81e8-1410-4326-8e33-0ee1a9fb1e80 | 60,58,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
cf34aa27-f5ee-46b7-9911-7f85e29b20de | 60,58,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
bb22ac5c-8a1b-4649-ab20-1c1c931e522b | 60,58,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5506f62d-7f6e-49db-8220-5e85f719959d | 60,58,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b2aafd89-faa4-4c12-90fa-0f431b186337 | 60,58,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
6e3717ff-b69c-4869-a877-1403f7a1e7b2 | 60,58,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
11561b27-051b-459b-a2f0-d080b0aea8ef | 60,58,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
4892f813-1e8c-4e58-adcd-0796b37a1eab | 60,58,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
3054c6f3-c8a6-4434-a231-1fbdd04b2499 | 60,58,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f3a64745-e499-487b-8505-8f7a1803ac34 | 60,58,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e5e3bf83-9b50-4554-a7cd-97715be21cf2 | 60,58,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
070a6baf-5a3f-43c7-a333-4588bf9008cb | 60,58,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
38009205-556c-4660-ba5d-21f9c405b0cb | 60,58,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
7afcd942-00fe-4e75-89ac-62cc81c1a82c | 60,58,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
54cab194-912f-4d18-92ac-f4dbb8a3b12a | 60,58,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
601342a9-41ec-4e18-b197-02445e3b334c | 60,58,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
091a4d54-c79d-4c2d-900f-f7e51429862f | 60,58,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c9c27b32-5900-412d-8289-696c52a0769f | 60,58,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0fbba3f7-1612-4ddf-a938-92e9759554d7 | 60,58,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a5254111-37af-40d9-907e-083a23e62aed | 60,58,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ca643e7b-8f7d-4c86-87f9-b8fbf267a503 | 60,58,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
65afe387-f92f-4526-8049-4e8e001199be | 60,58,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
7a23628b-44fe-4350-a51b-688b8071f41e | 60,58,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2ff1d07f-b364-477a-868e-b5eaa2789fa4 | 60,58,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
97830e4d-56ef-4555-8587-5f37ecfd99a2 | 60,58,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e761d8e2-1fd9-4632-843e-9c43a7568070 | 60,58,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
77488766-5bee-4f9d-b1b8-2d2cd02fdcea | 60,58,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2dba17aa-6f79-4d29-8443-3a74be64b760 | 60,58,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
fbebff99-ffba-4dfe-b3a5-01f426a5b7e0 | 60,58,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f9877a6c-2f7c-4bca-8fca-7be04ff55fec | 60,58,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
297be94f-d1ae-45b6-90e5-5b4cda2bd96a | 60,58,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4a474d01-7b37-49ef-a4e3-a935f25ae5fc | 60,58,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b23044f3-6ee0-4525-828c-6c64e3dd0856 | 60,58,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
976dbb71-904f-4c66-b249-5dc5df14a83a | 60,58,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
cb14180b-3dff-4ad6-a5ea-26fe0408b588 | 60,58,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7eeed0a3-85ff-4c54-b377-0e462c60e5e4 | 60,58,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e1793786-d07d-43d4-8deb-0f6d5459eb1c | 60,58,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
74a5090f-5c7d-40c7-a25f-e8e6cd5ad0b4 | 60,58,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7c840a56-f2df-458e-9b34-4e025d4bd8d7 | 60,58,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b0497030-54d1-405a-947c-3e59a2b1403a | 60,58,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ee5087c2-c4dd-4a34-a3e9-5cb9af673648 | 60,58,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
9e8d13b2-30f3-4823-a41e-7ad8c50090cb | 60,58,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
625ccfe4-be8d-454f-a09a-58d3b5649423 | 60,58,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
eaa9a774-0c7c-4dcf-bbbc-b8561b0051b5 | 60,58,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
437c290b-e3fb-42a8-ac60-1a121e527524 | 60,58,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6c358b4e-2b02-4dd4-9744-c0c53f8f881a | 60,58,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8d9a6116-f6b0-4e82-8ee9-6130322e848d | 60,58,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
bb62dfea-6d1f-4c73-b9f0-8e16bff6ce58 | 60,58,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0c8e79b9-db4a-4f1f-9747-ad46cd4423b6 | 60,58,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
888c26b0-542a-4aa1-a382-3d3720624f5b | 60,58,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f929943e-215e-4ff8-8e00-0eeb40708c6b | 60,58,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d3a5a4a1-f4e0-4b73-ac62-41a93ec16c05 | 60,58,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1bbeb91c-6aa2-4c4d-b632-a94e327aebb5 | 60,58,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
27ebfa5c-1967-4a1c-a8d8-bb02912c08ed | 60,58,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4fd53ea0-4a1b-4374-90cb-a90b2aea6cec | 60,58,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
eaa47156-ed0b-4d92-a721-bd489207c024 | 60,58,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
583a0256-78f3-43ce-9d06-3d9b55d8f2b8 | 60,58,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e6afbeb9-f084-45c9-866f-9eca7ce15912 | 60,58,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
3e5c87ba-4b77-469c-8834-3b3319624b97 | 60,58,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
67eb61b7-2f28-427c-98be-c82b7276384a | 60,58,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b5ad5a02-a031-4b0c-978e-51dad769f05c | 60,58,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
df97a4a2-ea8c-49a9-814b-5af1d9516975 | 60,58,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
35c2cb98-c7e8-4efe-b5e9-0169056ef87b | 60,58,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ed610f0a-c4c6-4636-a6b1-fa33fe97c31f | 60,59,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5542a846-1478-4e05-bfab-306db962a407 | 60,59,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
00494432-ee81-42a6-bdda-8f49389ef9bf | 60,59,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7f14cd90-6927-4f55-8694-1e63489ff38a | 60,59,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
6da91e76-b234-4988-9777-5dc4fe5b2791 | 60,59,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
ae975802-9dd6-4ca3-8b86-b6c5cd290467 | 60,59,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e48c4ee2-bb8b-49f7-8f76-d5f4e0cc6cc7 | 60,59,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
5e231ffa-5b88-4ec3-8f11-d4aaf770dc6d | 60,59,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
457fcc11-bd11-4b04-a4f9-6dec371ef1f5 | 60,59,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7929e14b-6b69-4dfd-8870-a165545f4ee4 | 60,59,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
b3054f44-ae11-44ae-aff1-181269a8195b | 60,59,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
f67f0b10-480d-4cfc-8ba0-3e51a8d75fcb | 60,59,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
0f1aac79-cd5e-47ba-a30b-a941184b5b69 | 60,59,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a793301c-4b43-4f3c-b057-a34da3793534 | 60,59,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
0db64315-9ad8-42fb-8a8f-5cc2fd378ec6 | 60,59,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
eb402838-1c0a-4853-80e5-173df080534a | 60,59,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
608debce-4dbe-45f8-8705-1526362b1751 | 60,59,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
8be520aa-29cb-4c8d-8599-996b7ea6b77e | 60,59,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
a9fb0158-3d79-4142-a7cb-9c663011a8eb | 60,59,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
24e5c1f7-b89b-4fd6-b903-df8a81e28a7b | 60,59,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
39976bf3-a8c7-4a45-b9be-463eccb2dfde | 60,59,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
153232d8-736c-4325-b794-64687bc6f424 | 60,59,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4219b027-3f0d-4a48-a689-0ed6d908f072 | 60,59,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c9fbde11-08b7-46c7-b283-2f8145a9c5a7 | 60,59,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
9ec7ed0b-f687-429a-bb6b-42ff833d6774 | 60,59,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
3877a20f-cb8b-4efc-8e39-30045df2d453 | 60,59,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
12cca6e4-8dbb-443c-9ef9-4eb916de4333 | 60,59,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
24782288-8912-484b-8791-b7eb03431b80 | 60,59,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
bb93b91a-fa65-42bf-853c-0c9d7333ea00 | 60,59,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9677e231-bdf3-4985-a3f6-cf73b4da8b74 | 60,59,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
24c818f1-4528-45e5-9934-a10db237a8f3 | 60,59,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
4bb05882-e31e-4e28-a5c1-a7635d3df8dd | 60,59,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
7737c9d8-9566-4104-ae4c-8d5eef6fae43 | 60,59,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
dfd170d7-761f-4a3c-ae8f-4845bfe0c34c | 60,59,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
40bb517e-8e51-40f1-afe0-5ea7ea3e1361 | 60,59,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
8addb620-22c0-4cd7-8412-e6e4254187e4 | 60,59,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8b131918-2edc-45bc-9012-9110f0c600d2 | 60,59,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
ff17518d-f218-4755-98e8-5072d973ace8 | 60,59,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b60a63dc-0c1e-49d2-82b7-47f7eba8cec7 | 60,59,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bcb37c55-9764-4f56-9d48-6702b9c69a5d | 60,59,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
12877775-3170-4e0d-8c5b-988096b8c202 | 60,59,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
70055ba3-e345-4732-ac74-1495e7b0a9db | 60,59,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
93f69281-3812-4dd4-a045-4c1369b059b6 | 60,59,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
033668fd-0532-4d8e-8e85-e3123bcee4ab | 60,59,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
50422b65-0a75-4ebf-9f61-1ad9fe2da520 | 60,59,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
f74c10f1-8e8a-47fd-b52e-74e64896efea | 60,59,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f2225e02-98bf-49ed-bf50-af94af32fc32 | 60,59,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
4cf05aef-ab99-44b8-bdff-911a4e628a64 | 60,59,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
81c84f00-4bc8-4fa6-bc02-d63f48f47ec6 | 60,59,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f25515bd-33a5-4885-a739-1c189def8e4f | 60,59,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
b6060c25-bed2-4e18-af8b-bd9af17152f5 | 60,59,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
7c89a037-d30d-40de-a37e-5fa43eeb9126 | 60,59,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
48e56edc-07ee-473d-89f4-4ece319a13ad | 60,59,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
2803b8d7-e2b1-4180-8f73-d1d0808c6f18 | 60,59,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
cbee6343-7765-4b76-8d6f-b160145c00ad | 60,59,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
afee8408-f081-43e6-9348-5b9b1124a101 | 60,59,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0aaa664b-8697-491f-921f-f370b82bec0e | 60,59,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
20bfd70e-6381-4cfa-87dc-d53a903720b1 | 60,59,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
317f7630-4b01-4e02-a2b1-0abb42791895 | 60,59,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
52d0dcdd-8a54-4239-9202-281940a4239e | 60,59,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
d45b9810-6080-453d-bc75-814520194283 | 60,59,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c7e56e67-2a8c-4900-b41d-f5717486ed39 | 60,59,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
30b429c8-ee91-4ace-ac1f-253799a5f731 | 60,59,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
8967397e-004e-46a4-bcb1-3e419500d4d8 | 60,59,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
525d3d8c-b8de-4d9b-9fe8-ebbb4ed786a0 | 60,59,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
63da3d0d-63a6-4fda-b021-462276bf4cbb | 60,59,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
41f00b02-2b39-4b06-a5ee-b401908888b0 | 60,59,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
3dc062d6-c003-422a-88f4-afdfc184cc31 | 60,59,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
5204417f-c055-4463-ae73-5acdcf006770 | 60,59,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
87c05f7c-90f1-4268-bd7c-cd0b81b7fbf6 | 60,59,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
c2f5997f-86fc-4888-b952-eb151dae2b30 | 60,59,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
954a1b41-908b-4aad-ac46-4c0afba04440 | 60,59,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b7152569-fa53-425e-9a8d-0f176fc0e918 | 60,59,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f646fe6e-f834-4d93-af01-9c235460e299 | 60,59,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
43de87f9-1b53-43c1-b005-4c044e9e61b4 | 60,59,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5e127f6b-b2ea-4b2f-a08f-ef32c6d439cb | 60,59,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e6d3cb75-b712-4372-a039-0db758409235 | 60,59,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8805d23a-a52c-4256-aa62-b00cb7d94082 | 60,59,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
13dd6bfe-9670-44e7-9040-42c2a8cf88e7 | 60,59,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
a82341e0-2006-4e6d-9ab1-82d261133fd6 | 60,59,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
5b3cdf98-1426-42c5-88a2-7102b33ec2b8 | 60,59,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e0d21f41-993c-41af-aa46-f0e91f9ef4c0 | 60,59,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
113e8991-b315-4fc7-a045-48949851db76 | 60,59,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
64f4058a-79d5-4ce5-abc5-358d6e8f2ae4 | 60,59,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
dc6ca24a-b86b-40d9-9a27-c5866424a09e | 60,59,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c127f493-4ab0-4d62-9dc4-4ba090e5ab53 | 60,59,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
88f251e9-98ba-4a32-9515-53ff3024a30a | 60,59,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8624e693-0434-442e-8d55-af1ae2556385 | 60,59,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a8650d6e-7dc0-48b8-b29a-8aad2fd03db3 | 60,59,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2ffbd6bb-e328-4d50-9fd5-890d114dbc86 | 60,59,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
81d01a93-9bfd-443d-b4d0-9aae1699f24c | 60,59,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
215dd72b-0611-4271-a5d1-7ff62972ba14 | 60,59,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e8448bea-d0f7-41c4-9507-72edd69f478d | 60,59,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a9e1da87-10fd-4711-bde3-c4d3599edee7 | 60,59,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0bb79b08-d27b-4eee-b810-2f7443542c66 | 60,59,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
aa577fe4-2a59-4a83-ad09-b71c90467d89 | 60,59,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
2d54e711-f5f2-4b25-9be6-40ecf888802f | 60,59,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
273743f6-6d60-4a1b-9594-1707ae74277a | 60,59,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
142dfcbb-72e7-4faf-957b-a08f4c3e4ca0 | 60,59,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4731461a-e4b2-43ce-8024-fb4b06570253 | 60,59,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
20054e6f-1ab2-4851-aa7d-8a8166d50423 | 60,59,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e15ba5da-e374-40ae-82e8-973aa989d3a6 | 60,59,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
22d5626c-ef46-4302-895a-9ea8f1a8b5e6 | 60,59,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
cb24521c-cb2d-4175-acb7-1b18ade7306c | 60,59,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
37b4bff4-b1a3-4896-b0ee-bfb2227e61b8 | 60,59,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
258a4a78-a288-47cb-9e1a-bddf77000932 | 60,59,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3198fbf7-c81e-4af5-aa37-efdd0da6129b | 60,59,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
61b4a6ef-9dc8-426f-9c55-e2417e7e3ea6 | 60,59,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0fb59a8a-99a9-463e-8366-a20b56f9a83b | 60,59,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9ca5478f-249e-472f-8839-cb1522482a17 | 60,59,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9490b666-0d29-4216-9928-d3361d7ec76b | 60,59,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
b7ab98c0-42ec-4d10-b6c3-7222f54dd9e1 | 60,59,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
dde47fc5-8310-495f-bb51-02d0745856fe | 60,59,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
be62f29c-52be-4f68-b64b-610e50328689 | 60,59,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ffb6c4f6-8e88-4e49-a003-21dccf4e8401 | 60,59,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
f09099a1-32d3-46ae-9d86-257e47056022 | 60,59,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
53adb09e-36ac-4d40-8004-309354b7fa65 | 60,59,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
11ed1ad6-d0aa-4244-a5eb-de0d222a855d | 60,59,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
a7c3d5c4-2a2f-4c4f-959e-a84c064e02dd | 60,59,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d74f7a33-cecc-4602-9c2c-9fbbb9f45be8 | 60,59,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
fdf18eba-66e5-42b7-bb2b-3afcb2ba6a72 | 60,59,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
c9e8cfb6-3275-489e-b0b3-0468a936772a | 60,59,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4ed720a4-cbe0-4f32-9e66-ac500fd7a6f1 | 60,59,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
adb4dac4-79d4-4bca-8e2c-939ccfbc3e2a | 60,59,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
927425e3-637a-4c2a-8886-94303d93c218 | 60,59,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
3887f624-0834-4517-89b0-ee78387b239a | 60,59,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
79600ecb-9819-48d6-9432-3db387d00fd8 | 60,59,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
b82cca5d-eff7-46f5-8ab5-892ad6f28ee9 | 60,59,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
edba74ba-beb0-446e-a6ee-e29c8f54154b | 60,59,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
055f764a-7416-4387-9cf2-d624eecd44c3 | 60,59,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3f71285e-471d-45bc-afee-06d7c5cabd0d | 60,59,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7a5d7784-c700-49c6-befe-a4a5eac2d192 | 60,59,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ff52bfb7-9a32-4b2f-93fa-25272cff9b25 | 60,59,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c64acb46-0aa7-4813-8cd6-a356a76e24f7 | 60,59,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
49110339-6819-4fc9-9211-dc7b18fddfcc | 60,59,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
bb8544bd-5bfb-4f5f-8dae-84070cc71d0f | 60,59,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c81987bc-bd11-4a35-9abc-222c9240ca9f | 60,59,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT DAMPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5d483b4b-f203-42f1-97a0-adde4096ab25 | 60,71,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
09a9b855-72f9-4785-a70d-548b5c8c739e | 60,71,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a4d0fa2d-5a09-43a7-8b32-3cc813a3e370 | 60,71,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
585db2f4-8301-428c-a85e-9255d8cb6d00 | 60,71,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
662a2f4f-bf60-476a-bcda-6f763aa9e489 | 60,71,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
43086d1d-c526-468d-a5d1-34a924fe1efb | 60,71,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9a1088ff-af81-4cbf-8439-3110911d6fab | 60,71,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
de848d86-4fc5-4d94-a2d0-c90a94563bb3 | 60,71,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d49c6736-9158-49c6-b227-5a79751c06be | 60,71,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7238e175-3fcf-4417-8452-7c27ed786861 | 60,71,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
e6027f0f-4079-4331-a2e1-54c36e3d155b | 60,71,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
245a6c46-a97c-4b75-8b1f-923100589d83 | 60,71,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c654ce86-d705-4737-84d5-d6780e4108f8 | 60,71,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
60622247-53be-4ce9-9984-a9cca0be2b1b | 60,71,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
9fd6de78-905b-4173-b004-6f9c388746d6 | 60,71,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
312c451e-400c-4f60-ac23-5e42941159e7 | 60,71,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
65037e64-c6b3-49c7-a68b-595b9e0deb17 | 60,71,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
9a122070-b2ff-4f02-a507-c09d1d324b60 | 60,71,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
77733f42-2497-4247-b6aa-a53d16d53807 | 60,71,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
a482fa36-6703-4ba0-94d6-9c01de08d4b8 | 60,71,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
2b17c536-8323-46e4-bff1-8c481fef3fd9 | 60,71,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ecaf2431-e2d3-4d8f-b29a-fc3457f7cb17 | 60,71,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9a6b5a80-1b5b-4f74-835c-4db768fbc8c2 | 60,71,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
974bd0e0-43f2-40da-9305-a46e740deefa | 60,71,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a62f03dc-d91f-442f-81a9-829df9176a4a | 60,71,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
57438d5d-c317-4327-bd72-337cfc0f09ae | 60,71,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
539fcd5c-4686-43ec-bd67-2221875e49ed | 60,71,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
145bd3bd-275b-4714-ab6d-3e14715abefc | 60,71,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3d2ac12f-2ab1-4448-8755-8a1482020502 | 60,71,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a75bfbab-a6d2-4a13-aa96-9b3854177188 | 60,71,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b937408b-14f0-421e-bd1b-7964010ede95 | 60,71,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b360055b-43e8-4e40-b246-30ca3af00974 | 60,71,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
539854a2-3286-436d-830c-e4cbde2aba00 | 60,71,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
20bc7017-84f4-4fb6-a17a-492837688510 | 60,71,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a36f0039-ac1e-4174-8d2e-65211145cef3 | 60,71,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
4152756d-6402-4d20-9482-3f82dcb43986 | 60,71,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
033b584b-4451-4fbe-9f8c-f371866c24ca | 60,71,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
2d261e15-9312-4559-92d2-9cb0901cf5c2 | 60,71,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
22303f10-34fa-49ea-99eb-568a16abfe20 | 60,71,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1dd0a999-d187-4143-8eaa-a633b58ea117 | 60,71,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
78aa6783-94e7-401f-b79c-4e183401c50e | 60,71,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2f53c565-e383-478a-aae4-13e751c8a371 | 60,71,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
06214471-2b10-4c66-a056-95cf7794e46e | 60,71,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
66a50b81-d900-445d-981f-34aafeb5ce61 | 60,71,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6b45ba30-dfd1-4c90-8ce7-b9ede6db5948 | 60,71,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
57baae2a-c951-4ec6-a319-75c7aea7288d | 60,71,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d709f31a-0233-48f2-b937-5918d81cca03 | 60,71,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
fcde83b2-0c30-4e6b-947c-840e46b8b65e | 60,71,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9c349f8c-c344-4f47-b86d-2357869e38d2 | 60,71,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
e75779fb-c819-4ff9-bc16-5a529f0fb6dc | 60,71,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
9502fdb2-19bd-41fe-b922-644cf73443bb | 60,71,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f12df2fc-c705-4904-9624-a8e4c9f5632b | 60,71,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ed9eb876-d1ec-48cc-99c1-72698a95070c | 60,71,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
c40c4ad7-6786-4c9f-aac2-401b87b42863 | 60,71,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
fd45d468-c582-443d-9183-b43f9c9c6875 | 60,71,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0d72411f-50e7-4396-be35-01f4965da366 | 60,71,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5252f0ea-c82e-4372-98d4-f6f4de01ad03 | 60,71,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
708e30de-caba-44ee-b712-c6f54ed2b94a | 60,71,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
3304fd5f-3763-4e9a-94ae-65fd49645150 | 60,71,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
d946d589-a5ad-42b7-8b32-e2fed4cf3856 | 60,71,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6442f112-ba15-43ba-bd69-3b47f356def6 | 60,71,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
27d037de-832a-4fc3-a436-073ae739655d | 60,71,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
0b6cf337-fd3a-4f4e-b57a-56569d5211d8 | 60,71,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ec4cce74-6a62-4548-8d64-e155b3edcf6e | 60,71,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
96c99601-0ffe-44b5-9cc4-e0fe895a23d7 | 60,71,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
349e09bf-8e5f-4630-a37c-79a23b488319 | 60,71,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
8939ed0b-e0a9-4926-94c5-a2437d33474a | 60,71,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
d4c4cfcd-497a-4968-83e1-c2adc70cd68b | 60,71,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b3f5aab7-7d4b-40bc-86f3-886aa4ebecf2 | 60,71,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ac1ba94b-647f-46fc-bdf7-9d1be489316b | 60,71,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
17b64e81-5937-4a08-a769-7dbbd5d8fc73 | 60,71,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8e23c16d-f6f5-4f53-9aa9-1b514f5d5e50 | 60,71,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
891fb359-dd5e-4fb3-9968-6498606f75f2 | 60,71,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9c007c35-f9e1-4a28-8c85-3fd75d10826e | 60,71,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c6f5d88f-5c10-4f6d-8fc6-6493b356941b | 60,71,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9658fa3b-ea10-4b15-8c73-2afae1c4308e | 60,71,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
3011602d-4968-4250-a10b-43b63a8acf5a | 60,71,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c54c0367-0cf9-4ef1-93ab-c26a26a76f84 | 60,71,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
edc72ab6-4ed0-4191-a49b-d1d73e942f71 | 60,71,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
68453dba-77cd-42fa-b919-76f899169f9b | 60,71,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ea221201-324d-4aad-989c-fd8b3a2f286c | 60,71,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
1b0f1e2d-62b8-4942-a401-bce2c4c336fd | 60,71,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a30d6a95-0fcd-4581-a4cb-5b3eea651532 | 60,71,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
dc507df6-b993-4a28-8325-66d7e909e7cf | 60,71,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
438ff627-8b2c-4a83-8a2c-3921800638df | 60,71,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
e1b620c2-602e-4441-9e75-2ffbaf49e3a9 | 60,71,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3d192c9a-004b-4e6f-a9c5-9ef0e007b1d3 | 60,71,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
33edc8d6-a1a2-41dc-aea1-1dd9c35393c2 | 60,71,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
7a7a2c86-6325-49f0-a883-7cec5b94ccd8 | 60,71,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
cba9a132-8d1c-4969-b636-36e847e8221b | 60,71,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
32bce0f4-c1ea-422b-9d3d-0e59f24e0a23 | 60,71,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0524f8f5-2f59-4923-851e-f6662ac579ea | 60,71,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f69c2fab-8c27-469f-87d4-9d7fb6e2b968 | 60,71,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
60303e9c-84df-42c9-8431-68cbd626668d | 60,71,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3803188e-4994-463d-a132-4100fab636cb | 60,71,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f978796f-c14b-464b-88da-2a6761c8a79f | 60,71,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
1e10f393-4100-4442-bc4d-e6c641f252d3 | 60,71,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
5d98c09c-4f77-4ae6-bc15-85b63a759334 | 60,71,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
1973cb3c-520c-43f1-895c-8664355ffd6b | 60,71,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
190dc7c1-6f32-4bb1-a807-5de45323d59c | 60,71,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
01e86598-219d-4bdb-8efb-a2675d59b8ce | 60,71,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
0b7c6cdd-87d2-44cb-a443-022a7f714b8b | 60,71,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
def40b7d-26b4-4135-a63b-4bdf9871f358 | 60,71,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
95b8f7da-a388-49bf-bf9f-fda9d2cc08cf | 60,71,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
0a6f46ae-c6dd-4ec2-ac62-2d723f13ecaa | 60,71,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
481da6fc-9522-434e-93e9-505b51987a1d | 60,71,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
d9ceb826-d5da-4898-805e-b4608fc9c4dc | 60,71,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
cdb4330c-9c9c-4b03-9b22-beef27bd4c47 | 60,71,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
146fd97c-4d7e-4011-bb21-16e2cb701208 | 60,71,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
55af3be9-b8b0-4745-aab2-df60d3b9f400 | 60,71,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
fa14d2df-f7eb-4e75-acea-273c5daef2b7 | 60,71,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a5d64373-137b-43c0-a045-8e5c31434d63 | 60,71,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
80b53fc6-f1fd-4551-bbb0-84da0c73c9c8 | 60,71,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
527d6bf9-f47f-4588-b51f-426d898334cb | 60,71,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4895a90e-e5ba-480a-a92d-b1ce5f7ba8d2 | 60,71,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
393c5fa6-619d-4d26-b3dc-49a82f6273e2 | 60,71,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
06d19608-6c7e-4839-95e5-5da80a77fcb5 | 60,71,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9b7c6fcd-fa79-4213-bbb1-27af488945ea | 60,71,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
739277dc-d969-407e-b6bf-0f9c8be8e145 | 60,71,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
48580cf3-724f-4a20-91fd-322edb6d2df8 | 60,71,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
c03bf83c-9673-45f5-9961-e4c9c80045b7 | 60,71,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
5d922a90-b805-48e9-87ad-3cdb6f521ffa | 60,71,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
feb832e6-ab4a-4d35-99cd-aa094c9ca7eb | 60,71,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
af32d29e-1364-462b-ae96-77985d498661 | 60,71,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
4d86705e-2d6d-4436-bfac-3ab1b6fb5b63 | 60,71,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
b4bb2004-6d65-440d-b1ee-07dda72c6242 | 60,71,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
1473d3d5-abcd-4491-866c-6bdcd8b13a88 | 60,71,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
37e78138-1db9-42ad-af27-f17b9c5e540a | 60,71,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a4cc0280-3db0-4498-bd3e-e0ae6cbe4c43 | 60,71,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5c75da47-dcf0-4e47-b51b-1931adce91db | 60,71,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
3a474388-1c4b-459d-b23a-82d407d5d70a | 60,71,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e69aa1ff-e077-4f04-a5eb-f30bbb0f3985 | 60,71,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
f13f0240-1d0c-4c0f-8bfc-56c096e48187 | 60,71,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
59ccaaf7-e257-4f84-a068-5d1de715c612 | 60,71,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
96a626b8-7802-47ec-813b-e5fc134b4eb2 | 60,71,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
6060924c-a876-4731-ab08-07d521176502 | 60,71,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
968dd3c8-eaa2-4bf3-ae21-2578dd22f2ed | 60,71,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
b326a5f9-2e79-43c5-b886-78d20d0e3974 | 60,71,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
13a0afee-6494-42fb-a674-eebc19487405 | 60,71,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
0198254e-5bbd-42d8-b43a-671fbe04bc87 | 60,71,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
772ba8eb-f645-4193-8533-beb48a74143e | 60,71,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
bac79861-ef60-42e4-b264-f3e446f9a22f | 60,71,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
ce89462a-774f-45d7-b736-1fa6076bb0f7 | 60,71,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
48960028-2dbc-48ec-969d-fe72906def23 | 60,71,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
29c32d71-2f41-4357-9f59-539ca3e39d73 | 60,71,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8ec724c4-7b41-4d43-9e1d-4d32724b5420 | 60,71,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
180688c5-38ec-4f76-9666-b430bdaccf17 | 60,71,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
d7ac621c-15b6-4db2-ba05-736ba1717e71 | 60,71,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6d5fbbfc-d555-4d63-a570-4152125b3c0f | 60,71,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b339c2f9-c56c-43b3-b8d3-f3ea98a8b0df | 60,71,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0c6b181f-2129-41fd-823a-9fc88bafbdf0 | 60,71,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
3c6ae9f0-ee45-4a9a-8d4b-1db3894ee84e | 60,71,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
ab49b1a7-c9d0-4b57-af22-d38b14f94fc2 | 60,71,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
78c5b538-eca0-4ccd-9d90-a9d7ebbea1d7 | 60,71,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
7bf78ba7-8778-4823-a7bc-bae261023af9 | 60,72,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
cb514ff8-112f-4c64-9dea-69d53ea62180 | 60,72,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8a224da1-6537-49cc-b81b-b8ac66e0ba84 | 60,72,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
498077ea-06de-4521-a9c1-c6bc9839456f | 60,72,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
3b2c1609-ab6c-435e-a8f9-9c1b6a47838d | 60,72,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0dd1efc1-3e82-442e-b586-cffee04d71e3 | 60,72,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
48ee1ad2-e7c4-47c1-964d-54a6425efba8 | 60,72,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
614d8224-9b63-4b5b-97f0-ecfacb0fc621 | 60,72,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c8ac88f3-062a-4868-be75-e7597b543bb8 | 60,72,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
bc3fd531-98c8-480f-a776-87cf08dcc6b2 | 60,72,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
6f8e272a-e564-4a7a-87c2-3855db8d660d | 60,72,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fc56d4ce-75ca-4354-9395-95f51483ad92 | 60,72,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
ddce56e5-9a4d-40df-a1ff-bf6b5bc22ff2 | 60,72,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
017398ed-3df5-43ef-9e9e-ce3399f50e4e | 60,72,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c4fe1bed-5446-443d-9041-fb68cac3f137 | 60,72,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
28e34b66-3729-4eef-b139-cca3d41e2d1e | 60,72,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e82462ea-936d-4862-8714-06cf077ae773 | 60,72,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
f2d5bd71-fff9-49f0-9824-12fc09b967a9 | 60,72,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
d4dc02c8-c0e2-454e-b953-bf42560af503 | 60,72,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
7b4b0450-f7b9-4641-812d-7ea88f73b6f7 | 60,72,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
477ace0a-9f8e-4e4f-8fbb-787350d17575 | 60,72,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3e6b1ff2-d73d-4ee0-88d1-d7f1afd04040 | 60,72,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2ec7c442-d5b7-4587-b21f-d26ba2844f2d | 60,72,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8b5e0fac-95af-4a6d-ada4-64f5b9ae01a7 | 60,72,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a21668c1-9e08-47b9-9ebd-518ffae93790 | 60,72,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9206fec2-bdfe-41c1-893a-06377a3f2789 | 60,72,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6c0b72e3-767f-4f5b-bf0f-0f4e270bd1e9 | 60,72,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
52363cc4-bb9c-4ddd-8674-421d93d07456 | 60,72,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
bae5eeda-d40e-4c0a-8ca5-adec3b60fba6 | 60,72,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
246bda41-c760-4c9e-8693-474d0b15618a | 60,72,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
44da2f31-614c-465b-b489-0b5824e60ba6 | 60,72,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d6fdfbda-725a-474a-8233-e1263ad184ee | 60,72,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
eb5e32a6-1454-4bcf-9a83-41a7b7bc5c80 | 60,72,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
0c6fbbeb-1368-4bdd-8bda-8b641cd1cfd9 | 60,72,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
34838231-3572-4f6c-be5b-45532c77aeab | 60,72,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3ef7904d-90ba-4edd-889f-50947ca59a4a | 60,72,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
71c0a2c3-1fd3-4a41-bfd8-dedc06840b2d | 60,72,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
abbd2fd4-29d9-4d05-aca2-6953d4e317ce | 60,72,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6453bf48-06f9-48d6-9a52-d1047e5d91a3 | 60,72,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
773ed736-e942-4f28-a3cd-0169ab5171a9 | 60,72,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
23fabfab-5bda-405f-97d4-852a19721567 | 60,72,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
00b1853e-fcac-4543-9feb-278c138385f1 | 60,72,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
7847c7ce-844f-4af9-b15b-d272ed4e0fe2 | 60,72,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
51a146b3-a95f-4e3e-a9f6-e49571f19ef4 | 60,72,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e6eeeb6a-6516-4fd2-8e27-90f1d31d7995 | 60,72,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
307b1619-e03e-4ac3-b6ab-d3007a861346 | 60,72,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
40ad6e23-70d5-4a49-ae65-bdc450657a1b | 60,72,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
5d2f563d-5b65-4100-9524-837d5f84ad12 | 60,72,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
65c8190d-c742-4c35-a84f-5f1865522ed4 | 60,72,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9c0e3abb-b80f-4835-bf97-0ed17f2d219b | 60,72,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
c7380d4d-2db0-46de-ad04-0c6329a70058 | 60,72,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c8462a28-7687-4967-80d8-842b162b1f3d | 60,72,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
fc5d047e-5ac6-4ac6-bb2f-1c5fe9e839c0 | 60,72,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3d6d83d7-41ea-41f8-8a3e-ca4d7c76134c | 60,72,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5e338ca7-be85-471f-b0c5-8eafd24e866b | 60,72,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9e6803c0-abad-413c-93d2-cd0acbc6fe44 | 60,72,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b79655d3-816b-45f3-bfe6-b5ee6b194527 | 60,72,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ba5962b3-d69f-45da-bd2f-d41bfbf61958 | 60,72,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f8cad1e9-0004-4756-a744-817be96e6ed1 | 60,72,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
c3a57758-73e0-46ec-892a-43677120ae2f | 60,72,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ebbb7432-b51f-4922-90c5-de2f309038e1 | 60,72,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
824ddb5a-c409-43dc-869c-1c574993b44b | 60,72,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
ecce262d-2384-4cb1-88f1-dc08cf5c16d0 | 60,72,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1377a992-760e-4589-adf8-3b8cd53e90ec | 60,72,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
c3bdd2f8-c715-4d34-8ff1-4140a5f1d1c6 | 60,72,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
15b8fde8-5977-4cb2-83db-79489a7c5aa4 | 60,72,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
ad24a596-918f-4794-a971-fa237be729f0 | 60,72,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e97a44ac-4a28-42c2-9028-a810332afd3c | 60,72,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
cceea7fb-151d-45a8-94c0-827a11594ba0 | 60,72,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
9e815833-a7fb-47b5-9418-d82413277036 | 60,72,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
812bb446-7921-4e42-b9dc-ff23b46dcfac | 60,72,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
dbf30fde-508c-47e3-a811-e862fa157b91 | 60,72,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
100eb060-1c3e-4503-92c7-5135bcc2d3b5 | 60,72,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
76fbc6bf-2e41-4877-bed0-1ad07588c7aa | 60,72,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
efb14e54-77e0-4e79-8808-c8d5f139b604 | 60,72,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b247942e-5e09-4365-9043-54cafdea88de | 60,72,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
64c30e52-e2b9-4c3a-8ea3-c482854ce85e | 60,72,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
bca7449c-1b8c-4d94-89ad-aa84a845d776 | 60,72,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
71c52ad0-89d0-48dc-90a9-3c15c0eed26d | 60,72,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
85ac1b23-66d2-4758-9978-edf497d03300 | 60,72,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e4d57aea-00cc-4f12-a306-443ad5fabf85 | 60,72,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
8aba6025-abd1-47ed-9169-007651d41f96 | 60,72,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
050bb253-dff1-4072-83c2-8dd78e04da54 | 60,72,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
038e6706-2c42-49f6-97ac-f1b3cca87255 | 60,72,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
5ab64d40-6fa7-4126-92d3-7267da2dec60 | 60,72,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
fcf94f63-d451-491e-a2e5-801839623b65 | 60,72,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2e92cf30-14a9-4f15-8ac0-265c7f75d7f5 | 60,72,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
15bfb35f-25a0-4a3c-9ed1-0fb4ed1886dd | 60,72,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
14d19b2f-456d-431d-b88e-b3bd854da736 | 60,72,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ff6073ba-5b53-4cda-8c2d-6f8157516a88 | 60,72,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3d6679b6-cde9-464c-8a30-195e5967c57c | 60,72,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
443caddf-2b3a-43e8-96b9-4a9be5e310bc | 60,72,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ec97d22f-151a-442b-b969-d9b4b1f7f910 | 60,72,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
36ec5eae-b591-460f-8401-4b412a5a7ad0 | 60,72,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
859f124b-63e3-43d6-b5d4-70b196b2f485 | 60,72,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4998c338-b830-4ad9-9ea3-358e7ff4cc62 | 60,72,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b4d5fd75-5d12-48de-8dfc-34ba3606b813 | 60,72,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
959bfaa0-e1ef-4a43-8f31-eebd64862beb | 60,72,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
35e8b660-e07c-4003-abaa-4f374f8857d3 | 60,72,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f3a127f2-2e8c-45ff-bc19-0866ee18b396 | 60,72,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
bf4c4e21-a6db-4554-b19f-ef210431b51d | 60,72,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8792a849-3bb7-4d8e-afb1-046892d5710a | 60,72,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f3a5b1cf-8e64-4703-944d-53d3a5bfef95 | 60,72,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
16034803-4be0-4f88-a8e5-cba283016755 | 60,72,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
9dc64d66-10c1-461f-8d99-e1e153f8ec29 | 60,72,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
917c0b19-e96e-4f09-89cf-a46c33cba30d | 60,72,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
93852893-dc01-4b21-867d-13d3c09a0111 | 60,72,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
dd1dcad7-9db4-4646-9dc5-1671f8da5dd3 | 60,72,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
5fad8637-7e2b-441e-8284-0ecf48be2751 | 60,72,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1f975892-7eca-49a3-aa8a-01960635ba4f | 60,72,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
8acdd5b7-744e-4051-b681-cbcb67879523 | 60,72,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e8b42c11-840d-4265-a000-71d0ea27dd07 | 60,72,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2d91581d-06e8-47c3-a806-28307d7e7adb | 60,72,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
33bcf30a-bfe2-45b5-8383-50c8750fbfc1 | 60,72,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f8c812a4-a3e2-4c07-aa23-9f7b0ab8f2b4 | 60,72,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
04c264a2-5910-4e0c-a78c-461be573d522 | 60,72,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a26c8f40-8125-43c2-ba6f-d246c9493e71 | 60,72,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9fe4f143-0c3d-4aeb-9bf1-ae17cd43c919 | 60,72,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8f8f0fa4-4e4a-44e1-b8fe-e994c78b2b0d | 60,72,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
edaf01f0-780c-44b0-82b1-6ab12a03a780 | 60,72,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
f4a42eaf-769e-4bde-b75d-7a1033f40045 | 60,72,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
e0c65dab-fc74-4e66-9fd0-1f8e8a140294 | 60,72,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3707ff98-9027-47bf-ba7d-ec857cde14d5 | 60,72,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4d390b01-80ac-450e-adaa-503a1799a024 | 60,72,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
e6bb15df-5449-4023-8234-edac6bf22fb9 | 60,72,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
6e2ce5ed-83b4-4776-ad79-55298fc22fdc | 60,72,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
41d6dbee-cc8f-47e4-a665-22015ead83d7 | 60,72,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
406c96c0-fd61-4f05-95b4-2cbf9f7c834c | 60,72,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
69963ac4-0395-475e-92a4-91c932c5e61b | 60,72,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7bd6f7cc-e2e9-48cf-878e-7a4e6978e85f | 60,72,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
e89ce669-da34-4df7-aa8f-be18d26787e9 | 60,72,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
5a915fcb-bc33-4b82-b6f4-af55047c9a53 | 60,72,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
f80f42d6-ee59-420d-9ab7-58a1e4508c5b | 60,72,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e31e6176-e4a8-4a82-8c41-697153135ab5 | 60,72,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
672a0db4-a825-40fe-bc29-778939e62916 | 60,72,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
5271c460-48c9-4d0c-8696-176fb8821242 | 60,72,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
234136d6-a7b8-456a-89fe-2e2cdf8dca93 | 60,72,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
9f80cbb4-9cac-4c12-b31a-8864c536f8f1 | 60,72,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
6a60f4b7-29d2-4b3e-8597-735e3d078ce5 | 60,72,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
17ce7c15-4e06-46e5-85ac-7473bc65fbf1 | 60,72,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d54e69aa-9040-48e0-9c46-5d8f27850026 | 60,72,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d0ed79ec-29ad-4a29-b3b3-eaae14d9fd4f | 60,72,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
62d8296e-3e81-41d1-8551-f014fec011f1 | 60,72,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a47f2bec-b04b-4710-9f8a-aae4d5462c1e | 60,72,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f0156578-d17d-49b3-8b53-4cde8c813ab8 | 60,72,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
90eae62a-6755-449d-aeb3-808842d8d449 | 60,72,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b3b55912-425b-4f3c-82bb-b9de15feb5bd | 60,72,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5a955971-b6a7-4394-949a-af00607ce6a6 | 60,72,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c52cd350-865a-4801-9d2a-cd12c5fae727 | 60,72,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
6591d03e-1926-44bb-8673-c83284956c6a | 60,72,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
35be4406-ad38-4168-a7c2-5b2c86aff3be | 60,72,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
5a4a47c3-1fcf-4d4c-87d5-bdfbfac6437e | 60,72,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
277b3110-974f-4dcd-9bc8-d42942ec88f6 | 60,72,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
3fb7f9c9-ceb8-479d-89f0-961785d6901d | 60,72,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
fbb9b702-1d20-43c2-9bad-9a70ee3d54ce | 60,75,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b06a011a-59b1-483f-afc2-e5f7025c9a98 | 60,75,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b90eec34-15b5-442e-ace8-ed1e4107069b | 60,75,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
21febf5b-3a80-4bf4-a767-be6437379090 | 60,75,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4c759441-9627-4666-9644-6d1806f06f62 | 60,75,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
a2363302-a049-43cf-9860-b632bb03f3cb | 60,75,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
86d76a2a-9d7a-49d4-972b-94c0a209dff9 | 60,75,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
fdff11be-459d-4815-bccc-14ca5fb7b1d5 | 60,75,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a79680f5-25ca-4e63-b17c-c461066e15aa | 60,75,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f484e6d4-1fd7-4787-ba1f-4726cc9d9300 | 60,75,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
be8fae92-9d32-4e9e-9558-8ce383b3e466 | 60,75,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
19376e87-c63f-4c70-9a26-3f6da64b905f | 60,75,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
bd1ea3ac-5880-46cc-9686-89f3348bce32 | 60,75,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
62ae9d82-0799-4f64-9a4c-8439a6972dbf | 60,75,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2920c59f-e461-4262-b795-5b1ce611fc9f | 60,75,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
37f7b1c2-36d9-4df5-9c63-5249cee5ef83 | 60,75,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
f0e64b7b-7ec0-44d1-9083-d4fb55c73987 | 60,75,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d4645462-16fe-40cf-b2ed-52c05babf0ae | 60,75,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
8305551d-8a23-4a1e-81e8-bacb8cd58526 | 60,75,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
383b812e-9944-4bcc-82fe-d5562d1a6788 | 60,75,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
518d3182-75d0-47ed-b21d-0b13c8e945a5 | 60,75,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3cd3b05a-d2ac-44e3-af47-02b48464da1a | 60,75,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
82c6e7c1-3b03-4e84-8db1-008230e9b497 | 60,75,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
18941137-6fd7-451e-84d5-50ae34b57a73 | 60,75,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2eaee762-c338-4ae2-91cd-dbe77e10df83 | 60,75,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
19ce530c-cb91-434f-b266-6c7acf7cf6e9 | 60,75,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0267d6e7-513b-4aa8-8bdf-0f6c4fe93d94 | 60,75,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8d3163f7-510d-4909-abc8-5ffa323b9ee3 | 60,75,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
e922f3c3-d6fd-418b-9b85-b32c5cc9f735 | 60,75,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a839d68b-441b-45e9-80f8-96801f30beca | 60,75,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
d3116417-5e17-4e07-baf9-6373ddd3204c | 60,75,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
09835e6d-a3fb-4fb9-b855-230684ef5be0 | 60,75,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
16e7a0c9-ef01-461d-9759-36c7a404f740 | 60,75,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
113a6a86-4a04-4f82-9a31-521a56d1e20f | 60,75,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a2c1a625-078b-44f4-af89-3cfc1a9cb336 | 60,75,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a1461333-34de-4535-8dec-e7ec735f041a | 60,75,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
2ccf1e57-ad23-4b73-bfff-e4d94b2a8a5a | 60,75,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
682be972-51bb-48ad-bf35-26ce0c6c518a | 60,75,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a5936452-409e-49a2-b95a-30a3803ca94e | 60,75,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fba549fe-8daa-4322-aa2b-93d69ed266ee | 60,75,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6f03de9a-959f-4137-9879-2695a6890c14 | 60,75,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7f7e9570-82e2-40c2-8736-38d51d0d2602 | 60,75,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
edb581fc-9fa4-4f63-8626-f08b2d37e4d4 | 60,75,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
51cc14f8-9522-4ea6-a8ae-cb9b6990ffb5 | 60,75,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
52706361-b1c5-4c50-8387-87fdfdf8ec18 | 60,75,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
01921fda-34e6-44c1-a443-4dd307783f10 | 60,75,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
aa50439f-cdf5-4a4c-b982-7a30231e8512 | 60,75,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
30972143-d1b1-4aa9-a292-16a9f7cebabb | 60,75,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
36c6f285-b7c1-4e7f-a32b-1da940dff88b | 60,75,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
2560ed2c-15c7-418b-924b-3e3011c05deb | 60,75,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
fca6ffc5-2e33-4f24-b03a-7686a14ce277 | 60,75,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
8ca837c7-ef6a-4076-a9ab-69671710e70e | 60,75,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
58a6a8e5-c893-4a46-8f83-05b21dabe85b | 60,75,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
058c0f44-fd2d-4071-8877-ee6fd469ef04 | 60,75,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1317a987-a91f-461b-916b-0f2e070a723e | 60,75,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
67de5c48-3739-46fc-ac50-441267944df2 | 60,75,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6c489895-56fd-4ce3-a6cf-4b8f0bc3de06 | 60,75,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a6df4d43-0457-4c8a-9bf1-49504c26d3bb | 60,75,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1688f408-5993-424d-8482-a6f95989bb2f | 60,75,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
33d61801-d66f-4ea1-b598-9ce1e004dde4 | 60,75,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
01f932cc-de8d-4fdc-b587-e14802fa569c | 60,75,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
262111c3-a7d4-40af-b78e-2077efb53fba | 60,75,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
877a2599-4442-434a-9055-4e3336e13418 | 60,75,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c39f430c-1c69-4b05-9e4a-4ad05062da94 | 60,75,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
6f6641e6-f357-4966-8fdf-f47b99c20457 | 60,75,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
433e23a4-83d9-426e-bb03-718780187ba9 | 60,75,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
4e0ff4f1-6f1b-42c7-859a-627307081bf4 | 60,75,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
cf0b7c8a-4d74-4deb-b99c-3fdd5923c741 | 60,75,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2c1a7e59-26e0-4b22-906e-0725b0d84d52 | 60,75,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3f00a5a1-aca6-4ffb-b083-7057e8bddc92 | 60,75,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
1ea4b74b-7e7f-4320-a083-fa5b8f3aad0e | 60,75,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b072183b-6886-49fc-9cef-4ba6d7f7650f | 60,75,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2f221510-887a-4b19-b670-252eff15123e | 60,75,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c4af3c7f-4acf-40f7-b07b-ff620db72c44 | 60,75,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
25551116-e1e0-4d06-92b9-b3e3e6c9bed2 | 60,75,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
cdb7309e-6561-4944-8c15-cef4a1b08a75 | 60,75,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ca6f3560-ee94-4d5b-ac75-9a2b5d72c265 | 60,75,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5e4c19be-641b-4b1d-9bec-df59bec716c3 | 60,75,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
afaefb44-7d4f-4ab5-9379-617d14f52ca1 | 60,75,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
46b8e55c-748e-4906-8a18-7b9ddaaff5de | 60,75,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2d84f9ba-86f3-4d56-a486-2830f88239d9 | 60,75,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
68f201d2-1989-46b8-b824-6a44b3485798 | 60,75,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
579f44f3-c89a-463d-abf6-b49a6879a8da | 60,75,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
11f43a19-4bcc-4189-993b-a4c76156fc48 | 60,75,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
5326cbcd-0c89-4e10-a9b3-86b52d7563c8 | 60,75,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d187885a-e299-4c22-ad32-8c0a465da2fe | 60,75,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
b777f790-3019-4aea-b3e0-58f981464e5a | 60,75,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4820a956-02ba-49ea-b2d9-ad107a73aac6 | 60,75,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
959db9bb-34b4-447e-a122-31a57bf269a0 | 60,75,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
bf03a24f-6123-4ee4-adcf-e7e4bf2fe58e | 60,75,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d277bf15-7f90-411f-92c9-b3daeb1f8d48 | 60,75,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d21bfe38-1f2c-4d0d-b099-da06040380d7 | 60,75,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
36f38f75-f137-4baf-86d3-09a06d6dd98b | 60,75,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a73f0e2b-a43b-4df5-8c33-b5ea742e7c4c | 60,75,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ca5db55e-3eb8-4de8-90b3-4ad138d47c43 | 60,75,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
023cb26d-91f6-449c-97d0-6bcc911249e0 | 60,75,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
d339f676-4812-4fc5-9690-5b4402e86ce9 | 60,75,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
64f0ddfb-b96e-406e-8071-4f2f726918f5 | 60,75,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7f6cb333-8e54-48e2-8c01-79bc78ba16f7 | 60,75,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
08c9c109-fd9d-4c4b-9d9f-fd1e32c81029 | 60,75,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
536e6666-05e2-4489-9add-051a3644272c | 60,75,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
279172ba-db66-49a9-adf9-b58fde5099b6 | 60,75,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c4e84f91-9045-4a4a-bb74-736dc744acb8 | 60,75,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
6cfa127e-8904-4861-a172-82fdae59a0d8 | 60,75,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
bba1657a-d9f9-47ca-931d-85d727d5076b | 60,75,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
e3744c93-00db-48cc-9872-7b50493ec9b8 | 60,75,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
442961a5-af83-449c-b591-9b73321466de | 60,75,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a412f79a-0d36-41c2-a11e-3f7b2beb106e | 60,75,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
eabf86df-2d76-46f1-9474-e3b6ad74aa62 | 60,75,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b4225202-9b95-4714-8a7b-28309b490768 | 60,75,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5080b647-c767-4b12-9cd0-f5caa21ff78f | 60,75,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6eeefce0-1b7d-4498-9fd2-3cd73323a507 | 60,75,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6a910fd8-69e2-49ac-8c30-402ef94366f4 | 60,75,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
c0cd609c-9aac-4b45-a810-63255e0533e4 | 60,75,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9e44509f-edaf-40eb-ae90-442ffcd571c6 | 60,75,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7ba34e86-ff5f-444c-b897-7d97c05273cb | 60,75,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
80e1a4a0-7148-4a2c-a635-0f3c998b078b | 60,75,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9452b5f9-4be8-4943-b921-7a38d9ce8b4b | 60,75,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
ac422ca5-db76-4346-872c-796f3dac1a03 | 60,75,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a9a4952d-9a50-42d5-8935-e2251a2e35f8 | 60,75,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
52e273fc-e246-4a75-bd36-6e7a50423ba0 | 60,75,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
fe35cafd-35d1-4bab-b0e3-fadd53c1e270 | 60,75,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6025f7ec-2d8b-478e-bf01-3367de15fd1a | 60,75,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8e1a6cc4-f0f3-496b-a778-67485ac2e18a | 60,75,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
df111108-eb73-4880-bbb3-318c9d98a631 | 60,75,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
5fbb5f1d-3db7-43b9-b3dc-3cc37f85d789 | 60,75,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b32680a5-6227-498f-aa2c-ad89af9d0db3 | 60,75,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
21d04f7a-0a0c-4df9-8454-7dc884328fe8 | 60,75,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
6a936a26-0b0a-4f47-8cdb-f5f375202f8b | 60,75,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f25f83ec-a3fb-4a5b-9dca-aa7930e11474 | 60,75,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
8c70a837-5514-4fb8-b64c-479dc8dfa2ec | 60,75,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a38a365e-7f97-4a1c-ae92-f1f388fd109c | 60,75,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
df27ae84-ea82-405f-a21d-cea921a22e35 | 60,75,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
36c9419f-021d-41bf-aaed-41461765b50f | 60,75,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
b08727b9-c546-421c-9230-358ede231c41 | 60,75,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
2dfe6dd7-d23b-41c0-903b-2f0cf8c9b65c | 60,75,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
f301d679-34d4-44f6-ab68-6c187ec8dc4b | 60,75,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
1e03e3d0-f95e-485a-92f3-65654f115e52 | 60,75,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
1dca6569-7331-42e6-908a-9b6c0a8eb6cc | 60,75,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
5cf21ce3-c03b-4934-8708-688947b23425 | 60,75,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
687f5323-b54e-4daa-927c-77d24a5537c3 | 60,75,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0830475b-e3e3-4694-bddf-c08e116a3587 | 60,75,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
465f4853-fbae-400f-bcbd-e3230817d4b5 | 60,75,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c6f3e52c-d503-4faf-a897-c825e7c1bb1f | 60,75,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9df570d2-07ca-4e96-b9ed-35691a147859 | 60,75,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
60c329d3-bdf7-4366-8b5f-347fb2d7e7dd | 60,75,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
971ccdaf-f2a5-4545-8a72-1cd783edf79a | 60,75,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
428c9a1c-d5d5-4bce-ab70-9b758ef071ee | 60,75,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
2dbd9e73-2871-43c7-8d35-ca8ea7cfce4e | 60,75,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
996544ee-68bc-4047-ad13-0fc65b450e2f | 60,75,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7b9c6dab-358b-46c8-821b-cc1bc3a0763d | 60,75,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
42c3e0d5-8d88-4783-8ead-46588e8ce575 | 60,75,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
95d535d6-74a3-4b7f-94b5-ec97a1f679af | 60,75,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
f6c28ff6-deeb-4a51-978e-987aff2d1fa9 | 60,75,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
4b255a3a-7410-4548-be0c-170baf9734bf | 60,75,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2c87f0d3-bc10-48a2-a1b3-821d1829748e | 60,75,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
bdb0fce0-9cad-43d2-8d5a-e2c554591d78 | 60,75,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
bda61b2f-5a43-4d82-b2d3-9eaf45cc75e5 | 60,75,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f8ad1a2f-7200-47bb-8bd6-73bc044c6d77 | 60,75,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
396339db-68ee-4fab-b100-0b0bdab210da | 60,75,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8221227f-b0f2-462b-a05c-1c1456138542 | 60,75,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1c6e0351-04a5-4d37-b1af-b4c508e45957 | 60,75,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
bc0ad98a-d2dd-4270-a652-1d3e15235aec | 60,75,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e06a3374-1c48-46b1-8cfe-5ab890a2ac9b | 60,75,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d308da6a-e920-4c8b-983e-6599e32134aa | 60,75,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
79a78241-baf6-4541-ae90-8dcad07d6eaa | 60,75,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f261da9f-5daf-40b2-82f9-e8558b12c869 | 60,75,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ddfe8933-b9fc-4e68-9685-7277c2571ea1 | 60,75,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e695a7d0-8e95-4617-9c3d-9b76ac80f2ff | 60,75,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
eccfd7d2-c4f2-4c0c-9446-3cce11d7a6e0 | 60,75,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e8a16491-cd1c-44f9-a848-cefe851059b5 | 60,75,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
17a879d6-471a-4a13-b82b-d32b41fa9cbf | 60,75,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1e0f4dc0-eba4-4e95-9317-f6ffb1677439 | 60,75,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
17092411-df7a-4031-bc69-757f3ec60041 | 60,75,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
be508a10-04bf-4f4e-a92f-0b2f9c67a375 | 60,75,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a71bd774-a516-45d6-a44b-d85ba3dc4400 | 60,75,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e47500ce-f4cf-4588-a1a3-9fb1d75cb017 | 60,75,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6ed1b948-ea03-48b1-81a8-455de1f4a03e | 60,75,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
adb57ef6-ea03-478e-b11f-d387e2893e8a | 60,75,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
fad213f9-0de9-42e6-9079-aa7f927ffd31 | 60,75,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
200da426-5959-4f01-a365-f72ec841b5d2 | 60,75,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ed2ddf6f-cab8-45a1-a7b5-7963a8e31292 | 60,75,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
c195e32d-d0cc-433c-84c9-942955c90bc6 | 60,75,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7668d176-a4fa-4ca3-a70a-e20781fcb614 | 60,75,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7a2fdeb1-fc96-4dab-acce-b9e25b0d40e2 | 60,75,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
726fb169-1acd-410f-9c8e-fc91dd94393c | 60,75,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
dd806168-5887-4ce8-a198-2912d3b70b5d | 60,75,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
40be28bb-bd0e-423f-ab65-82fdad8d0182 | 60,75,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
f11e08eb-d76c-4057-af93-1890322cdb64 | 60,75,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
14c8c0ca-0804-4be0-84de-388f42f80a79 | 60,75,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
23b4ec9d-9a58-40f7-ac1d-ecb0f5de6a56 | 60,75,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
51e6a83e-2a3c-4cf5-9461-5238b64c762c | 60,75,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
70564eea-49d4-401e-85e7-99fee2feffa7 | 60,75,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9b40dbd8-a610-4a8a-b214-7799559aae01 | 60,75,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
639122f8-1344-4103-93a3-859b3a21681d | 60,75,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5975e2cc-e265-4d56-8bd2-3db2f721e526 | 60,75,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
939f563c-58c1-43dc-9429-6427940cfeaa | 60,75,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e1b23593-b939-4202-a0de-78a1020a2543 | 60,75,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0cccd74d-42a6-4898-9fc0-7171d579a6a9 | 60,75,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3aaeb12a-5105-47ef-be3a-b9d23e9d1be0 | 60,75,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e09ec384-e58d-41b6-acb8-5dcd6a7eccbc | 60,75,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
d70a7fee-1b97-4c08-8f60-a6284dcdeb34 | 60,75,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
96f17fc2-cf2e-4a4f-b2fc-7bfa373796a8 | 60,75,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
acaba6cb-3d8a-4f6c-a11b-ac581843ad0a | 60,75,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
47642fa0-3f23-42e7-9851-f1dc01a325d5 | 60,75,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a6435033-9ad2-4a47-8ea8-81085dce744b | 60,75,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
4642646e-7885-4a79-ad49-82496b7242f5 | 60,75,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
d5c95cb7-ce0b-40e2-a7cf-16da46684cee | 60,75,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
cd9ef525-2494-4145-ad1d-e9ddcea77614 | 60,75,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
236ff5b0-bbd8-4a36-b2fa-4b497a8a0733 | 60,75,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
03a8a61b-056e-4dc2-887d-53295b95c58e | 60,75,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1f9e290f-580b-41a7-bcc1-7d0f9ec59afe | 60,75,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
adde1648-e919-4f4f-b0a4-7843c0da56e0 | 60,75,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
f3c1bc22-8166-4a6f-b86a-0023922ea9ce | 60,75,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9991c996-894b-4f4d-9789-1d82aac5643c | 60,75,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4a8a9f76-b5df-4406-a9f6-1ed995df3086 | 60,75,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
7fe4fc58-8d3f-4e4d-95ff-9ef2346b5bd7 | 60,75,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1ccba29d-315d-4606-8d49-e97219aa5953 | 60,75,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
84096ebf-99fd-45a1-b481-449a2ae7c791 | 60,75,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4e7059b2-05b1-4efa-b45a-f2a4a7af770a | 60,75,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
d2d4f4ee-d5fe-42b5-a9c8-8a47d991bcb4 | 60,75,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
17f0975c-ee0b-4109-93db-bb9d5d5c87a6 | 60,75,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
8d41a7b6-bfef-48d0-923a-0110eb186ef9 | 60,75,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
794333a1-f5f2-45b1-a1d6-b831ffa7ed18 | 60,75,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
82ec3dc6-8154-447e-8b0e-d1ebfac633b1 | 60,75,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f4b5f4ab-598b-409e-961d-ad841f83992f | 60,75,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
0b719e00-150a-4e47-bc92-59e75f231fd3 | 60,75,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3b3168af-c2b5-43e1-8dc0-d1e97416c3d9 | 60,75,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6b80cf0e-81af-4cab-8952-43478688b4a3 | 60,75,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7920e64c-cfb3-41ed-a404-03758b4ff8d6 | 60,75,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ba43b17c-5530-4e63-b6c8-a47a1030eee1 | 60,75,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
af1f6075-b235-4712-91d9-76e0e4a03a72 | 60,75,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e8fdcac8-7416-4750-a4c5-ce7fa8711c03 | 60,75,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b439f6da-390b-4c7c-9f85-1312a799d700 | 60,75,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e701a0d6-c1e4-4ca6-9a11-83b5478c932a | 60,75,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
8f7b8044-1a39-43de-b6f8-6b77901d13c3 | 60,75,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2879b57f-22cc-4387-a24f-3d9af04d948a | 60,75,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
1c2bfe07-92d7-4aa8-be45-7a3b1e2e0db0 | 60,75,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
5fb9608b-3081-4745-ba1e-5eef3d4c4489 | 60,75,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
553bbabc-abc4-4802-9abf-052251b7e18f | 60,75,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1e39ad16-5ce4-4010-81de-4f57cbecdcc7 | 60,75,71,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
4d1575ad-674e-4a9a-b3b5-2d5287719446 | 60,75,71,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0f2031e0-c5ae-4c87-af21-5961a7950096 | 60,75,71,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b31cdf2e-9bce-49f6-abcc-c9cb7d48a5c0 | 60,75,71,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
af2f4da2-b9c4-4ed4-a2e8-cdf155d8882c | 60,75,71,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
475c1fa5-3062-4afb-82de-04fe13f69317 | 60,75,71,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
50040596-434b-4bc4-8a47-6c53f4fdffd3 | 60,75,71,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
40be7d99-5859-4e24-8600-52309ea7d374 | 60,75,71,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
aa09c2da-706b-4ec6-9d0c-cb9c6b17ffeb | 60,75,71,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
bb19d09d-1292-43d9-90b3-bee73a747e75 | 60,75,71,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
f52866e8-d5a2-40a8-a3ad-331f562751ec | 60,75,71,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f778b611-8f97-4783-a7f5-2448f622779e | 60,75,71,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7c3ca09f-2c3a-412e-a1b8-98a35c3789a7 | 60,75,71,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b0958312-c364-4e08-9ede-28e9fc641220 | 60,75,71,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
75956697-cca1-4b39-ad3b-0ba2b57e8f81 | 60,75,71,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
9611f8a1-dcf4-40c9-bb82-65b9b05889c4 | 60,75,71,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
dfe323f7-9e34-4e0b-b5f9-e1e77484fa04 | 60,75,71,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
dd439cd3-bc42-4006-9a2a-992fa3b4b96e | 60,75,71,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
1aff07bc-6f13-4269-a4b6-fbf9f582e7ec | 60,75,71,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
abcf1367-bda5-467f-a1a6-9dfaa0663af4 | 60,75,71,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
bfc3b78c-39e4-4f0e-866a-444652676706 | 60,75,71,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c41d2c5e-425e-4fbc-8565-b0f6904b2479 | 60,75,71,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
25d79522-5ef1-43ba-bb94-377f6381e5c1 | 60,75,71,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
533709fd-cb48-4681-8470-865f5d85d73a | 60,75,71,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8b9cd537-198b-43f4-ae44-f795309e37c5 | 60,75,71,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
2084e4b6-7c70-40a1-8fe7-c87a20cbbafb | 60,75,71,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
4aa2336a-7703-49ea-8eb7-360c911ec3b3 | 60,75,71,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
464699a2-f713-4c28-9f57-72eded3e226c | 60,75,71,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
ff789602-6010-480d-b038-782915c4becf | 60,75,71,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
b19a30ad-e131-4a17-a109-d3ad286a40ad | 60,75,71,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
07b48ba4-ba59-435b-9be4-1beecbc7e552 | 60,75,71,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
b5b29893-db65-4936-bf54-eb8741fe4c21 | 60,75,71,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
9dda97f5-ca75-43c8-816e-2529a33ccdf2 | 60,75,71,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
8f197f12-6989-4fd3-a90d-cd4c2ba417b9 | 60,75,71,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
1c399bce-2a98-4825-abbf-2309d3c96259 | 60,75,71,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
578f0f78-c5cc-42d6-b3e0-f446ecf61260 | 60,75,71,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
be807f9f-5c1e-4b47-8571-f2bd5ce21a31 | 60,75,71,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
6fa8e1cf-2c2e-47df-a2a9-7b59ef5cb46b | 60,75,71,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
1de4679f-a9d8-483e-ae30-b74a9d95b7ea | 60,75,71,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6d512da5-0b92-4e2a-a792-dab732c06f2a | 60,75,71,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
b562ca4a-9313-4e35-b7e2-5128238bff1c | 60,75,71,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a626dded-c2b4-4f38-9f17-6a159d5a85e1 | 60,75,71,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
c26d1433-c882-4358-98a1-9ae2c286e40c | 60,75,71,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
2cbbd113-0575-4ad9-82f6-e96f80b39855 | 60,75,71,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e37688c3-13b0-4f55-9fa2-fee6dfabab8e | 60,75,71,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
797b5c14-b455-4b8f-8749-9756ea7a1077 | 60,75,71,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
fd9c4130-e5d3-4bb0-b4e9-11771289fa38 | 60,75,71,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
ae7b9698-01d3-4cc6-8307-8d5a6d082054 | 60,75,71,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
735eae5a-231a-4b71-bf5c-22bc39c095c5 | 60,75,71,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
42a606b2-904b-4990-a89d-d5fe25dbad16 | 60,75,71,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
78381d6e-a745-45a5-95fd-c2234436b889 | 60,75,71,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
33ff657a-01b4-40e1-b049-e4bf75151bd5 | 60,75,71,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
6def3c50-542f-419f-85dc-73668ac4fafb | 60,75,71,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
9cb8e68d-c993-4f74-ae5f-0d3361914da5 | 60,75,71,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
6f595556-322b-48e4-a8c7-c03914d99476 | 60,75,71,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
efa9b787-144b-4a29-9327-b52b99b8690c | 60,75,71,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
de6ff6b2-d1d4-4ec9-9325-8053f9e8f731 | 60,75,71,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
5e77ca51-6043-40cf-be4f-b62738d2cff7 | 60,75,71,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ce90742e-aee8-4ba8-b369-98963f92c6bd | 60,75,71,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
5e297207-fcc6-4768-9b66-ec2289c91465 | 60,75,71,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
57e539b3-635a-470a-8f3d-1f406697d8d8 | 60,75,71,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
4093fe54-03b8-4457-848c-fb61dbdc2b95 | 60,75,71,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
d6388e83-8db3-4930-97fa-1e7ab4fbdea3 | 60,75,71,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
f374d935-b065-4a07-ad26-01bfbbe1f781 | 60,75,71,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
256525d5-1a87-4271-9b33-3fff01844494 | 60,75,71,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
daa950bf-09bb-42b3-98ac-ebc9284600af | 60,75,71,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
f35f9b0a-b681-4d94-8816-80b435c0d5fc | 60,75,71,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
038d8490-cc08-4ce4-ba33-9f19f48350c3 | 60,75,71,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
7a36ae22-0804-488f-b348-7edab450e3ab | 60,75,71,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
5ef48262-bf55-4e7c-938d-5d96cca24705 | 60,75,71,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
d46b8d02-59fa-4fb3-a737-20e08079a9ab | 60,75,71,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
8284addd-d911-4269-a4a7-3ac9bc715aa9 | 60,75,71,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
32a79953-7985-45d0-8918-90377f60fc19 | 60,75,71,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9fa0f7b3-95e6-4df0-b194-c36313e94c79 | 60,75,71,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e06ec92e-5aa7-41c3-b621-93779397e0fe | 60,75,71,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6b1b0673-ac73-4739-9f66-0336dd12d8af | 60,75,71,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
169c2838-5782-451d-bf46-87960fa1d0f8 | 60,75,71,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
16763b35-dd0b-4e54-887b-9a0baf11b604 | 60,75,71,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6013fa56-eeae-4701-89f6-a437a85db642 | 60,75,71,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
96f90e3c-06cf-4cc4-bbe3-402c72657845 | 60,75,71,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
2d726eec-f76a-46a0-8a70-e501ccd7a560 | 60,75,71,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
2f361d4e-c7c4-48bb-81ee-8274095789ca | 60,75,71,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
87f9ad8c-b5ff-44bf-9b81-62492b4281a6 | 60,75,71,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
98f1c817-1ef8-460c-a9f9-2faa0adc23a6 | 60,75,71,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
e856f13d-f966-418d-9749-2ec8fdbcf365 | 60,75,71,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
c7b26776-8fc7-4bdd-b3e3-f1a0c80a6f16 | 60,75,71,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
f9980873-ac4f-46cb-bcb0-6c3ecf479cd5 | 60,75,71,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
9cf9a186-6841-43a7-afd6-86cc50cdbd54 | 60,75,71,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
18bd308a-5c10-49ef-94b2-3a633b36c880 | 60,75,71,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c77f7ab6-c276-468a-babf-f1c4cc602b66 | 60,75,71,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ccff15a0-1f6d-4ab3-bb9a-52b78ffb9691 | 60,75,71,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a7644db7-ab69-48b4-920f-c7aa8c013047 | 60,75,71,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
79180f16-575d-49cc-943c-5600c1942d82 | 60,75,71,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
c52833a4-f8c9-4418-bbac-b6668afcdd50 | 60,75,71,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
1a60fa3d-bce7-41f7-b015-3bd232bb0254 | 60,75,71,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e101bb93-7afd-43a7-a53b-032487ee205f | 60,75,71,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
3162c4f3-2424-4856-8fda-8624443a423a | 60,75,71,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
9a97e621-3054-4d66-96fa-64920d8e4ef1 | 60,75,71,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
fae9d36f-1d22-4221-bdeb-2ebcbd4b879d | 60,75,71,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
56f11628-9324-42c2-bb2c-6b3811310393 | 60,75,71,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
599ecc23-488d-4b0d-b50b-35870535b031 | 60,75,71,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
36235151-5f9c-44e0-bc1a-d67ea7e5ee39 | 60,75,71,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
5f4df013-a64f-4b70-a289-3f3e78e47d17 | 60,75,71,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3c4f6dae-4759-4204-9cc9-ee1fd5de1ad7 | 60,75,71,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
98804576-af4f-484f-829d-22d2fc6ab0cf | 60,75,71,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
b7b1ff47-5470-4d3c-acbf-fb3adfe874e2 | 60,75,71,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7cab7c0f-be7e-4bdf-b7e5-aec9fb3e361e | 60,75,71,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
aae0bed0-163d-45ea-b1b2-1909493e13b0 | 60,75,71,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
532f2649-f987-4d0b-b72b-35178a0e1474 | 60,75,71,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
7cf0faed-6527-40e4-8067-5de90fabfe04 | 60,75,71,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
377be0c4-b680-4519-894f-627388500548 | 60,75,71,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
a628a665-7793-4e03-9eb2-3fe28026fc5a | 60,75,71,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f3611fcc-ff5c-4e52-ac65-b14db0272722 | 60,75,71,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
f3838b7e-2432-4628-8e0e-f8d124559881 | 60,75,71,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
fce81fa0-b6f6-4eae-81fc-4a175d295ce8 | 60,75,71,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
9df3110c-4679-4020-a924-da83fdc9fdfb | 60,75,71,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
25333af0-96f7-45f8-b71b-2f94f8b810cd | 60,75,71,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
64f86bf2-093b-4b7a-ad2d-dd5be10bc4e7 | 60,75,71,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
6b251da3-0b34-4fb3-bec4-daa4aaecfaae | 60,75,71,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
33f0500f-f4bc-4c05-9632-f5c8fb76d276 | 60,75,71,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
8e295108-ee32-4716-be84-bf5476a46d19 | 60,75,71,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
e43283d3-c936-4f07-9541-71d460f2d4d6 | 60,75,71,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e1cda734-a658-424b-aa63-a41751be281a | 60,75,71,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
5d0207be-6f51-4a07-8a45-8b0a5cb51c82 | 60,75,71,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
008d152b-9fd1-45ed-a4df-b7f204a520af | 60,75,71,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
cb6a1b2d-1b7b-4d06-a8ed-8181bb28625c | 60,75,71,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
39dc73bc-67f0-421d-bc4e-768a811464e4 | 60,75,71,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6af1a042-0b76-4f18-91ff-919fe0207988 | 60,75,71,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
36e72ad6-9e53-4d3a-9bef-20534dc2786b | 60,75,71,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c30418f1-b52d-40c3-b67b-7572bddb7f80 | 60,75,71,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
36de0d42-27c5-4263-b5ee-79b801c09b25 | 60,75,71,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c3b82891-d6b0-4825-b350-e819b11d2dae | 60,75,71,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
05098fab-74e4-4cae-b528-617911c3837a | 60,75,71,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3a3eb09b-f5b3-4af3-8a81-f7b085581e90 | 60,75,71,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
af135627-85a0-4fe5-8feb-5249ed5d7965 | 60,75,71,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
19a6b90b-6502-4846-aa95-f8f4938f63c1 | 60,75,71,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8060921e-f685-4db4-9662-1ee2d4820593 | 60,75,71,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
5cacbade-1db1-49fa-95fa-e0fe7369da5b | 60,75,71,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
bb9d8840-0993-4f1c-ab24-dc4259a35e1b | 60,75,71,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0baf0fb1-e729-491b-84fb-febdd148fb38 | 60,75,71,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
342d7b71-24c4-47a3-ac76-8536a5ef866f | 60,75,71,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a515488e-7e18-4c8b-9ade-6e3bb8cd8ee3 | 60,75,71,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b1d17878-0a76-42aa-aebd-5da1fd84469d | 60,75,71,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
26287400-30ac-4282-9147-6613784a8fba | 60,75,71,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
892b80bc-a8eb-4136-904e-15a266366864 | 60,75,71,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ff3e79b7-b66f-4940-b2aa-edf2e367de93 | 60,75,71,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
498a07d5-c2c3-470e-8088-d00c2699d189 | 60,75,71,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
2412c11f-8293-4e3b-ab36-a4f89b2845a5 | 60,75,71,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
73681540-9721-461f-9609-6a3390e9937c | 60,75,71,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
c5bf594f-5866-4392-a9c9-ae3d95f67820 | 60,75,71,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
54e54a95-7257-4935-9551-b263037e30a3 | 60,75,71,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
a5f9d54c-6dee-4bf7-904e-49c7279ce586 | 60,75,71,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
3404549e-704d-4b3e-af07-6d71fbdc6bbf | 60,75,71,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
002c56c0-3ec3-42e3-8515-26b12999d487 | 60,75,71,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a84e7a09-11cd-493c-8db8-6e2411ebfb1f | 60,75,72,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
90d450eb-5815-46f3-959e-9271dc6dae8f | 60,75,72,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
733be287-90ee-4c7f-b634-e02f01added9 | 60,75,72,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e0610203-f7dc-4cdc-8c8f-b8f952c2baea | 60,75,72,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
53afa839-4a99-4e99-9fdd-1fcdb22fbad0 | 60,75,72,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a8a67dca-3cd5-4420-a16f-9ab6b0df75aa | 60,75,72,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
409176b8-1498-49c9-841f-b2daa7af7547 | 60,75,72,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2541305a-6ef3-4de5-8ad4-adf5703c4747 | 60,75,72,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2a4725a5-95ae-49e7-9d45-9fa6c07fecf1 | 60,75,72,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
753ac6c0-20c5-446b-91a5-b1c0dce06d60 | 60,75,72,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
8f57cf3f-1305-4245-a9c5-b115a850d0a7 | 60,75,72,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1d56bf11-3133-4a76-b0c6-8c301ef28444 | 60,75,72,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
535c49a5-4f5a-47e6-91c5-aa7d054ca336 | 60,75,72,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
a54c7306-bb1a-416f-93bb-f2ec89795d1c | 60,75,72,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
370dfbde-e32e-4f07-b1bb-a34f03e1cf20 | 60,75,72,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
86c60d57-2804-4a68-9ca6-dd8f29d6d942 | 60,75,72,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
1e3638ad-f850-4187-aca1-f4649a2c706b | 60,75,72,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
057c5890-a994-4b51-9328-281a17265e67 | 60,75,72,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
211e2b76-8cc9-45d9-857e-b833ba4bb639 | 60,75,72,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
e9ab83da-ebab-49c2-a134-c72fc6088cd0 | 60,75,72,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
d979cef1-9d95-45ce-bcfe-a0aa153f2bb7 | 60,75,72,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a7fdfe54-78df-47df-b4b0-ce4dc67e0b9b | 60,75,72,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
07c95845-4259-4607-b24c-d6168b19f273 | 60,75,72,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
c8995958-4dc2-419b-8e56-88ce7cf66743 | 60,75,72,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5bc96ba1-c3ff-479c-b22e-44c86c65a9ed | 60,75,72,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
f67e2924-a4ac-450b-bf3f-0da0f68154b2 | 60,75,72,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
97f2168e-5f9f-4aaf-86c0-b2271ffd674b | 60,75,72,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1648fbe3-a891-433f-8830-064559092bf2 | 60,75,72,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
47f25b69-07eb-4659-a749-7be166d89b5d | 60,75,72,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
f4b56579-f18c-42c6-9083-21e2e89735d3 | 60,75,72,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
0090087d-045b-4313-9238-83af9ac0f636 | 60,75,72,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
c2da009c-e015-4894-8717-70287cb4a05e | 60,75,72,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
555131ca-f59b-4aea-abbd-2e8b0ae27eda | 60,75,72,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
985f08b9-a285-4895-a949-39a2dfcd5c58 | 60,75,72,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
bdb73fcf-ab7f-47c9-845e-c22eb49c7c52 | 60,75,72,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
95b7b115-af1b-4163-929b-890e03ee0b19 | 60,75,72,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
92a9d4f2-007f-4ee4-a61e-1c7d039eb265 | 60,75,72,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
6e3ecf33-c251-40c9-950b-3c43d1b9588f | 60,75,72,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
f967a702-0f2b-40d2-b0aa-11f0e372cc59 | 60,75,72,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
86523f33-4810-4d10-aed2-c55d98177f65 | 60,75,72,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
77a6ae81-1038-4f8c-8b5c-d93f92f08c94 | 60,75,72,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
dfbd3f08-d3d8-431b-b584-aea589d577a1 | 60,75,72,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
6dcc3328-7dcd-44be-97dd-243b15ac8213 | 60,75,72,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
e4a99312-9cdc-49b2-b4d8-b9d767cdfa21 | 60,75,72,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
c43afd80-a193-46cd-a3bc-c972d2899909 | 60,75,72,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
d5029c7a-645a-4032-843a-c05d4aa56eac | 60,75,72,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
d9577551-e8aa-44a1-b021-c8e83e53ffb2 | 60,75,72,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
e1c7bff3-0eca-4947-9a91-6618a760f6a4 | 60,75,72,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
15589ee9-4770-4047-bcd3-b8664d26348f | 60,75,72,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
45e10768-741d-4ddb-9e61-92924c356141 | 60,75,72,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
aadf70b8-7c42-48f2-b175-92a6ab4d4aec | 60,75,72,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
72bfe0bc-a5d4-4d2d-93ab-ce329cbc5a60 | 60,75,72,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
1b4d3347-c211-41cc-a4b4-ec32e2b4b36f | 60,75,72,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
b447fa92-813f-48b1-958b-fb3ee832be7f | 60,75,72,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
794c3fa9-baca-467b-8084-0ad82569dbae | 60,75,72,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7e27337b-50b4-4177-a60c-7a74383038af | 60,75,72,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
24a6f09b-92fd-48be-86f2-3732f2a218e7 | 60,75,72,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
46637990-9f97-43f4-b6d4-323c79634ed7 | 60,75,72,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5faeec49-6b57-4030-a2fb-561123e1c498 | 60,75,72,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
2bb25232-19de-4c3c-8efd-3b3e7a72f37a | 60,75,72,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
f61bb927-2400-4e7e-bc33-fe064c2dd0b8 | 60,75,72,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5238fc66-f27d-47b6-8222-97fbaaed58bd | 60,75,72,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
085b3224-000f-4a10-923b-31bd71583cf7 | 60,75,72,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
2b07d890-f7b2-4d65-a31d-42e08a636b56 | 60,75,72,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
9e7c4411-09a8-431d-98ea-356cdbff5df4 | 60,75,72,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
7c3cef00-12e6-43f5-bbbf-eed95a30b8e7 | 60,75,72,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
58757139-730d-4a3e-aea8-6e728f4fce00 | 60,75,72,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
0daabef9-48bd-445d-8933-ef775038518e | 60,75,72,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
eb3f1a86-cdf3-49df-b904-b068cb01a470 | 60,75,72,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
6dd3137c-38cb-476e-874c-660d991d0b69 | 60,75,72,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
48a9cb3f-48fb-413b-bc15-3704da0ae658 | 60,75,72,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
c096d76e-c4ae-4b5b-ac76-97793df1eeb8 | 60,75,72,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e61924b3-64f3-4ba5-a5b8-7bf802034f13 | 60,75,72,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9e9417e8-d53f-482a-bc8c-26a819a2c1bc | 60,75,72,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
c6a48c46-70a1-4eff-b22d-513f14f9a5c9 | 60,75,72,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e13a2b89-fb30-45f0-91a1-689d8f25d168 | 60,75,72,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
f839ff76-955f-4676-a4a8-ceae6adaebb1 | 60,75,72,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
c13b696f-3a80-458d-b4bf-d905d3b48e9c | 60,75,72,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
adee053b-7e29-4b7d-a53e-9f4d9a0dd255 | 60,75,72,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
9e14728f-30f8-4560-8178-d22130585b8a | 60,75,72,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
13dc716f-d731-4f43-855c-cb6b0c66ff94 | 60,75,72,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
56744649-7184-40b6-bafc-503988203a1e | 60,75,72,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
0bfe63fd-0498-43a4-b7fb-58fbe9e0973b | 60,75,72,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
5caacdd5-daf7-4a62-9a8d-04767c504d76 | 60,75,72,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
f5dd6754-8e9f-4be9-8abc-d03a05c0cee0 | 60,75,72,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
e57fefbe-93d1-4f0f-b28b-ea76f66eec1c | 60,75,72,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
2a3b8282-476b-4832-858b-376dd6c9b97b | 60,75,72,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
04ea0cfc-99fe-4d59-bc33-23305992bc96 | 60,75,72,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
5225bbad-6b3f-4451-9b20-7a67ed2d4c4a | 60,75,72,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
43f13cf6-509e-44a5-8b82-d6ed778c87ee | 60,75,72,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
bb1b39dc-dafe-4465-9fee-1bc613d6c14b | 60,75,72,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
01c660e2-f51d-4290-95bd-2e1aa9eb8074 | 60,75,72,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
d3f78ea2-4353-473a-a035-62fa81b4c0e1 | 60,75,72,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
ce1e83f4-3d3d-41aa-a301-b47d953b2571 | 60,75,72,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
f141bff6-eeb3-40f8-bd74-4bbe6f666add | 60,75,72,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
bafbe0d5-6f26-4521-885c-ed071fcf6f6f | 60,75,72,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
5fdeaadb-7996-48af-a371-16b0bc59dbe7 | 60,75,72,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
768269e8-ebfa-4391-a2fe-0b92f77be59e | 60,75,72,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
0a995fa5-b3ae-4a2c-9758-8646d8fd33e2 | 60,75,72,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
585ec428-14f1-4900-aee4-05abeab10978 | 60,75,72,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
47b1fd13-a1a3-4b10-9af7-6f9dc9ea2a7b | 60,75,72,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
a52bd449-b60c-427f-ab97-31306e934832 | 60,75,72,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
4448aa8c-840f-4e2c-849f-3001d87455ca | 60,75,72,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3ebd1b4d-42de-44a2-abed-490ff51d047d | 60,75,72,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
21483c36-ca6e-4fdb-8385-ad2f04d75568 | 60,75,72,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
9b36142d-65d7-4142-861f-d35d036a8d38 | 60,75,72,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2c951f61-0457-4165-a6c2-4047f0e42033 | 60,75,72,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f95d21ac-cfe1-48ce-a8b0-55290b23a48d | 60,75,72,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
98cb83d8-3ec4-4740-a39e-e9a076649f2d | 60,75,72,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
54a68331-0ba5-4568-a99f-234643336626 | 60,75,72,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
95235afd-70ef-40f6-b89d-1503907388b6 | 60,75,72,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
8d223e9a-2866-4483-88c0-807119d4d4e6 | 60,75,72,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
c6471d2c-1d2a-4890-bf60-4a4a0af8bfae | 60,75,72,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
6126d00c-788e-4016-9069-aee467e114a8 | 60,75,72,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
4d62c192-dc97-4e13-a258-81acaf9f127e | 60,75,72,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
5492f8b2-4646-40a6-ad4e-ae9cdd3c8de9 | 60,75,72,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
92f67b69-6007-4adc-935e-79965f70e6e6 | 60,75,72,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
6fd123d1-7415-4a89-a0a6-512efdaae298 | 60,75,72,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
f7067978-7e9a-4622-a1af-481bba1f1fad | 60,75,72,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
898d4154-8483-4076-857d-47d364c217bc | 60,75,72,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
dddff4b5-5a25-4278-b1af-9de2d8f3cdac | 60,75,72,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
11407d2f-7dd7-4e0d-9d4c-7544654e5a2c | 60,75,72,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6f396b92-a911-46d6-bada-6443a398de70 | 60,75,72,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8ad7e643-986d-47e8-a8f5-6e0b7c6e46c1 | 60,75,72,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5c63a7eb-8d7b-49a2-86ab-1032857d8f31 | 60,75,72,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
07915fcd-aa08-4763-a75e-4f4d7379f236 | 60,75,72,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
41b8c86a-6c33-46e6-a771-902b65dff534 | 60,75,72,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
793fba4e-c124-479e-bbe6-b867cd4136cf | 60,75,72,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e81a6680-8836-44b9-991e-b97afbc68efd | 60,75,72,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4b7143cb-44ea-4123-9f7c-15f70f05c8c3 | 60,75,72,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
3faaef18-1fe3-4f02-94cb-077ca98fefb8 | 60,75,72,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
776cd679-afe7-45ee-a0a7-dac79130ae86 | 60,75,72,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
ef9af767-3c45-4575-8daf-7100deb6fdd9 | 60,75,72,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e5acfca2-9249-4794-8d6b-48af20119418 | 60,75,72,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f3bae2a7-e20d-4813-b905-a6bd7bed871c | 60,75,72,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e20cb73f-cc65-4eb6-9a54-65ba6ee572d8 | 60,75,72,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
382eabff-9a85-4b7c-9e87-b85592dac617 | 60,75,72,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ec99d63e-0f33-4e64-86d6-20db46ff1f48 | 60,75,72,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
5408bdf8-0096-4b93-a5dd-effab4b11de1 | 60,75,72,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
be2f650e-733f-47fe-b686-4c87ea706302 | 60,75,72,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
dae745e0-3674-443f-9943-963dc89cbc90 | 60,75,72,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6b2d7fcd-fd93-4fcf-89f0-ab864e27d01a | 60,75,72,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
55ebd8a8-db65-43a3-afc8-7f87b9ed4551 | 60,75,72,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d0f48edd-314c-4281-976d-71257a2f82b9 | 60,75,72,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
309d6e68-28f4-4ebc-95c1-5b1564d9865f | 60,75,72,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
fe3f8f90-0985-4f8d-a7b7-586fd85bc2a5 | 60,75,72,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
29370a2e-bb5d-43b7-a03a-ce64ada84138 | 60,75,72,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
0319805c-cc7d-4fc3-bdf4-4032c0dabb3a | 60,75,72,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
15162a5f-fda9-4c17-9eeb-401c31d6ce14 | 60,75,72,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
9ef0493e-1510-4597-ba8b-2ef1d725a2d4 | 60,75,72,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9b47db60-98d4-480d-86f1-724c7c7e5705 | 60,75,72,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
a5a89dec-280d-493f-978f-9928d3b20b7a | 60,75,72,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
3694e168-d83c-47e3-8503-45ae7463b354 | 60,75,72,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d56622d8-2e77-4b9f-b536-598af42b5ad7 | 60,75,72,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT CALIPER - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a35983d0-efe4-4e22-972f-c37c57e1186e | 60,75,56,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8959e37c-9e78-41d5-aa7b-428417a8bf8a | 60,75,56,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
80eb7e4e-af1b-4dbb-a049-f7e0f139d768 | 60,75,56,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
dcd6a1f2-9f25-429f-afb7-a8f59d5e7056 | 60,75,56,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
61a4a534-249b-4c30-815e-a18db374164d | 60,75,56,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
6d724012-b876-4405-8fa1-0065c60882d0 | 60,75,56,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
42732d60-bbc2-4d7e-a875-979be57868fb | 60,75,56,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a425192a-1420-43ff-9c76-b801e0552bf8 | 60,75,56,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9423088f-d4a4-4760-8243-6af4e122d550 | 60,75,56,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2ad9d4a5-796a-49d6-8455-64f2c2c76441 | 60,75,56,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
6973022d-e928-4d4d-8e60-9ab90a622f05 | 60,75,56,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
6b695ade-c744-4445-aa7d-c7d4b05aedd5 | 60,75,56,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
3664c1b7-3362-40eb-949d-cf4357b2d415 | 60,75,56,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
afa192f5-bedf-4e59-9ae9-98da5a7cdc9b | 60,75,56,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
47ebfcdc-f663-415c-8892-6a573f7e1b12 | 60,75,56,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
48ad6bc5-a07e-432a-a7d0-bf6089fb372f | 60,75,56,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3fd59eb4-a1a9-443a-9d71-5220b4604705 | 60,75,56,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5b9b7226-4b0b-4429-b0e0-03fe5a0233f4 | 60,75,56,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
a246f6d4-1cb0-4faf-944b-043336f1ec72 | 60,75,56,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
ac7fccb2-efca-4c25-9070-4d0520793a54 | 60,75,56,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
40fc628d-9f20-47f9-9241-01eb77e44019 | 60,75,56,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2839da64-62f9-43a3-8ee6-604263f5686f | 60,75,56,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8cfe7d40-94bb-4165-80ec-a00f671880b1 | 60,75,56,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
0f0676a4-4a79-4251-9740-191bb91f4fe6 | 60,75,56,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
f8b155f8-e6ac-4126-a225-626438fc0348 | 60,75,56,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
98d2ba4d-4d24-4b16-be2e-8093d68b623c | 60,75,56,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
40044ace-235b-412d-b5b6-43ae7df01f10 | 60,75,56,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5dc15860-0343-4f80-bf10-8ac1df1bb075 | 60,75,56,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
2bf60b1e-2b6a-44ec-aa0d-6f9b37765b02 | 60,75,56,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
6475d963-e56d-4b32-b189-ce44879a8fcd | 60,75,56,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
ea92b2e5-1ad5-4910-a232-2b9f53168982 | 60,75,56,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
acf9f3a3-763d-4fd4-8be5-da7d1db1e26f | 60,75,56,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
e97791e2-f1f3-4f33-a909-5c2525470a73 | 60,75,56,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
0fbe4779-3ada-4f27-b3f1-c7ec9fa5d4db | 60,75,56,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
37a40d8b-e75c-4d3d-80cd-8ed210b4ec71 | 60,75,56,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
63dd13cd-8e7c-41c9-8db0-016bbad9e69d | 60,75,56,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
99fa414c-7f1c-49e5-9df3-88e47683fa62 | 60,75,56,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
8d95025d-0d65-461f-afca-1d82eaff6f71 | 60,75,56,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
13721786-9abe-4f55-9b60-22440041739b | 60,75,56,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
902322bb-7cc0-42c2-8c23-17505c4d3846 | 60,75,56,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ea62c516-5cc0-4d0f-ba65-8d0ba6f698ae | 60,75,56,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6ff11ba8-2265-4a9f-8e4c-af74e00fa229 | 60,75,56,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
09907774-e265-41c3-9f2e-a46277cc1eca | 60,75,56,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
ceab3ed6-14a6-48da-9198-557f699b74c9 | 60,75,56,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
11f0b926-48b0-4889-b2f5-6fddd95ecec7 | 60,75,56,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
f6859b13-e10d-4fc3-b70a-579731eff309 | 60,75,56,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
60b41a19-993f-48f5-afe3-aafc66dcc4e9 | 60,75,56,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
fbb744c8-6e13-4272-aab6-79c0ca5b0621 | 60,75,56,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
9b9f5621-4570-4686-afc5-eba2fa2663d6 | 60,75,56,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
dc4c3f47-c7b8-4510-8ca1-c88e9b3ddf7e | 60,75,56,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
9692abf4-0a9f-4cae-8597-9a6e6bcbed6c | 60,75,56,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
0de16c5d-8dab-4f6d-b78d-9280d3972cd8 | 60,75,56,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
ff25714d-0e29-4394-a43c-b69e901eb4de | 60,75,56,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
851c1982-fe72-43f2-9924-e931df5b225a | 60,75,56,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
2a1ac01f-b72a-4890-a117-698796ee5d13 | 60,75,56,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
85ee0477-4a33-4a02-8ef1-029849df178c | 60,75,56,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
14b1b4aa-0e9a-411e-ba19-668119204752 | 60,75,56,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
493b46cf-17bf-42dd-9307-ebc2e757fccf | 60,75,56,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
e806033c-b74d-4c63-adff-1231dd1666c2 | 60,75,56,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
244d0727-88cd-482d-8735-4bbd1bc275ae | 60,75,56,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
db7f8dc5-a44f-481d-b4e5-9670a696321d | 60,75,56,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2f558d75-b9ae-4f99-849e-a3a04280a732 | 60,75,56,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
47c92ed2-4e24-4efe-a752-e4deb7c6d63d | 60,75,56,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
9efa1a24-8c93-4188-9446-3fd7e6f34bdf | 60,75,56,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
50d3c0c8-61f9-43b8-aa1a-57aec5a87bc7 | 60,75,56,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
b8f68b49-9c0b-432e-ba0c-665cabe56f60 | 60,75,56,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
4fc5a52c-6148-4ce5-b4a3-88b0e024a08c | 60,75,56,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
f81f4ac9-3681-463e-b114-04551880204d | 60,75,56,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
eab3f5a5-5a39-4c8d-87b8-11bde5bc6ce9 | 60,75,56,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
247aebd2-0524-4a6e-a0e4-8865e2f34ed5 | 60,75,56,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
9229c84b-7527-4eb6-a22e-f32479190178 | 60,75,56,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
b5944e7d-60fd-49aa-9e19-760862524512 | 60,75,56,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
06d086dc-ae36-438e-815f-967ce4c945f5 | 60,75,56,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3fb93182-6719-41e4-ac2c-305c61003b17 | 60,75,56,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9ebdb049-36e0-45b7-9411-db2ddf97d3f8 | 60,75,56,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a27156e5-4f5a-4d01-b239-bde02aee8745 | 60,75,56,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
8e6fb126-3c26-425a-b08f-d88c497570f8 | 60,75,56,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
72f8b6f8-44ff-41b2-a305-facfc8d39863 | 60,75,56,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
47778a1a-d058-40b9-81eb-cee01f272e48 | 60,75,56,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
67b7e6aa-5487-4f97-a173-b6f088056d26 | 60,75,56,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
8b12581a-d108-4285-9945-be8d5e85e245 | 60,75,56,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
a37819db-c8eb-4388-9d24-2f1fc571e564 | 60,75,56,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
7469f429-dcca-4da0-9530-cffdfcf5fb35 | 60,75,56,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
a9b8ae6a-649e-489c-b687-b952d849bf58 | 60,75,56,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
4783566c-309c-4c52-a413-0fd83f196aa5 | 60,75,56,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
c6a79904-5603-4e04-8bc9-7e792d3f2018 | 60,75,56,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
6f4b3161-5a30-4a35-b354-6c5c0bf89cc4 | 60,75,56,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
ffb11212-a4b1-451a-88f8-53dab419f6eb | 60,75,56,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
7ba2d71d-94c6-450a-a8bb-5d1b2d6818ed | 60,75,56,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
77d0ea32-ca38-4ea6-8209-a4c64502142a | 60,75,56,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0ed86f59-3ef6-4925-97e5-aedd902adf78 | 60,75,56,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
c4469e35-7756-4836-8622-36198f6186ea | 60,75,56,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9f49ab1d-afa3-46f6-9856-f401e6b73e28 | 60,75,56,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
2f0d412c-ef42-484e-a784-dbab709e01eb | 60,75,56,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
b1053523-eb6d-4a49-95ec-92bb3b36e411 | 60,75,56,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
926946d6-3016-4604-8d0a-7beaf11d2bb7 | 60,75,56,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
a6ed0042-762e-4260-848d-760f29727ac9 | 60,75,56,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
e67ee59b-54e7-4f7a-b71f-b4fdaf4b762e | 60,75,56,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
a14ab32f-2fc7-450f-a06a-2f1c90afc596 | 60,75,56,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
0b2c4e93-f5a3-4b59-9a2a-179dcbc186ff | 60,75,56,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
ff367854-d85b-4538-b5b1-ff9235cfd71a | 60,75,56,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
2f74d000-dd38-4fe2-b590-f402570d4ce5 | 60,75,56,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
257fd8d5-eafd-4273-944f-d251af8ae086 | 60,75,56,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
0dcece84-c05c-4d5c-9281-02eceb00e27a | 60,75,56,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
d146bc15-0845-4556-8a1f-d963365390fe | 60,75,56,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
4ce8034c-a18d-4c64-bbfd-310eca05393f | 60,75,56,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a98641c0-4025-4f04-9121-4bbc862b46d2 | 60,75,56,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b9cede14-e61e-40fb-9f73-9fb2d46cb299 | 60,75,56,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
24b4a10d-a533-49ff-9698-484134dfaabd | 60,75,56,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c4642aad-9f27-4e31-afb0-99907777aa34 | 60,75,56,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
eeb562f0-07f9-4cb3-9790-f19073b217d7 | 60,75,56,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
cf507263-53c1-4d3f-8305-e7b138bb0363 | 60,75,56,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
63dc515b-b8bf-423c-b29e-0f03aa0ea1f0 | 60,75,56,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
1dbe8df0-6177-42c9-93f6-b4a7ec4e3ce0 | 60,75,56,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
ae2bb3b2-15f3-45bf-88e7-3d8157e3f317 | 60,75,56,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
d9b7c9ec-6da2-4acd-bad7-bcfa5071d5c8 | 60,75,56,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
cb0b167d-6db2-4710-acb4-855c941e00d9 | 60,75,56,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
8012037e-5593-4f1a-856b-b07da3bb92fd | 60,75,56,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
8c588b85-d5df-43b3-a9b5-f9bc5254d055 | 60,75,56,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
26f83096-eef2-46b5-b880-cb70d87c12a8 | 60,75,56,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
f86d7b11-070b-425a-a742-55d77c2cf362 | 60,75,56,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
9973f4bb-f030-4b08-aa36-5feb0e20fdc8 | 60,75,56,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
823bad91-392a-44d6-9b9c-bc25923ec805 | 60,75,56,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
52c41035-74e0-4bd8-be78-4f578b3d7de6 | 60,75,56,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
052c8f35-8034-4de3-b359-e4313412bcc2 | 60,75,56,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c725fcb8-6de7-4146-a820-2b3529e0b2a5 | 60,75,56,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
cdb1c378-c917-46fa-9443-a76a095e3bc4 | 60,75,56,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0d362bcb-e910-4c37-bfcd-d952d60b317c | 60,75,56,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
aa253e12-2f05-41c4-bbd5-35af9a3fe086 | 60,75,56,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5f631a2f-7833-4fc3-87a2-4d37cf71aa1e | 60,75,56,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
293f77b1-d0ee-414f-82a7-9c34b793820d | 60,75,56,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
230b07db-588a-41c6-9b66-1f53f90afb39 | 60,75,56,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
289a5ccd-1b24-41e1-9213-7f6b66075759 | 60,75,56,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
10128654-43f0-41f4-9fc5-f44d7f4702b9 | 60,75,56,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c872f44a-d4fa-4e17-b414-058990434967 | 60,75,56,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
6ce10506-2b02-41db-8e4d-a3d52a2e280a | 60,75,56,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8a59f7eb-2b7d-4b0b-9391-f694511d36f6 | 60,75,56,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
4938ea4f-de78-4731-9ca5-20378897ff19 | 60,75,56,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
0c942d9a-8db1-4086-936b-e32ef703160d | 60,75,56,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
d96937d5-6aa5-4344-9d67-50545a3cf9c5 | 60,75,56,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
0c5089a6-a6da-4704-97c2-3a5b087e274d | 60,75,56,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
20168f10-b52a-46aa-9e20-01d435f24d26 | 60,75,56,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7c481ca6-4906-48eb-8bcf-3d9c5dac66e1 | 60,75,56,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
047c2401-5a19-40ae-bac7-c23c0e798960 | 60,75,56,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c03b0ac8-cc85-4b50-8ba5-d333e037b5a3 | 60,75,56,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
ade5635e-000e-43ea-bd3c-29d363c36a09 | 60,75,56,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
96522720-3c95-4726-8d31-956e0f5e61a7 | 60,75,56,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
47b2da11-d487-49da-9f76-0b5ee924c250 | 60,75,56,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
9cf695f6-bb47-4f06-8b8a-873b21721fcc | 60,75,56,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
3f9a8a9d-0efd-429d-9690-c4751d14abdb | 60,75,56,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
3c2fced4-e84c-497b-a680-8a25560e34b4 | 60,75,56,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
b10fdf97-4b16-4c4f-ac20-1ccd8dd47364 | 60,75,56,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
be6c3ef1-cdf3-4194-898e-bf3aca2a0de9 | 60,75,56,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
11273b45-a213-4877-bd90-53cd4e97256b | 60,75,56,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c8e84280-fe7e-42b8-a03e-3c18b71d8318 | 60,75,56,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
645bcc87-e6be-4915-8fe2-c1133d1ed324 | 60,75,56,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
95a32b61-4b50-4194-8f13-8053b49279b9 | 60,75,56,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4f0ef967-860e-49f9-af19-2bb4503cc36c | 60,75,56,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
39a32755-c0b0-47ea-947e-9a821436ef80 | 60,75,56,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
7e0dc1ae-63ca-4c08-bb8b-20fdab63d485 | 60,75,56,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e547ed5c-efe9-4de4-83ec-5c674edb351d | 60,75,56,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9b11e016-be33-4661-8d3f-8f95ac194d92 | 60,75,56,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
1799f862-1758-4696-8e70-7ca5b7f7ca3d | 60,75,56,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
d9f73955-7cdb-4bf7-9bfd-4bb49a46e5c9 | 60,75,56,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
e03f3eb3-ad56-49df-8402-b29132a6b975 | 60,75,56,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
8dbdd2ac-8cac-437e-94d6-6f7027d745a8 | 60,75,56,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
da148187-3104-4f60-a979-6935e927ac96 | 60,75,56,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
1eb26974-9fa1-466d-b23b-3db794936682 | 60,75,56,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
72eee650-53ba-4e37-9ff0-190100417ef8 | 60,75,56,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
10e35a72-801b-4b3a-8289-49e29ad46fb5 | 60,75,56,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
be556685-d06e-44e6-a524-fca525ac8cbe | 60,75,56,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a0601239-9e70-42fe-99be-901d0a9a8d36 | 60,75,56,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
334f59e2-a212-49d2-a203-36ba6c377add | 60,75,56,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
a2e1240d-e06b-4b7c-a736-80ebbfaa5756 | 60,75,56,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
03cc7ca2-195e-47b2-b674-f8bd05ff1905 | 60,75,56,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8ad6dc02-18e6-4440-8d63-3138a098e2e9 | 60,75,56,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9b89b233-6c9a-4d94-8158-2756c3ef80bd | 60,75,56,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f453d351-a69d-4520-ba48-4f1e2c735a44 | 60,75,56,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e28a2ccb-583b-4ccc-9d9c-4579096f27c0 | 60,75,56,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
8c10f05e-7209-48ea-95ef-e9c76fc32525 | 60,75,56,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2cd417aa-fa48-4a99-83d3-ca590c25546a | 60,75,56,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ed2e0ec8-0975-433e-8e99-05d07431d90b | 60,75,56,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
9a422e85-de80-4485-bd47-27450c4be324 | 60,75,56,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1e8d3f70-a5d8-4891-8c9e-da24657d6a5f | 60,75,56,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
4bf4003a-3576-40be-b61b-01e59ff9f00e | 60,75,56,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ad0b0a09-a7ad-4269-add0-113cf5980e5c | 60,75,56,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b6a969f5-4f4e-4bc2-9c92-c878208a3d9c | 60,75,56,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
f2b668ac-4e7f-44fb-9f34-882ffda76da0 | 60,75,56,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2db560b9-436e-4c0c-b59d-affe2acc5aad | 60,75,56,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d0b13f2d-9968-4e1c-a364-ca64fb822a24 | 60,75,56,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
1df5e23d-c11f-4486-9ee4-23f1386c3f3d | 60,75,56,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
909103a9-6e4b-4b10-a59d-365f7a3db5c1 | 60,75,56,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e81233bd-fb00-4a43-81e4-bfab9fba70aa | 60,75,56,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
98d185ec-b8d3-487d-adb0-bc29828109b7 | 60,75,56,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
4c90906b-c2b2-464f-bccb-108f6d657d1c | 60,75,56,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
691f2bfd-72d6-438b-940d-64cc4d90bdf9 | 60,75,56,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
1e37e639-7c92-448d-a6f4-383670ff1f97 | 60,75,56,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
d0ce472c-536d-4816-8f03-7347a142c2f5 | 60,75,56,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f801d927-3b1d-4da7-9f16-a378a3228c94 | 60,75,56,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
53a3bd9f-5b6f-4530-94c5-325266a9de02 | 60,75,56,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f85ace49-5904-4a64-a6e5-92eee3b83a6c | 60,75,56,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
bb1d4c38-be74-48ae-9f20-a8bcadf0bafc | 60,75,56,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
6cbfdf0a-e916-42d6-835f-070f88f58ad0 | 60,75,56,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
de7311ef-9481-415a-9506-42d814b11c86 | 60,75,56,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
0cbb6515-42da-4818-9771-448fb14580ca | 60,75,56,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
94a8f992-6902-406d-8d20-3d086ea9e064 | 60,75,56,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
3701ea0c-4524-46d6-b59a-17207cf65bd4 | 60,75,56,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8d5fdcf5-cc3a-47dd-a7b9-67dfa78e414a | 60,75,56,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d8cf9051-9199-44c7-8812-832ba484803c | 60,75,56,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
fef7aa15-c984-4fcb-afc9-c6e08053edce | 60,75,56,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f32c767d-7f5a-49fd-aafd-f27c7cb63563 | 60,75,56,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
71c6f90b-7c3b-48de-a2ba-6debf1bf0205 | 60,75,56,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
45742240-cd6d-462a-8f45-8b975159d90d | 60,75,56,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9d5fca37-81fd-4115-9136-2f89ea8d31d1 | 60,75,56,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a3222122-9774-4aed-94c9-f4be3d7b7ff4 | 60,75,56,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8eb06c73-45a3-4734-a891-9046a2ba47a6 | 60,75,56,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3d775f85-136d-4d32-9224-38854d275ad2 | 60,75,56,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f1fce1d5-583f-4edd-844a-f6cb148c6e42 | 60,75,56,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e0e5ff73-2422-4533-bb3f-cdb8cd1ff459 | 60,75,56,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4d395fc9-8725-46a2-8ed9-cfdd73afa504 | 60,75,56,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
ab534000-da42-4515-88b7-710c9def90bd | 60,75,56,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
a43b3663-24aa-4859-a23f-0e01a48e0ec4 | 60,75,56,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2725030b-5275-4e89-ae73-98b84fb14ccc | 60,75,56,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
09923391-0b26-4f78-8212-95849b4370bf | 60,75,57,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
9f19f10e-b565-481b-9b65-5d9ac3d2bcba | 60,75,57,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
374a9cdc-f840-4463-8084-4962442303f9 | 60,75,57,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6d100f0c-4172-4fe6-a7e7-f55c336fce3e | 60,75,57,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
289486aa-0209-47cf-b127-65766fcc5fc7 | 60,75,57,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f3a65a92-6b96-4afd-b9ac-ebd390f20e1c | 60,75,57,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
15fadfa2-2a74-48ef-b2bf-350b15a5b3cb | 60,75,57,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
bbe870d5-4370-4d73-a521-3bc66f565ec3 | 60,75,57,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3eefa9ab-a582-4590-919a-8181d1bd949c | 60,75,57,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ca3f8d19-3b5c-4152-b2e7-ba7cb26d5ce9 | 60,75,57,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
0a3ed26e-b16f-4746-9c02-66fc3146668c | 60,75,57,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
23cfe9d6-c2ac-48a4-b5b5-debec57eed49 | 60,75,57,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
be9bedf9-8dae-4f99-b267-8b63e0ea912b | 60,75,57,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
aab64b0c-9272-48ec-9cb5-744e50156ba8 | 60,75,57,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
dc52e70c-2712-45f5-8a39-41dba1d90220 | 60,75,57,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e0b7b7ea-63e3-4750-87fa-81d009c0043f | 60,75,57,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6cce43dc-c67b-4737-8233-a48f23746e26 | 60,75,57,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
b1ff24d6-d451-41df-9f40-0483935b686b | 60,75,57,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
1a4fc5ba-be2b-4e1f-ad6a-34798fd96f46 | 60,75,57,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
2dee014d-7972-460e-a931-7fb6b8c1f992 | 60,75,57,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
51f0d685-95e2-41fb-8449-5f000ebd2f0b | 60,75,57,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6c185b99-c63d-44e7-982e-6af164f1265b | 60,75,57,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
de08e6b3-ee9b-45c1-b74b-0cbcf788c574 | 60,75,57,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
6fe45349-3dbb-4dca-a9fd-580c50924def | 60,75,57,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5f11ffde-6686-4535-8fd7-9f33dc77af2f | 60,75,57,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
510a556b-591a-4b1e-8d4b-34a97af38858 | 60,75,57,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
b786463c-31f6-4a55-b7c6-c17f29a4984f | 60,75,57,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
4b682a0f-603e-4323-bd24-38ca8ece3cc4 | 60,75,57,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
b578d297-de06-4114-ab78-97475541af10 | 60,75,57,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
fcdbe864-07f2-422e-b80e-7f7fdb2745fb | 60,75,57,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
b8f2d721-d35f-4298-9e91-21c349b15cd8 | 60,75,57,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
6f470ac2-eaf6-4f8f-8054-4fb85b6f87f5 | 60,75,57,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
6834d66d-916a-4169-a830-3e050f8638b1 | 60,75,57,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
ffc49277-0f32-4472-8f41-19b9680bb2dd | 60,75,57,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
6eb8364d-8caf-4848-af13-55db5e474f6d | 60,75,57,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
96a9b0bf-e1b1-4899-ba5d-5b53073a3a0a | 60,75,57,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
facdbe57-82de-4d54-b63e-5c7433e882c4 | 60,75,57,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
cdc6eafa-e649-4581-b55f-fe89146392cc | 60,75,57,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7d1f4e01-b0c9-4074-a814-24e64c84c749 | 60,75,57,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c581f50a-5a32-4dda-97e2-5f06e5331031 | 60,75,57,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
9e7c5a85-95b9-4a81-9175-40971beaac62 | 60,75,57,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
18e83dc9-6326-46e0-b1cd-b936db70ac9b | 60,75,57,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
d34eaa16-830e-4a06-9fd8-e7d40894589f | 60,75,57,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
0e7c97f0-f0f4-4592-b737-7362f71c5519 | 60,75,57,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2b988a5a-e73d-48c4-b553-b4e01bc044c1 | 60,75,57,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
85d9d686-7e5f-4ed1-ba13-7bb252690775 | 60,75,57,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
d881c12e-bca4-40a4-ae90-31e18c09321b | 60,75,57,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
e71bcb33-bbe7-4504-9b71-be93881d8e76 | 60,75,57,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
1150caa9-a3e4-4a31-aefd-b51d384a9e84 | 60,75,57,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
9426bd9a-418a-42d3-9712-38945d20c694 | 60,75,57,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
eab6c29c-2efb-4f33-8d83-cf22ccee52c1 | 60,75,57,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
a452f670-0bb4-41a1-ac05-23926d68516c | 60,75,57,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
125c87d9-942e-4b77-b3e0-40e43aa973dd | 60,75,57,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
c6723358-adc0-4010-b51f-a8370fd6eb68 | 60,75,57,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
35ff1862-7cbc-4535-b44a-2f255ee29456 | 60,75,57,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8ab32c4d-a641-451d-8ada-0c51d9f2de0c | 60,75,57,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ee2ca981-4ccd-4a92-923a-0cb9887c6473 | 60,75,57,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
7f21dd92-71b3-4612-ba3d-adac628c4870 | 60,75,57,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
912b0f95-17d0-433d-a39e-bae9ffea9d7b | 60,75,57,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
16f153e9-e8ed-4c30-b97a-deb004473da0 | 60,75,57,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
803d6841-cbb6-4bc4-83f1-f75ab71ddb9a | 60,75,57,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
233f3f13-88c8-4603-83e3-440ddb05a36a | 60,75,57,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
d1f14eb6-033d-4965-a1ca-262de47fb63b | 60,75,57,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
fc106894-c0df-4977-899c-731422a9c248 | 60,75,57,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
879322d2-a6c8-4cc2-a2c7-a20e0e76bf99 | 60,75,57,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
3700d281-99e5-4fa1-a780-e60c98d9ba07 | 60,75,57,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
85c57fd4-6741-48bf-8822-14fbd93df54a | 60,75,57,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
e1064286-37d3-4007-9b01-c7421f833dd6 | 60,75,57,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
51e386b1-575a-4865-9d4c-61585a847946 | 60,75,57,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
6065076e-c789-422e-bef1-e49332765f78 | 60,75,57,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
8543952e-d83e-46e1-aaae-a45b08635dcf | 60,75,57,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
cd5e3cae-0b82-4ec2-83a4-60265449c9aa | 60,75,57,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
6a2ac471-18cb-4d9b-9b48-822618a554e5 | 60,75,57,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
90b97215-e183-43cb-aa8b-93b806811b2c | 60,75,57,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
8dc30b20-f8f6-4c0c-8171-2aa11484f725 | 60,75,57,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a01cd9be-7558-43c4-8a1d-5815ff70c391 | 60,75,57,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
d1ebd40d-b649-4644-adc0-33532e96744f | 60,75,57,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
042eb452-58ef-4b45-b540-a948cd339488 | 60,75,57,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b0264f5d-436e-4343-bd2c-f3d59e5ee8db | 60,75,57,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
2144526c-9474-4098-9824-3814f5a1f0da | 60,75,57,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
c0eabdf9-41b3-4023-93b3-3a3d22e73c57 | 60,75,57,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
9df37e9f-db6f-4e78-832d-d7342c5fdc21 | 60,75,57,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
19b81f69-be5f-4339-bf03-40642e87c5f7 | 60,75,57,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
fce88d9a-0967-4fd8-b749-6c5bf20701b1 | 60,75,57,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
6e79f801-8e39-45aa-944e-a6db32d014a3 | 60,75,57,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
c0544a45-c306-4427-aab2-cedcc5dc4d7b | 60,75,57,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
32345db6-4391-45b1-8e13-acefaa905f3d | 60,75,57,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
843bfda6-1360-4a5a-910c-19d68f6fdf05 | 60,75,57,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
a5d02ce3-6e9b-43dd-b328-9e03f2f06eb0 | 60,75,57,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
37c23967-79c5-4601-8587-3635b4ad297d | 60,75,57,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
70c4dbdd-4265-4ef7-8b1f-9c334d26c354 | 60,75,57,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
225b57cc-d444-404e-b09c-7dafc7677028 | 60,75,57,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a415e5b4-a48d-4ebd-9ca1-0086f493ff87 | 60,75,57,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
622e5c57-f002-400d-b5d3-c6d5ecd8f8a0 | 60,75,57,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
5d7dfe9b-2650-449e-8199-da2cb1f6dac1 | 60,75,57,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2ed692b6-32f8-402a-9cc2-49e974ee923f | 60,75,57,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
2c144abe-6ed8-4540-9828-d6cab0e457ac | 60,75,57,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
e1c639b8-0d6b-4dec-aba5-8ea78ff4edb9 | 60,75,57,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
743de223-ab07-49a0-8002-045c998a190c | 60,75,57,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
d4a77659-efe7-4b24-93c9-3d29862f1998 | 60,75,57,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
6c688950-22c1-4bd7-ba7e-f293bc8e11e9 | 60,75,57,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
20c1ccd1-af26-457d-ad46-eaa4fcbd0974 | 60,75,57,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
e23324e5-2203-4dd1-b15e-2087c0599299 | 60,75,57,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
e78fc13e-934a-48c7-be9a-a949feb29d3d | 60,75,57,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 30 | FALSE
d325db3f-3746-4bfe-b959-1caced20daba | 60,75,57,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
baa9457b-024e-45e0-8009-1604ad0d4882 | 60,75,57,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7b80183c-2615-4add-8e16-e5ceb4dfd5bd | 60,75,57,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
94cfafc6-777b-4f7a-a947-145614b947f2 | 60,75,57,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
31cd07e9-b8b3-4231-9752-3264beb9d24c | 60,75,57,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
960a5e52-3ea1-401c-9f74-cb79214a48ea | 60,75,57,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
1f3855f2-0fe3-48b9-8bd4-128957c030b2 | 60,75,57,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
a19313ca-04f5-4ba4-a6c5-a267ed8546e1 | 60,75,57,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8716270b-b655-410c-8093-cbe60991c6ed | 60,75,57,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 20 | FALSE
8a1fc78c-1fb0-4f7e-80ef-e144255d2b40 | 60,75,57,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
e8dfe3f2-26a5-41a5-b87a-316b5a49b221 | 60,75,57,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 20 | FALSE
48b19675-765f-4353-ac07-b1fbc848db43 | 60,75,57,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 24 | FALSE
03944d20-8d49-4cab-a34a-80df1c68e4a8 | 60,75,57,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 17 | FALSE
e64bfe2e-7613-4563-a897-8055f8f7d262 | 60,75,57,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 17 | FALSE
66c433b3-6b58-4176-b288-0e779d63c4a4 | 60,75,57,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
3924ec10-4a26-4b70-9060-ed34fc400b4d | 60,75,57,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
48a56288-d02c-4561-a832-bc7df5685315 | 60,75,57,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
99f5b449-8fcc-4170-9a48-861d1fd8f071 | 60,75,57,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
c4584223-2a00-44b9-9f25-8551115b750f | 60,75,57,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
6e910cb6-bd34-4432-be78-c3509baabf50 | 60,75,57,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5cc1e839-a8e6-4dbf-a2f0-4d48ba6e65db | 60,75,57,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3ea7f609-a667-405e-9155-51e174a8bd07 | 60,75,57,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b4d02151-faac-4e30-a705-a2754144f9bd | 60,75,57,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
087b9be4-686d-4e1d-8ca9-fb2dad9d4485 | 60,75,57,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
4357bde6-3061-4380-92ff-9681ae7ed97b | 60,75,57,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2e9c050e-fd1c-401e-8496-021d9692fd8a | 60,75,57,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
33ee8af3-7880-4e0a-9066-a8af0aa31970 | 60,75,57,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
d2d199a6-8154-4190-8037-3fb7d1d0bd5f | 60,75,57,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
18fb5b54-97ba-4cd3-b099-9a87c916b70a | 60,75,57,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
87ec5ddc-f444-4e60-95b4-a3d616eec33e | 60,75,57,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4c0c38b4-f45f-4898-a8e7-cf983941f6ec | 60,75,57,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
ab29415a-f006-4036-a576-68daac2fceac | 60,75,57,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
1187c3e7-24fb-4b62-b237-dde67cde1b7e | 60,75,57,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b143f158-dc15-453b-b15c-8696008656ea | 60,75,57,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
9d53a8fc-8f94-4c29-ac32-7892c56a327e | 60,75,57,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
2faf64d9-8252-4a17-b5b1-1e452bdcb26a | 60,75,57,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
367d0739-84d4-4cb5-b586-9e7631e7052d | 60,75,57,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1ed9c0a3-2cf9-4e0f-b047-6f3d7f96db00 | 60,75,57,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2289646e-44cb-459e-a9a1-a013e3796fc2 | 60,75,57,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e89df78d-5f01-45ad-9866-3f5d32e0a180 | 60,75,57,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
52906a83-b627-48e7-ab27-9192a4f9e2cb | 60,75,57,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
3fd47905-9be6-4a01-b1b1-27006a2e63d9 | 60,75,57,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
59bc0272-1be3-4421-8476-8e4647314545 | 60,75,57,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1d8afc10-188d-4e09-aef0-fca9263bcb64 | 60,75,57,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
90f1eff3-17ef-436e-bb65-0ecb5baee84e | 60,75,57,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
aa8431b9-7463-4a7c-af9b-f3435141114a | 60,75,57,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
0d8291ed-1698-457d-990e-68a255776269 | 60,75,57,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
166253fe-a3b8-4459-8ca3-999b1f6c6f58 | 60,75,57,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
6078e49a-be50-4cf5-9e10-5274d5edf159 | 60,75,57,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2d42bca6-f371-44f1-85d5-48e93b96ec8e | 60,75,57,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
23aa27c6-629e-4bed-88b1-6486c7bff67c | 60,75,57,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5cab56e7-fc04-4da8-8c74-4d3e16bb129b | 60,75,57,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
8968bf65-c21f-4588-83e4-7a93bc7f56fd | 60,75,57,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
85b9794d-d3a4-4050-803f-bdc62ac901ff | 60,75,57,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
d2b528a6-f936-47c4-8ae8-6525b8a9104e | 60,75,57,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b3796a6f-0c33-456f-af57-eeff0948b18b | 60,75,57,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
48c9f3d9-77e6-4470-a152-d84cb595d6cf | 60,75,57,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b33ce096-6cac-42da-8d5d-393f47409344 | 60,75,57,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
fe2430cd-2f10-48d6-ab4c-f6c8c87d6b65 | 60,75,57,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8c8d236e-841f-4fc2-b251-fbb5df00ce8c | 60,75,57,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
02345056-50ee-4f70-a178-13cf6554b721 | 60,75,57,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
196a4881-3ce4-4ecc-b6c2-28409e60362d | 60,75,57,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
33e0b789-0d63-4ee1-9971-051344c1f94e | 60,75,57,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
13e73081-674f-4303-99c5-543b195760c2 | 60,75,57,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ab490d24-5b87-47c4-a26d-69e0b4687b10 | 60,75,57,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f76fcff1-7839-4b25-8adf-f57771977182 | 60,75,57,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
c804be75-ec09-421c-a521-6352adc2e563 | 60,75,57,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
8af5c512-cf07-4c91-a38d-8802f1c25875 | 60,75,57,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
6e85033d-a4ab-41d7-aa68-31401923cfd9 | 60,75,57,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
17bf75e7-ec68-44a7-ab1e-a7924c282b78 | 60,75,57,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
63dc8cd4-5efc-43d4-8e10-f20d46b47f33 | 60,75,57,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8713646b-ed0a-4c2e-b822-825669e42dc2 | 60,75,57,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
725f8d7f-f7be-49f4-818f-170d0d746528 | 60,75,57,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
35f6ddd8-c348-45a4-8f10-85f466dd58ec | 60,75,57,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
453d80f3-7e0f-4ec3-8b1d-e6d580eda592 | 60,75,57,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
dff0b3b1-3778-4a3e-8751-71122bff17dc | 60,75,57,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
28f3f6ea-9d20-41eb-950e-1c632dbd8e77 | 60,75,57,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2185f905-9a18-4d75-b7b0-05e9844778aa | 60,75,57,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
bac64dc3-0a69-43d4-9c5d-dcd7b6cb25d7 | 60,75,57,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
85f305ba-d7bf-48e9-96c5-4b801998870d | 60,75,57,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
743a11d2-ec94-4cdd-bae2-01e9cccba1a0 | 60,75,57,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
2246f60f-8b94-408a-b6fb-af51801fadee | 60,75,57,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
a5f2be5f-ed9e-4ac6-afe0-b73b8c0a7b61 | 60,75,57,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
73fc6b44-08d1-4cf2-9d77-6976794970d1 | 60,75,57,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
414a690a-61fa-4266-bc0b-97f83d01ef54 | 60,75,57,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
066f0766-95dc-41e4-b3b5-205e95096a4d | 60,75,57,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3c98692f-b19c-4cee-88fd-9a6f4512a771 | 60,75,57,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
b4f7e859-51b7-44cb-aaf2-ab984dd61d83 | 60,75,57,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1a8ee4a3-e786-4d6e-af2f-22a47f14cfb1 | 60,75,57,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
062644e6-2645-4914-8573-e8f464c9ca84 | 60,75,57,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
9c6b0975-257d-4fe3-80a7-07dcbd0fca4b | 60,75,57,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e97ba879-35bd-4f39-8245-3678a4f04f26 | 60,75,57,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
4ed10225-1f62-45a6-891b-5e58015ced1d | 60,75,57,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
65af7614-d604-48d7-925a-46502444b51c | 60,75,57,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
837bee23-dac6-4205-a2b7-37d0ee849f61 | 60,75,57,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
9218d470-56d9-4190-b794-8bfc5317d482 | 60,75,57,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
34ee2312-463f-488a-8792-4e25ce3bab3f | 60,75,57,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
45d35ec4-4439-4b93-be2d-027365425c0e | 60,75,57,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
176c8562-3c71-4db6-9476-e7c92777faed | 60,75,57,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
c366b374-e816-46b4-94f7-43a57dbeafe3 | 60,75,57,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
75c74692-862a-491f-80b9-93166a570c97 | 60,75,57,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
30f87cba-c57b-4c16-b485-2c07ede2cb11 | 60,75,57,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
98077d7c-4c0e-4d48-9abc-85f672959054 | 60,75,57,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
2f76f623-946b-484b-a97e-d35915733d80 | 60,75,57,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f1d9cf4b-1949-4b48-a869-6b7ef6382bf1 | 60,75,57,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
97081700-b565-4251-b428-f09b3d83e8fd | 60,75,57,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4008e159-f6cf-4618-b247-db95730ab1b8 | 60,75,57,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0d63d24d-3c5c-425c-b6c3-2e264ab800e1 | 60,75,57,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
fa79692b-34a4-431b-8373-22c8f7af5b6d | 60,75,57,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
cc93c2ca-d87f-42e6-a92b-72b991113f79 | 60,75,57,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2cd9e8d3-0ce3-4fae-b918-37574068e725 | 60,75,57,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ccf90c29-7efb-4b54-b3b0-6dcd8e610093 | 60,75,57,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
99e94153-0de8-405c-8154-112c3a0d3fc0 | 60,75,57,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
8bfa48f8-026f-44fb-8cc5-a43e4a32bba7 | 60,75,57,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ae946beb-b64b-4913-a74e-5b7ad453bf8e | 60,75,57,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
21f4909c-26c5-44fe-81cf-3cb3187c0fc2 | 60,75,57,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
4c26ce84-0e7e-4805-a3f1-a7b5dd7ee1a3 | 60,75,57,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
489a6443-9ecf-4619-a1cb-ecdbea4ebefa | 60,75,57,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2a57c079-b8d3-43af-9c24-a1ef31f3edab | 60,75,57,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT BRAKE DISC (2) -> ASSY - FRONT UPRIGHT - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2bc47180-8647-42e5-9e5b-2769c906f5c4 | 60,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
66501b54-2dd9-4bf2-8050-14053648d351 | 60,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
cd1e4c13-71fe-442f-b773-bb9429f21e20 | 60,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
8a75be3e-9d61-486e-9617-6a3a083fe600 | 60,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
b17e03db-89f3-4322-9c84-bd469013b25d | 60,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
53f0724d-44a2-4e7f-8963-32102623f4b3 | 60,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
fb457413-c8e1-4a0c-b009-bd7aa8ef52f4 | 60,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
19eae2ae-6bc8-43a8-8b46-6c95d81affe4 | 60,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6114bf92-fd43-4fa7-8553-63316181fa4b | 60,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
76e390e4-6f6d-475f-98f9-02b2a806605d | 60,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
683720d8-2f5b-4666-8c7b-0eea914ec49b | 60,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
2d176f33-840b-4300-b251-e13f98220725 | 60,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
64a1203a-9760-4f4d-9373-0c7110d03f5b | 60,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
b6528431-70c0-4f8e-ad6a-e76fffe8711a | 60,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
aea84417-21eb-4cd2-ae4c-1c618e328f52 | 60,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
32893797-85b1-49ae-863e-800031d693e3 | 60,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
ce3aa3f6-8768-463c-81f0-0b7456897c87 | 60,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
f11b68b5-dc90-49c9-8b31-af815a02431e | 60,54,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
1d54da2a-1f3e-4895-9a7a-c61a4fbe832c | 60,54,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9632767e-0005-41a5-a146-d6081fbb62f7 | 60,54,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
17bfaafc-c0b3-4803-832e-7d702a8cb879 | 60,54,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
dd5bce1c-2f92-4f6e-9eeb-8603aa97228f | 60,54,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
3ff28ec2-240c-4463-bea9-c594046e97ca | 60,54,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
ad267753-e8da-4b45-b14b-1f835d28a598 | 60,54,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c896ccda-cb74-4f7b-a9d9-ac3493ae9f52 | 60,54,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
091f3bfc-2b95-4f05-bff0-b2a1d82683d8 | 60,54,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
84701769-9a08-4180-aeb7-9e64a81008f0 | 60,54,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
d1e96030-022d-4906-8e88-3510a4e5bb31 | 60,54,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
fd71b73a-e3a5-4fdd-b5be-d19ad176d17e | 60,54,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
d049df91-1a08-4ee2-9c2d-a6f39c4c0a56 | 60,54,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
a582b8ba-30fc-429e-9ca5-63c748967821 | 60,54,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
ed5ba419-5178-4d44-b138-bdd7c87633a4 | 60,54,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
964ec7a2-866a-412f-90d8-29eca378f65b | 60,54,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d2dc1397-0676-4224-b57f-6a1fa10be834 | 60,54,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
379d3de3-e840-424c-80bc-8d2fc96a1117 | 60,54,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
49b9e77d-10e2-432d-a915-c7d1005e24c9 | 60,54,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b06bf683-0ebd-4bdc-836d-94d6790df261 | 60,54,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5511bada-5c1c-4bf0-b87b-66bd6cecc5b8 | 60,54,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4a3aaa4c-2bc5-46e2-8330-55cca8724f20 | 60,54,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
f8f5e238-5adf-4884-9199-122b1ef48c75 | 60,54,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8c4c8187-c457-4cd7-af0a-7e0d1b2b2842 | 60,54,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
0d398b68-455e-4c9c-b57d-791896d09f19 | 60,54,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
47ddfe43-a316-4323-8639-f4345f840dcb | 60,54,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
dfbdc086-a3de-47a7-8e5d-053978b52afe | 60,54,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4347da63-f147-4160-8c44-c106270fd6a9 | 60,54,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
67816b52-a098-40f4-bf7e-0a6d086448f5 | 60,54,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
eda38c9f-923e-4efe-ab5d-083076a6a170 | 60,54,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c45f7835-d4ab-4d97-b2ad-de7be3e6e31c | 60,54,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ddfd296e-b3fe-4629-a126-6b77cf4cbe84 | 60,54,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
6231ccf8-4f37-4885-b574-0510a5e0dea8 | 60,54,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
68c56af4-228c-4722-8a75-6bc0388ef18b | 60,54,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
0047fd8b-dcaa-46db-9c8f-7705508d15bd | 60,54,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
8f34b29e-420f-4442-b86c-e45293b8156b | 60,54,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
6511ef9a-7806-4f89-b716-d8556c24f913 | 60,54,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
070cd0a2-3800-46b2-ba00-1ef4916c989d | 60,54,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
058e6440-f8e2-4505-bb23-a44859aeae7b | 60,54,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
e7749b40-a783-4b34-bbc5-1ae10b56e293 | 60,54,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
26bd381e-1228-4530-8cdc-f58ea3f7f34a | 60,54,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2cc91943-ce81-4017-97be-6bf2112fa192 | 60,54,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
60f37d92-39be-4fbe-aa0c-85ff9a3583a8 | 60,54,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b24d42d2-4f47-4c09-a437-549f5ae45b38 | 60,54,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3befac33-6a0f-4250-b882-227babcb5b93 | 60,54,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
6c913b29-0d7e-4075-985c-eef4938f6414 | 60,54,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
03ac8d9d-36a8-4622-9012-551b9ad9ad86 | 60,54,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
edc91e57-dcdd-402c-be7c-5e2009180561 | 60,54,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a430313e-e56b-414e-8982-5b0c10330274 | 60,54,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
71044e82-c6fc-4314-9827-d0f548d6e221 | 60,54,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
0b12872b-3a07-4bda-9a48-13970c8e59ae | 60,54,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ef43de16-66ce-4309-af05-e5e496369713 | 60,54,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
5adefa97-41c1-4a37-8734-2fd38d0b3355 | 60,54,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
e1662924-32c7-463e-b206-92db4147f905 | 60,54,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5330c44d-b89c-46d2-8d0c-ccac31f8fda3 | 60,54,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fdf33166-06f1-4da8-a8e6-0e51cec88626 | 60,54,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
fc955172-d1b9-4491-a6da-57b582f1dc88 | 60,54,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
3db2aa85-1cac-42b8-9eaf-e359b29f82aa | 60,54,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6329c68c-006e-4282-855f-32454c6f53ca | 60,54,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
125687a2-4ee7-4a3a-80e8-044ab5595d05 | 60,54,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
21c4698d-ec9f-4f75-ba59-a3015a0f2aee | 60,54,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
547f1f1a-423f-43ec-82f5-3840a7e8a93c | 60,54,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a029b0f0-3b29-470e-b217-941a3e5da21e | 60,54,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3c0ddba8-2fa5-4cba-b29e-356d08cc09e8 | 60,54,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
ecd4e100-9361-4381-91e4-c2de25c9103d | 60,54,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
559353e1-a934-4fe1-af27-2f0075ea5682 | 60,54,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
fc0779c2-a30d-4f6e-8836-22ffa3da57a4 | 60,54,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
489c7991-a81b-4baf-9a45-cba1143f49a1 | 60,54,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
891ff82b-89d4-4f21-8226-3c5f3daef814 | 60,54,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
7ba7e5fc-fcdb-4112-ba0c-0e8ef5e73864 | 60,54,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
d5b5c34f-c24e-4155-a354-2b654d1c9ae2 | 60,54,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b039da9f-4fdf-4cb9-937d-f43c1ce151e5 | 60,54,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8caa64df-09f5-4f11-a1b9-170a640871a7 | 60,54,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c49ddfdd-e664-4748-b303-e72b9a9314ef | 60,54,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
24ed08eb-e9db-4797-bd2e-fd0ac41524ea | 60,54,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3509e699-47fe-4595-bda4-0855dd686182 | 60,54,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
3d6f47f5-569f-4174-9749-5370446aed3e | 60,54,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e0c704d9-b29d-440e-a765-ebb55e68bd75 | 60,54,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2b29a3ee-5a0f-4745-ab4a-0996e3ea17d3 | 60,54,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ce03b87d-9469-4576-aa67-5d5064b12a10 | 60,54,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
971d0c0f-2c90-4522-ad32-4099e3c5549f | 60,54,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
066aef2f-f16d-465b-acdb-da6b0a20da89 | 60,54,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
5304fc83-b728-4988-ace9-ea99593efccf | 60,54,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
d0d1c4a9-0e61-4129-8e5f-c4eb30ff16ed | 60,54,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e5313117-e8b5-4d8c-b4f1-42fe47642c3c | 60,54,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
bf2f0420-570f-4317-a8be-15d6594f4bc4 | 60,54,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
bf967a12-429f-4c02-ac9f-950d48f2428a | 60,54,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
16bd0374-fb6b-4c8d-b501-aa8ba3484320 | 60,54,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5e52d364-44e4-42c1-9604-33de8719f9fb | 60,54,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
604a994d-106f-42f5-9f88-2dd08a994d13 | 60,54,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6a07e9ab-7b2d-40f8-9298-e9a5e77677d6 | 60,54,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e398842c-da22-4293-b8df-306696e02c9d | 60,54,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
54f47e96-043c-4e1e-94be-7aa38dec0f28 | 60,54,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
d2b7412a-39ba-461b-bdb9-5e972debc675 | 60,54,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1d3cddc6-abb5-4c4b-a016-f218543ca276 | 60,54,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
33a7e511-f55f-483c-8d2d-2d373de4f4f1 | 60,54,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
8c6668c4-03dc-42a6-be72-e7b0e9d2e2c8 | 60,54,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a25e73d9-902c-4075-abc4-9ce41c53f6aa | 60,54,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
32ac3ce8-fc1b-4997-b5f5-9985f8be3e03 | 60,54,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1c3a839e-b84b-41db-b405-a90c6f7f780b | 60,54,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
8483ae33-ed30-4be4-b7ee-bb1a82845013 | 60,54,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
28f4844f-c56f-4b36-bf89-f2a986e4e0d9 | 60,54,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
44147e5c-19a3-4801-b9ab-0f049abeb49e | 60,54,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
5bb2f506-22b0-4831-aa96-2850d4bb8b6b | 60,54,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f7e8d45b-d408-4bd8-afb1-70642f4f0e86 | 60,54,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b7d25129-e875-4fe9-83c4-425c85551672 | 60,54,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
4701a8ad-eddb-4e5a-ab28-ba0dad86b57c | 60,54,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
61347fba-fdab-4ffb-a936-9ad42b3bdd8d | 60,54,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8bc10c54-1210-417c-a2a5-47301941b8ea | 60,54,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
5163c050-9691-45fc-89fc-28cc888716e7 | 60,54,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
ff5b685d-db70-4f04-9c44-c53cd30d8080 | 60,54,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0d49a382-f011-4b23-ab26-b03e434de2fa | 60,54,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b726d3f1-5b13-47e0-8b39-ccfa8d7fc654 | 60,54,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
6f192011-a403-499d-9194-7dea1823d841 | 60,54,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c7950b68-3fde-423a-9a00-deb110c1d78b | 60,54,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
cbb7cdf7-469a-434d-900e-5b3d71b51e87 | 60,54,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d87fc901-340e-45bf-b8ee-9f8c659bedb5 | 60,54,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
5fab60a6-416b-4210-9688-ba0b7bafb405 | 60,54,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e94d819d-ac67-42ef-8e06-989ddf28342b | 60,54,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ae0b09ab-3f03-42c1-8dab-142b17377b8c | 60,54,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - LH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
90c4afac-4c5a-4951-89f5-1f221e6476cd | 60,55,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
35965434-28a9-4889-ab20-f79dc983fa77 | 60,55,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
345a5697-158e-4cd7-866f-e719fe5ee750 | 60,55,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3379bb10-a454-4d35-a02b-aa08c6b97de6 | 60,55,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
eeb0d793-67a8-4f1c-a02d-280cff98f713 | 60,55,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
cac0ae20-d55e-4955-b2f2-08f817031f82 | 60,55,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2282006c-daf6-4c49-b304-34019e9e7430 | 60,55,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
3ca31cae-4e5d-4a78-91da-5b735105c692 | 60,55,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f70f8ba1-fcb1-4028-a435-8d58e1863d33 | 60,55,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
d63bcb31-650b-4f50-86e9-57b8afd2641d | 60,55,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
17656df7-db4b-4549-928b-e89ab8f5fdda | 60,55,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
10513c83-6747-46db-92f7-66d874369c88 | 60,55,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
38c18881-6fe4-4e50-9a61-1995f8293890 | 60,55,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e40530ad-c8a0-4715-90e0-f5668af589d3 | 60,55,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
e863ee57-b0d3-4e15-9402-210c0ba3b9e2 | 60,55,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
154c2877-cee1-4f2a-8245-4bda4d4d4dc0 | 60,55,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
172bb2ee-d834-46f6-8ccc-5a239173275e | 60,55,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
f4900281-f691-4529-aa6f-310cacf52144 | 60,55,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
c5bbf02b-15d1-499c-a64e-2b534c03f4f9 | 60,55,74,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
5c74fc31-5933-4f08-9464-fc4f0d5d7c8e | 60,55,74,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
5b6c829a-efab-4b3d-9e5b-def5d2473268 | 60,55,74,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
64b480bf-8798-4485-8ba9-320c1e2cc00c | 60,55,74,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
b14193a1-6761-4140-8b1c-e85f60125e79 | 60,55,74,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4632927a-89ff-4ba7-bcc3-e6f4ef79a117 | 60,55,74,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c41defc3-ea23-446d-932c-0061088bdcd1 | 60,55,74,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
249ec1a8-cb48-41fc-801c-9f79600ff2ca | 60,55,74,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f7c608e4-2c2b-4bf9-80e2-87f7bedc140b | 60,55,74,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
eba05f44-e756-4f0e-b01d-119b5ab49dcd | 60,55,74,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
b93f4c5f-80db-4f5a-ab30-2108f61f82f1 | 60,55,74,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
025fc7cd-0889-4776-ab05-aed2c6f8465f | 60,55,74,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
e2b841bb-742a-48a2-af82-50098b03783c | 60,55,74,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
70680b15-b84f-45a3-865d-5d1de3f06626 | 60,55,74,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
c7c84c09-6c0a-4a52-98db-83f23421736e | 60,55,74,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
10978c92-df90-4e95-88ef-c490dec54e37 | 60,55,74,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ec3d6a9a-873c-407f-a067-b75d9d619dc1 | 60,55,74,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
90a3ab99-50fb-46c8-be44-18e29761b17c | 60,55,76,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
ec783b9e-cba9-40bf-a355-d01fca2a8206 | 60,55,76,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b604ff59-9104-4f8d-9892-9cfd701dd0c9 | 60,55,76,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
08276eef-92db-4262-8029-59aa546cd346 | 60,55,76,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
61f06d80-1345-499e-9885-7525031e8abf | 60,55,76,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
bd5bc9f1-2924-4883-85c2-aa18a2bb295a | 60,55,76,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
f39ab865-162e-49c0-85a6-8ad06bae3c71 | 60,55,76,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
598fdad2-0086-4a5b-b9ec-b3aced7bd8ec | 60,55,76,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f426e0a6-fe37-4522-ac3a-a408e46956cd | 60,55,76,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
eac8f9db-0b8f-4954-b12a-99e74df76dc5 | 60,55,76,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
ab00a8fa-9aea-40a3-b708-fa87715832fc | 60,55,76,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
033bbe72-4bc8-4868-8c89-18cfe4547ad6 | 60,55,76,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
7cdb60ba-b4fd-472f-9696-e49bfa78ab95 | 60,55,76,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0eabae66-7cc2-443e-a624-2b5527d8728d | 60,55,76,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
88aec0be-b537-4f1c-8806-ef8446ee6251 | 60,55,76,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
c21b6a5b-6f1b-4e60-a96f-9a10387b4901 | 60,55,76,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
2d64a561-14a5-4eca-8594-fa88e32394b6 | 60,55,76,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d27989e9-0eaa-4d60-af1a-0d12d8822491 | 60,55,77,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
ce1cb212-b793-49d0-9458-c503a38ca070 | 60,55,77,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
939ee9ee-c40f-48fc-8544-1741d3987583 | 60,55,77,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1c264cce-8111-48dd-b85e-a5800e767377 | 60,55,77,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4032e423-d07b-4912-8ab6-dadd32658e28 | 60,55,77,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
7ee21e8a-efad-4619-905c-eb9839a11b86 | 60,55,77,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6ed0af03-1ed2-4efa-9916-57cf37f6c223 | 60,55,77,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
61f94dc6-ef47-42af-bc66-dffd1daf490f | 60,55,77,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
299a1147-299b-49d2-85e8-55e861c0677a | 60,55,77,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
94593374-f89c-4d07-8aa3-9a37300d0b5f | 60,55,77,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
aa61189f-4996-43d5-8b75-57c4b2efeffe | 60,55,77,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0d003cda-48f6-46fc-aae5-667f17eaf862 | 60,55,77,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
f7687fc4-a044-4cc1-82a2-b489d5bef644 | 60,55,77,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e827abd8-40b6-46ba-840a-969b764b9166 | 60,55,77,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
86a3d7aa-5f2b-4791-86e5-a7901bc8f845 | 60,55,77,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
fc4241ea-afc3-4341-bf75-a7117d126659 | 60,55,77,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
480a11b2-ed12-4d3f-ad47-a76887aa7fe1 | 60,55,77,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
d46aaaa2-c072-4e29-bb63-ca03f1e1765b | 60,55,80,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
b9117d06-78ba-444c-baa0-e48650a0313b | 60,55,80,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
afe9a6d0-c715-4c74-9a79-a5c38647c6c7 | 60,55,80,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
38eaf529-a43a-4f0d-b026-0501ecfa4d2a | 60,55,80,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4bb9ff50-2eb0-49e7-b06f-dc10b22bf4f9 | 60,55,80,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
651c3553-9516-41f1-8156-52a5daf29913 | 60,55,80,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1668972c-f33f-430b-86d8-380bd6b29d21 | 60,55,80,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
fb86f714-f974-42e2-afd2-1d6b344d1550 | 60,55,80,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
cbb05e27-6838-4606-80e7-86e7c4161099 | 60,55,80,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
74268121-da78-47da-bb64-7404592b478d | 60,55,80,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
181e2f80-eea6-4268-a974-8753b09836e6 | 60,55,80,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
9667004f-8866-4177-b469-a8cfe28bb4b3 | 60,55,80,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
73d41719-af3e-4673-88e3-ce71f84c64a7 | 60,55,80,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fa62bfcd-7f7c-42bb-9f7d-b36e359c3a9c | 60,55,80,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
8eba951a-c4df-4241-b6a7-65c6d8e81737 | 60,55,80,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
5b294cae-8599-4f74-93c8-23d43b1ea92f | 60,55,80,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9b7807d7-7890-4d43-8b80-f0a5bcf59b09 | 60,55,80,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
cc99fcd2-e30b-4fab-b4ab-4a3b289f250a | 60,55,81,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
1ca3125b-68b8-492b-8d14-95a530a673e8 | 60,55,81,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4617ab61-a0f7-4e6b-897d-ca2e923dc6c6 | 60,55,81,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
b352d5aa-563a-45af-b515-fa4212c4fdf8 | 60,55,81,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
97e67583-05e0-4826-a32e-4e5a13a363ae | 60,55,81,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
8f628869-227f-4f20-ba6e-92f548ec2b1d | 60,55,81,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
556aa4fb-c42c-42dc-b78c-4c50fd4b9201 | 60,55,81,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
50aea2ac-1a21-4092-8fe5-7ccd5f78236c | 60,55,81,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
86730476-f8fc-4fd6-b926-c9d0671e2d2e | 60,55,81,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5e9008df-f298-4df3-ae21-d20cb6dd9ad1 | 60,55,81,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
86b38efd-3771-46ae-ae1d-28997935af82 | 60,55,81,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c54ecf74-091c-4ab2-9882-915b18b0cff5 | 60,55,81,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3f41dd57-9b83-4e1e-bed8-6d1860f6080a | 60,55,81,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
414425b2-7363-4d51-954f-b52b709721cc | 60,55,81,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
ebd33b02-64f4-4c6f-be0f-605389c6b2e9 | 60,55,81,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
36886ef9-3086-4b9c-9584-e683a627dcd3 | 60,55,81,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
77a3a868-f569-4a4c-b46d-8ecd7da7e8a3 | 60,55,81,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
18aab0c2-e42f-4133-9c86-f9739b29ed5f | 60,55,83,2,16,21,22 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
78b25188-a0d0-4c66-b987-abf1e803d8fa | 60,55,83,2,16,21,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c6083e1e-0aa2-498a-946b-078284ef172b | 60,55,83,2,16,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fabfd1e8-410b-4ba1-a231-01afa744906a | 60,55,83,2,17,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c4e1e50d-a110-4dba-91d9-da4fce756d4c | 60,55,83,2,17,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
6420f034-f628-47b9-a056-395594b10c2f | 60,55,83,2,17,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ff9b78f8-e4e4-4b96-b0df-9ebd29dbe28d | 60,55,83,2,18,19,20 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
7d85fec5-1ebb-46dc-94c5-369e8bfd13ba | 60,55,83,2,18,19,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
685b1333-de90-4e02-b550-19a483a636ee | 60,55,83,2,18,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a8a60337-3ad0-409b-8b5e-ddff04119084 | 60,55,83,2,35,25 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
a05c69f4-faf2-466f-a8a5-df1532373afc | 60,55,83,2,35,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
dd427660-db6c-4b2b-a2d0-5e4f62dacde4 | 60,55,83,2,36,26 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
215ebb97-d492-49a8-b92c-389ea477bb0e | 60,55,83,2,36,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6e610761-b255-4898-807b-e6b91982703c | 60,55,83,2,65 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
f34ffd83-138f-4fcb-936b-c8d83b8b65e8 | 60,55,83,2,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
1c890a91-94bc-4e51-be52-a3dc166d208c | 60,55,83,2,101 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
23bf8739-8fb4-4d9e-9eae-4dfb28aff512 | 60,55,83,2,188 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT TIEROD - RH (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
3a288f39-02e9-475c-8a17-1d8dedf53838 | 60,73 | ASSY - FRONT WHEEL (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 4 | FALSE
cc73fce9-55fe-44b6-b664-3720bec3dd98 | 88,87,85,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
ce54c072-d653-49b6-9ed0-fd72ac361f25 | 88,87,85,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
ef07d5c0-1496-4e28-b4f9-71b938d85161 | 88,87,85,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f39083c9-cd4e-4365-b736-557915c29268 | 88,87,85,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
f501f577-5ba1-48e1-9b56-4ee65e39337d | 88,87,85,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
2b780f89-d124-4761-9b5d-b71b3045a6a6 | 88,87,85,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
122ad751-6e6f-4b96-bcc2-aa1df06abbc9 | 88,87,85,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
8ee99a96-f57f-45b5-bec7-71720078c9f1 | 88,87,85,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
a4329585-7161-48d5-92c6-5ae499c4c04b | 88,87,85,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c5964814-c4b1-4d47-9843-11a52106cbe5 | 88,87,85,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
03801b58-eafd-4aa3-954e-3ea6c33a6cc0 | 88,87,85,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
4b3da39e-6f6a-4e89-bb79-0cd61a679eee | 88,87,85,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
5ad4dd41-9967-4e05-bf96-577b4ff06bd0 | 88,87,85,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
1b87a1ea-5fb0-45af-9ddc-c7baf06a3cc0 | 88,87,85,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
caec2f67-8619-4aa9-b8bb-2cb56c9e1a4c | 88,87,85,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
a10f559b-28fe-415d-b4ff-4d1ad55e4d57 | 88,87,85,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
f3f52373-130a-4979-860b-e521d6816c4f | 88,87,85,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
81933f6f-0dfc-41ff-b822-87629c7ec91a | 88,87,85,3,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 34 | FALSE
2d76ea2a-875e-4e55-a1ac-3ec7c327e60c | 88,87,85,3,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
61c87d41-8887-474e-80a5-7434b6e3de4e | 88,87,85,3,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
1ab137dc-3496-4728-84a7-9e278f1a3c55 | 88,87,85,3,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
9957859e-3035-492b-b274-5cd5ceb12d4b | 88,87,85,3,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
acfecc12-22c8-4f71-81b4-6d2b8eba762a | 88,87,85,3,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
279ad542-cd25-40bb-ab1a-8326672bbaf7 | 88,87,85,3,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
372c9d31-9a52-4669-a81e-56da77bb9a30 | 88,87,85,3,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
4642994e-11bf-49e5-92ac-401b2450e58c | 88,87,85,3,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8d80328b-ea5b-4c77-899b-774ceb3c12d0 | 88,87,85,3,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 24 | FALSE
d3459dd5-f853-4a9f-bf59-901eae417475 | 88,87,85,3,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
c842f97f-c64d-44e6-9fc5-5fa2987af2d4 | 88,87,85,3,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 24 | FALSE
9a706ced-761c-4b5f-a726-98ab958c08db | 88,87,85,3,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 28 | FALSE
c2fd0b04-cab7-4855-9af2-f612af2953dd | 88,87,85,3,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 21 | FALSE
ce0a9ccc-cab4-43d0-ae6b-ed5b9a0c029c | 88,87,85,3,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 21 | FALSE
69ed59a8-d56c-4f8d-a0b6-024c2858e3ff | 88,87,85,3,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
f5091a60-101f-4fa2-8be8-3c68dc905cc6 | 88,87,85,3,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7e94753e-84bc-4758-b3a3-b6d298e742d0 | 88,87,85,3,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - STEERING COLUMN MOUNT (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
10b13c7d-72cc-4a54-baf2-7e2447494ea2 | 88,87,85,4,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 36 | FALSE
69aec05b-9476-408b-b857-ae75de3b2eed | 88,87,85,4,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
4c8f7a05-ab1a-4976-a552-3ba1f0b3fbdc | 88,87,85,4,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
5a03fb6b-e6ed-41e1-bef9-7fe6c5aab987 | 88,87,85,4,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
973ee6ae-dbb1-4027-8035-37958f7393a8 | 88,87,85,4,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 33 | FALSE
3a6880fa-9621-42ad-9edc-1eaaf5965e04 | 88,87,85,4,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 31 | FALSE
6652ee77-aa67-4659-a8a8-cd239bc869ae | 88,87,85,4,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
4423db88-9866-43ed-9b36-da262534e694 | 88,87,85,4,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
c55e59e0-1ccd-456c-b53e-c18f037763b1 | 88,87,85,4,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
678634ca-2efd-4856-8b87-d538de447954 | 88,87,85,4,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
5cb9f499-900a-492c-a156-a51e03c8d835 | 88,87,85,4,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
fd875188-bb28-4199-8d93-35a2bbd8f71a | 88,87,85,4,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
f0a9b49e-15ad-42a8-b24f-2354f0851bc0 | 88,87,85,4,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
f3a7e6ac-dba2-4771-af45-ac00e785c887 | 88,87,85,4,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 23 | FALSE
541e3d81-9f4b-4229-bfed-39e5c4ea811a | 88,87,85,4,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 23 | FALSE
9ee90a3c-a0d3-416f-9cc1-c17fe96d45b5 | 88,87,85,4,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 27 | FALSE
04c04f5c-f713-420d-9cbf-21acbb65b732 | 88,87,85,4,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
404452a3-53ea-46e0-a7df-6ba5a2dfa561 | 88,87,85,4,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
47e7fee2-dd36-4761-9c12-560fea87373f | 88,87,85,4,74,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
f9e8dfb6-f441-41f9-a7da-89349244739e | 88,87,85,4,74,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
7cb8d9fb-82d4-4e1b-849a-173cd1299ede | 88,87,85,4,74,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
d30b7490-877c-4beb-a1af-079b05e331d6 | 88,87,85,4,74,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
7e55e3cf-ac05-449e-b738-5711c74dd956 | 88,87,85,4,74,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
dce3b30e-12b9-4400-8fa6-4ae63818437d | 88,87,85,4,74,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
ddb7effd-1fd0-49c7-8026-336b50bc760f | 88,87,85,4,74,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
ad6ff759-4162-4f67-a411-3993bd15ab00 | 88,87,85,4,74,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
86cbdd81-b1ec-4606-9183-b6c95f57d684 | 88,87,85,4,74,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
8a744fb3-6d1a-49b3-b704-9996ac7c0c98 | 88,87,85,4,74,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
7d1ee74a-7a1d-43af-8d24-e5bfc60aeb7c | 88,87,85,4,74,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
71a167b7-79c6-4cc3-b185-4527041321ab | 88,87,85,4,74,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
124140df-a4ce-49a0-b375-7f211a290db7 | 88,87,85,4,74,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
b1d7baf1-8832-45d0-8f09-104b24845553 | 88,87,85,4,74,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
f0cd16e9-017e-4d61-ae2e-a4f773ccfc6a | 88,87,85,4,74,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
8ff6b54f-5016-44b4-a545-ed630a603311 | 88,87,85,4,74,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
0d17f34e-54ca-4d68-9800-75bf9efe0826 | 88,87,85,4,74,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ca72b925-4d45-4e60-8702-f2de8c0c9a98 | 88,87,85,4,76,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
343be9d2-54c9-4fc1-bc02-09b5552f9945 | 88,87,85,4,76,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
acbe21c7-9e95-48e6-8a94-811a4203bcfd | 88,87,85,4,76,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
c34d1367-be8c-494b-ab19-f3f1eb074ec9 | 88,87,85,4,76,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
46a0f6a6-ab98-418a-8a4b-ba79f9079f2d | 88,87,85,4,76,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
b4cb1c67-9e80-435a-9d6a-43f79773650a | 88,87,85,4,76,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
325cbdc1-8491-4895-b8a0-158adbd7e31a | 88,87,85,4,76,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
f6701d12-4779-4689-a1de-5dc562d739df | 88,87,85,4,76,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
ef729313-a4fb-4c35-82b7-898e017aadd2 | 88,87,85,4,76,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
3d2e3136-eb99-4595-a525-47369e67c9d2 | 88,87,85,4,76,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
4c0397ee-3733-4b2e-b5f5-c1a7738ea8dc | 88,87,85,4,76,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
ca437d62-cf54-4e92-930f-3dd411705bb4 | 88,87,85,4,76,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
ee0153ff-79ed-45db-9d8b-432203e6267d | 88,87,85,4,76,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
074489a6-cad5-4c94-8689-72c42f011204 | 88,87,85,4,76,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
2876b8e5-890a-4e5b-8add-4e77e664c76c | 88,87,85,4,76,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
66e97424-6012-4b0b-a7e9-3f0544b2eed0 | 88,87,85,4,76,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
342ee679-1ca9-4645-84b8-06bab8554560 | 88,87,85,4,76,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4bee6899-2575-4e0c-bd1d-c37d073acfaa | 88,87,85,4,77,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
527e39ed-3a4b-4017-94e7-dfcb345db1c4 | 88,87,85,4,77,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
c30d276f-9b24-4857-b442-546c25e86f87 | 88,87,85,4,77,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
b003f893-1a88-4dc0-9fa0-08a61c71e902 | 88,87,85,4,77,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
4089c6c5-9fb6-4abc-a879-4df6e3197180 | 88,87,85,4,77,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
40b8c19c-1465-4f9b-8082-654dd3b3b91e | 88,87,85,4,77,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
b3987249-3e41-4eae-a135-8795102ac0e3 | 88,87,85,4,77,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
80f544a0-fd29-4a42-99dd-b961e4579fef | 88,87,85,4,77,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
1ee9d7aa-1184-4789-b84c-eda602f7bb39 | 88,87,85,4,77,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
82e493dd-38fc-469f-8c9a-4cc4dc684d19 | 88,87,85,4,77,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
deac60d8-ac86-4b3f-9bba-d13d3c2b6373 | 88,87,85,4,77,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
d4a48fbd-8818-475c-9a0a-c3ed8ad91ac1 | 88,87,85,4,77,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
2213aea2-e3b2-4edf-9f16-d5a4fafea2b3 | 88,87,85,4,77,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
e5239287-38a9-4a4d-90cc-798e5ad7dac7 | 88,87,85,4,77,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
31735f8f-fde6-438e-8a4d-6e5793b8676e | 88,87,85,4,77,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
bb53d108-5b89-4617-908c-fb46f8bf425f | 88,87,85,4,77,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
b7c333a6-bf10-4a38-8f0e-eb9dd340ec19 | 88,87,85,4,77,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
bee7ff4a-cf8a-4699-8f36-e73e2f66a0df | 88,87,85,4,80,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
568663d4-8a17-46b9-a868-3a1f8c54004a | 88,87,85,4,80,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
a14a42cb-125e-4ce2-9bd8-8433870ca326 | 88,87,85,4,80,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
63696feb-9c14-4ed3-a742-9a8a2026a85f | 88,87,85,4,80,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
14a69d2e-b0ce-4838-9a42-dc716dcaeaf8 | 88,87,85,4,80,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
46440e2e-513d-475e-a7d8-43ea4234531d | 88,87,85,4,80,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
904c9b83-aab0-408b-80e0-a1bd76e52b82 | 88,87,85,4,80,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
030e0856-1b9f-4005-918b-baac68c75dca | 88,87,85,4,80,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
975d5a27-20d0-4fb1-bfe5-3043a78444ef | 88,87,85,4,80,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
f90cb35f-1391-4a4d-b17b-d622f40721c9 | 88,87,85,4,80,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
4962268d-aaa6-4b20-8d88-f49e382072fd | 88,87,85,4,80,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
7d61c49b-515d-4144-8436-e9b75acbad36 | 88,87,85,4,80,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
1514900d-f7a2-40aa-9840-2c1a1f66be74 | 88,87,85,4,80,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
e6ba92ac-e47f-4df7-af46-ee168f87da75 | 88,87,85,4,80,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
1bf74d9c-f455-4ef2-a6b5-ab3c4a1e0fe9 | 88,87,85,4,80,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
48d0b0d7-257b-40cb-b0a1-b7646a35eeac | 88,87,85,4,80,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
6e12dcaf-9d27-4932-8623-f13b206e0c57 | 88,87,85,4,80,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3c0887e3-04c4-4587-b9a7-98efe77e8a74 | 88,87,85,4,81,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
f959f5f7-956a-4cfb-8c37-c05449c2ef5a | 88,87,85,4,81,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
2da120f7-e4b0-4645-be0b-3abfc427ea73 | 88,87,85,4,81,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
8bbc11ed-b343-45f2-99aa-d9ef05b30648 | 88,87,85,4,81,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
4bfb4896-d07c-4317-85af-404fb3b25487 | 88,87,85,4,81,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
affd7cfa-0493-4b43-b7cc-d82263eb4a1e | 88,87,85,4,81,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
41493704-fc7a-45e3-93a5-13b26de20d7c | 88,87,85,4,81,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
10583e49-1170-4e82-9a33-0fa856f5e459 | 88,87,85,4,81,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
88a2f144-1af0-4e45-849b-c7c8f049da6e | 88,87,85,4,81,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
52100c20-7dcf-471f-9df3-f975279661c3 | 88,87,85,4,81,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
3db9c58e-9304-4591-80f0-e1cc1b1ffd95 | 88,87,85,4,81,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
5ee95cd8-083a-4c73-83c5-82c3463f26a8 | 88,87,85,4,81,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
60edb7be-a351-4671-b9d2-ae7d8880056d | 88,87,85,4,81,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
c66046bb-3845-4455-a678-bd05106ff31c | 88,87,85,4,81,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
c4f3abcd-6b9c-4d4d-9377-c0646e73f41c | 88,87,85,4,81,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
6376ae13-3d57-47cf-94bc-0cd6fc19dc72 | 88,87,85,4,81,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
ae241e58-1e58-4d3e-92b3-70122cdc42f3 | 88,87,85,4,81,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
47145917-f497-4309-977f-7952e4989e81 | 88,87,85,4,83,2,16,21,22 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 38 | FALSE
7b8483ce-3366-41f7-b217-d4c7bf2eec53 | 88,87,85,4,83,2,16,21,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 36 | FALSE
8b788bd9-e37c-40d7-8e6f-0291cdfe550d | 88,87,85,4,83,2,16,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
aea0c2c7-716a-43d9-9f36-d36e10e3f8f9 | 88,87,85,4,83,2,17,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
9a6c89f9-8a13-48c9-9af5-81df4a8a1a0a | 88,87,85,4,83,2,17,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 35 | FALSE
5496cfde-93dc-4bec-87e1-81e8a7371934 | 88,87,85,4,83,2,17,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
2aeb2b06-298d-464e-9aef-c96fc899cb39 | 88,87,85,4,83,2,18,19,20 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 37 | FALSE
8e666424-a46d-4765-80ac-52a8391f25ae | 88,87,85,4,83,2,18,19,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 35 | FALSE
cf44e17d-02cd-45c1-8259-feec54f0f283 | 88,87,85,4,83,2,18,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
c9f20a6b-f0e8-4a5e-9f81-c3e606f9428d | 88,87,85,4,83,2,35,25 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 28 | FALSE
d9059554-b08f-40db-bb77-0f10e6c7008b | 88,87,85,4,83,2,35,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
bfce0e9d-ad68-43b7-aa41-2f5ec2acb6cf | 88,87,85,4,83,2,36,26 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 28 | FALSE
dcd331f3-e2a1-4e7e-b1d2-f6884de0aec4 | 88,87,85,4,83,2,36,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 32 | FALSE
530fd517-68a1-4f15-bee5-e2f9985482d8 | 88,87,85,4,83,2,65 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 25 | FALSE
9a378813-6867-4996-98cd-eedeee32efab | 88,87,85,4,83,2,73 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 25 | FALSE
e377dbe4-3db0-4ea0-8486-1a7ac599f4fb | 88,87,85,4,83,2,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
6b277094-cfa9-4abc-9759-ea437cec445a | 88,87,85,4,83,2,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
52dfdf2f-c74a-48d0-a1ed-d3be0b1b9745 | 88,87,85,4,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - STEERING COLUMN (2) -> ASSY - FRONT CRASH STRUCTURE (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e8e27f5e-e4eb-4641-a849-a669e7896f0d | 88,87,103,101 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - DRIVER DISPLAY (2) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
7e70813a-eceb-489a-ac7a-78dad5140144 | 88,87,103,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - DRIVER DISPLAY (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
f4256f66-b63e-48d9-aab7-fa7a9f858365 | 88,87,188 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
5134bc15-1fb9-473a-9ea7-fbf042091f98 | 88,191 | ASSY - STEERING WHEEL PCB (6) -> ASSY - STEERING WHEEL PCB CODE (4) | 10 | FALSE
32814b13-eacb-4bfa-b5ee-3612a223e7d5 | 89,2,16,21,22 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
1e04a8d6-4d56-4618-b692-229b7182c8e8 | 89,2,16,21,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e2105b59-16a0-45fe-881f-6b40a3bc7ac4 | 89,2,16,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d3b42963-974c-4d8e-b342-7bc2a5634a80 | 89,2,17,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7fe31c28-e2bd-40aa-b792-61b3cdaccf6b | 89,2,17,19,20 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
3f301b8c-f805-4bf3-9fff-03b182d4e012 | 89,2,17,19,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1359e23f-0afc-4a9d-87d6-beb96ad23697 | 89,2,18,19,20 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
e5c057a1-8422-45bc-b288-56b6b24c5e09 | 89,2,18,19,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
92ae9183-8f55-4495-85a2-7b912ce8dc6d | 89,2,18,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0262972f-a919-4cda-a37c-1c05970e1473 | 89,2,35,25 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
38ef70e8-6576-448d-9881-5271f3d90af5 | 89,2,35,101 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
91d6dbc5-7ed7-4620-b499-e5e2eef5228c | 89,2,36,26 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
2106df85-50b7-4d47-9358-e231304434dd | 89,2,36,101 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6a4605b5-5fa5-4f0e-8fe6-3c745c6d3e74 | 89,2,65 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
341f13ce-c107-4e1e-a556-08d0589a00bd | 89,2,73 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
262b0dc4-9e2b-4374-809a-8482f327d265 | 89,2,101 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e15c94b6-6e40-4844-91f6-f5d4ff01546a | 89,2,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
3207a226-5dc1-4ab6-acfa-1a8ef2e797bf | 89,1,35,25 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
eb0c2f2d-53e1-41ab-b637-94fd655ccf82 | 89,1,35,101 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0e25c4e1-9544-4bbf-b73b-20fc65e1c530 | 89,1,36,26 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
0d344e99-4ab8-4e60-8f95-d332999499b6 | 89,1,36,101 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e6d2a201-32b8-4ad3-ac52-b057e2476a28 | 89,1,98 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 15 | FALSE
19f11ac2-1e28-4332-9224-e8113b8646bf | 89,1,44 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 14 | FALSE
217476d7-4560-42f1-99b7-44bd0fe0ea76 | 89,1,47,21,22 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
be83a43e-7cef-4b37-b5b2-478a1357f0c4 | 89,1,47,21,188 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f0444f14-709e-48eb-9422-98c8042cc313 | 89,98 | ASSY - INTERIOR LIGHTS PCB (6) -> ASSY - CEILING (4) | 10 | FALSE
93f6bf51-c946-4f0a-ba6a-3e3b539441eb | 90,98 | ASSY - REAR VISION CAMERA (4) -> ASSY - CEILING (4) | 8 | FALSE
129f08ff-1887-4b8b-ba57-ad131c3b7da5 | 94,93,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 5 | FALSE
4428ddfd-6784-4877-aa24-46f85b658945 | 94,93,74,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
e4339d76-8a66-4202-9f29-0949ee5b543c | 94,93,74,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
123f2740-460c-4038-bccf-cfb85ce5db0d | 94,93,74,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7824b461-c79b-4603-a7d0-9e9766748cdc | 94,93,74,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ad192cbf-b5e8-4cff-bda6-d9b8d189bd87 | 94,93,74,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
f65b4674-9529-4814-aaf0-be8f634de643 | 94,93,74,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
86626d49-66a4-484a-a0d2-3403bf3fc75e | 94,93,74,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
7ba2310c-9de0-4e0e-aff7-f4233ea82aa8 | 94,93,74,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
bc2d5e92-0ee2-4a8c-ac71-c64e32df21bf | 94,93,74,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
48c6fd5b-310b-40ae-8137-fd4690519265 | 94,93,74,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
1157d065-a761-4966-b686-18fa3ba3dc91 | 94,93,74,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
4d86294c-eae8-4e5d-a2cd-0cba2821cea0 | 94,93,74,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
cb53fa84-1038-4358-a370-b2693d21b8d4 | 94,93,74,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
7de800f6-740b-4e02-a016-f4de7ba4bca2 | 94,93,74,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
2be01bb2-bcb2-4c26-9280-fc4480138ec3 | 94,93,74,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
320684ce-9a4d-4a42-a5aa-74b876fa7f8c | 94,93,74,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
f7316402-4b8e-470f-9624-845259b5dd9e | 94,93,74,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
763ad923-41f2-45bd-9d82-13576485e314 | 94,93,76,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
2a1288fe-298d-4284-b327-ec0948fd1f4b | 94,93,76,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ca80815e-654f-4f00-9daa-225e3059a9b5 | 94,93,76,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
492998ed-9df6-492e-a323-f999ad44b9dd | 94,93,76,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
c49bacc6-da27-4aec-b474-cbcac9dbbf0e | 94,93,76,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
bb5f849c-220f-429a-81e8-e050efe32fdf | 94,93,76,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2bf926df-6227-4a87-990f-68dfeb8f5e23 | 94,93,76,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
17ce4e2a-029e-44d6-941b-d19407c70782 | 94,93,76,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5b357491-beb2-43a6-a0f2-f032aa18251f | 94,93,76,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
8376d999-fed5-4d9a-890e-d572857465b0 | 94,93,76,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
285ce079-75b8-4eb0-b1c3-a7dfd7b5c937 | 94,93,76,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
41c2d32a-059e-45e0-b541-6925dc6571d5 | 94,93,76,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
c1e3da4f-8c21-482c-82dc-434b1496b4bd | 94,93,76,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
46d40707-bd0a-4964-8270-b4aea038581b | 94,93,76,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
a4c822f7-ad35-4e7f-b4fe-8199dbf951a3 | 94,93,76,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
bdf2c333-7848-4708-8411-cf97307d2dc4 | 94,93,76,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
23b9d7fc-fadd-4249-8a5f-0cda9f6d42b6 | 94,93,76,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
3a25f100-bda3-4777-8518-71efffc7f61a | 94,93,77,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
d6619c7d-72a4-4cdc-a09a-7a6af2f82eb2 | 94,93,77,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
fc0084a5-1e72-4883-b250-74495a8b1190 | 94,93,77,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
4cb7ceb4-1c88-46a7-b304-3b2e154b0ca2 | 94,93,77,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
15d62e55-0778-473f-a088-a881bfc70472 | 94,93,77,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
201dc4e8-7c95-4586-b9ce-9ee032797f19 | 94,93,77,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c4b66a70-0726-45b0-bf6a-10b4bfe374ff | 94,93,77,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
05b893c4-f3ec-4fb3-9817-ecd477706a0c | 94,93,77,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8016315c-1234-4515-a226-0da75eb92218 | 94,93,77,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
8655ff87-1e3c-48c2-a7df-d4b511572eb5 | 94,93,77,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
d0bbc5a7-62bf-49fb-89da-8d28e4ef7429 | 94,93,77,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
cb293fe6-3a9d-4b86-80b7-564e8245dfbe | 94,93,77,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
71697e84-fa49-47bd-bf4d-25c58f86fcce | 94,93,77,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
ddc3afcd-fd86-46b6-b6a1-10110bc3cc6d | 94,93,77,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
ed717ba6-fe2a-4cb0-8ece-09d36b2563eb | 94,93,77,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
192ebb05-39f4-4dd3-8591-66648042fad6 | 94,93,77,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
150e08b7-5074-4fde-bb87-96982fa53115 | 94,93,77,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
3d47d5f6-7b3b-4649-94f6-08b81de7ea91 | 94,93,80,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
bdb19048-8bad-450c-bf99-0a07671b0ed0 | 94,93,80,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
3ab1fcf2-a5bc-4fcc-9bd5-d8c4300a583d | 94,93,80,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
48657197-da74-42f3-868e-411a5093b140 | 94,93,80,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
32771d72-d7f5-4d7e-9bee-18f70f25d44a | 94,93,80,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
e8812a33-4a76-45b4-b197-04e175aab530 | 94,93,80,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
5d2c1b18-0c59-46d7-8b5b-644702b8cb6e | 94,93,80,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
357b575d-fb9f-4d98-9f2e-46965cc407d8 | 94,93,80,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
02b71be1-632a-48f6-8c7f-5e1e17124a35 | 94,93,80,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
b82fb547-2454-4f10-839d-e2337c940168 | 94,93,80,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
f91f378e-d2d7-4c36-8ed4-62244186a59d | 94,93,80,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
93acc707-d148-4774-9fc6-da14060a16df | 94,93,80,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
20856934-af7d-4001-9c50-544c4e233893 | 94,93,80,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6e66da2a-7edb-4f80-a777-07c23f2c1251 | 94,93,80,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
eb76fcc6-2823-4b08-a219-1f6fe171d2ce | 94,93,80,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
56ac2cd3-3431-456c-884f-ec6de2be8a21 | 94,93,80,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
ba1f64c7-cce5-4a86-a5be-2611450bcbca | 94,93,80,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
50d5889f-bfca-4f65-b661-805e5862c4de | 94,93,81,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
59416a90-8a85-45c8-bf9f-2511864128a8 | 94,93,81,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
68481da1-82ed-4ee2-9019-5a885a2b022f | 94,93,81,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
8c943a9c-5519-44c4-804a-d3d7023a9a16 | 94,93,81,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d6fb374d-79ac-436a-83fe-f9c1abb9ab69 | 94,93,81,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
d060d38e-6b18-497d-bdee-f650fdb115fb | 94,93,81,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
fabc4650-7cbe-44d1-936f-ebb07b22635a | 94,93,81,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
01b76a16-c8e4-4c3c-b0bd-80726733fbca | 94,93,81,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
4e07b520-f5ba-4adc-9311-f6644b20bb0a | 94,93,81,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
8a86b1ae-e861-4986-99be-b87402286d1d | 94,93,81,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
8dde9705-c359-4251-9c5e-f2527312b347 | 94,93,81,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
36a6f3ca-8c31-4248-a420-66bb44ed711f | 94,93,81,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
04556706-108e-4945-a77b-aeac50370237 | 94,93,81,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
e513beb3-7bb0-45c8-903d-43f7d03b0107 | 94,93,81,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
6608fbbf-abcb-4b05-a9f5-92b1e2b3213d | 94,93,81,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
7ae01bc7-aab1-4278-8a2d-710c65054275 | 94,93,81,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
d7a29686-181b-4237-8624-b9f69d89c9d0 | 94,93,81,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
9a7f25ca-0df8-4417-816a-0a9bc7dcb81c | 94,93,83,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
d42f0e1d-474b-465d-a81e-196554d86c88 | 94,93,83,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c04a6fdd-ba26-4212-906a-dcd169d49e8d | 94,93,83,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
473496a9-1c40-43fe-bcb1-3f43e658ce43 | 94,93,83,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e4d9155e-f80b-47a0-85d8-7215eed529c5 | 94,93,83,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
3deeb582-f559-48f3-b0b3-fc72ce0a1b64 | 94,93,83,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
889a69cd-6552-42a5-bccc-78aa24fed2fb | 94,93,83,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
33abfaee-d7bb-40f5-93e5-f62134338e7f | 94,93,83,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
2cf2dc30-e440-4ec2-80ce-19b3e136a12a | 94,93,83,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
20ba855d-bf6b-4b27-8e34-d81a7d17912f | 94,93,83,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
01ff1e69-f7d4-4eca-a472-ca5751b1c0a9 | 94,93,83,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
43730a70-9991-4587-87d2-585d6a3e00e5 | 94,93,83,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
96005630-62f3-4d79-8a48-dcdb293e5cb8 | 94,93,83,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b8ead2b8-bed7-4107-98a3-d17da48e0db0 | 94,93,83,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
5796a697-ccd2-44e9-897e-f3685bb391c3 | 94,93,83,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
ea30ec6d-3a3d-4de4-97b5-9534d523021c | 94,93,83,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
8ad44141-3b54-40b9-8ca9-eae53883124c | 94,93,83,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
0f4e909e-53a9-4fbd-8d67-c188de73d7ec | 94,93,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
5b9436e2-807f-418d-b080-22665a3084fa | 94,93,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
46e98515-9afe-4001-850a-66ba7ebed45d | 94,93,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3ae8c5b8-1c6a-440a-842e-b0f32e16374a | 94,93,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
33fdb216-6653-4f69-969f-e88b48e97dbc | 94,93,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
8956ccc1-ffa0-469b-97c7-3aa1831f0f13 | 94,93,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
f5740db2-956a-4f0c-b258-1619d594d4af | 94,93,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
ae67a0f1-7811-42c7-929b-4bd284072cf9 | 94,93,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
954be11f-5cb8-402e-8f01-302592672328 | 94,93,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8b40c664-c0b7-4895-a1a3-acf0bbaa6ebf | 94,93,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
a2222916-ff4a-4d65-be68-809c1b4531a3 | 94,93,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8e4e5a54-4211-40a8-87b5-80e2601bf952 | 94,93,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
ab2edb75-8077-4397-8139-e939789fe896 | 94,93,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
6c4e8adf-b91f-45ac-a1c6-b4606a96bc69 | 94,93,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
093c4bf8-b9ce-46e0-aee0-d50fb32b6a39 | 94,93,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
71e3f9e6-cc4b-46a0-bc65-1f5f64238de1 | 94,93,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
3795ea50-53ef-4036-885b-4903a601b392 | 94,93,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
72345aed-b26c-4fe7-9f36-815cebc44e14 | 94,97,93,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
db92442d-836f-4be6-be76-bdc5f8c28f6b | 94,97,93,74,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
48936045-2b13-4888-a629-dba37aa7a834 | 94,97,93,74,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
cb6b889f-1dac-4df1-aa4c-7f09e8afd574 | 94,97,93,74,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9fc4e0a5-e321-41a0-bcaa-c455a6ba7b1e | 94,97,93,74,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9624572d-1ce8-4d6d-b8d2-77f02d6aa722 | 94,97,93,74,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f9ee8fac-4d8a-4153-b63f-64adc6617ae2 | 94,97,93,74,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ed457a9e-3a26-44c0-b347-2b42473109b3 | 94,97,93,74,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b7242cf5-661d-461b-9cc2-cab403e4a19c | 94,97,93,74,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
99e767a8-5d24-4d35-86fd-15ed95b6df9a | 94,97,93,74,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e5dce201-e31d-43c2-9b75-4b65cade28c7 | 94,97,93,74,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
c59b9881-20d1-42c7-a89d-4163d41f3f45 | 94,97,93,74,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a2e827a4-57a7-4478-85cc-24d78de77e12 | 94,97,93,74,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
61226dee-8291-440b-bc52-a65f81bab36d | 94,97,93,74,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c83465a3-6d13-45f5-920e-b9fb75e97258 | 94,97,93,74,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
98a9df98-5fc1-43eb-bfc8-e1ef3e62fc1a | 94,97,93,74,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8b6b9bcb-7bff-45d1-a6d0-bb9b3a6414ff | 94,97,93,74,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e66cf991-b8e0-4073-94e5-5296e9dfc3f5 | 94,97,93,74,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
7461fbb6-0de6-4329-927f-b9071d63282b | 94,97,93,76,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
3c30e5b1-622f-4348-ab96-c169c71a2605 | 94,97,93,76,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
3fa01342-8062-4b46-91ba-b1bf3b5b82ba | 94,97,93,76,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
36c81fe6-5611-4b6a-8972-0836c576cb5c | 94,97,93,76,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
03940e86-7a12-4ea5-ba27-5dbc0a371ef7 | 94,97,93,76,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
c77e72ed-abd1-4d48-988d-46fb58fa765c | 94,97,93,76,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6b9691b2-61e5-42a3-afef-e704499294c2 | 94,97,93,76,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f0732228-3b86-45ee-bba8-67a2d3363d88 | 94,97,93,76,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
04bf9c0d-ac55-4dd1-b204-edd134d39749 | 94,97,93,76,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
82f802a8-667a-4c16-9766-2c3ae61daacf | 94,97,93,76,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
cb147ddc-c78d-40a7-ab9d-8d262da2c417 | 94,97,93,76,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ed9d2506-a389-427c-b307-86a30f16213e | 94,97,93,76,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
f13e5291-99de-4086-958a-118413628c6c | 94,97,93,76,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
219320de-0c9c-46a9-ad97-42858604fe7f | 94,97,93,76,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
77f084b8-10fc-4f2e-8e6f-7857bba70e9b | 94,97,93,76,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
3cd0634f-598e-40f7-a136-2b27781e532b | 94,97,93,76,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
66170e3c-45e2-46cf-8372-2dab43c475e2 | 94,97,93,76,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
f2107314-9dc2-45c0-b103-8671f98fcb67 | 94,97,93,77,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
256bfde8-017e-4e52-958c-67c8533fb88d | 94,97,93,77,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
cb9b783f-f36b-4bf8-a98e-3df6f1bdec70 | 94,97,93,77,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
46b727d4-caa9-403f-8850-90134cbaad7a | 94,97,93,77,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4e04e211-c035-4413-a8db-61ead0c91429 | 94,97,93,77,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d013f19f-713a-4e9d-9f5d-e9784fa134a7 | 94,97,93,77,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
09378453-400a-460f-8323-0cdede630160 | 94,97,93,77,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8553842c-b2c2-44c1-a7d1-0f5d65e9ab41 | 94,97,93,77,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
925e39d3-efb9-4645-98fb-3e03dc226471 | 94,97,93,77,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a6c2e269-b6d8-4630-b1b2-06c8a5567951 | 94,97,93,77,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
8d907edb-e40c-4b0e-9722-d32c080e2564 | 94,97,93,77,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4e4517ee-3dd0-4e0a-b8b7-07fc52dca9da | 94,97,93,77,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
47abb794-f546-4e8b-a50b-8f9b3cc5a978 | 94,97,93,77,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
01e003ae-9b56-4f3a-9d8d-04d126e35d90 | 94,97,93,77,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
2fb0daec-8f58-489a-a825-05092f9f98fc | 94,97,93,77,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
fe8202f0-4f1a-4c39-8bfc-9972ca19bd62 | 94,97,93,77,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
b8164096-da33-4392-99d1-950796dccc29 | 94,97,93,77,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
9ab7fc89-18fe-4f53-816a-103f375581f1 | 94,97,93,80,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
6b4c6144-f986-4883-961a-172ad4998c2b | 94,97,93,80,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4395977c-d073-4184-b1a1-62e6e5d43bcb | 94,97,93,80,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ce968cf5-b6cc-4227-986c-2824d9a0c454 | 94,97,93,80,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4f973bce-3628-45c2-ba06-619f617a1d46 | 94,97,93,80,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
11ababdc-afeb-4fba-a5af-c0ba754c917c | 94,97,93,80,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
4bf1202a-0765-4868-8494-4da5d965b779 | 94,97,93,80,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c4f77aea-9e09-45a9-8c22-423d77252243 | 94,97,93,80,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
32c0a246-ab73-4b0b-91ba-c21fb0132443 | 94,97,93,80,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ae3e8405-fce2-45c9-8546-c0f43e0e8932 | 94,97,93,80,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
62e9f0bb-b3ff-4072-8fa6-8378d384868b | 94,97,93,80,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
11fdcb67-716a-44e3-9d24-70ffd48ddb75 | 94,97,93,80,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c23d532b-3800-40ef-a7d0-3e8ec41c56cc | 94,97,93,80,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
20cdac9a-1f7a-4c1b-8274-43a1d525af97 | 94,97,93,80,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
b03a92d5-8d7d-4672-b253-8ee269936975 | 94,97,93,80,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
800647e6-575d-48c7-b6d9-1d32ce0a807f | 94,97,93,80,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
f576499f-3c68-49e4-b9c4-f7300f6e3696 | 94,97,93,80,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
be2ef51e-4116-4f99-be6c-98f227cb6386 | 94,97,93,81,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
aaec4085-7974-402d-b9b3-89e3d88367b7 | 94,97,93,81,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
152e2576-8982-4c99-8914-dd3b80b43b92 | 94,97,93,81,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7aa97ec6-b1c0-4991-a0a0-4529dfaa558c | 94,97,93,81,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7c976fd9-d32b-4215-ad8b-8efba6abefcb | 94,97,93,81,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
4d314fee-93a2-4d7c-93e3-fd55a215467b | 94,97,93,81,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1c82a2b8-40dd-4ed4-b6db-a69440e85f7e | 94,97,93,81,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
42051747-52a1-4913-aa45-114e0ac12e6a | 94,97,93,81,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
855ca697-b9a4-4dd7-9fd2-92cd28e0f751 | 94,97,93,81,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3eabd32b-956e-4786-ae84-9ff3e523ba79 | 94,97,93,81,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
c408c3e7-c1d3-4e01-a725-ae8860863a70 | 94,97,93,81,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
325066ea-78c3-41f6-a763-4ad73cf32dc9 | 94,97,93,81,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
272acd9d-8410-452c-b96d-b7eb1a2345e9 | 94,97,93,81,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
2d4fb76e-89b7-4ea9-b9bb-0d5100869735 | 94,97,93,81,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1022c6b6-956d-4e4b-91c1-22cc7decaec1 | 94,97,93,81,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8a980e7e-9014-45b2-a185-869056bc2280 | 94,97,93,81,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
5c888321-56d1-4cc2-9c4e-c1ce1f43522a | 94,97,93,81,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
e7dfe9cb-bb23-41ab-a57f-d408d89ecd52 | 94,97,93,83,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
9b8fdc43-493b-4b42-be64-56b1be5eebcb | 94,97,93,83,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b9cedf4c-741d-4449-bcd1-eacb2d90cea9 | 94,97,93,83,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1a685eab-f49c-472d-bee5-8690ce0e4814 | 94,97,93,83,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c5a9bbcd-d92c-4a5e-b22e-f80c696780f6 | 94,97,93,83,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
e6f14e2d-633d-426f-a740-b00af8fe633b | 94,97,93,83,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
69bf54df-36a5-49f1-a6b9-0c3ba4cfde8c | 94,97,93,83,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f04bf3a2-f2f0-447e-ac29-6c32c71a19e4 | 94,97,93,83,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
dfed720c-e7c7-4f3e-8fc0-31020c57dbae | 94,97,93,83,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6bdd57fc-be3e-47bb-93c0-a666e4353374 | 94,97,93,83,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
636768fd-6cb9-4af0-a25a-619428d02c68 | 94,97,93,83,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
4aa0d61e-897a-4212-9453-4359b04f3226 | 94,97,93,83,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
64b2299f-0ae1-434c-94c3-f3b3ddaff506 | 94,97,93,83,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
e8ce9c24-cc51-4cc5-99aa-a577a5b88b4c | 94,97,93,83,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
9d9155bd-638a-4c18-8921-963cb9839c12 | 94,97,93,83,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
c8ea46ee-301b-4b31-9db7-fe2d4d0a4b09 | 94,97,93,83,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9eb46d96-6d5e-4537-a7c6-bb4c044eb57e | 94,97,93,83,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
bee0986a-9081-409a-b897-58f2aaf2a9d6 | 94,97,93,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
db3f60a0-9b81-4881-a805-2d35f4b1c94c | 94,97,93,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1e4067bd-ac38-4ad1-b72a-19e74b4565de | 94,97,93,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8eb72f36-5170-498e-b629-2dd21c2488b8 | 94,97,93,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
83780ea8-d4a6-4485-a0ee-6d50d3ccce5d | 94,97,93,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
31de07a8-763c-47bf-b8c7-8a9e6a77a9f1 | 94,97,93,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
5ccce48c-236c-494f-a9ad-dca9885a73cc | 94,97,93,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
f00245bb-5a9e-4081-b287-91c93aa10a7e | 94,97,93,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3e668952-1f6a-4ac2-a7c4-ce9a696befb2 | 94,97,93,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
6110a6a6-0335-4c08-ae94-a85dcebfef43 | 94,97,93,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
75fee3ae-f797-4eb0-a137-8c17f82ace52 | 94,97,93,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
477ac734-fe54-4579-9b6c-56417963ced4 | 94,97,93,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
5817c11c-0f92-4da3-b26c-aee9bbcdc775 | 94,97,93,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
b5499f78-1c8b-4492-a2cd-3021a82df972 | 94,97,93,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
55250f05-6859-465f-b91e-c7dc7e7b8d0d | 94,97,93,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
68cfc6fb-46a7-44aa-8c0b-fcb0dc00d1ff | 94,97,93,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
b527ee12-2611-4aba-ae21-0dcd9ef8c62a | 94,97,93,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
db247fdc-8066-4f87-a5e0-f460d2f5cc54 | 94,97,96,93,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
4eb29fe7-59f6-4afb-a870-51f6b0613af8 | 94,97,96,93,74,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
fc3c7163-d037-4744-93f8-701184ba3996 | 94,97,96,93,74,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
20ecf2f3-c3f0-43d7-b586-0e1d4be63882 | 94,97,96,93,74,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
45c689db-8b64-47c3-aad8-df3bd30fad77 | 94,97,96,93,74,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d6b256a8-a3dc-43c5-8879-5b97fd1be151 | 94,97,96,93,74,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
afa3c412-2795-4ed9-8ca2-267a084df5bd | 94,97,96,93,74,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
d6cbad27-ec2e-49fe-abbf-02f11a5fac6f | 94,97,96,93,74,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
d2031b44-bd7c-4457-98e1-ca45dedcacbc | 94,97,96,93,74,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
41a6c9ee-4bd3-4a78-bbcd-104907267bf9 | 94,97,96,93,74,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f99e1677-903f-4a56-884a-56c9ceb8ddb1 | 94,97,96,93,74,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
b48fcebb-2a77-4f76-86c0-f09af5968f32 | 94,97,96,93,74,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
37ec25b9-ede8-4902-972a-9847e558ed71 | 94,97,96,93,74,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
600c4836-eb57-4197-8c27-7a4e94534bc0 | 94,97,96,93,74,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d0064c9d-25c3-4f60-be6d-60fde53b1d9f | 94,97,96,93,74,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
face9388-64d0-45aa-b601-16cc813676b4 | 94,97,96,93,74,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
32801e5f-299f-48c9-97fa-4e7f6aa86977 | 94,97,96,93,74,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
377eb5b0-cafd-44ef-840f-191aebcde118 | 94,97,96,93,74,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
68b98af7-fd02-444e-8591-29bb262d0350 | 94,97,96,93,76,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
3996a7c6-24d9-40e8-ab6a-3d719b76ff6d | 94,97,96,93,76,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
99e8183b-030f-4e32-bf78-8cc545599a6b | 94,97,96,93,76,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
71a534f4-2fdf-424a-b993-ba0ffe62407c | 94,97,96,93,76,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
64ed7c62-434a-4f1c-bf2a-a7fe1dd3ff28 | 94,97,96,93,76,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0203650b-6e3f-44a6-a544-26b16e04ee33 | 94,97,96,93,76,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8f94fe3c-b3bd-4fdb-b82d-6b94e14ab21b | 94,97,96,93,76,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
b6920202-6710-42b5-b388-0a75b6b8e553 | 94,97,96,93,76,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5a448923-4525-4ff5-929c-e06772f99e2e | 94,97,96,93,76,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
70b9f961-e966-45c9-ba92-b19e4f4634ef | 94,97,96,93,76,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
e5f77e5a-1588-4d49-b7dd-9ca4353e9b90 | 94,97,96,93,76,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d3a971cb-bb61-48a8-8eef-f5e1facaf3fe | 94,97,96,93,76,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
76209a48-c54f-4932-9e18-bedc9cb391e4 | 94,97,96,93,76,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
47916048-d181-4552-9a49-4880bf5e6cbb | 94,97,96,93,76,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b69f848d-8657-4f82-8d73-df0b16a9ae39 | 94,97,96,93,76,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
53875797-b4ad-4847-a43d-41f474a9f12a | 94,97,96,93,76,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a602f614-adc1-46f0-9b5c-11b7d57e6f75 | 94,97,96,93,76,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7b0b8e7d-291c-42a3-9337-aae63385ee8d | 94,97,96,93,77,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
b8c8283a-fd8e-4e73-9a0a-d3fa50a6de29 | 94,97,96,93,77,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5a20990b-1972-4359-a122-852f5d287898 | 94,97,96,93,77,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
a42389f5-bf32-4f1c-a265-deced0d4944d | 94,97,96,93,77,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
a4a6e418-c369-4ee7-88a9-4341faa22263 | 94,97,96,93,77,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
afe2215c-6635-44a1-97e6-eb323d66c64b | 94,97,96,93,77,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8cf6a4ab-7523-4aab-a61f-ce59dcc7045d | 94,97,96,93,77,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2f0d27fa-c00c-488d-b62e-8c4d6875bbe4 | 94,97,96,93,77,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
5134629c-9b36-4150-b321-6068f48343b9 | 94,97,96,93,77,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
6d046534-5995-4971-b29e-7d613a10e1dc | 94,97,96,93,77,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
faec0efb-8fc0-4a01-b1e5-34613ae6093a | 94,97,96,93,77,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
500c9ab9-c2cb-439d-a9e6-4ddd0e943305 | 94,97,96,93,77,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
1f835c7d-d963-470d-8086-163a27eab70f | 94,97,96,93,77,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7aa8c5c0-6c2d-45ba-9a46-1057e908c086 | 94,97,96,93,77,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f8ffd1f5-2b7d-4fa9-8088-07ccb41bcf86 | 94,97,96,93,77,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
898b5503-250b-4e3d-b5ac-ffade158c034 | 94,97,96,93,77,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
9383bac4-2c18-4a10-8faa-adfa5fad0ff4 | 94,97,96,93,77,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
cf644b3f-16d7-42c9-8907-126aaeb4c802 | 94,97,96,93,80,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
c3fefa55-c238-4494-89fa-a685efa72755 | 94,97,96,93,80,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
149bdce5-0ca7-4ea0-846f-5119cb10e3da | 94,97,96,93,80,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
84986b27-4918-4bdb-a799-f6b2a3d301df | 94,97,96,93,80,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
2651a54f-18bc-4df8-b9dd-27428513c8b9 | 94,97,96,93,80,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
fc2cddd2-f28d-4468-9196-e2c75e01a56b | 94,97,96,93,80,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2661fa59-eea8-43df-8232-1862975ff712 | 94,97,96,93,80,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
900ad354-edf2-4ea7-bb20-e8fec9f345b2 | 94,97,96,93,80,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
835ab891-a529-4546-98c0-0d241864c525 | 94,97,96,93,80,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
176ce066-72f3-4a18-b16d-efff0a5b01ba | 94,97,96,93,80,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
1505155c-89af-4b23-9335-58295c1f39bf | 94,97,96,93,80,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
58b1b4f9-7775-45fe-a448-b483541357f9 | 94,97,96,93,80,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
3fd1d975-261d-40e1-845d-e02a17ff4874 | 94,97,96,93,80,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
966a645b-13b7-40be-b387-946d6e3aabc2 | 94,97,96,93,80,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
4ec9fbad-a7de-490f-ba47-e9decef3cae7 | 94,97,96,93,80,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
d473142b-2097-48e2-835e-9c753da39161 | 94,97,96,93,80,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
5db3b3d0-54d9-4d73-9881-20a852e61f19 | 94,97,96,93,80,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d4d4f43f-3da1-438e-943a-a8264fc02dd1 | 94,97,96,93,81,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
d2921985-276a-4b0e-985c-f314c1ccd46f | 94,97,96,93,81,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
cc7805ff-79f6-4bb4-9494-2379ceca8d59 | 94,97,96,93,81,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
72dd522e-fbf7-44c0-ab2e-5fd8fc8e0399 | 94,97,96,93,81,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
262f0c5a-d942-4ebe-b931-d653b51dcda4 | 94,97,96,93,81,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f1e47efa-571d-4493-be89-ee7444dcf414 | 94,97,96,93,81,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b7bc0947-ed0f-4bc4-917f-c88ffbd3689d | 94,97,96,93,81,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
4f6b66a9-d188-4c96-b31c-c5120d0b643a | 94,97,96,93,81,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
2f85bba4-b26b-427e-aef6-470e2f2d0f83 | 94,97,96,93,81,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f9419ec8-2d7a-48f6-bf97-fdbe546db3f1 | 94,97,96,93,81,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
22b4dc26-9807-4a3b-8148-de059d3fd372 | 94,97,96,93,81,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
887d295a-c96f-44bc-9951-43536648724d | 94,97,96,93,81,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
74297e9a-193b-4ed9-8c28-48f015740cb7 | 94,97,96,93,81,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
7b90770a-4c8f-45a6-8456-2a85940690b0 | 94,97,96,93,81,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b1acddc4-33f0-4ca3-915d-61efcd4aa524 | 94,97,96,93,81,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
28faf036-90a5-489e-8b5c-bb7695181558 | 94,97,96,93,81,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
9e61a611-4f3c-4004-9a3c-2fbde9c3f2d2 | 94,97,96,93,81,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
be4009c4-6e5b-42e9-afc3-586e3419f0ee | 94,97,96,93,83,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
99dcd0a1-5452-4e85-9f10-429543197f7f | 94,97,96,93,83,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d72aea91-47dd-4b27-a305-3615d9bff296 | 94,97,96,93,83,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6c19a8da-44f0-4065-8f61-1dab72026017 | 94,97,96,93,83,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
af34ecfd-fc07-4f0b-b642-d742092a4229 | 94,97,96,93,83,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
4e3e0127-4905-4267-b87c-08f95d255db1 | 94,97,96,93,83,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5bd96e0e-81cd-4a03-95d7-dac2fd7efd9c | 94,97,96,93,83,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
57be5da6-a699-4d99-86a9-0b918fdc993f | 94,97,96,93,83,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
cb5ddab4-cb59-4e15-b8b2-65e373961c2a | 94,97,96,93,83,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
52814449-4423-4ea2-afff-79e6f05cabee | 94,97,96,93,83,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
112c16da-977b-49f8-ae23-39f5c3fc2e9b | 94,97,96,93,83,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
cb0affff-ce44-4637-add3-72cfb365100b | 94,97,96,93,83,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
51ea5d24-a2ed-4b4c-9236-0663e8d510f9 | 94,97,96,93,83,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
53df2685-431f-4346-9a82-9810c7c24b0d | 94,97,96,93,83,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
3b229885-71a4-4c28-99b3-3309a7e36dcd | 94,97,96,93,83,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
6208af5d-6c54-41f8-9127-c7ce9df29d90 | 94,97,96,93,83,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a0ea8257-865d-40c2-8d41-5d9958656b18 | 94,97,96,93,83,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
6e4c2740-fa47-484c-a268-6412db79005b | 94,97,96,93,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
23efd8d8-f903-44dc-a5e8-04190848783b | 94,97,96,93,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
561e1b24-3bf6-4e1f-a88e-e429b650c77f | 94,97,96,93,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
09a5ef8e-6604-442d-8374-a84c1ae5318d | 94,97,96,93,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ca775243-5bbf-42f6-a190-f7684ea9419f | 94,97,96,93,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
b9e6efb2-b295-4ddd-b77c-d681af024559 | 94,97,96,93,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
772fa2e4-efb8-4765-a276-2ed81927e800 | 94,97,96,93,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
8ec4cf92-c45a-4b90-8381-bc5fd9e14199 | 94,97,96,93,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9a06101f-7439-4456-a700-dbe36ce28996 | 94,97,96,93,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
4f4d7c77-2fc3-4614-9ffd-582bb75240e8 | 94,97,96,93,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
29e999f9-75a3-485f-be32-1cc4e66902d4 | 94,97,96,93,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
11d772c7-68a6-4188-89e3-463989cb5751 | 94,97,96,93,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c672bb05-b25d-419a-93b6-a061e8a96e9b | 94,97,96,93,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
289c836f-e496-464e-9914-de85a1de8f5b | 94,97,96,93,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
e442cd32-77f0-4544-b4af-5403b6aebeda | 94,97,96,93,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8c52c821-f7c7-40d8-977e-47444cd18a20 | 94,97,96,93,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ddbfa225-f873-4015-a3cc-abfcbd41b96c | 94,97,96,93,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
5d50a4d9-35c1-4779-b9bd-a7cfc15a7f14 | 94,97,96,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 6 | FALSE
3a226036-7a2d-4f03-bdd7-95d0e067f09e | 94,74,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
97de8460-1262-475b-963e-10130b6a8932 | 94,74,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ea13879d-c80e-47cc-b3e0-8fd39d7f35ac | 94,74,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
c98c8e1a-1a9d-4642-b2cb-60b7e02c2874 | 94,74,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
9a7fe210-352e-44e8-a3b4-2c455f4730be | 94,74,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
61cfbfdc-0563-4872-a809-fa8fc726002a | 94,74,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8cef106c-417e-4825-86b3-49b78ab73e2e | 94,74,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
58d36cfc-0d5f-4d53-8ed9-31a7956fa8e8 | 94,74,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f6e13696-f9dc-4faa-aff4-970eedc42aaa | 94,74,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
25a23702-befc-41eb-a7e0-8e578f442a16 | 94,74,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
1aeb7dfd-45b6-460a-9898-53f2913771b7 | 94,74,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
4bd2977f-98ff-4c1c-97ae-99e58e33dc0b | 94,74,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
8fd21f43-2958-48a0-8372-2e550e2cdfcd | 94,74,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
ee389a0b-0350-40b0-96dc-bfb17a5b3758 | 94,74,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
e4cc9eca-8607-4dba-96b4-e2839509ebf6 | 94,74,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
33418aa9-4422-4d51-bd2f-6ee52cb88b50 | 94,74,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
ed41269e-bd9e-4d05-97ed-8e61180018f5 | 94,74,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
d0585caa-e536-49be-8cc0-ce950e894776 | 94,80,2,16,21,22 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
3d786dfa-a190-4dcf-8b83-0b9e3c6d8442 | 94,80,2,16,21,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a4478d15-d6e0-4d7d-8eb4-c31d559c7ee5 | 94,80,2,16,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
06dc0e98-a386-4aef-bc8a-c7496da90a9b | 94,80,2,17,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
c68a3654-060b-41f1-9e05-b0e3b6834e65 | 94,80,2,17,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
d6e4535d-d71a-4c27-8b3f-bef4ccc0769d | 94,80,2,17,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
078d321a-d83b-4466-8548-e4c1f1ea1ff9 | 94,80,2,18,19,20 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
148cfa9d-0a67-4fc0-b5c8-7d2a95308c47 | 94,80,2,18,19,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9d8e6845-0c9d-4f4e-b243-5e374c8fc00e | 94,80,2,18,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1ad7249a-d394-498c-9ffa-d5a7f6d1de78 | 94,80,2,35,25 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
a5bcc851-efbb-4635-bdd7-b961579aee71 | 94,80,2,35,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e729e1c4-a0d4-40f7-a051-b1352a2656f0 | 94,80,2,36,26 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
7ec3b3d7-e149-4680-9c1f-e23a063a0d84 | 94,80,2,36,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
050bb424-d1d1-4f3a-8a4d-73ac256a2de1 | 94,80,2,65 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
25b4b283-936c-4b3f-88c5-366af0d7ccff | 94,80,2,73 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
509c0417-5747-4834-b64e-f2cc6fcdbf99 | 94,80,2,101 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
a4ded4be-6923-4c41-ba5e-4ba5c5f6b3c5 | 94,80,2,188 | ASSY - THROTTLE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
b4fc6d3b-bcaa-4e55-a76d-004f292308fd | 95,73 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 3 | FALSE
c6cb45c9-4e4b-463a-9218-03f3705e21b7 | 95,74,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
795bb558-3d99-406b-99fe-933445f2c604 | 95,74,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
14534865-6b6f-49b3-9d16-1c5d8d25e463 | 95,74,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
919d65c0-6d66-4cc9-bfe4-3f651bb237da | 95,74,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
509a28a9-0d12-46b1-bc43-5481193acf21 | 95,74,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
190664b7-9f86-4850-9de4-cf0fce6a870d | 95,74,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9e2592c8-44dc-48ba-9e1a-a676f03005b7 | 95,74,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
6e1b764f-2d64-41dd-9402-6aef0f65b3ce | 95,74,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
d287705d-cad2-412f-a2ed-44b5badc503d | 95,74,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e8067c30-cfdb-407d-806f-f9e8ba57d074 | 95,74,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
3c639967-481d-4ad9-a4ae-145f99b0867a | 95,74,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
97d317aa-50e3-40b9-b8e2-bbfbcc227ff6 | 95,74,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
b20b3377-7ac9-43cf-8b8d-56cf05b649b1 | 95,74,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
b6981ad1-2d5a-4b9d-92e1-828334c5a412 | 95,74,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
93fdde71-b2ce-40bf-9ce6-007c12d5cf95 | 95,74,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
ae89f2c4-2f52-4edf-9c25-c1e52f36c0f9 | 95,74,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
67a3cf93-5586-49f9-ab7a-ffeff6301c0c | 95,74,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
7b3ae442-05ca-4c0c-90a6-3808b63906e1 | 95,76,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
7258f590-74c4-4aa1-9a20-ff281b97ece1 | 95,76,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9cba42f7-b3f6-48fb-bed9-edda53af6b71 | 95,76,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7e0a7e0e-2d1a-4d7a-8f9c-d47fdb157ec6 | 95,76,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
c0cf8434-cdbe-4bd7-a498-f225ae93a303 | 95,76,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
5cd933b0-62e0-482c-8606-8a63a82d0eca | 95,76,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
15f50d73-0191-46b7-a8ea-108a980d8fd0 | 95,76,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
e12865a5-2445-4827-b505-2744988f891b | 95,76,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
a8d0cf4c-9b3b-4dd7-a996-e5795e196bfd | 95,76,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
581646ff-fbce-416e-b842-b32a49ea559c | 95,76,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
a749c77b-e71f-48e5-8e0b-053eab376339 | 95,76,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
c5e7c015-bcf0-4c8c-b97c-85ae66efac05 | 95,76,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
8ae73253-c71f-483c-b07e-bb9d513dbc6b | 95,76,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
16997dc3-adb3-4f9b-992c-d6d610c97490 | 95,76,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
6195e9be-31e1-4999-b086-2763c6bb9dcf | 95,76,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
6a1ca3e2-efa9-4fdc-9ee6-d3531cddf33f | 95,76,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
fec69935-2906-4130-b308-c4c1d9bbb991 | 95,76,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
8e15af34-a394-4677-a9fb-f53e66489a5d | 95,77,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
58f99986-873a-49a1-a4b4-97e9e9321259 | 95,77,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2a08ac29-4336-4b46-a10c-86119b70c368 | 95,77,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
03b4e303-dafa-45df-8aa9-421453517cbb | 95,77,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
f97425e9-46c7-4bd4-a6d5-84584e8354b7 | 95,77,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
f58ae51e-0c5a-44e8-899e-7d5525cac204 | 95,77,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
22bb3b78-08dd-4d2d-941b-803d7ed88322 | 95,77,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
48f3c4cb-d590-4f5d-89b2-d439c5090e55 | 95,77,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
af5dc510-4191-442f-b1f9-699df93e792d | 95,77,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
55e1416b-d69a-44fe-99ab-1cf753f33b87 | 95,77,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
d17e0fe4-1455-453a-a70b-08a3d463192e | 95,77,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
b5549648-e495-4a6e-949c-a7984587c9a5 | 95,77,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
cb12cd17-abd0-4372-9c28-923e19fbfeb9 | 95,77,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
0ebcaf39-7a89-4d8e-8f20-b2f062125b61 | 95,77,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
1cf7075a-79fa-49eb-9db1-cdd7bcc6a904 | 95,77,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
d1b31c9d-9b8e-4280-8a75-78130f1034f6 | 95,77,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
adce09d0-ba19-4c1e-b3ed-fb229bdfee57 | 95,77,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
5b6482cf-4f31-4889-8e25-4e73ec128df5 | 95,80,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
4e611462-d520-426d-a0c9-b4b43c27bd18 | 95,80,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
7990da6a-7586-4cd5-b338-f4a2ff92b650 | 95,80,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
e6f75444-242a-4cc6-8e07-c03db654169b | 95,80,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
0f7e23e1-a0a7-4909-b9fb-f5d1b96f862a | 95,80,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
5adf0d8d-9c31-4d4c-9efe-d36e2899467c | 95,80,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5908100f-fecd-45a3-8723-0466ed306b38 | 95,80,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
94681995-bf2a-4423-a5e8-f0c42ec17d84 | 95,80,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
104d1318-ac11-4a5c-8c97-41166493cb9a | 95,80,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d78feca8-414a-4c47-85e0-f48f33b6a468 | 95,80,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
4072c199-0e4f-49a3-a4a1-32cad64da4fe | 95,80,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9926ec7c-561e-4b11-9545-12eb93ccd31a | 95,80,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
2ceb5169-d7be-4046-a335-7dd07bf11602 | 95,80,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
431b3461-b715-4595-bed6-facb1a11b382 | 95,80,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
63b26e58-bbf3-4381-bdf7-b4e3d4065116 | 95,80,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
05e66c95-b6fe-4233-bcd1-6c753f727b5c | 95,80,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
968997c7-9d80-4938-8d03-280b15e19bf9 | 95,80,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
98e9825e-b00c-4690-8cea-b9bd55a5c0b0 | 95,81,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
41211e48-5598-412e-ae6c-5f832d73847c | 95,81,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3177781b-b864-4a0b-8f6f-de23b5398a4e | 95,81,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
3d3abfcc-14bb-4b7f-bec4-fdc38b9c5113 | 95,81,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
aaf339d2-0760-4b70-ae35-02ac3f3a11b1 | 95,81,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
6e536744-3ce1-45e5-af95-e63cc88a0ab0 | 95,81,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
51483057-7bae-41c1-bf0e-4e4f25a5e906 | 95,81,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
e68a5dc3-7106-4450-8a5c-f4fc1f8fcb06 | 95,81,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
836d516c-8bc5-4dd4-b7b1-944f2d7e09f2 | 95,81,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
429ff9b5-66f4-4828-a760-0398fd19b911 | 95,81,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
174ea6f8-1e75-48a7-82bb-86cd94946c10 | 95,81,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
99caa189-184f-4f13-96db-86221d7eb7de | 95,81,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
d1e646e8-eae0-4f12-82d5-f068e543400c | 95,81,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e9f31233-af25-43c5-84d6-3d8a7caa4163 | 95,81,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
ed2af770-03c4-4776-a4e9-e68da250056b | 95,81,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
3f3dfc06-fdfe-4a87-8c81-9f6eacb79caa | 95,81,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
b9afefe6-0c8d-4586-8af9-fa0d506ce60e | 95,81,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
d3c0e7b2-54d1-4f3e-8bf1-9013ea2b0f8a | 95,83,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
904b5efb-368a-4a7b-9df5-fa92a7c1fd3b | 95,83,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e5836542-ad99-4d08-9a50-27c8a2a4959f | 95,83,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7c73d037-d32a-41e1-bd70-caa5e1e91904 | 95,83,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
dc8247f1-d66c-499a-80e1-06f2e179e2f0 | 95,83,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
fc58cb54-8865-4b79-b51e-0c5fce3db3ec | 95,83,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fdab4348-7e58-477d-a74e-5791f9d9c4dd | 95,83,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
75deb2c6-a535-462f-824d-fc169afb5b76 | 95,83,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
db2a5168-7fa4-4a0f-8645-c2103155f447 | 95,83,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
276ca8ac-02b9-4c1e-b1fe-bcca63773670 | 95,83,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
33a7671b-d280-4776-8f2c-3781e2c89b71 | 95,83,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
3217703f-a009-4577-adce-954dc54e0b3c | 95,83,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
aebdc51e-81df-45be-960f-99b902e8342a | 95,83,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
4ae6eba5-3871-4427-be28-e88cf3eb84e3 | 95,83,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
e8154cf9-9d09-4413-9b15-d39f403ad9ee | 95,83,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
1afaeca0-fa4d-4a51-b191-7fe474c2c56c | 95,83,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
5ce91052-6849-4b29-b4a0-c55fe8af5def | 95,83,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
a37b8184-c673-4be2-b431-b0a92d679109 | 95,93,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 5 | FALSE
07711abb-cb0a-490d-a0e9-224f5a40eb9e | 95,93,74,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
3ac38569-833b-4a27-8245-7b20a7d688ee | 95,93,74,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
e74ce5f1-26d7-45fe-93bf-dd42efa87887 | 95,93,74,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6ff46655-976e-4790-b471-d9bf5ee15903 | 95,93,74,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5cfad456-363e-41e3-ad8c-cdb60b7883c4 | 95,93,74,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
a7b682b6-4ce6-4835-9c68-cc776c71f3d9 | 95,93,74,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
64ee51f4-449a-4330-a035-f12ee58f1fe1 | 95,93,74,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
ddba25ef-0c9e-4236-a772-2bf4240c8666 | 95,93,74,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
112fecc9-1f95-48d6-b7b3-fe4f5fd7acaa | 95,93,74,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
32e8630c-e803-4c3a-9833-17923c35ef14 | 95,93,74,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
d34abcdf-f545-457d-9904-d1d945053d67 | 95,93,74,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
9b56e47d-dd33-464d-93fd-c2d1f7f454e3 | 95,93,74,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
b69c7a72-9c90-48ba-9c74-5d95b08f2dae | 95,93,74,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
0963ae09-0988-492c-a947-8d686a650079 | 95,93,74,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
f64ec92d-8015-412d-b88d-c79819ef3539 | 95,93,74,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
429eb32f-055d-493b-be44-7eb415bcd2f9 | 95,93,74,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
e5ee8e5f-b878-4815-ab01-05c372c635a7 | 95,93,74,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
3a3863e7-65db-4386-bb54-d848e59b7dfe | 95,93,76,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
6245be72-84a4-4132-a7cf-d99995bb0fa3 | 95,93,76,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
23bbcc0a-d8fa-493f-8a36-4a31f31a0063 | 95,93,76,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7eaf7d05-33de-4d61-95fa-b4fe508c5704 | 95,93,76,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e716d104-2781-473a-a9e9-0fd2f5f9880c | 95,93,76,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
08f8c421-582f-488f-810c-d402f148fb95 | 95,93,76,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ba054939-a6fc-45cf-b6a4-91f5d4561c38 | 95,93,76,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
11972d31-5a65-47b8-a2a3-b1b029437218 | 95,93,76,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
aabcb478-0b73-4e4a-8468-9ecc02ddaa91 | 95,93,76,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7ce973ff-22e5-47bd-a24b-24601e660cc6 | 95,93,76,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
16675507-21db-48a2-b98a-189371dcdcc7 | 95,93,76,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
190479a9-0bfb-4cd2-9fe8-33122df1166a | 95,93,76,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
a3beb9a4-7631-44fa-bae8-ddb4e9e95770 | 95,93,76,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
380b5bcf-66f5-4ea2-9797-84e8e28595ce | 95,93,76,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
4f9e5e62-932d-40c6-b544-e90bc81a0188 | 95,93,76,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
98e3862b-b9ab-4b0e-83fe-0a63302f8a17 | 95,93,76,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
8e92727e-5a8a-4b08-89dd-b7e1787381f0 | 95,93,76,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
e9f798fe-f783-4608-bb8d-e63cbe5e155a | 95,93,77,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
fdd24b94-fdb8-4a65-8762-a0cf5f1e4a17 | 95,93,77,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
8e00d9ad-63f3-4356-9140-2ec85204719c | 95,93,77,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
abc5b580-2b00-4f9f-8319-ddd814bda42a | 95,93,77,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
69b60d29-743d-4e86-a206-23a87711f4f1 | 95,93,77,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
30c155ce-7d72-4ce0-81e2-94c875cecd34 | 95,93,77,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
696bd6f0-1631-433a-a9eb-d38f2958cf59 | 95,93,77,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
4c9e080e-4879-475a-ba25-54a9cd59750c | 95,93,77,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
1cb4bd5a-e39e-4293-ae42-b4ccf7c908be | 95,93,77,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
42e3b635-13c0-4d74-bf7a-6c12d3b03637 | 95,93,77,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
91f062f8-ff6c-43c4-b522-a26eafd9608c | 95,93,77,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
2ef7b9c4-d53a-4f44-a286-5c71da5ff847 | 95,93,77,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
1803434f-f997-4cf2-b543-034ff96b783f | 95,93,77,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
c4cb7058-7f4d-4fc0-8c59-fc0d3a2c9061 | 95,93,77,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
0d73e5a9-271d-41e1-bf8c-f8d2cdc7943f | 95,93,77,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
a6e14fe6-cfdc-4ce4-ad0e-64abedc6e1de | 95,93,77,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
fe054c61-7667-42fc-979d-75fa4725280c | 95,93,77,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
99eee5c2-5253-4559-bd62-bb993066b214 | 95,93,80,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
1d316991-81a6-4f03-be31-15c3b3fcf1e5 | 95,93,80,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
482c2141-403e-499c-a724-2b6ec874718c | 95,93,80,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
2efa7c42-7c1b-4667-a736-2f7f8e629cd2 | 95,93,80,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
7623bc40-7571-432c-82a6-8ea4f3f64cbe | 95,93,80,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
f82fbc4d-f102-4a17-9f43-db69a13a9fc6 | 95,93,80,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ca135655-9870-4a89-a9c3-5223d3b84c1c | 95,93,80,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
fb943406-338d-44a9-ae66-6534c84abacb | 95,93,80,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
85194685-b962-498d-9d98-0eb62b3a6d0b | 95,93,80,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
269d5cec-4552-4c71-bcec-f6a0124419cd | 95,93,80,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
00dee8fe-7621-4704-9fbf-6716b3759ff5 | 95,93,80,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d73e7b6e-71d5-48ca-a9b5-e0f1d8d51232 | 95,93,80,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
1bf65aab-20ef-4875-b56c-f0d2b03e016b | 95,93,80,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a3dbc02c-b94c-411f-a40f-d391154e5702 | 95,93,80,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
8752f20e-309e-43e0-988c-72b6a7bbd811 | 95,93,80,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
233eaac6-83a4-49ea-b11a-e18615b7048d | 95,93,80,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
66e0a9cb-8f69-4c19-b8fa-1abb92744409 | 95,93,80,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
e2c09117-305c-4991-9ed1-69989e9bce88 | 95,93,81,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
23c479b5-d53c-4dc3-bcc3-e78c5b4ece52 | 95,93,81,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
17cb9058-99d7-44a7-94d0-ad3610c86246 | 95,93,81,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
27b41986-7b1b-408d-8bd3-cd9a56e49714 | 95,93,81,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2af1f3f3-c7f9-400f-941f-41cc335611a9 | 95,93,81,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
c053c2fb-95a9-4e50-aba1-a15ccb7acd89 | 95,93,81,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
876ba53b-75ae-4f04-bb36-9964d16aaa76 | 95,93,81,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
e640396f-a516-4bdd-9942-24831150d7d3 | 95,93,81,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5852fcf6-99cf-4f2d-942c-810514b807f0 | 95,93,81,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
49e0a880-8d4b-4330-b694-b64f490d73f0 | 95,93,81,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
81a0af8a-7399-4544-947d-2d02241635d0 | 95,93,81,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
4cdf37e0-0945-437d-8ba2-920833bc93fa | 95,93,81,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
d3bdf9c6-0519-40d5-a8ac-70ecab0f0b7b | 95,93,81,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
56524471-0077-40d1-ba75-b16534ef5a9c | 95,93,81,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
70ccb8cd-0176-4fa9-a41a-2b654a89d47b | 95,93,81,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
1333fd35-c5e0-4121-9f30-a18dc4dfa5c3 | 95,93,81,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
4d67ceaa-1560-41f9-898f-d55ac0da98be | 95,93,81,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
940c00f8-2218-4c3c-8464-dc51912d2fa4 | 95,93,83,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
76694da9-1499-405a-a0ea-9a8187647beb | 95,93,83,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ea8214ff-83ec-46c6-b385-9dab8e28409b | 95,93,83,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
0edc3eb8-1c06-45b9-b4d8-6b30b5ceef5b | 95,93,83,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
af73ebc8-8bb2-40aa-9748-ee645cd0d22a | 95,93,83,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
5844be81-b4e9-402e-9636-fe2b4a216bea | 95,93,83,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2ca3df43-4906-48f7-813a-adea7cad9804 | 95,93,83,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
ec84cff3-7b2b-4030-bc1c-746a757f4e19 | 95,93,83,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6eb18061-ff63-4e5e-b928-cbc3f0a17ad1 | 95,93,83,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
9d255939-5c38-4428-94bb-1e648f161a67 | 95,93,83,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
9fdace71-4648-43c3-854e-114783aab5ab | 95,93,83,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3b877ca8-1658-4da6-965f-5b823368b857 | 95,93,83,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
b2ba403a-1a00-4fed-bb81-cdeb33111518 | 95,93,83,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
17dc953f-a494-4200-b2d6-66d1f3ceac2d | 95,93,83,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
851d37c1-0ac7-44f6-9f50-4331f5645a32 | 95,93,83,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
edc1da0d-b712-433b-8e63-d12cbb9871e7 | 95,93,83,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
35fcadec-e917-4f05-ab1b-d88cda4e0841 | 95,93,83,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
614e0e2e-1878-418f-8f18-f9e73834441a | 95,93,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
edc26c2a-1163-4514-9199-5fc43de06731 | 95,93,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
eb85be05-e9e8-46d3-89f6-e0ca6af0637e | 95,93,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
35f92175-6726-4437-9731-5fd29c117c9e | 95,93,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
4a300f4a-f70a-423f-b17c-67be31f19236 | 95,93,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
e2ec7199-7248-4921-8dc6-f71fe2d6c9d9 | 95,93,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
312aecb0-69de-48e3-8f62-5a8fd41e1299 | 95,93,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
75041c79-f7bc-48d0-b5f5-10eb67bfeca9 | 95,93,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9c776731-ea9c-4a49-84ba-ccfef9a348c7 | 95,93,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
0a5e9ff7-d3b6-460f-95eb-99871c3a3a05 | 95,93,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
2c93596b-b529-4c6f-bae6-570fb11d12d9 | 95,93,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
e3076435-7577-4e0a-b309-0a8cc99e55a5 | 95,93,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
db69ca39-dfef-4f1b-9fef-c882b29c4619 | 95,93,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
14ecf7e0-91a4-4b9f-b209-dff02a73bc1b | 95,93,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
2cc5e43a-4a9a-4c9a-b6b3-e8ebce15e81c | 95,93,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
16867655-3d4a-4df9-8a91-17fcee1401ad | 95,93,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
9bca1d38-d7b6-4764-89ba-33ce0fbfd370 | 95,93,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
16637ac4-1a88-4ba0-bd78-c55ed41fdcae | 95,97,93,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 6 | FALSE
ca7905f8-2d19-4cc8-bef5-b607503db813 | 95,97,93,74,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
92c4f779-ea5e-4627-8b33-42ca70e338e6 | 95,97,93,74,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
19e66acd-016f-4c78-9d75-0f4d46fc075f | 95,97,93,74,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1929625a-f5c6-46a1-a41e-88c53142b1f0 | 95,97,93,74,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
bc9dbb6e-6fef-4178-834d-66f3bfa8d69f | 95,97,93,74,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
586a3a4b-b890-4670-88ec-4e1d76059da3 | 95,97,93,74,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
32394595-d3be-45e8-9366-695ec1cac123 | 95,97,93,74,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
cff52a57-5d76-484a-bd65-1275c906fdd1 | 95,97,93,74,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
122ef4bf-5dce-4b59-8b3a-580e3f999045 | 95,97,93,74,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c1d98a41-ef4a-4cf8-a4da-c659da4a652c | 95,97,93,74,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
846a5f88-d056-4dec-9dd3-310a65450cf2 | 95,97,93,74,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
63b1d820-4816-42e8-bff1-4d7853d72117 | 95,97,93,74,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
828d5025-be0b-4e1b-82df-e64623816f20 | 95,97,93,74,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ad16e288-4391-45c3-9af1-81075a3c8e75 | 95,97,93,74,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
ae3757a0-c98a-4752-9273-b4bbc9d360ad | 95,97,93,74,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
502a6800-a21b-4d5b-8943-5cd5171e175a | 95,97,93,74,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
faf030d5-0a5f-4aed-b496-fc413a79ec7c | 95,97,93,74,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
85b1d834-3d7e-4e75-8de1-a003e3ea19bd | 95,97,93,76,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
8cbed7e8-a74c-4d94-ae9d-554a1c3d475e | 95,97,93,76,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
1e0c802f-497a-4c9c-aab5-0fe6fb2d64e4 | 95,97,93,76,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7de365cd-ef14-4976-959c-85185d121215 | 95,97,93,76,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
fac08054-0084-4710-b995-3454af886c84 | 95,97,93,76,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
09aaf92e-aa95-4743-94d1-213a492084e7 | 95,97,93,76,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d83f7f67-ed13-4836-8dce-96f71d44dc5c | 95,97,93,76,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f6fde007-9104-48e1-b6b5-9a684e4e6458 | 95,97,93,76,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
aea12426-372a-4898-856e-e3d9554e23a5 | 95,97,93,76,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
3e1d3ec8-472e-4835-917f-62e787129483 | 95,97,93,76,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
fd5d1eb1-fa7d-4d72-bb7f-b70c8717996b | 95,97,93,76,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b4d0dd9c-baa2-4394-8de5-9d355c55c174 | 95,97,93,76,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9cfe1051-dd6a-491e-8bfa-a09fb46f6215 | 95,97,93,76,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
34aa0636-839c-4157-8c31-51dfd5c3d92e | 95,97,93,76,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
4675ef28-694c-4c87-bd45-29982785fac5 | 95,97,93,76,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
e7f04ee1-56cb-43fe-80f4-f0f2bf769c26 | 95,97,93,76,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
8f6af3fa-8051-49af-908b-e6446bb74eb8 | 95,97,93,76,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
df8294ef-b37d-4c0a-b219-229d6ca10631 | 95,97,93,77,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f06c7d43-d64b-437d-b873-f36eb6892703 | 95,97,93,77,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
2091d7ef-1e0b-4ee7-9121-a3c711c4460e | 95,97,93,77,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
736b2ca2-df64-475e-8a52-36da0aff0570 | 95,97,93,77,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1b633ebb-6a9a-4431-90be-f2fe9aeeaf03 | 95,97,93,77,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
7d7cb79c-6550-4b59-bdb5-7bc6093d14c9 | 95,97,93,77,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
589cae49-77bb-48de-8e70-9ffcfee0fa57 | 95,97,93,77,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
539614cd-0b26-4619-8497-d1054c7eb5ff | 95,97,93,77,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
845860c3-9a01-4470-bbf3-a06073ad02bf | 95,97,93,77,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
85730b8a-350b-4c19-a986-e3f926293658 | 95,97,93,77,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
f238f09f-62f2-4b32-826f-c2dd8f2bcf5b | 95,97,93,77,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
29cecd80-3cc1-4a1a-9e13-64ba04580511 | 95,97,93,77,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
9551c339-625e-4668-a920-2abfdcf17c71 | 95,97,93,77,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a10413d7-c77d-4ba6-bfc5-00c396f6fb59 | 95,97,93,77,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
6d3e5717-0161-4171-868e-5dc20959f0aa | 95,97,93,77,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
dc4a9670-8da4-4caa-80c7-bfc80c82537f | 95,97,93,77,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
7a5fc0a0-c974-474b-a534-da8d9248e237 | 95,97,93,77,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
6fdb760b-78a3-4b84-84cd-f9147891781d | 95,97,93,80,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
21289d6c-a923-4cbd-a824-3ed2ae946adb | 95,97,93,80,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
1d4415d1-3da5-493d-820c-12bbbd330397 | 95,97,93,80,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
5d86185d-bfeb-4787-ba5d-4c480237f0ff | 95,97,93,80,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
de0c1941-b9f7-4380-9c71-f49c1d71e741 | 95,97,93,80,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
713103a4-7599-4374-8bba-38c77bb4bd37 | 95,97,93,80,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
2f06bce1-9e37-48b8-a8d2-31e25121c110 | 95,97,93,80,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c78923a8-94c5-4100-97b4-cf3663828ad8 | 95,97,93,80,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5be43384-add2-40e1-b6de-c7109b64918d | 95,97,93,80,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6c5426d6-bd6e-4f3e-9e99-a4e8453aa15c | 95,97,93,80,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
f4433331-88e8-4873-b633-a117a8189b5f | 95,97,93,80,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
585ad526-575c-485a-a848-ffb031285858 | 95,97,93,80,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
68defbdd-bbf4-420e-a206-e09a3961cad2 | 95,97,93,80,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6b882eb0-0a46-4c8b-b9aa-378bc5d5de71 | 95,97,93,80,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
0d8a68b9-410f-4d5e-a6dd-cb0b552e122f | 95,97,93,80,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
02566b6d-ee9c-4900-b309-d2c92e26f99c | 95,97,93,80,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
08284bfb-970e-4279-bffd-70a4680addca | 95,97,93,80,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
cd717ae5-5501-4e3f-9deb-f7baef79964c | 95,97,93,81,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
6f64f7ba-1d7b-4af6-be37-a97e962e88ef | 95,97,93,81,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
4a0ea8fd-f1ac-4878-9fc2-e3f924a2bff3 | 95,97,93,81,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
82a5f198-ccb2-40a3-9dcb-1fcd95e1ec05 | 95,97,93,81,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c1a6a9cd-4692-4a3d-9952-90e6ddfbc238 | 95,97,93,81,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0fcf54fe-d367-4513-b36e-dc58d3aeb6b1 | 95,97,93,81,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
91989c34-1118-46c5-898c-e1dfd3f63815 | 95,97,93,81,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
58b0f06d-078f-40f5-a639-0d0e3a093f34 | 95,97,93,81,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ec9ad42d-4ce1-4853-9613-6e9159b93153 | 95,97,93,81,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
519b0ec3-2d43-4b82-bcf1-bbf43e7f341b | 95,97,93,81,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
5ea0b10f-8e8e-465a-b366-6a31748b89f3 | 95,97,93,81,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
f69a1061-1d3b-41cc-9607-eabbb021284c | 95,97,93,81,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
bacbe54f-001e-4c6d-a4f6-13dd2eab68f7 | 95,97,93,81,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
c56080fa-1171-49a9-88bd-19a7fc3e765b | 95,97,93,81,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
9ed632eb-5129-4ce9-9884-49d2a019da1e | 95,97,93,81,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
b83522a4-3c19-4e3a-911b-40a69fb9ffff | 95,97,93,81,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
fb48b70a-140d-4b10-a49c-6fe737f0c203 | 95,97,93,81,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
902b3aa5-6439-48b9-bcd6-896684d5d363 | 95,97,93,83,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
a9e903dd-675f-4f47-93b4-2d05ed46668b | 95,97,93,83,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
084ede70-3011-45e5-b1c2-0f3197a42985 | 95,97,93,83,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9b93224d-a9a6-4970-8766-30fc37170130 | 95,97,93,83,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
381f3cca-9dfe-4dd8-920d-009426911500 | 95,97,93,83,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
61f69572-e8e5-4fd5-a1c4-cb02f79fbc83 | 95,97,93,83,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
69436d5b-1716-4e90-a27e-7596d8263a17 | 95,97,93,83,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b6028293-0df3-4578-b43d-8141542daf6d | 95,97,93,83,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5c13a543-1446-453c-8099-f36f5ef37168 | 95,97,93,83,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
07258c4c-aa21-4750-82e8-320998c51806 | 95,97,93,83,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
e92213f5-bfb6-409e-b6b3-24d80afdc4a6 | 95,97,93,83,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
d4cb30b9-bda2-4dcb-a71e-4d41d2eb5299 | 95,97,93,83,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
988c8dfa-ba95-4b08-b9f7-c679f1e5d6f0 | 95,97,93,83,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ce9ed2c0-b3e9-4f1e-b142-eb727cd93fb5 | 95,97,93,83,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
1752c956-0b35-47b7-9d69-ca7a1a6171c6 | 95,97,93,83,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
03cbc468-45d2-4640-96df-1682dbe0e9d6 | 95,97,93,83,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
bf458995-af7a-4b1f-b67c-6cc6d90bb27c | 95,97,93,83,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
55527f7d-ef26-4dcf-9c52-90831de5eaef | 95,97,93,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
1ab4e9dc-4b28-43f6-9a1b-8c7272e1ba0f | 95,97,93,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
cc449a06-316e-4cf2-8ed6-4039908d173a | 95,97,93,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
9ab73d94-cc2a-401f-abf9-7bdf775c4c80 | 95,97,93,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
43cabf12-12e6-453c-8e44-79840fe1a2cf | 95,97,93,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
96418a61-3155-4b44-b4cb-b82d3c2774a4 | 95,97,93,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
133cf06c-0fa5-48d0-936c-85dca87ddd6f | 95,97,93,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
1e152fa9-5f4a-4e48-b9a1-7bcb8ef24764 | 95,97,93,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
c46cf7a3-160e-418a-a707-1a9756481986 | 95,97,93,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
25527d29-faa5-4c7a-8c97-f5bf71046136 | 95,97,93,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
0b7401f6-44f5-48b0-ae94-88eb270f200f | 95,97,93,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e523fc0d-c5cc-4914-b6d1-da88468b460f | 95,97,93,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
08ceb2d7-fdc8-4a89-8347-8ea5e6411666 | 95,97,93,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
ba7b12a7-9392-4925-be7b-5ef98a9d84da | 95,97,93,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
7349d087-009d-4802-8745-ac41d8c51740 | 95,97,93,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
0ec13c9c-6ad0-43d6-8ed8-cd361724c7a3 | 95,97,93,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
e9c8dacc-4bf6-46d1-8c76-dfe27976ffa2 | 95,97,93,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
a2b19884-ba16-4924-8145-041d09cdecbd | 95,97,96,93,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 8 | FALSE
cf258b79-babb-427b-8c99-dafbe816e64b | 95,97,96,93,74,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
ebc0eb1c-cb68-484c-aa03-25f5c0908255 | 95,97,96,93,74,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1c1fe4cc-472e-4ef9-9401-408ec8363819 | 95,97,96,93,74,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
21c34dad-6626-4dfc-aa6e-e515b798e6a4 | 95,97,96,93,74,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
fdb01777-ab86-470a-872d-aa0118b3f00a | 95,97,96,93,74,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c6789c19-04cd-4430-ba6c-e4be10688b8d | 95,97,96,93,74,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2102d929-5e6e-48ce-ab7b-22e26ff53551 | 95,97,96,93,74,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
cf1c0c18-1d3f-451b-808e-d24842a7ce13 | 95,97,96,93,74,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
dced3a97-1491-45bb-933b-a842725530ea | 95,97,96,93,74,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8ad6ac29-41fb-49f0-be97-199e0940151f | 95,97,96,93,74,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
ce1d2dc4-b592-4e48-b34a-a82cc1a2f72d | 95,97,96,93,74,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
0bea7f64-46e0-4a89-80ab-a2090b436adf | 95,97,96,93,74,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
a4ef781f-60c9-4a71-9a0a-4132a91679c7 | 95,97,96,93,74,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
f6f663cf-5ac9-4f5d-abd9-fcd0acc6515e | 95,97,96,93,74,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
27d35108-28d4-4645-a9d0-e8616dfc8157 | 95,97,96,93,74,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
2c1b56e6-ad0f-4ab7-a9a4-b33103ee122c | 95,97,96,93,74,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
5537eea3-bfa9-4930-9238-d9e02b7402f8 | 95,97,96,93,74,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a3b296de-ee5a-4ecb-8349-6b5452317358 | 95,97,96,93,76,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
47a496d7-fefc-479c-9e86-41b469a49610 | 95,97,96,93,76,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
85c77dbb-5de4-42ad-b0df-a4ef696662a1 | 95,97,96,93,76,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
b0245999-7906-4853-8077-69f6cc4433c8 | 95,97,96,93,76,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
71f0614f-8b7a-4e06-889f-556522dd7e72 | 95,97,96,93,76,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0fd31804-3bb9-40f6-9bf9-9c6ecf3650a3 | 95,97,96,93,76,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
4fb0325d-06f5-4ca0-b32c-a9387fbd9210 | 95,97,96,93,76,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
208704d5-e58a-446e-898d-951af2ab7ecc | 95,97,96,93,76,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6b751933-8fca-479c-be8b-b88ded138002 | 95,97,96,93,76,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8b1ca70b-44ae-4495-adcc-36888fe0a36a | 95,97,96,93,76,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
bd9c9742-7417-412a-b102-1fc8ed8bd286 | 95,97,96,93,76,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ae86c5f1-9ef7-4049-abd1-7bc4bb88c032 | 95,97,96,93,76,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
46404b24-6454-4919-b0b3-9a4ef8075179 | 95,97,96,93,76,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
4ea0afa2-1709-4c97-8efb-e52f34ced4f8 | 95,97,96,93,76,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
1ae518cf-d702-4756-8297-bfceabd9e62a | 95,97,96,93,76,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
d7742437-897d-434d-ad7e-a85cbf81dc4d | 95,97,96,93,76,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
248cc303-c3bc-423d-b81f-c5c5bef9767c | 95,97,96,93,76,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - FRONT BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
6feaf0f4-44e7-417e-b93e-0bcde40b2d0e | 95,97,96,93,77,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
7f7c333f-1a30-4a4f-a276-ab7b0bfa6b86 | 95,97,96,93,77,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
97186b87-bfde-47ac-be7a-18c4d20ecd54 | 95,97,96,93,77,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e4875d37-06c7-44b7-bd0f-adafcf6dff72 | 95,97,96,93,77,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1962d16c-97db-4064-8245-a13599a9a8ba | 95,97,96,93,77,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f960597c-177a-45fb-bb8e-4684ed0cbb0f | 95,97,96,93,77,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
efcb4108-cd50-430d-a1f8-995d3c8de632 | 95,97,96,93,77,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
834e1f63-fbd7-4013-a2a0-5140fee7ab82 | 95,97,96,93,77,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
8a153c69-83c8-4eb2-a681-95c080608cb6 | 95,97,96,93,77,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8e92e722-3351-48f1-9830-2eb344bb9cdf | 95,97,96,93,77,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
72270f57-9238-4055-821e-2be4aa8beeb4 | 95,97,96,93,77,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c74269f3-fc79-4d5c-9f02-9372ce5f4342 | 95,97,96,93,77,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
87d8e2fe-9731-4ab7-87d2-316f5f44c647 | 95,97,96,93,77,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
742c830a-c1b9-4b7d-80a1-80ba17d1ac23 | 95,97,96,93,77,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
0cdb8bc0-8d93-4702-8718-87893aa05028 | 95,97,96,93,77,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
530ced35-d52a-40a9-a61e-81c262148559 | 95,97,96,93,77,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b3fcbca8-7e52-4b5f-b94f-4aeea1851d24 | 95,97,96,93,77,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY CHASSIS BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
b91bf33d-d6e9-4967-bbe1-748499460112 | 95,97,96,93,80,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
37f4d18e-328a-41be-a7d7-c5e7f4767db4 | 95,97,96,93,80,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f995d89c-0daf-461d-b126-bb613d26d6f6 | 95,97,96,93,80,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
835a7a58-1a35-4da3-b82e-ff6d9c56c525 | 95,97,96,93,80,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
51075add-2196-447c-9b0c-882ca1cee5c6 | 95,97,96,93,80,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a72aea3e-e8d4-4e57-838f-de70b1007df7 | 95,97,96,93,80,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c5a8fd84-3c17-4a51-b5a7-2fd61f1d7a77 | 95,97,96,93,80,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
afac53b1-ecc6-4b7d-85db-f2bf8b01401a | 95,97,96,93,80,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6e7b9d62-5e77-42de-9912-9b8c6b07bc8b | 95,97,96,93,80,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
18a75571-7e46-4dd2-aa3a-22df6ba0c18d | 95,97,96,93,80,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
52d2a71f-b90b-4e8a-a46d-edf644d43124 | 95,97,96,93,80,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
d5c26eda-2975-4012-86e2-d02553618a9e | 95,97,96,93,80,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
97bcc423-34a2-462e-8c1c-4a214e4a4a14 | 95,97,96,93,80,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
002fc3e7-e2c4-47cd-be92-828871f97813 | 95,97,96,93,80,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
8e997e06-1d36-4129-a0dc-4eb02c531d58 | 95,97,96,93,80,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
7eb94796-4282-43b7-94b7-311afa231b84 | 95,97,96,93,80,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
472002cb-7519-4005-ac82-beae225fca9c | 95,97,96,93,80,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1427d020-6065-4c37-86a8-343b035aebd6 | 95,97,96,93,81,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
09fba07e-92c8-437a-a208-6a5d38e13836 | 95,97,96,93,81,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
62b6fd28-c417-4ae5-884d-6bf4cec6daeb | 95,97,96,93,81,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
52eb43ec-56e7-4dc3-9271-97af57c0e79e | 95,97,96,93,81,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b5e75b15-e5fa-42e1-a297-6616cf780532 | 95,97,96,93,81,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
c8c5e336-706a-4486-b74b-285741fb486f | 95,97,96,93,81,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9268ba28-3526-46c7-a52a-260fd80d7751 | 95,97,96,93,81,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
21d2c8e0-1df3-42de-910b-f0c37b7dd3aa | 95,97,96,93,81,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
41a8739a-45d2-46f7-8b8b-b7f097f30b42 | 95,97,96,93,81,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1670e7f7-377d-4e4b-bc37-e425e54548ca | 95,97,96,93,81,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
927ec941-ce34-4261-a56c-a5dca5fd7c2b | 95,97,96,93,81,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
436f0e6a-be6f-428c-8210-eda06f86b816 | 95,97,96,93,81,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e5f8b111-4fd7-4300-aa56-fa67f63fff2a | 95,97,96,93,81,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
6fe54bbe-1619-47a6-b344-b570bd2bfb9a | 95,97,96,93,81,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
b9fde02d-dd46-42f3-a250-95739ee56a74 | 95,97,96,93,81,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
e940fec2-46fd-48e4-889c-705bda0f3cf0 | 95,97,96,93,81,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
85a88ce9-bc1c-4d48-8dcc-46784baf50e8 | 95,97,96,93,81,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR MASTER CYLINDER RESERVOIR (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
0b775d98-67b1-4048-8ad4-d8e661a95443 | 95,97,96,93,83,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
0502c1bb-9b2e-45ed-87f0-cf9593c3e608 | 95,97,96,93,83,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1884b672-a033-48a2-9077-22fe0bb86095 | 95,97,96,93,83,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
52ba0306-b490-4d23-9344-23cb9bfcacc6 | 95,97,96,93,83,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d17946ec-52b1-4484-8383-accd66cde8e3 | 95,97,96,93,83,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
b15abe73-29a5-4a95-bd93-78567520fdb3 | 95,97,96,93,83,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2c828b8a-76e6-4c90-abb8-fa7c271a807a | 95,97,96,93,83,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
19dc71f4-cc7b-412e-b1df-02135311ef2b | 95,97,96,93,83,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
a992d6a6-bb0a-4bd8-9dfa-efc4fe89e0e6 | 95,97,96,93,83,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
c827d11a-6539-4d58-926d-adc5081284e8 | 95,97,96,93,83,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
9f9638b5-7ae0-470b-8bdb-b2fa956d8048 | 95,97,96,93,83,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
78a8107c-85ed-4dc4-9805-2d60ca1a0b30 | 95,97,96,93,83,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
7cb58ab9-9fbd-4c0a-954c-52a1281211b1 | 95,97,96,93,83,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
aaf39f0a-9711-48e1-8854-d334c918ae7b | 95,97,96,93,83,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
41e90f5c-eec8-4526-8b55-6358a053c876 | 95,97,96,93,83,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
3e1a12a3-d4f5-480e-90ed-3db33b77f3da | 95,97,96,93,83,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
74976d06-fe15-4cb3-9742-63c8df727925 | 95,97,96,93,83,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - REAR BRAKE LINE (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ef1f7907-6bdb-4624-9adc-79a427d5986e | 95,97,96,93,2,16,21,22 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
4f320a2e-ab90-4a4b-bf58-188f9fea37d5 | 95,97,96,93,2,16,21,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
ff98ad6c-3237-45c2-99c2-0d654acf5a7d | 95,97,96,93,2,16,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
be81b127-31d7-4ba2-8b9b-ddb93b5ff239 | 95,97,96,93,2,17,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
442f3e5b-9414-4e4e-8ed5-dbf65f093ec4 | 95,97,96,93,2,17,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
d864abf6-3452-498d-9041-42ba0f1420b4 | 95,97,96,93,2,17,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a99f7a37-d00b-419b-a4f0-017302a9d1ae | 95,97,96,93,2,18,19,20 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f1a1ae6a-e93e-42e1-a4a0-c7f6cf528ef5 | 95,97,96,93,2,18,19,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
a6145156-1aa6-48e1-b71d-8e8b4aaf4e90 | 95,97,96,93,2,18,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
75186d6e-e61e-40ed-b6e0-8c9761ca9572 | 95,97,96,93,2,35,25 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
b626301b-0560-4163-a828-8e8217e8d47f | 95,97,96,93,2,35,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
78f32e2f-22ac-43a0-a0c6-2957d0918037 | 95,97,96,93,2,36,26 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
5181567b-ab22-4ff2-ba52-ec5af781c987 | 95,97,96,93,2,36,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
1182a722-7fa0-4940-bcf4-88284a8bdf9b | 95,97,96,93,2,65 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
383142b4-f280-42f3-b591-bf1ebf23ebf8 | 95,97,96,93,2,73 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8dee3ccc-60df-4e0e-a4f0-97776a824cff | 95,97,96,93,2,101 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
aa1a0d27-b3eb-4a84-8aba-5db505b1a94c | 95,97,96,93,2,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - PEDAL BOX (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
bd2bcb36-07cb-49af-8e26-f880fc633320 | 95,97,96,188 | ASSY - BRAKE PEDAL (1) -> ASSY - PEDAL PRESS SENSOR (1) -> ASSY - PEDAL BOX CONTROLLER (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 6 | FALSE
0f5baab5-fdb4-4480-a2fa-67b3fd43b13d | 99,98 | ASSY - SUN VISOR - LH (3) -> ASSY - CEILING (4) | 7 | FALSE
ce2cae91-7f86-4fd7-9901-9eeec003a1db | 100,98 | ASSY - SUN VISOR - RH (3) -> ASSY - CEILING (4) | 7 | FALSE
1dbd279b-ffb7-452f-b953-56925e65fe8c | 102,101 | ASSY - CENTRAL DISPLAY (2) -> ASSY - DASHBOARD STRUCTURE (6) | 8 | FALSE
df04395d-6868-4c6b-840d-92931e11f437 | 102,188 | ASSY - CENTRAL DISPLAY (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 4 | FALSE
5759eecf-e2ab-43a0-adcd-a187ffafefa0 | 104,101 | ASSY - HEADS-UP DISPLAY (2) -> ASSY - DASHBOARD STRUCTURE (6) | 8 | FALSE
2e1140d0-4ab3-4a0b-8885-ebf174be4b16 | 108,2,16,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
d82cbaf6-2a30-48d4-9055-b3dcf9c24e5d | 108,2,16,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5b6d0b71-8098-452a-9091-bf9d4df1ec6c | 108,2,16,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0f53861a-205d-4902-b886-108a544f8242 | 108,2,17,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
7e3d5504-269c-4672-8d05-796b953f1729 | 108,2,17,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
ee0a3ac7-afd4-4db2-b63a-87fad7f2e919 | 108,2,17,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
e63a3151-f764-4b74-8e15-ae361b5eb7b1 | 108,2,18,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
fe185db4-40f3-4ee0-8dcd-bcbbcc7f8789 | 108,2,18,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
567470cf-304b-43c5-afd9-297043a5ce3b | 108,2,18,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
1ecdea6b-1df8-4916-b813-0fd0312a613a | 108,2,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 14 | FALSE
25564899-1afe-4e94-b6c8-ad94a25580a4 | 108,2,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
65eec7ea-298a-405d-8165-8b24ca5437b4 | 108,2,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 14 | FALSE
c43e615b-f595-4e49-9d02-79f46283c9e6 | 108,2,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
e21038da-f5f6-44f3-a6fc-80360cecbd4f | 108,2,65 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 11 | FALSE
9a6527a3-b06c-481a-8b6a-4c681dc2e736 | 108,2,73 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 11 | FALSE
713ee81c-9545-419d-8ac3-b93706b8da9c | 108,2,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
ddf20b3c-bf70-4108-b14c-02b77cc43c12 | 108,2,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
831706a9-c09a-4549-9fce-c60d5b54e247 | 108,111,2,16,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
0218ecef-5a9b-46e2-af6e-41723b5ca19f | 108,111,2,16,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
2790a15f-f5df-40bc-a580-322670ad0d61 | 108,111,2,16,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
48b79aad-d774-47e2-a4eb-51f4cb027d5a | 108,111,2,17,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e39626be-4265-42f2-925f-ca8e0cf8ed83 | 108,111,2,17,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
cc17b9ce-ebf0-475e-972e-64320a63ebe4 | 108,111,2,17,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
0c09ffc9-67af-4e45-8c0d-7c48372def74 | 108,111,2,18,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
91791205-4f5f-47da-8f1f-4d80be488b40 | 108,111,2,18,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9bd02ae0-df0a-4bd6-a8d5-65c0d114ce57 | 108,111,2,18,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
7061bbd1-a136-4bbc-acc7-e1d557bebfef | 108,111,2,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
cd154bbb-9d96-4493-888e-26eb5f278182 | 108,111,2,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6bb4aa70-df76-41f5-9bf1-54336837386e | 108,111,2,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
22bea878-129c-4305-a0e0-dc843ec5afce | 108,111,2,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
377ada08-d983-4b8d-b4bf-b2c8f4cd422a | 108,111,2,65 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
a4096643-7732-4018-95b0-237a8086e341 | 108,111,2,73 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
eefde537-4940-4141-9857-72f9a955f7a8 | 108,111,2,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
71d3282f-0f97-463a-afb5-410296149513 | 108,111,2,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
1b1219db-a1d9-421b-bae9-223e01a246f6 | 108,111,1,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
50ca1e55-3270-4437-9b33-0ccbf234b8cb | 108,111,1,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
d92b4eec-1b01-4792-b2a6-d3f045063c7d | 108,111,1,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
fed3d909-975a-43f7-a1ea-d6a2026ad0fb | 108,111,1,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
12957917-f508-4d82-82bb-ee43b1d943fa | 108,111,1,98 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 14 | FALSE
5cf18c01-dff5-48b0-846c-f1d7abe0c010 | 108,111,1,44 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 13 | FALSE
60e3a9b6-b030-4b7a-ab40-5d0f3700feef | 108,111,1,47,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
d10f7a82-58c2-41c6-b48c-e4067b98761b | 108,111,1,47,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
30a7ef6c-7cd7-4d42-b121-bb35cfe146d8 | 108,109,2,16,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
415788d9-d0d3-4385-93dd-1f93e13f1601 | 108,109,2,16,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
671795b5-ba57-4541-9a44-7d2fa380aae4 | 108,109,2,16,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
25d31331-e4da-4a55-acf6-f0452df662d4 | 108,109,2,17,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
209e19a8-2fa5-40f7-9955-86e200a738c7 | 108,109,2,17,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
a2f41fae-e223-4473-9789-3317190f8e62 | 108,109,2,17,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ae4d4243-9054-469d-ad3c-941f4e88b9a6 | 108,109,2,18,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
e15654e0-58ea-466c-966a-c23cd19c22fd | 108,109,2,18,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
b0a45a5f-3a9c-4154-936e-5891267271dc | 108,109,2,18,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
1b9aa708-9258-4fba-b2b9-da7acd6324f0 | 108,109,2,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
4176014d-efe4-46ad-95b9-cba3681649a3 | 108,109,2,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
e6a3115a-a87a-4159-8274-dd38474b6a0a | 108,109,2,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e49edc32-b19d-4f01-9d11-11ef92ec55e7 | 108,109,2,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
14ca4064-ea70-453e-abf8-cfff9278a98c | 108,109,2,65 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
d0140966-7344-4b4d-a401-93117fec9383 | 108,109,2,73 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8bcf7ad5-0947-41cb-9783-4b16e429b2bf | 108,109,2,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
25dd8bed-275d-4256-9e47-1aad65ab5244 | 108,109,2,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
2803c6b6-f75c-4e99-b090-ff7ae284bc55 | 108,109,111,2,16,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
44998761-703b-4c46-ae5f-52c6d8434af7 | 108,109,111,2,16,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
e41a3763-a58e-45ec-baab-224bb31612a7 | 108,109,111,2,16,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
88caa1f3-8043-4f63-9464-7a2671632441 | 108,109,111,2,17,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c509fb85-9198-4d5f-a72f-e2a47bc16b58 | 108,109,111,2,17,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
12364b2d-dd22-4d65-a13e-3b9b29d6f255 | 108,109,111,2,17,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
e28e62ee-3c16-440c-86f6-8b66be310e3d | 108,109,111,2,18,19,20 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
adb3d400-491e-457b-8f7f-1e97214699a7 | 108,109,111,2,18,19,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
67d5bf43-1a99-4556-82c6-ad845b7887e0 | 108,109,111,2,18,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
9e289d99-0097-4be4-bef0-a943ed2788c4 | 108,109,111,2,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
dc7b906b-036a-471e-8ec1-833008d90471 | 108,109,111,2,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
561f3c5f-4303-49da-a6a4-8920a2088863 | 108,109,111,2,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
8ee96f8c-ea51-45fb-a95b-412dba6af520 | 108,109,111,2,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
e45e762a-235a-4542-ae49-1cc1053919ec | 108,109,111,2,65 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
1a4a0680-e337-4f18-a01a-549569b9163e | 108,109,111,2,73 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
e25c8239-40a9-40aa-ad49-666bcabb2667 | 108,109,111,2,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
64d39039-d5c3-48a3-8905-d5346b4a9121 | 108,109,111,2,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9e3e4d28-6b08-441e-880a-24ee3366e179 | 108,109,111,1,35,25 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
c287e28c-39f5-4dba-ad4a-97e37cab3a06 | 108,109,111,1,35,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
8a0981f6-fb6e-4662-b61a-acdc25d58d8b | 108,109,111,1,36,26 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
3a182a0a-9fc8-4a2b-bfb4-e4d79f911b35 | 108,109,111,1,36,101 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
87ef3187-4cb7-4789-9e19-3fdc066aa803 | 108,109,111,1,98 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 18 | FALSE
da6cc9ee-0849-4f44-9783-165ed7cd5bdf | 108,109,111,1,44 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 17 | FALSE
cc67fbfe-462e-4927-a1e7-e045bfb614fa | 108,109,111,1,47,21,22 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
f956166e-d775-4a64-af10-83809c3c1d78 | 108,109,111,1,47,21,188 | ASSY - FRONT SEAT PASSENGER (4) -> ASSY - FRONT SEAT MOUNT PASSENGER (4) -> ASSY - FRONT SEAT BELT PASSENGER (1) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
eeb096c0-75b3-4469-b373-57d19f3a6022 | 112,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
98be4370-d410-49c2-8f88-c3c160e7532d | 112,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
cb2f5ad8-df66-4785-8ac5-82ae9d62d6b8 | 112,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
4bd18eb4-0ae9-401a-81aa-6f277867a923 | 112,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
1fdfb7d8-25ba-4ffa-8f07-12e89943e947 | 112,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
e72099fa-6cd2-41fc-a0b6-ceb9a4795c8b | 112,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
360ba58d-aa34-4c86-91eb-79a82ace9200 | 112,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
0090a15b-1cad-4ffe-ab2a-2b958eef6686 | 112,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
fdecd336-a76b-4344-a632-ea53f42f11f7 | 112,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
33c151fd-d2d4-4ba5-870d-6a33e2d1300c | 112,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
b2ef7c8d-a734-462e-bef1-5871b589dfae | 112,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
027cea90-33df-4d12-b972-4cc44aee371f | 112,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
63154b09-834e-4222-b6e5-eb8234cb32d3 | 112,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
d95d8f31-681d-4c74-8e33-4424ceca6a23 | 112,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
a8958b06-319b-448f-86f4-98bec5f79016 | 112,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
26614a82-a0f2-4f22-a88a-4ad0fff63d70 | 112,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
1db62bdf-7f31-4bf1-b7be-ce47f9f97336 | 112,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
044b2924-ae00-47f2-a45d-58b1c77bb0a0 | 112,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
de484bd7-932b-4600-89f2-9b78f36a575d | 112,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
109221f9-2632-4842-8de2-6a5d59e648c2 | 112,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f685ce6c-d5e5-455b-a1f7-580ce2f975e0 | 112,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
362cf3ca-2620-4d0f-a686-c73894cba8fa | 112,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
0109a1e8-c008-484e-ba00-3a501ce70538 | 112,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
3fc8aaac-76e8-4cc4-8aba-5d7252ac1ba3 | 112,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
46b03fb4-24af-42c8-9b0b-78a5cebade8b | 112,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
03fb458a-4412-4179-8548-52f64afa5e25 | 112,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
d191a705-768c-41ee-a38c-171682f04db9 | 112,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
6a376221-e9a2-4c25-a736-20a12836e991 | 112,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
a1ce2df1-576a-41c6-a046-581dd86aa48a | 112,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
3b2e3a32-9be2-450e-97b3-aad322afd877 | 112,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
fc9a1f02-dc03-4d6e-bcea-ad4d7e79235a | 112,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
790019cd-2805-40d1-b70c-4ee74f3d8a2b | 112,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
954bcc54-c376-459d-b587-683448c192ec | 112,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
3fd4bdb1-aefc-4f0d-aa14-17883492d368 | 112,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
1c7cab20-156f-4c68-893b-83510d9c4a2d | 112,12,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
ceada1f4-ac33-44dc-a6fa-d8d2d2ed3d59 | 112,12,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
3c747da6-0cbd-4c0d-a104-48ad7d12e7a4 | 112,12,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
d5b4cfd6-467c-48ac-a127-5e566b106a97 | 112,12,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
2d0c72a1-d044-46ae-a513-fe542fbdf280 | 112,12,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
e05fca97-80ae-4c0e-b9d6-ddd4d6779e1c | 112,12,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
8cd4b074-4272-4718-b2b1-52ae07db0557 | 112,12,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
0be66f55-f6b9-4f3d-b08b-8cb53e6341db | 112,12,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
48801102-2d25-4026-8e55-2acc224e8b1b | 112,12,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
17bb5437-089a-4aa6-9f4c-203eb35e132e | 112,12,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
e0fb178f-8199-4d5b-a823-7218d51dce07 | 112,12,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
306f9cc2-26f2-484d-bb02-2ba21c3474fd | 112,12,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
7937df80-6897-48ce-8966-eb7c988b396d | 112,12,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
e9862f79-a2f5-4d7e-af5c-662f8287f483 | 112,12,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
cf9ecb4e-0ed2-4b06-8489-208a451e3be2 | 112,12,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
f8be4045-eaa9-4618-a10b-65984f33a947 | 112,12,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
1c5b8afb-a82d-4ce9-b574-2fff7c77e6b8 | 112,12,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
a1b6c53b-5b66-46a9-8195-d0b1f2853fd6 | 112,114,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
b4e217a7-8099-4caf-b818-fc406ac45eea | 112,114,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
76168c71-ccdf-4ee0-b1d4-2fe5b2374dfd | 112,114,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
99aad1b8-2d76-4470-97a3-b252f37bfd32 | 112,114,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
ac8b74fc-9cf6-4983-9991-c1d741c78f53 | 112,114,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
cf1196aa-4aa2-4a55-9b0e-1ce3a3ae1174 | 112,114,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
f8a36968-900f-4c05-92c0-e9121ae4ebf6 | 112,114,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
8a250bf1-9f2d-4c38-8174-a45abad435f6 | 112,114,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
cb5832ab-a48c-40c4-9914-3f90542f0855 | 112,114,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
88f80d7c-f2ff-45ba-a9cb-40b6ebe87739 | 112,114,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
358ad268-03c8-4fba-a31b-e6c39718d66f | 112,114,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
bca4722b-7224-428f-97cd-0f40d977214a | 112,114,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
75fd09f8-90a8-4dae-910a-932981b9ee76 | 112,114,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
621e9cd3-e590-47ce-b9df-c4463c1ec066 | 112,114,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
b5a5ff4f-298a-4385-8a62-fe62a95dcfa6 | 112,114,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
c0b6454e-e7c9-40df-aa55-7c612f09d910 | 112,114,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
e8182d25-325b-421b-8beb-f8a06ab61204 | 112,114,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
a96a8bb5-be27-42bb-adc7-9b2cb3f3060b | 112,116,118 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - INVERTER MOUNTING FRAME - LH (6) | 10 | FALSE
165ead2d-b23c-4ce8-bfba-95080d5ec8b8 | 112,116,120 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - PWT HV WIRING - LH (2) | 6 | FALSE
bcd570d9-a34d-4e70-b977-51be84db8092 | 112,116,182,12,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
da881e98-7085-45bf-8422-cd7c1ac25468 | 112,116,182,12,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
06c71965-c8bc-41ef-8c78-eb9dbdfe34ee | 112,116,182,12,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c4a886e6-df04-4cb0-af14-e28fe9a8ec19 | 112,116,182,12,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
a7551323-c25b-46fd-8460-1822b750f56f | 112,116,182,12,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
7a8914b4-03b2-4fac-97c0-a5536504ba77 | 112,116,182,12,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
8c5bcee3-20a7-407b-b384-b4b6908ab5f3 | 112,116,182,12,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
dce21b04-1624-488f-8355-da5745969096 | 112,116,182,12,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
26de3b19-a8b0-42cd-a70e-578d17cbbbd7 | 112,116,182,12,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
b1bf5d77-81a8-421b-9eb2-67453d229c79 | 112,116,182,12,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
4a590f74-ccfa-4608-b028-44f3d70f4f31 | 112,116,182,12,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
7a892c5d-c3df-4219-8a96-e1526c2c17a7 | 112,116,182,12,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
cfce50b5-3844-45ce-bc21-98e34739069c | 112,116,182,12,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
6b916020-e4fd-46be-b649-9cc94c281cee | 112,116,182,12,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
0060b77d-92ab-44db-9ea6-82fa93938788 | 112,116,182,12,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
c62805f9-90be-4b4e-8a79-48d3a0a78536 | 112,116,182,12,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
b81b1b52-b6f0-4da8-98c2-e99e08a7461a | 112,116,182,12,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c862ee89-9427-4245-a0d8-f8c319e4dc2d | 112,116,182,183,177 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 4 | FALSE
7b441f31-029e-45ac-a3a5-2129bda3adc4 | 112,116,182,183,187 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 4 | FALSE
b7d8c366-0a1a-489f-8709-a48577c06f3c | 112,116,182,184,185,178 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER - LH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 4 | FALSE
b6cc2b3d-2bdb-417b-93a6-719b6af68759 | 112,118 | ASSY - MOTOR UNIT - LH (2) -> ASSY - INVERTER MOUNTING FRAME - LH (6) | 8 | FALSE
0d418f22-6dcb-4892-a4cf-478375dcc0d5 | 112,120 | ASSY - MOTOR UNIT - LH (2) -> ASSY - PWT HV WIRING - LH (2) | 4 | FALSE
32152d93-42b7-4a0f-96a2-43e05888c915 | 112,122,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
f09b7ace-1d70-4d6e-8d19-4f82048050d4 | 112,122,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
3cb65def-7e4f-4ffd-8fdb-1869068bdd7a | 112,122,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
0d63f33c-2dae-4123-bf0d-54e9cc45d1c3 | 112,122,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
4068a317-372d-448c-b3f0-6cda33e19e9c | 112,122,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
2bc6950b-8879-42cf-bc09-71f67aec7905 | 112,122,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
7f319404-e6d0-40d9-9f05-2581aad46920 | 112,122,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
e65624cc-f7d0-40ac-a60a-f28922e959ef | 112,122,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
4971c7e7-4d90-40d9-865d-625fa60a6da3 | 112,122,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
6783a3f3-2648-476a-9216-ac2469db170b | 112,122,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
acf46f2f-07b6-4b40-9cf5-bcce4c96feb8 | 112,122,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
bb43614f-1ca6-4b11-b7f4-ff44e71c6834 | 112,122,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
cac56ae1-d738-4478-bd69-3e0d21bea217 | 112,122,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
68121d1d-4d92-4e20-83da-77bf4fa2e0ac | 112,122,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
4628ce67-7d54-444e-9c3c-e532421437ad | 112,122,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
734b06da-9ec1-4a75-b387-9067adc983ec | 112,122,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ef90dc87-82c4-4057-8f5b-c44d3545b3d9 | 112,122,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
5a96c414-145e-44f4-aa6f-19fe794ea136 | 112,122,114,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
c5fa86db-49d9-4186-bb99-94c1e47d72dd | 112,122,114,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
acbb74b6-7ece-4d86-9fd6-10469b9a0958 | 112,122,114,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
7cf15e1a-25cb-41ae-a827-edf6fbe09f2a | 112,122,114,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
cc037172-02d6-4ea5-b446-e357f21199df | 112,122,114,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
46b74f99-6ef4-4d03-bd55-42e05e809f37 | 112,122,114,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
32d91e96-1530-46bf-bfdf-629523f20707 | 112,122,114,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
cbf7c31d-5092-446c-970f-67f597cb11e6 | 112,122,114,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
1026def5-a7fc-41fd-b2e8-a7328098d569 | 112,122,114,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
d6b62b4d-53ac-4526-9f32-b8fda2b1ea4d | 112,122,114,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
e7268e0b-7723-4c89-a41f-fdfd7f801770 | 112,122,114,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
bef0fd49-4722-41db-a1f7-a9875c9abc3e | 112,122,114,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
ad02888e-3240-4261-9bdd-6d3b542ed137 | 112,122,114,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
a9f303b7-d45c-4151-ab87-8055e636457f | 112,122,114,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
0542263f-438f-423a-9387-f70abaf2024b | 112,122,114,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
73a32800-bf76-4555-92d8-9406dae48ef5 | 112,122,114,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
5af86c98-6bec-47ed-b533-2b9676a86d75 | 112,122,114,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - MOTOR MOUNTING FRAME - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
149d872a-5dd9-4604-ae50-17ac74bfa7de | 112,122,124,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 31 | FALSE
85182c6c-a7dd-48ef-bcec-655a8cd8c3cb | 112,122,124,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
1298dd58-0745-4df9-b549-202cd308b6e4 | 112,122,124,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9250b9aa-fc66-443d-ab4e-7422a0978615 | 112,122,124,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
a8fdc8ca-f41e-4b61-a785-85dbbee7c1b2 | 112,122,124,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
4eaf7f3d-48ee-4b23-ab18-b8c92e831ed0 | 112,122,124,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1684bf8e-c3fb-403d-bf56-e9cf5314d9ac | 112,122,124,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
c186a8e6-cb76-4585-a20a-139a2091be06 | 112,122,124,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
f730d327-6d95-43f7-8928-25ebded32827 | 112,122,124,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
7df065c7-f952-42e9-bdf0-dfc2b4ef60d6 | 112,122,124,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
b341b607-cb63-4ee0-bf87-1e2bcb878ffe | 112,122,124,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
82589555-fed9-4041-a726-c368432e77ef | 112,122,124,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
e18c28f1-3647-4105-9277-0bfabde627e2 | 112,122,124,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
02c57ced-11b4-4189-a603-d96dfaa78a2f | 112,122,124,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 18 | FALSE
9d374d3f-9897-4fe8-8528-bc43dd991b7d | 112,122,124,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
ea649b3a-ebb8-482a-be44-5d6246fbb8c2 | 112,122,124,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
ad74f302-85d9-4106-8a62-8083df2dfbf9 | 112,122,124,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
0c08853d-28b8-4c7e-bf61-b2a8fea83932 | 112,122,124,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
4078a239-2ee6-4574-b405-034887fc931f | 112,122,124,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
141b3dd9-ba97-4857-a880-a0f0cb0bf4c7 | 112,122,124,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
ae2cd841-65b7-417c-a17a-b60a1e75420c | 112,122,124,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
d6a94176-14b6-404c-92c4-af60512cf12c | 112,122,124,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
bd2ce8db-68a2-435c-9a9a-4af879eab83a | 112,122,124,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
854a530d-8cec-4280-bfe3-18253ce42ab7 | 112,122,124,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
a92a4931-7eca-4255-b98f-cb11c8469562 | 112,122,124,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
efd7f843-d831-4061-9945-a275f9ce95d0 | 112,122,124,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
0ab7bc31-89bd-4257-ba6b-d81a17a9063e | 112,122,124,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
0fe530ce-5c25-406d-a436-120ecb685b99 | 112,122,124,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
ab790e7f-7d4f-4913-bad3-899d025b86b8 | 112,122,124,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
4293cb7e-0f4f-4ac2-ae80-a8ff1632d100 | 112,122,124,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
0accecb1-3cce-4ceb-8481-164b7d37fde4 | 112,122,124,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
8989b2f0-8fb6-41fc-99f3-c687cdd3d427 | 112,122,124,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
e6c97471-978a-4ebc-a5ac-f4065790889e | 112,122,124,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
dda3dce3-1354-4248-9ecb-77c229315f93 | 112,122,124,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
71b741ab-e1ef-48c5-96d1-34d6a3731b0d | 112,122,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
bd91da61-4e4d-47c9-a5c8-ed94073675e5 | 112,122,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
3a5ebcd5-796d-4b88-b0a9-a65b65c3cd2d | 112,122,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
4c3ce456-50e6-4f65-b278-8fa6ec8c2182 | 112,122,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
47c28dbf-a437-45cc-9771-a576a43923fe | 112,122,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
7fbf1dbb-aa6e-498e-93d8-dcff0c1d84c3 | 112,122,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
7a16e7bb-0aa6-4987-86d5-493c9d0b0d64 | 112,122,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
ace4e4c8-9b22-4c14-93dd-aa9c7ac56cd8 | 112,122,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
95956e11-5b37-40d8-8e20-ff035ae989af | 112,122,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
deeb4d0b-73f7-40c5-8152-aa7e79fb9e7e | 112,122,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
f76804a9-4d7a-4668-b977-980e48f80258 | 112,122,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
b67e99ce-1262-412c-9f00-79799dcbc70a | 112,122,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
ab144f2e-b386-4cce-be99-5f2fbaca9cb1 | 112,122,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
6e2d0012-f26f-41b9-b526-94df7d34dba5 | 112,122,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
36b249f4-5594-4f9d-93bb-c21129e018ed | 112,122,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
03c2eb12-0f0f-4c25-99c7-03897ae445ea | 112,122,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
467ee1aa-f6b2-4550-92b0-606cd9a65bd1 | 112,122,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - GEARBOX - LH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
fb336b13-d756-49ed-b624-dae0ebaaa186 | 112,124,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
0a666350-439e-44ea-9be1-2f3194ac205c | 112,124,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
1ee3f574-c55c-4aec-b380-79e02f056191 | 112,124,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
77d5065d-792b-4fbf-aafa-b5d214ec86ca | 112,124,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
210ead6f-b3f7-4b2b-b3ed-de9270ba9e91 | 112,124,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
88818f99-b7db-4ab3-b18e-d10a748aa383 | 112,124,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
5550f1be-9b13-4be3-b29c-914606e6efb4 | 112,124,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
a8c0ea8d-89ec-455c-ab27-12f9768fcbfa | 112,124,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
4efc5d39-f083-4328-9bed-467d556ff383 | 112,124,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3f356dc9-4f1b-4a78-bb3b-ac743be1bcb9 | 112,124,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
01478939-320a-4215-b1d5-fdfe36fa465d | 112,124,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
cfe42436-b86f-4e95-b2d1-99b6a34de80c | 112,124,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
ed90f83f-3bd3-462f-a586-8a306b4e1fca | 112,124,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
10b91c6e-df35-4e31-b499-354289294403 | 112,124,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
f4c0021d-8fe9-4cfc-ae77-d64af43db8bf | 112,124,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
f431c5a7-96ff-448b-949a-784631abee63 | 112,124,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
776230d4-d1f7-4044-bcf9-20b2b2e9a8fb | 112,124,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
9d63a752-0278-40f3-ab9e-a97055c09237 | 112,124,7,2,16,21,22 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
d6f2e374-15e1-4394-9124-d31c9a4194c9 | 112,124,7,2,16,21,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
93caf168-3010-4058-9afa-17ab0571d1e3 | 112,124,7,2,16,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a5ccd5c7-f9f0-453f-af41-b8f8f8ce3a22 | 112,124,7,2,17,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
95e85f86-c9ce-4cef-b12d-3891940d4be1 | 112,124,7,2,17,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
43f5fb72-bf90-4613-809c-9348a4ef84c5 | 112,124,7,2,17,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
c928ab08-5869-448f-84a4-48cf6ae19544 | 112,124,7,2,18,19,20 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
3bd9524b-c81e-4950-b3bd-eecdbed16f17 | 112,124,7,2,18,19,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
a797c0d8-06ac-41b7-b0a6-a1f20ded5431 | 112,124,7,2,18,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
26a2a646-9dc1-4572-afe0-c591981e4d7b | 112,124,7,2,35,25 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
bc741b48-5979-4686-9a88-db2d89ac834d | 112,124,7,2,35,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
472eecee-363f-4f26-98c5-1d615903bf79 | 112,124,7,2,36,26 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
670c31aa-0596-4f89-88a9-9e4a5fbe991f | 112,124,7,2,36,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
a894e2b9-f315-41cd-9525-f63808a8a603 | 112,124,7,2,65 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
0c204525-4995-4b2b-a552-ba21b797a6d5 | 112,124,7,2,73 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
cb3914de-4c9e-497a-91b3-b8c5aa75121d | 112,124,7,2,101 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
c7f66ff9-5f53-4762-bc7b-1a384b3348d3 | 112,124,7,2,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
4de72803-62f2-4a95-854e-8078b1348c9d | 112,161,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - DRIVE CONTROL UNIT (12) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
753a996c-5f32-4088-b09a-7a2ea9b0caa6 | 112,161,190,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - DRIVE CONTROL UNIT (12) -> ASSY - MAIN COMPUTER (1) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
d6dacc8e-9dbd-4812-b3b1-0b4ff0c32003 | 112,190,188 | ASSY - MOTOR UNIT - LH (2) -> ASSY - MAIN COMPUTER (1) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
5ba73464-5d08-4018-ac2c-3bae6a7f4ddf | 113,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
038f26ca-85e9-488c-9615-15cc290739b2 | 113,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
be38bd8a-b401-4f4a-8cd1-c75770e3e91e | 113,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
23cdb9f0-8995-4cd9-9e41-b6ca81b4e1f6 | 113,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
43b38019-d105-45a5-870f-1579200c3807 | 113,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
57d5694d-ae06-43b1-b424-c8c7d0cbeeda | 113,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
fcdf2fa5-c0ec-4856-b552-ae58d0f4b888 | 113,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
7901112f-25bc-47ed-b576-879d107952b3 | 113,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c0e3e256-a013-4746-af53-ebec832af3da | 113,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
5e4c2a67-c5cd-4531-9c7b-eb996f56d4e4 | 113,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 12 | FALSE
2cc76e1d-a350-4f61-96f9-345d07f6c73a | 113,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
1c8b66de-693f-46fc-9ed8-f191d980708c | 113,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 12 | FALSE
36ae6807-9292-4060-958e-da2ffe59a7de | 113,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
8468eb08-f05c-42b8-aa9f-dda724bd3a7a | 113,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 9 | FALSE
4769b85d-9272-4291-978d-d8086d9dfaff | 113,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 9 | FALSE
52976c74-4251-4659-bc9d-efd7a67013f7 | 113,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 13 | FALSE
33c9d206-4ff7-4b6f-abc4-14a3d18ca72f | 113,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 9 | FALSE
2e60bd83-c8a6-4e8d-83d7-4a07727feb3e | 113,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 26 | FALSE
f22f4a86-0730-45a0-83d6-0d1ca93ef4ac | 113,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
b34ef309-640f-414f-8845-237b6b60b85d | 113,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
f7cb0534-5206-4797-a6c8-626bed23fda6 | 113,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
ce1cbc8a-f13e-4d01-adac-2c75604dd517 | 113,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 23 | FALSE
9c707d06-3b0e-4560-a9fb-3d8ad789eb38 | 113,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
dba84cc0-aad9-40d4-bdab-71303416e6bb | 113,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
1c40e397-e62e-4230-9d15-aaf4936ed312 | 113,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c1f8dda8-336e-45fe-93d3-d2477d18e72a | 113,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
007efc77-0b97-41ee-8c8e-601af7462598 | 113,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
595aacae-eb94-40ad-afcc-a99567453f09 | 113,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0b98db0c-2281-4eee-9daf-48032da4e5b7 | 113,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
c227c216-750b-4cc0-85c0-c8fc9248562f | 113,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
593985ff-bce9-434c-9819-9d2dfdc8371d | 113,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 13 | FALSE
5a8cfb5b-f90f-4d90-8d91-25f3efe5b47d | 113,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 13 | FALSE
8c89e615-27c1-4590-83c9-7ccc2839fd93 | 113,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
3dd38d6a-71d0-408a-86c2-32df39d292bb | 113,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
782aebf1-c2f9-4acd-978d-ecd04702da2b | 113,12,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 27 | FALSE
58795c33-2a75-4902-836e-f049a7eaf510 | 113,12,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
ab199308-ea77-4319-9bd0-84f3c70be54a | 113,12,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
e2e769e2-3709-434f-ba1c-666e3a139d70 | 113,12,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
802f6e41-a0c7-4fe5-89db-b57972f52823 | 113,12,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
bfd8dab2-8f9d-4bec-8556-ae64b7df8b19 | 113,12,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
764e0c4d-d57c-4715-9406-a64622684dc1 | 113,12,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
e4f8c0d8-e90e-41a3-808b-e7d04ff16c96 | 113,12,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
16d54777-a83c-40a7-9f68-e94c3d9833fe | 113,12,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
9f3e6c3c-b585-46d9-bc2e-563b3537565e | 113,12,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 17 | FALSE
9d15c862-5438-46f9-95ce-7b3a9f54f5db | 113,12,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
00a5867a-af76-44da-b952-3d18067536d1 | 113,12,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 17 | FALSE
c9f9babe-5989-44d0-baab-b617707d2aba | 113,12,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 21 | FALSE
28ce2fa4-2d3d-4a62-8543-0528e6ad1732 | 113,12,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 14 | FALSE
8030c16b-03bd-457d-a468-7804cea79abf | 113,12,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 14 | FALSE
eb33e7d3-6f22-4427-8391-f0811716d2de | 113,12,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 18 | FALSE
43754f71-b561-46e6-a73f-ec67018745b7 | 113,12,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
ac544480-1f03-4f2b-8e42-59d00ff15e9e | 113,115,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
51cb9ba3-6c98-40be-b909-c6cf31397015 | 113,115,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
34ffb408-7cb5-4590-a7d4-1b939cdac6a0 | 113,115,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
9c2ae7ba-397e-413c-968c-1e2f0fa2ce21 | 113,115,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6d0f17e2-2e05-4b0a-b6ae-0ddff198f3bf | 113,115,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
cd613095-9f30-436d-ae44-0fdb89a1226c | 113,115,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
3e02b34e-5fa7-48fc-8535-5ff9de560019 | 113,115,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
51f7edbb-6432-41e3-9c34-20c619c1bd7a | 113,115,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
ea67e187-7e71-4add-965a-fb2dde867bf5 | 113,115,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
593aedbc-3086-4f8b-a9e0-867cc8a8be50 | 113,115,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
27a05603-d3e9-4b1b-b9c0-f032de54c29f | 113,115,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
1a43edae-d686-4ef3-bc36-e1f79b5e588e | 113,115,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
cad0d728-01dc-429d-8884-149c8a59a178 | 113,115,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
c4e2db23-d8d5-48d0-b74a-0e8c057a53ea | 113,115,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
0af4cdb5-5a32-4d30-ae5c-4487b05af4b8 | 113,115,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
44876be7-4ff5-4c0f-b218-7dc3f207ab76 | 113,115,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
f987390b-6c98-4c27-be98-9e094bd1916f | 113,115,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
36f1339f-fda4-4077-8ea7-d876923df6df | 113,117,119 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - INVERTER MOUNTING FRAME - RH (6) | 10 | FALSE
6c4f70b8-83a2-4702-8ac2-f076fa502c5b | 113,117,121 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - PWT HV WIRING - RH (2) | 6 | FALSE
0ba66202-1c6a-49a2-a4b3-ea8efaddb5b0 | 113,117,182,12,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
e2132eb0-3dd2-4728-a4ec-cf53d6f5f0f4 | 113,117,182,12,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
83bbcef8-835d-4948-af0c-da5173d4c3a3 | 113,117,182,12,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
494728db-76fd-4427-90c5-51b9a25e24ed | 113,117,182,12,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
b7cfd6aa-947f-491b-8653-e893001a4ab1 | 113,117,182,12,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
a16afb9b-3044-4852-9372-113f6bdf7a03 | 113,117,182,12,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a2341a78-9325-468f-8c30-5dda033a4bff | 113,117,182,12,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
38c4c6c6-7c08-4725-b717-56d91a74427c | 113,117,182,12,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5c129bf4-e9aa-4683-a60a-59850d2cfd8b | 113,117,182,12,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
ea08394d-80a3-45bb-990b-eabfd14a6cc5 | 113,117,182,12,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
1c6e53db-e68d-4c80-8a2d-5d2994156cab | 113,117,182,12,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
b90696fd-c70b-4577-ac1a-056729d4a314 | 113,117,182,12,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
f12ef343-345f-40f8-a030-95d13594089d | 113,117,182,12,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
a493ed2b-3a5f-4c7b-8d3f-ef830b3bd08c | 113,117,182,12,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
00d788dc-03e1-46a5-b47b-f10c9704dde1 | 113,117,182,12,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
7cc2fc86-61c6-4c71-81ab-968ba2728c1b | 113,117,182,12,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
6362f387-f5ce-457d-adae-fbb7e9d38d20 | 113,117,182,12,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - REAR FLUID MANAGEMENT (5) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
7ea7feec-88fa-4a94-9586-6537cc0d4217 | 113,117,182,183,177 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 4 | FALSE
627268f2-858e-4476-b6a9-c8cfc8142d7c | 113,117,182,183,187 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 4 | FALSE
1fe94287-97fd-47a0-bda5-0c725acb43cf | 113,117,182,184,185,178 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER - RH (2) -> ASSY - HYDROGEN COOLING SYSTEM (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 4 | FALSE
ad7e0a24-6d53-4891-8500-4ba9f2b13b20 | 113,119 | ASSY - MOTOR UNIT - RH (2) -> ASSY - INVERTER MOUNTING FRAME - RH (6) | 8 | FALSE
98c4ee5d-6e8f-4fef-a52f-84d148c4196e | 113,121 | ASSY - MOTOR UNIT - RH (2) -> ASSY - PWT HV WIRING - RH (2) | 4 | FALSE
0564ef35-95bb-4388-8869-227d9480f294 | 113,123,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 29 | FALSE
b5ffa93e-677f-41e8-acf5-7e821c0afcdb | 113,123,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
58244dac-6ff9-4d85-9e89-63b602c8fadd | 113,123,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
f945c3e5-c021-4621-9fec-7c7996642b15 | 113,123,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
32afceaa-a6d9-4705-9563-c6fee8766dcf | 113,123,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
e3a028fb-0069-42bc-abdb-811455ec22bb | 113,123,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
c93e439b-15d3-44b4-ab24-c615d03826e6 | 113,123,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
f4747215-3c89-4040-b4b8-5cfa3d515503 | 113,123,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
f95aad06-0771-4e4d-a62b-d75e2e861f0b | 113,123,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
91b68efa-86a3-47ee-873e-2ff0fd794368 | 113,123,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 19 | FALSE
469a3712-a206-4526-b7e2-b3940e482a08 | 113,123,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
8cc9a385-407b-4bc2-8680-24d165ddbc4c | 113,123,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 19 | FALSE
cca092af-88cf-411f-8eca-cad324dbf9e8 | 113,123,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
0fed454b-418b-4662-bfad-068a42a4f3d2 | 113,123,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 16 | FALSE
df2f5658-0f5e-4069-8697-c73ac4804c49 | 113,123,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 16 | FALSE
391e1559-485c-4226-beb7-a266c4ecd497 | 113,123,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
45d8b7b4-0b7e-41b1-9ebf-a023cf7df2a0 | 113,123,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
619073a6-506d-401e-9749-f7efc58c7ded | 113,123,115,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
d013a0ab-d788-462d-b7e3-eebc060b52b4 | 113,123,115,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
4ebf82e4-a1e6-47d2-999c-c6e3c9451bc1 | 113,123,115,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
0bdb31fa-4bcd-4cd4-9f53-53249aa39c90 | 113,123,115,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
0c85ea7b-7690-4356-8546-b79ce7afa2c0 | 113,123,115,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
50322dd8-dc5d-413f-9eeb-700753a33195 | 113,123,115,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
89d4b3fb-4f96-4258-b7bf-6b1e4c345b5d | 113,123,115,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
3688c39a-5c11-4623-b0ac-f782a9d939fb | 113,123,115,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
d7474d07-3773-475d-abda-8a5e87e44f25 | 113,123,115,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
841b8357-4252-45c1-80e6-5841587fdd6b | 113,123,115,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
bd742664-72e7-4815-a12b-cfeed0cf4c84 | 113,123,115,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
ccc05344-f399-4055-aacf-e5f5f2283e73 | 113,123,115,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
139ccf71-8ca9-4b4a-b51b-a74153218ebd | 113,123,115,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
4dccabc4-d7f0-4227-827b-74aed4837316 | 113,123,115,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
1751bb6e-6fb7-47fa-ae73-8871bbbdb167 | 113,123,115,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
1be4a33a-ccb9-42c2-a376-64edbd31e2b0 | 113,123,115,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
43f96cf9-6772-4def-a086-e2c8c0c4c769 | 113,123,115,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - MOTOR MOUNTING FRAME - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5d26abfe-aa81-47f6-910e-1cb3da95e85f | 113,123,125,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 31 | FALSE
ca22108b-f004-487a-affb-a847dd88fab1 | 113,123,125,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
94700f07-b5a6-4a00-9374-bb947eebd85c | 113,123,125,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
aaf43370-b062-4d0f-9918-dea62588bb2c | 113,123,125,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
1f1445e1-d3b9-496b-88f1-d03636dc65fd | 113,123,125,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
7a71c58f-1bd9-4147-be60-8031a44138f5 | 113,123,125,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
8b348140-8c82-46b8-bd8c-84d84c060370 | 113,123,125,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 30 | FALSE
78d1ca02-13d4-4c64-ab74-00fc4ae171e8 | 113,123,125,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 28 | FALSE
f7faea5a-c788-47b9-a0d6-0e491f01f975 | 113,123,125,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
ae3feca2-114e-47f6-9701-e0780ee3a182 | 113,123,125,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 21 | FALSE
f4b3a489-5b02-4b5b-8afa-80a4a707dc8f | 113,123,125,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
b38f8da3-783d-4da6-b209-ca9fdc703e07 | 113,123,125,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 21 | FALSE
0d2311ee-9dce-4b62-9423-621e332b1476 | 113,123,125,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 25 | FALSE
cade9e34-813f-4bb8-9294-c2608caba96c | 113,123,125,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 18 | FALSE
94f36a8d-72b7-417e-a246-0a40c9aa1d15 | 113,123,125,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 18 | FALSE
093b2fcd-8565-4abd-8477-134a3412271b | 113,123,125,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
1471c22c-1d36-4087-af98-40d4e6dab626 | 113,123,125,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
6e85a587-c6c8-4d77-846d-d3008af940d5 | 113,123,125,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 35 | FALSE
323af00a-5b0a-42d4-9207-00e5ed3b6307 | 113,123,125,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 33 | FALSE
3e0afb8d-c07f-427b-b038-269bda398a12 | 113,123,125,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
339e97c8-4f9d-4872-9d1a-891fa6c0d27b | 113,123,125,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
b0dd1639-b662-425d-8a58-a8cd9772b0b0 | 113,123,125,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 32 | FALSE
d2f23364-c6f2-4e93-a356-334641880956 | 113,123,125,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
b1b52463-8913-41dc-9ba5-759f7a90872e | 113,123,125,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 34 | FALSE
0ca3e95c-77d5-445c-82dd-1b2ca45f123c | 113,123,125,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 32 | FALSE
01977371-00c1-4a58-805d-387533bdfd26 | 113,123,125,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
1406a5a8-facc-4de0-98c7-ddd7b254cc08 | 113,123,125,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 25 | FALSE
97cf4092-2fe3-4a1d-9f32-ade6f5d67999 | 113,123,125,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
04e1906c-9cb3-4c34-a742-98b93def0a8d | 113,123,125,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 25 | FALSE
3e7c0f3f-9134-4e28-88f0-066e7e76e4e2 | 113,123,125,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 29 | FALSE
4e27c643-804f-4dc7-86ed-a5f6b11b2044 | 113,123,125,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 22 | FALSE
3478bae4-a1a0-4373-b4d5-021efc6ea90a | 113,123,125,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 22 | FALSE
aaebf292-fc5e-4b44-86c5-ff1a63621c8f | 113,123,125,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
a5db34c5-407d-410e-9216-25ae11232e3a | 113,123,125,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
efa1107e-f912-40ea-857f-835c19e52953 | 113,123,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
f54e3bb4-7e66-4572-998f-d44eb3c6b294 | 113,123,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
89f09d3f-e0b4-4316-a007-27fec80d9ce4 | 113,123,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
76ae7272-a558-4ac8-95f0-ba9f1f35c221 | 113,123,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
d13ccb39-68dd-417d-acf2-17ecd131cf77 | 113,123,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
522c0962-7fb4-45ed-9829-0229cb0e7389 | 113,123,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
381814b1-19c1-456d-99c8-5cddc4e6fe41 | 113,123,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 24 | FALSE
c3b66875-57d7-41a7-a104-220cd8ddc93d | 113,123,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3f6d6394-05d6-4902-bd04-c516d587b04e | 113,123,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
40101792-5555-43df-b170-d65c669f582d | 113,123,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 15 | FALSE
5f6154b8-7743-4f60-8a68-d41cb64dc665 | 113,123,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
a504b1ed-ce4e-4d77-ab5a-848a2597af28 | 113,123,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 15 | FALSE
88b3efee-69d7-4e0d-8e84-5ad5fc355e45 | 113,123,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
e378b0b5-b83b-41e5-a0a8-622e990cde1e | 113,123,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 12 | FALSE
976ce1d7-f249-4598-9113-5f31583c9de1 | 113,123,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 12 | FALSE
bc9135d9-8754-44e9-b24f-44f4fd940d8e | 113,123,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 16 | FALSE
31de812a-4c39-4566-b00e-ed4cdd9037d1 | 113,123,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - GEARBOX - RH (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
2d981291-dda3-41c2-bba8-04e3c890d55e | 113,125,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
fb78ff42-dd5c-41be-8239-bea1b2acf99e | 113,125,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
81aa2414-7b1b-4e1f-899a-3c270d867a07 | 113,125,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
5d19ba91-d5af-407a-894d-39f6963a17ac | 113,125,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
56d6a8df-0a1b-475f-8cf3-5b950dd9d228 | 113,125,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0fbb5f43-4121-435b-a784-9df6bf358aae | 113,125,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
3a579cc1-d56c-4c52-97cb-d2f610928657 | 113,125,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
2dae1804-4661-4260-9806-b66b7bdfd8af | 113,125,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
6fc4ad6b-9270-4896-a4b1-2edc9c5cf970 | 113,125,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
3cf271e8-9891-40a2-998e-2103b0cba566 | 113,125,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
38c031cc-e32f-4bf2-9772-7a39eb367512 | 113,125,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
c92f8746-9c19-4cd9-95ad-b6a618ef1194 | 113,125,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
4ded55fa-c1d0-42b1-ac77-f71614e27611 | 113,125,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
84e5e080-dd45-438f-9efe-4d828336b2bd | 113,125,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
903ab479-96cd-4482-8050-b7ba52652da2 | 113,125,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
ec18f22f-226d-4b6f-9dea-34fb4d7255fb | 113,125,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
ebd6149a-f3b8-412d-812d-d4b7cdfdca4b | 113,125,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
cdc5cdf9-517b-4457-ade5-27fb341e2a12 | 113,125,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
db9da017-33f5-4267-b595-374017653e01 | 113,125,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
62fb42e6-d8ac-47df-8152-6e72f5088cd2 | 113,125,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a89577ed-4700-4e6d-97b2-bdffe0a35986 | 113,125,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
3b5d5cc1-a972-4fe7-974a-9ca19d6912e2 | 113,125,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
bfb4f72e-227d-4587-a179-c3239127ff48 | 113,125,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
9c163a06-be40-48d8-a51a-4982c6e0c7bc | 113,125,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
93c81f22-5c4d-4330-8653-30ece871de57 | 113,125,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
45d6f6a0-6e62-4878-a0b8-7fda06be5d29 | 113,125,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
76ac881f-e292-4a97-98be-c140d16bd13b | 113,125,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
4997eaa1-45cc-4766-ba5e-8409919a1660 | 113,125,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
8a73a92a-080d-42d5-997f-312a28863062 | 113,125,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
6f52925c-150a-472b-bce4-ba56f5717850 | 113,125,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
2cfa268c-d86f-40f4-9107-15a7284ae8a6 | 113,125,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
fdbe0e71-d13b-4f84-9371-079eec66f1a6 | 113,125,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
875cf503-12e8-42ef-8daa-0ff0a664c21a | 113,125,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
8d6b3941-8197-45fb-8ca9-8cd7c7441bf8 | 113,125,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - RH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
db3dfd6d-27de-41c9-8dd3-d423de6df5f1 | 113,161,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - DRIVE CONTROL UNIT (12) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
c010a07b-756c-4a09-bc8b-9129acacf042 | 113,161,190,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - DRIVE CONTROL UNIT (12) -> ASSY - MAIN COMPUTER (1) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
b48dda2a-635c-491f-b0cd-36c20dcdff30 | 113,190,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - MAIN COMPUTER (1) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
8fc26eb6-95cd-4b7b-9024-08e05b867ca7 | 113,124,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
0ba99bc2-5f8d-45b1-a5c0-e96117713eb5 | 113,124,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
85b01618-fac6-4eda-94a1-9938b54d21d0 | 113,124,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
6283ba4e-077c-42eb-9ca7-d4c8d6c911f5 | 113,124,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
8376757c-b59e-4f24-abc5-7770228f9b24 | 113,124,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f7387012-1b07-4890-9854-0f3483ba9849 | 113,124,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
1394d666-5c35-4307-8587-8312974d19bf | 113,124,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
3e534f34-61bf-4d7e-975b-2dfea3384996 | 113,124,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
848a6fb8-398a-4b26-baf7-200e2531421a | 113,124,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
2461df5c-6bde-4d0e-8d9e-9c8d435dedd4 | 113,124,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
1ecf9c54-8326-4e28-aac4-f8b06c2a3c43 | 113,124,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
915d5e34-a0f4-4746-956c-21adbac27046 | 113,124,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
e6fa83b5-56f4-4c74-8aed-eecf2a1c1d77 | 113,124,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
893a1a10-039b-4290-95c5-9d1c774d63e8 | 113,124,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
65ad7e89-e08b-4736-b191-d24d5df7d9d9 | 113,124,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
3e83146d-36ed-42d3-949e-2f87d807c4ed | 113,124,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
3c3972c9-2a2c-4eae-89f2-40718400b7c1 | 113,124,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
5a77443e-b98c-4859-b31e-1c0da4a501b8 | 113,124,7,2,16,21,22 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
545e34a9-daa1-41d1-94c4-78ee50fa3c6f | 113,124,7,2,16,21,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
066aebf5-6018-4dcb-929f-357d8c7276d2 | 113,124,7,2,16,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a1ff45b0-d682-46d6-982b-e5073463a42f | 113,124,7,2,17,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
01ed1c8e-eacd-426e-a4d2-9085c8cd091e | 113,124,7,2,17,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 29 | FALSE
9b039b25-50f8-46f8-babf-cc58754b69fc | 113,124,7,2,17,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 27 | FALSE
93f4fca1-2445-409d-b94f-7a146ca95925 | 113,124,7,2,18,19,20 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 31 | FALSE
cbb37b69-0aab-4466-b630-855d270f09dc | 113,124,7,2,18,19,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 29 | FALSE
69eff708-8bc4-481f-93ab-237535d3e73c | 113,124,7,2,18,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
063fc36a-87af-4e87-b22d-41d320088cf2 | 113,124,7,2,35,25 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 22 | FALSE
d2f56a94-db60-4328-a13d-9482aa7b4098 | 113,124,7,2,35,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
80979333-7d2f-49b0-ae90-7d17c2f0c7a8 | 113,124,7,2,36,26 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 22 | FALSE
ed5c6702-a701-4e0d-a189-fa21ae290a9b | 113,124,7,2,36,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 26 | FALSE
84a95357-6192-496a-9f1e-4e7c8a4a90af | 113,124,7,2,65 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 19 | FALSE
0bf49e2e-1129-44fe-97ca-176f25c217bd | 113,124,7,2,73 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 19 | FALSE
e0012970-c6bc-4bfc-b38d-c64af04840ae | 113,124,7,2,101 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 23 | FALSE
959132b4-ffb4-49b1-ba7c-be8d147d76db | 113,124,7,2,188 | ASSY - MOTOR UNIT - RH (2) -> ASSY - AXLE CV - LH (6) -> ASSY - CHASSIS SUBFRAME (4) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
69fdad92-fc70-4764-b571-08501ad195ba | 139,138 | ASSY - ONBOARD CHARGER INSTALLATION (3) -> ASSY - ONBOARD CHARGING WIRING (2) | 5 | FALSE
e5e1c3e6-fefc-4f16-973d-315a6341d917 | 146,19,20 | Assy - Shingled Matrix Panels (12) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 21 | FALSE
942fb32e-1826-452e-9057-8fe369e54ddf | 146,19,188 | Assy - Shingled Matrix Panels (12) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
c45d47aa-cac3-4b2b-98db-6b28f288ca24 | 146,141,140,134,136 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 23 | FALSE
c17e2464-9248-46e3-b8c5-179ce0d8c340 | 146,141,140,136 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 21 | FALSE
098f33e6-8cc5-4af4-8d32-e31666aa796c | 146,141,1,35,25 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
42396de3-c713-483d-b04f-63ed03dabdfe | 146,141,1,35,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
55c3f7c9-cfd2-472f-b792-5f9e805254b8 | 146,141,1,36,26 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
52444665-6a3f-4085-9aae-7227fe34f3f1 | 146,141,1,36,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
eee7872c-b9f2-4a7f-954f-b9071a8a8d25 | 146,141,1,98 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 25 | FALSE
70b3bae2-e41b-4d19-8b75-66de791376e3 | 146,141,1,44 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 24 | FALSE
1088935d-2a5a-49ea-86f9-967df814d1d4 | 146,141,1,47,21,22 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
365d9d08-f187-4ffc-9c26-cc12f8aaed53 | 146,141,1,47,21,188 | Assy - Shingled Matrix Panels (12) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
a1ad344a-6612-45a6-89eb-cea05e532f34 | 146,145,1,35,25 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 26 | FALSE
56d7e38a-401c-4621-af38-f336e1cb5ad3 | 146,145,1,35,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
3cb75737-9853-454b-9c3f-87ecd34e666b | 146,145,1,36,26 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 26 | FALSE
ba78d996-b4e3-481e-8ad8-989a61546610 | 146,145,1,36,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 30 | FALSE
8ae804b8-0229-4709-8071-87628f5536ab | 146,145,1,98 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 25 | FALSE
018805b6-0d9b-492d-8765-e55654e3a8dc | 146,145,1,44 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 24 | FALSE
b1c0d914-05e3-4522-afa1-f399b38df727 | 146,145,1,47,21,22 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 32 | FALSE
1dc59a9a-3238-4983-8c97-b07f459fd2a4 | 146,145,1,47,21,188 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 30 | FALSE
164208e3-360f-414c-bca9-bcd572e6a24d | 146,145,19,20 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
f65bcccd-512a-4cc7-aee5-fcebffea5bc1 | 146,145,19,188 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
c7ae4e73-52ab-4678-bd20-c578287ceff9 | 146,145,21,22 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 24 | FALSE
34bddb50-cd50-4d3d-820c-1ff54deb5f24 | 146,145,21,188 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
e8b199ea-5a0d-4cc8-80aa-8a167df01522 | 146,145,141,140,134,136 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - ECS HV WIRING (2) -> ASSY - CONTROL LOGIC (3) | 27 | FALSE
64cf92ef-48b6-43db-ab07-887d1522844b | 146,145,141,140,136 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - MPPT JUNCTION BOX (2) -> ASSY - CONTROL LOGIC (3) | 25 | FALSE
dd8f7e0d-39ef-418c-90e3-d6d89259cfc9 | 146,145,141,1,35,25 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 30 | FALSE
5776b345-707d-4440-b4f8-b8388b930b70 | 146,145,141,1,35,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 34 | FALSE
cca4408a-2827-43c0-b43f-b3614cb257ac | 146,145,141,1,36,26 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 30 | FALSE
c9bffc0b-bb09-4e7b-9268-6645f42a4e90 | 146,145,141,1,36,101 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 34 | FALSE
961d066d-067f-43ff-861e-6ccf58a86a0b | 146,145,141,1,98 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 29 | FALSE
2b4226c7-49cd-4cb7-bed0-2d6ffd4ebf10 | 146,145,141,1,44 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 28 | FALSE
4c444914-dca1-442b-87e2-f2a96246eb9e | 146,145,141,1,47,21,22 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 36 | FALSE
232a40a5-1cbf-40a6-a08a-6bc8a5eb7529 | 146,145,141,1,47,21,188 | Assy - Shingled Matrix Panels (12) -> ASSY - MC4 Cabling (4) -> ASSY - MPPT (4) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 34 | FALSE
cf21f5b0-3c48-4aff-9357-9d562d2c07eb | 151,19,20 | ASSY - CENTRAL STOP LAMP (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 12 | FALSE
4fa77c27-bbf0-4987-8c56-c5e348bdf60e | 151,19,188 | ASSY - CENTRAL STOP LAMP (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
e3c3d6a1-a34c-428a-b7ed-80f2d1f6e7b1 | 151,152,19,20 | ASSY - CENTRAL STOP LAMP (3) -> ASSY - CENTRAL STOP LAMP PCB (4) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 16 | FALSE
7d641a67-2fb7-45c5-89a5-c8a5084c2347 | 151,152,19,188 | ASSY - CENTRAL STOP LAMP (3) -> ASSY - CENTRAL STOP LAMP PCB (4) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
5216ff90-16cf-4734-a847-8ad234a111a6 | 151,188 | ASSY - CENTRAL STOP LAMP (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
9534087c-db16-4bcd-be0f-7d6b8ccadb34 | 155,16,21,22 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 17 | FALSE
82a8046a-398e-4f14-92f4-9cce72bd1eb5 | 155,16,21,188 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ebcd1cc5-cc02-4b56-ba21-c2efd8bf254c | 155,16,188 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
6debc3d3-8d66-4123-b90c-189bcab74700 | 155,188 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 4 | FALSE
d77fdc57-dff2-4b19-b28c-7543a02ad68a | 155,153,16,21,22 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - HEADLIGHT EXTERIOR - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
017d7cb2-c524-4e1d-8e9d-4f33946150ca | 155,153,16,21,188 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - HEADLIGHT EXTERIOR - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
b08ec1c1-7adc-4a6d-92e2-8ad0993c4cf3 | 155,153,16,188 | ASSY - HEADLIGHT/INDICATOR PCB - LH (2) -> ASSY - HEADLIGHT EXTERIOR - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
4798191a-c340-442b-a67f-e00823cef763 | 156,16,21,22 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 17 | FALSE
96771e07-40e5-4b2a-bb2a-899dc24ccd67 | 156,16,21,188 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
fdb266d8-78e8-4a19-bd56-049a42b257d7 | 156,16,188 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 11 | FALSE
c664887b-182b-456c-a25d-8ce26aacddbf | 156,188 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 4 | FALSE
02dc79ea-f152-468d-8d1c-e21d877e0580 | 156,154,16,21,22 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - HEADLIGHT EXTERIOR - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
f55bd116-987f-4cac-9e31-06e6e8cd7e3c | 156,154,16,21,188 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - HEADLIGHT EXTERIOR - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ca12e495-0374-4fde-b004-9646c279abbd | 156,154,16,188 | ASSY - HEADLIGHT/INDICATOR PCB - RH (2) -> ASSY - HEADLIGHT EXTERIOR - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d3f90955-625e-47dc-9ce7-946fe11a2f5b | 157,28,1,35,25 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
62b55b59-a800-48aa-8f19-c9a2c7027eb7 | 157,28,1,35,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
ad2912f7-2d9c-4e11-b207-a59174d14486 | 157,28,1,36,26 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
7a9c88b0-b739-432b-ac82-3c3c35b61f16 | 157,28,1,36,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
3fa93445-13cd-42ca-b588-1861fb436cfb | 157,28,1,98 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 15 | FALSE
be64d446-5af1-4948-9254-db7e54b4fb2c | 157,28,1,44 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 14 | FALSE
340d9886-02d2-481a-9717-d38af3839377 | 157,28,1,47,21,22 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
9046042d-c0b5-409b-8917-ab4b236a47bd | 157,28,1,47,21,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
391d427b-88c8-498d-81bf-3cf3392fa8b6 | 157,28,16,21,22 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
495b5ebf-d2c8-4577-8768-0e8d42fbd2a5 | 157,28,16,21,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
036b4318-d1cf-4195-be84-80ffd339332b | 157,28,16,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
e9ce970e-979e-44d5-a91e-f875f6f74240 | 157,28,34 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CONTROL BOARD - LH (5) | 11 | FALSE
49b687e0-362a-411f-9719-ed2fb34edd99 | 157,28,36,26 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 11 | FALSE
5ccda2be-15cf-4ebc-b396-bcb37a1c076b | 157,28,36,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
e8e29f4e-2f28-4552-b33a-d94dfcd94b42 | 157,28,14,2,16,21,22 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
b3c7ac7f-41c1-4f35-b5a1-967e810f8a00 | 157,28,14,2,16,21,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5cfa8a06-270a-4bdf-b6c4-f6897d8108e4 | 157,28,14,2,16,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
9612dd2f-a326-45e2-a22b-18dd63b5f4ec | 157,28,14,2,17,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1a5e7d67-f597-405f-8721-470d393e2880 | 157,28,14,2,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
0df846a5-d5a9-4dce-b686-0cfee1de1b29 | 157,28,14,2,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
b3108e01-25db-41e0-9ec6-a0d952ab6c5b | 157,28,14,2,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
0f42ca2b-3f17-4a5f-a496-a88587aacf98 | 157,28,14,2,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
9f861d57-bb92-4f62-a3e6-d0e00bce6e27 | 157,28,14,2,18,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
ec8acc18-87a7-4d9a-9bc9-6ee90caee367 | 157,28,14,2,35,25 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
3553791c-7c14-4e02-a14d-213f7f83d622 | 157,28,14,2,35,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
9f831196-c05b-4a66-b326-6d711e64b1df | 157,28,14,2,36,26 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
6c6c3251-d433-4ac7-9152-3317c43aab97 | 157,28,14,2,36,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
be056c03-9660-46c6-b2f8-682c44e8072a | 157,28,14,2,65 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
918fabc3-f482-4f17-bbb9-56860ab03dad | 157,28,14,2,73 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
8f06bc38-21cb-4766-b930-db0443a897f2 | 157,28,14,2,101 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
82772115-73e3-4324-a1c7-a054e87f3b8d | 157,28,14,2,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
74712482-93ba-485c-b01b-232b654ebbcb | 157,28,14,13,17,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
54e974da-1746-4272-9dd8-6b98a622c7d0 | 157,28,14,13,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
ea93090e-7b9e-4f84-b7bd-cc291364c37c | 157,28,14,13,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
a4d62d2b-be54-4a04-a28f-6558fb4b87b0 | 157,28,14,13,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
e64d4eb7-f064-4833-9dca-969fdd96cd97 | 157,28,14,13,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
d5757351-87fd-471b-9642-75c76f1be6ea | 157,28,14,13,18,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
fd49d1b8-55ab-4da1-a822-58cb0de254f7 | 157,28,14,13,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
11342d72-c425-4fa5-aa2a-0a2b4a813694 | 157,28,14,17,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
ec54c9b8-9407-4416-8d8a-7b936e49cbfa | 157,28,14,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
ef7ef368-74dc-4c36-a19e-fb5e7b66f9fc | 157,28,14,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
196b633a-6097-49f3-9131-e0d7db877071 | 157,28,14,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
70e3b224-cc91-405b-a7e0-967f08b1c2ae | 157,28,14,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
52524533-e290-4525-a9f5-9ff6f348092d | 157,28,14,18,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
67373029-4b29-4cab-97b8-2c1c7b4d1e1b | 157,28,14,19,20 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
d7027356-0750-4650-b42f-29a7ac187911 | 157,28,14,19,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
8492f7c6-2257-40fe-8bb4-dbe4b1ed1683 | 157,28,14,188 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
0d6b0dbf-bbb9-4322-83f6-135556d4d0a3 | 157,28,14,24 | ASSY - SIDE INDICATOR EXTERIOR - LH (3) -> ASSY - DOOR SHELL - LH (3) -> ASSY - REAR QUARTER PANEL - LH (2) -> ASSY - OUTER DOOR HANDLE - LH (2) | 10 | FALSE
cc63013a-cf1b-4c55-a6d3-a0752049fd6f | 158,27,1,35,25 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 16 | FALSE
bce05c98-a393-44e1-8b7b-bdaec0d8b018 | 158,27,1,35,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
5de184e1-263d-4487-bebf-97e2052d7f51 | 158,27,1,36,26 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 16 | FALSE
b29f1009-1987-4856-9007-c2cf0688e98b | 158,27,1,36,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 20 | FALSE
0ca39616-b7ee-47ea-a3d6-a3fdc499c15c | 158,27,1,98 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - CEILING (4) | 15 | FALSE
0b05eb54-5a6f-4d15-80fe-9e8737f323a8 | 158,27,1,44 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN (3) | 14 | FALSE
b7604817-c3d8-407b-b4ef-d0511d5395de | 158,27,1,47,21,22 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 22 | FALSE
23128e5e-e879-4cd0-b765-19cb61c4b159 | 158,27,1,47,21,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - OCCUPANT CELL SPIDER (5) -> ASSY - WINDSCREEN WIPER AERO GUARD (3) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
bd45b163-7a42-4028-a6bb-0c41bda6b9c4 | 158,27,16,21,22 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 21 | FALSE
cc8432fb-89ba-4600-9596-c61bcade28a2 | 158,27,16,21,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
3591ed6e-20c9-44c3-a85b-46a43cdbf9d5 | 158,27,16,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
43aea950-c394-45c6-a139-85a26de48df4 | 158,27,33 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CONTROL BOARD - RH (5) | 11 | FALSE
c0fc1427-fd68-4150-8b25-4f68b10efce3 | 158,27,35,25 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 11 | FALSE
d7786751-8485-4b1d-b9d8-7b47266dcc63 | 158,27,35,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 15 | FALSE
d61250a9-918c-4262-8e00-ed53ab8b3325 | 158,27,15,2,16,21,22 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 28 | FALSE
6ee6662f-551f-4b98-a036-38bb1728cdd5 | 158,27,15,2,16,21,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
5daeb30c-f536-42e5-97e5-0be8c195a534 | 158,27,15,2,16,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 22 | FALSE
78ce8890-17f1-4198-aa2a-ff5717d6c660 | 158,27,15,2,17,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e2184aa9-6d05-4442-b93d-3ee16e5a7f9a | 158,27,15,2,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 25 | FALSE
18587a4f-429f-4198-8947-350a3df247c4 | 158,27,15,2,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
de96e23b-b566-4e01-a9a1-d3acb682cb1c | 158,27,15,2,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 27 | FALSE
02d5ecf1-2335-4ae7-90cc-6dc36d751c4f | 158,27,15,2,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 25 | FALSE
c4b749fe-dd20-45f5-a7f1-3fdd83b58c6d | 158,27,15,2,18,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
84649d24-be58-49c0-ab24-fc4b85a039d2 | 158,27,15,2,35,25 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 18 | FALSE
6c41ef4d-d022-4bd3-a20f-1f4fe83ff7e5 | 158,27,15,2,35,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
eae7200e-74a3-4ef9-a4ab-5c003c288d6b | 158,27,15,2,36,26 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 18 | FALSE
b8876ba8-5565-47e0-8304-d6f7e951dbab | 158,27,15,2,36,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 22 | FALSE
0a7d7e72-aa61-4b50-9e45-537697986c75 | 158,27,15,2,65 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 15 | FALSE
9203908b-d9f2-4ea6-b6fe-0714d9b8377e | 158,27,15,2,73 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 15 | FALSE
f68aab8f-ede2-4efd-8ffc-1a8ce8454fc3 | 158,27,15,2,101 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 19 | FALSE
00a9b4b1-cfd8-4d0d-bfb6-15bca65ea14f | 158,27,15,2,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1ad6fbe0-d36b-426b-8217-fe4615330124 | 158,27,15,13,17,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6f5103ae-7d2b-4857-87eb-acffbaa93266 | 158,27,15,13,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 26 | FALSE
e8fb9575-f885-42bb-8dca-be9650a3c818 | 158,27,15,13,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 24 | FALSE
474bb4eb-9d76-4bb4-8eda-da63b0738e3b | 158,27,15,13,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
a2c4c5f5-3879-4d5b-8968-eb7eae3c419f | 158,27,15,13,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
2cc0a137-b189-4df4-8001-a850f9cd6a6c | 158,27,15,13,18,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
98218f9c-bd2e-40cf-903a-988b721dc240 | 158,27,15,13,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR BUMPER (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 16 | FALSE
9378ec99-f9fb-42c8-91c0-baec9fe17e80 | 158,27,15,17,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
beec9ee4-308d-42dd-bf32-7d837b187860 | 158,27,15,17,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
5946d904-fa67-4527-8aab-21a7d98a2de3 | 158,27,15,17,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
ac8c1cad-b98e-4a4a-9ddb-47ba14aed334 | 158,27,15,18,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
dd07e7af-30a2-43a1-9619-7ad18de6ee7b | 158,27,15,18,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
8aab9d3b-3ccb-4f36-8492-0db2ba3bba1b | 158,27,15,18,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
1f49c22b-5d9e-446d-9f43-e12143d41701 | 158,27,15,19,20 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
d1824aa8-302f-4422-af79-b827db876b11 | 158,27,15,19,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a62640e5-0a07-408e-92a4-d02e1e0832ba | 158,27,15,188 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
43273568-1e39-4c5e-bab6-0de6fa4b6768 | 158,27,15,23 | ASSY - SIDE INDICATOR EXTERIOR - RH (3) -> ASSY - DOOR SHELL - RH (3) -> ASSY - REAR QUARTER PANEL - RH (2) -> ASSY - OUTER DOOR HANDLE - RH (2) | 10 | FALSE
6f8c3cc8-ee87-4bf1-ab3a-d6cf1a2f7c91 | 159,16,21,22 | ASSY - HORN (1) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 16 | FALSE
6bbd5b4c-93d9-468b-8d4b-1580b32b8eca | 159,16,21,188 | ASSY - HORN (1) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
73d57538-4d49-4b2a-9ee8-802f3820c24a | 159,16,188 | ASSY - HORN (1) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
78c6b5f5-2ce7-4ad7-98c5-8b1b3281b93e | 160,188 | ASSY - HORN PCB (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
44df8c6a-03c2-4692-82c4-7f9e4829371f | 162 | ASSY - SENSOR MOTHERBOARD - FL (12) | 12 | FALSE
0e9535aa-4b40-4c32-ba91-6362836a4440 | 163 | ASSY - SENSOR MOTHERBOARD - FR (12) | 12 | FALSE
ecf343c0-a612-4b0d-8024-0915a4ac70b2 | 164 | ASSY - SENSOR MOTHERBOARD - BL (12) | 12 | FALSE
dc7e07e9-32f2-4b99-a760-31242a8348ff | 165 | ASSY - SENSOR MOTHERBOARD - BR (12) | 12 | FALSE
231bb15c-354b-4929-ad17-2bdb81d1e2f7 | 166,167,188 | ASSY - SUBWOOFER (3) -> ASSY - AUDIO CONTROL SYSTEM (8) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
147ec2d7-f2f6-4251-9b6f-d8d0a4de49cc | 166,188 | ASSY - SUBWOOFER (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
b931a771-33dc-4f37-bcec-d690fce60151 | 166,2,16,21,22 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 23 | FALSE
0a4ac2ec-5a4f-40c3-b384-2bdee863379b | 166,2,16,21,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
facb92a4-692b-4688-b453-b79873db7420 | 166,2,16,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
020595df-719c-4719-a24d-64d124817b48 | 166,2,17,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 13 | FALSE
4df549e5-aae5-4a6b-b1e4-81eab42ca48e | 166,2,17,19,20 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 20 | FALSE
ad2e7789-f972-470e-ac5f-58dfd0bb4daa | 166,2,17,19,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
495cc1c5-fce0-4f3b-9c01-8de1cd45af3d | 166,2,18,19,20 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
ab2cb8cf-5fa4-4bcb-8641-aecd057e2a04 | 166,2,18,19,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
9053c7e5-4f4a-48e0-b6e8-1326bd3609e7 | 166,2,18,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
765ddccb-3d81-4385-8877-fb4baa42da00 | 166,2,35,25 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 13 | FALSE
8c229136-0183-44d7-9a2d-0513a5c64e8b | 166,2,35,101 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
fbe420ba-12be-42f7-a61d-47a74c5ab420 | 166,2,36,26 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 13 | FALSE
9d47ef1b-12f7-4c24-859b-c6384c24e575 | 166,2,36,101 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 17 | FALSE
9027a5a5-0b35-4067-b50c-a04fe5a8e575 | 166,2,65 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 10 | FALSE
b62a8a83-7ca8-4ac8-9776-fa5e3f6f89ab | 166,2,73 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 10 | FALSE
4b4fa37a-4eee-48a9-a972-edc5e90af48e | 166,2,101 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
69bdc413-72cd-488a-b340-c45951ea37e4 | 166,2,188 | ASSY - SUBWOOFER (3) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
a83ca450-af37-4b17-a8b5-21680efbbae2 | 169,168,2,16,21,22 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
31fc23f0-e976-404a-979b-621ef590e3db | 169,168,2,16,21,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
1da479f8-012d-4c29-8cd7-4609e1015382 | 169,168,2,16,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
6763868e-9ab9-4bc8-ab23-435f80a72b7b | 169,168,2,17,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
95dbe1e9-04ce-4bef-83c7-55ea0dae5356 | 169,168,2,17,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
61b435e9-89d9-4c40-914f-0d6faa558f15 | 169,168,2,17,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
bc7202d0-3047-442a-b726-4ad1ff71da8a | 169,168,2,18,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
e4fbf2f5-854c-4050-b8c4-68bbc2523e04 | 169,168,2,18,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
cbc0dce1-26c7-4352-90b6-1152094300a6 | 169,168,2,18,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
932c223a-9df5-4a44-850d-3ee1d3177c30 | 169,168,2,35,25 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
9e82e66c-588f-4a65-9685-4f55915b5ad2 | 169,168,2,35,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
93ce7280-e6ce-4036-9880-4ad5a7e6efa7 | 169,168,2,36,26 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
a5034e5c-889f-4c92-8b5e-8ebde3047f6c | 169,168,2,36,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
0053c800-b4de-429d-9121-c9d5b2162d64 | 169,168,2,65 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
6861a3a7-5410-4fab-8fef-8cf651f9d260 | 169,168,2,73 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
92259bc1-1704-4c6b-91fc-85b0ff55ef18 | 169,168,2,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
10db4a9a-3503-47ad-93da-12570b13ee94 | 169,168,2,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
0066222b-01bf-4f3b-b89a-cf2be53728a9 | 169,168,170,174,2,16,21,22 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
2c538ecb-7128-40bb-8f04-d378f41e693c | 169,168,170,174,2,16,21,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
c0c5d9c6-85c0-4f54-a661-718ba288384f | 169,168,170,174,2,16,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
d7c84ef1-3f44-47ac-a026-8710fccfd96f | 169,168,170,174,2,17,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
043c6778-6a9e-440e-9b5a-5248664918cb | 169,168,170,174,2,17,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
79a391ac-a95a-4974-a8c2-8a390b173540 | 169,168,170,174,2,17,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
a4560822-7899-4a3f-af7d-75ba2d1f124a | 169,168,170,174,2,18,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
6c89f14e-c8df-41b3-8900-30dc93c84876 | 169,168,170,174,2,18,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
ccab106f-78e9-41b8-bf2e-2cd7c14f7a88 | 169,168,170,174,2,18,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
b7a5569f-e83c-4293-a726-f6fa139384c7 | 169,168,170,174,2,35,25 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
a5446a5c-9b6d-4a1b-bb6b-129eb40ebc59 | 169,168,170,174,2,35,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
eaffa6d8-4c19-4ae0-9e0c-ebbfb6ef7021 | 169,168,170,174,2,36,26 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
191f1e93-ce97-4115-80b3-bfae484d98be | 169,168,170,174,2,36,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
3ab86a7a-c178-4ec0-b4b6-a70d31aefe9f | 169,168,170,174,2,65 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
3114fcf1-0d00-4071-b839-142d373ee59f | 169,168,170,174,2,73 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
1ab4b2c4-95ad-4c4c-af28-54c5ddc27df6 | 169,168,170,174,2,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
7ad1682b-0269-4fdc-b7d9-c736151a50a0 | 169,168,170,174,2,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
58fd7bd6-2492-4fe4-b6b4-bcbef6572288 | 169,168,170,174,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
6c83a8c3-c37c-4568-afce-06e2300f218c | 169,168,170,174,186,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
c5ad006f-ee35-4546-9b97-96f004d8bf08 | 169,168,170,174,186,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
e5fe8820-2048-4d1f-be2f-dc58fb3be11f | 169,168,170,174,186,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
b80ae3c1-cbca-4c8d-8612-064f9ad91a0b | 169,168,170,175,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
957e2181-a2d6-4613-87df-997e824726b7 | 169,168,170,175,183,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
63c363a9-ee33-4099-8329-c76850980932 | 169,168,170,175,183,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
78c82a69-ffe8-4ece-a3fe-00702daa84a8 | 169,168,170,186,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
03a5e5a8-565e-49d9-a6d8-70f7c82ffc23 | 169,168,170,186,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
b9ac99e5-3e24-4e6f-b78b-025236fa086b | 169,168,170,186,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
76d6e754-8dfd-4af9-b7e0-d6786eabd72b | 169,168,171,172,173,176,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
8e7c2753-7068-4a8f-8f2e-e200cc21b9aa | 169,168,171,172,173,176,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
34dc4376-6bf7-4118-98a6-2ecffdf371d5 | 169,168,171,172,173,176,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
e4224c55-b1b2-4843-9ea4-9659ec63fa20 | 169,168,171,172,173,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
d6187863-b328-4f2d-98e4-984d25e3ea3b | 169,168,171,172,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
caa6a6be-c2c8-4654-b085-b32553612116 | 169,168,171,172,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
47a285cb-5434-4302-8c52-e76a06514f00 | 169,168,171,172,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
ab43c360-ba5d-4987-b21a-b793117fd9a6 | 169,168,171,172,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
3d5ffda6-b1dd-42b1-bc0d-1ff779e9d087 | 169,168,171,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
7058d5c8-cc2b-4b30-85ca-1276e8b1b978 | 169,168,171,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
cb4d5ee1-d051-440e-b4d3-184064bf3b00 | 169,168,171,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
dcf0c9f1-310e-432b-8d9c-58f3a827289e | 169,168,171,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE VESSEL SHELL (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
f06ce383-555a-4d06-aee6-d36786eeab04 | 169,170,174,2,16,21,22 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
8f18ad10-cff8-4409-8b00-dc9d0215b1d7 | 169,170,174,2,16,21,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
e93e628e-f0df-4325-8328-57bc1587282e | 169,170,174,2,16,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
b211743d-f239-45ed-b03e-5e4699787136 | 169,170,174,2,17,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
7780d894-b91f-4ce4-8245-02bce54fbb06 | 169,170,174,2,17,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
bc2d3f0e-e727-47c4-95c9-08b57e6bb88c | 169,170,174,2,17,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
ea11dee9-f9e9-4cd1-abe8-2e0cf9dddb21 | 169,170,174,2,18,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
6344a78c-3217-477a-9983-ec529005a9de | 169,170,174,2,18,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
e138b422-2d98-4243-bb7a-324b3e4c29ed | 169,170,174,2,18,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
c2413ff8-5dcf-40a1-a373-a38daed67be2 | 169,170,174,2,35,25 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
69796af6-3f23-4faf-8f09-8c802e51dee9 | 169,170,174,2,35,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
4c089fa2-10b6-48e7-ad68-9a2a6f2b87d8 | 169,170,174,2,36,26 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
15043bb1-0f0c-4dba-92e5-e6c355097ff4 | 169,170,174,2,36,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
f07b38a3-2fcd-4faa-855b-cab0c338bdb6 | 169,170,174,2,65 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
8552acf0-d8f8-4029-b118-aa84eb5b2cea | 169,170,174,2,73 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
dd8de52b-b3d9-47db-b1a7-64edf5b9c8c9 | 169,170,174,2,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
4f161837-00f5-4f77-972f-276593cd0008 | 169,170,174,2,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
15cd9c9d-80ae-4657-bca0-c818194f33a8 | 169,170,174,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
24792fdf-a419-4f0d-a2f6-c5acf8667793 | 169,170,174,186,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
87ba5a6f-8754-4440-aa7d-acc3ac939d29 | 169,170,174,186,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
582b7fed-2078-4eef-9b8a-ad73ca416207 | 169,170,174,186,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT VENTILATION (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
31e2a13c-5978-43fe-b10c-d2a674de4876 | 169,170,175,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
6b047d09-9a02-46ad-b4a2-9fef33843cea | 169,170,175,183,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
03a205a2-f13d-4902-ac3d-b22ef701eb1e | 169,170,175,183,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - OCCUPANT CELL HYDROGEN SENSOR (0) -> ASSY - FUEL CELL ELECTRICAL CONNECTIONS (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
89d68c3f-be16-42d5-bb5f-62c879100012 | 169,170,186,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
4572e4ab-6ca2-4355-9ca4-17f368fc5ab9 | 169,170,186,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
e4ec1dd9-b3fc-4176-aec9-b0e92a0fdbeb | 169,170,186,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - HYDROGEN COMPARTMENT STRUCTURE (0) -> ASSY - REARWHEEL HUB AIR INTAKE (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
9f89c948-bf8b-47dc-8fe6-448af91b8a9c | 169,171,172,173,176,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
2dfed8a3-6b02-4157-8bcc-8f3c549e17eb | 169,171,172,173,176,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
1950f75c-5235-41cc-a9ba-52d9c25289c9 | 169,171,172,173,176,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN RECYCLE STREAM (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
6d97e6af-f4fe-4342-b9bf-8bba1e24092f | 169,171,172,173,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN PURGE MANAGEMENT (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
9fce1c3f-37ee-420b-9e02-ee49aa5174ba | 169,171,172,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
33d5c3e1-e706-4773-9ed4-a45035831551 | 169,171,172,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
b199b7a8-81be-4ad5-973e-89cb6288e3bf | 169,171,172,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
0c67db63-2348-4925-83c7-7592c68a062f | 169,171,172,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SUPPLY LINE (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
d1240d26-0aad-4f67-8caf-49bbb4c91493 | 169,171,179,177 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN SYSTEM PERFORMANCE DISPLAY (0) | 0 | FALSE
6137bce0-9487-4d32-bb86-b9517ffad9e5 | 169,171,179,180,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
5f76cab1-2b66-4d93-8820-3efe551facc1 | 169,171,179,180,187 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - HYDROGEN SENSOR ARRAY (0) -> ASSY - HYDROGEN CONTROL LOGIC (0) -> ASSY - HYDROGEN CONTROL SYSTEM (0) | 0 | FALSE
b4494b95-512b-49c5-a448-c4ca0e940676 | 169,171,184,185,178 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - PRESSURE REGULATION & SAFETY (0) -> ASSY - P&ID HYDROGEN DOWNSTREAM LINE (0) -> ASSY - P&ID AIR SUPPLY LINE (0) -> ASSY - OCCUPANT CELL SHUTDOWN VALVE (0) | 0 | FALSE
4925e806-7322-4f49-a5ab-81ca3dadabc2 | 169,2,16,21,22 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 20 | FALSE
f36146ae-d752-4700-94dd-f3ece67a97a4 | 169,2,16,21,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 18 | FALSE
5a9a7942-d98d-4469-83c7-9944e44e616c | 169,2,16,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 14 | FALSE
eb3b060c-2cfb-4bba-bbc9-0703483d60bb | 169,2,17,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
dafea6c6-4646-49ff-9717-e9680b67024a | 169,2,17,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 17 | FALSE
ba963789-a96e-4ef3-bbe2-b31e3a5f6001 | 169,2,17,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 15 | FALSE
b9132247-7ce8-4814-83df-08397d9a3802 | 169,2,18,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 19 | FALSE
357246b2-b438-4c30-81ff-348baa58e884 | 169,2,18,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 17 | FALSE
fdcd7c21-12a9-4b91-bcaf-b342be895ca2 | 169,2,18,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR SUPPORT STRUCTURE (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 12 | FALSE
08fafccf-233f-448c-9681-973f1e1f774b | 169,2,35,25 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - INNER DOOR HANDLE - RH (2) | 10 | FALSE
2a2f0fdb-30f9-4a6e-b175-9513cb644a5c | 169,2,35,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - RH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
b066e9e2-24fb-42a5-a3dd-69c2329c193c | 169,2,36,26 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - INNER DOOR HANDLE - LH (2) | 10 | FALSE
43ce328c-3401-4401-bbf3-f7527c825f5f | 169,2,36,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DOOR CARD - LH (3) -> ASSY - DASHBOARD STRUCTURE (6) | 14 | FALSE
3d98e323-69f6-4ce1-b940-de1d0adb66ee | 169,2,65 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - REAR TOELINK (2) | 7 | FALSE
35fd3675-f28e-42ed-845e-77055afa21e2 | 169,2,73 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - FRONT MASTER CYLINDER RESERVOIR (2) | 7 | FALSE
d034d25b-aee6-498b-813a-98882cba5bfb | 169,2,101 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - DASHBOARD STRUCTURE (6) | 11 | FALSE
3cd5147c-732f-45cc-87f1-f28ff6efa03d | 169,2,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - OCCUPANT CELL TUB (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 7 | FALSE
38b8459d-e62a-4013-b7db-fb6dd51d17d9 | 169,17,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - REAR FLOOR (3) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 5 | FALSE
1aab30b6-bcf8-42e0-8490-7957f5332a37 | 169,17,19,20 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 12 | FALSE
858e99e0-89bc-45cd-b42d-c7f419681a14 | 169,17,19,188 | ASSY - PRESSURE VESSEL SUPPORT STRUCTURE (0) -> ASSY - REAR FLOOR (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 10 | FALSE
ec4a9345-d663-4492-8a31-f8efede29671 | 189 | ASSY - INTRANET (0) | 0 | FALSE
1166b4f9-cd8c-40d3-aac4-dcc2c382173d | 192 | ASSY - DOOR ACTUATOR BOARD - RH (5) | 5 | FALSE
bfe2011b-62d7-41ed-9201-6e2131c7cb43 | 193 | ASSY - DOOR ACTUATOR BOARD - LH (5) | 5 | FALSE
ccef1386-60e9-4d9b-9aab-e605f6361931 | 194,91,16,21,22 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
6472fba0-67d7-43b3-a1a9-bd8b314c372e | 194,91,16,21,188 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
9532586e-bdfa-49c8-8d2c-a57cf7d86822 | 194,91,16,188 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
6491a08d-7af4-4bc8-89a4-407cecc7d872 | 194,91,147,19,20 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
6124e877-3250-4c8f-ba8e-8c586eb5df7b | 194,91,147,19,188 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
75457b97-d669-446e-804e-f935e0df2908 | 194,91,147,149,19,20 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
f301d5fb-95e5-4c96-bb9d-0e8a2c6b8fd5 | 194,91,147,149,19,188 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
a6b377c1-297f-47f9-b090-02e2ccbe413d | 194,91,147,149,188 | ASSY - SIDE INDICATOR - LH (4) -> ASSY - SIDE CAMERA - LH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - LH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - LH (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
8a9ef733-5e5f-469d-be0b-f10f877873fd | 195,92,16,21,22 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - BONNET LOCKING BOARD (4) | 25 | FALSE
8058da6b-3d54-4b60-b081-1c611a2685b4 | 195,92,16,21,188 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - BONNET (4) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 23 | FALSE
65241684-004a-47ec-becb-f044f8a95a52 | 195,92,16,188 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - FRONT CLAM SHELL (7) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 19 | FALSE
7662783c-2335-4d90-be73-d70e075f9170 | 195,92,148,19,20 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 22 | FALSE
87b6b102-374c-49a2-900b-235d59033ae2 | 195,92,148,19,188 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 20 | FALSE
948edd2e-797a-45a7-800f-4950b754788e | 195,92,148,150,19,20 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - BOOT (5) -> ASSY - BOOT LOCKING BOARD (4) | 28 | FALSE
8a4ad0e6-b9fe-4aab-8f5f-84b43b084746 | 195,92,148,150,19,188 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - BOOT (5) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 26 | FALSE
2d557375-4061-4838-b6fb-e2bf8bb1f7c0 | 195,92,148,150,188 | ASSY - SIDE INDICATOR - RH (4) -> ASSY - SIDE CAMERA - RH (6) -> ASSY - TAILLIGHT/INDICATOR EXTERIOR - RH (3) -> ASSY - TAILLIGHT/INDICATOR PCB - RH (6) -> ASSY - INTERNAL EMBEDDED NETWORK WIRING (2) | 21 | FALSE
5a2821df-c2b2-4056-a921-52576d8db70b | 196,197 | ASSY - CENTRAL STOPLAMP (3) -> ASSY - CENTRAL STOPLAMP CASING (4) | 7 | FALSE
9539cacc-b4b6-4a69-a18f-48b0e8b68aea | 196,198 | ASSY - CENTRAL STOPLAMP (3) -> ASSY - CENTRAL STOPLAMP CONTROLLER (3) | 6 | FALSE